## PMR
PROVINCE OF DAVAO DE ORO | [11 empty] | Procurement Monitoring Report as of December 29, 2023 (JULY-DEC 2023)
[5 empty] | Actual Procurement Activities | [20 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column1 | Column2
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
23-2715 | INTERNET SUBSCRIPTION FOR NETWORK FIREWALL SECURITY | PASSO | No | Competitive Bidding | 2023-05-16 | 2023-05-19 | 3 | N/A | 2023-05-30 | 2023-05-30 | 11 | 2023-05-30 | 2023-06-09 | 2023-06-23 | 10 | 24 | 35 | 29-06-2023 | 2023-11-07 | 13-07-2023 |  |  | 2023-07-24 | 2023-07-24 | Government of the Philippines (current year's budget) | 800000 | 800000 |  | 799112 | 799112 |  | 0.00111 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | Completed | FALSE | FALSE
23-C0360 | SUPPLY AND DELIVERY OF MEAL AND SNACKS | PGSO | No | Competitive Bidding | 2023-04-04 | 2023-05-22 |  | 2023-05-30 | 2023-06-13 | 2023-06-13 |  | 2023-06-13 | 15-06-2023 | 2023-06-23 |  |  |  | 2023-06-30 | 2023-07-18 | 2023-07-24 |  |  | 2023-07-24 | 2023-07-24 | Government of the Philippines (current year's budget) | 2136959 | 2136959 |  | 2089350 | 2089350 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-05-23 | 2023-06-08 | 2023-06-08 | 2023-06-08 | N/A | N/A | Completed
23-C0526 | SUPPLY AND DELIVERY OF TIRES | PDRRMO | No | Competitive Bidding | N/A | 2023-06-05 |  | N/A | 2023-06-13 | 2023-06-13 |  | 2023-06-13 | 2023-06-15 | 2023-06-23 |  |  |  | 2023-06-30 | 2023-08-23 | 2023-08-23 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 451976 | 451976 |  | 330400 | 330400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-06-08 | 2023-06-08 | 2023-06-08 | N/A | N/A | Completed
23-C0539 | SUPPLY AND DELIVERY OF MEALS AND SNACKS | PHO | No | Competitive Bidding | N/A | 2023-06-05 |  | N/A | 2023-06-13 | 2023-06-13 |  | 2023-06-13 | 2023-06-15 | 2023-06-23 |  |  |  | 2023-06-30 | 2023-07-11 | 2023-07-24 |  |  | 2023-10-02 | 2023-10-02 | Government of the Philippines (current year's budget) | 711620 |  | 711620 | 694025 |  | 694025 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-06-08 | 2023-06-08 | 2023-06-08 | N/A | N/A | Completed
23-1898 | 1 LOT CONSTRUCTION OF WATER SYSTEM AT CANP 4, BARANGAY PINDASAN, MABINI | PEO | No | Competitive Bidding | 2023-03-21 | 2023-05-08 |  | 2023-05-16 | 2023-05-30 | 2023-05-30 |  | 2023-05-30 | 2023-07-06 | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-20 | 2023-07-27 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 1446387.8 |  | 1446387.8 | 1441107.78 |  | 1441107.78 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-05-12 | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | Completed
23-1467 | CONCRETING OF ROAD, BRGY. NABOC, MONKAYO | PEO | No | Competitive Bidding | 2023-04-04 | 2023-05-08 |  | 2023-05-16 | 2023-05-30 | 2023-05-30 |  | 2023-05-30 | 2023-07-06 | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-20 | 2023-07-27 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 9660453.88 |  | 9660453.88 | 9655390.73 |  | 9655390.73 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-05-12 | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | Completed
23-1833 | CONSTRUCTION OF COVERED COURT, SITIO MAG-ABAY, BRGY. LONGANAPAN, LAAK | PEO | No | Competitive Bidding | 2023-03-21 | 2023-05-08 |  | 2023-05-16 | 2023-05-30 | 2023-05-30 |  | 2023-05-30 | 2023-07-06 | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-20 | 2023-07-27 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 3751603.89 |  | 3751603.89 | 3711578.49 |  | 3711578.49 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-05-12 | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | Completed
23-1629 | CONSTRUCTION OF MULTIPURPOSE BUILDING, MAYAON NATIONAL HIGH SCHOOL, MONTEVISTA | PEO | No | Competitive Bidding | 2023-03-21 | 2023-05-08 |  | 2023-05-16 | 2023-05-30 | 2023-05-30 |  | 2023-05-30 | 2023-07-06 | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-20 | 2023-07-27 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 4891611.84 |  | 4891611.84 | 4841459.64 |  | 4841459.64 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-05-12 | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | Completed
23-1630 | CONSTRUCTION OF SLOPE PROTECTION AT BRGY. PANANGAN, MACO | PEO | No | Competitive Bidding | 2023-03-21 | 2023-05-08 |  | 2023-05-16 | 2023-05-30 | 2023-05-30 |  | 2023-05-30 | 2023-07-06 | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-20 | 2023-07-27 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 1241109.13 |  | 1241109.13 | 1235416.8 |  | 1235416.8 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-05-12 | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | Completed
23-2521 | CONSTRUCTION OF STAGE WITH BLEACHERS AT ARAIBO, PANTUKAN | PEO | No | Competitive Bidding | 2023-04-19 | 2023-05-08 |  | 2023-05-16 | 2023-05-30 | 2023-05-30 |  | 2023-05-30 | 2023-07-06 | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-20 | 2023-07-27 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 2883242.63 |  | 2883242.63 | 2875607.97 |  | 2875607.97 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-05-12 | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | Completed
23-2520 | CONSTRUCTION OF WATER SUPPLY SYSTEM, BRGY. SAN JOSE, MONKAYO | PEO | No | Competitive Bidding | 2023-04-19 | 2023-05-08 |  | 2023-05-16 | 2023-05-30 | 2023-05-30 |  | 2023-05-30 | 2023-07-06 | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-20 | 2023-07-27 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 3198096 |  | 3198096 | 3180712.35 |  | 3180712.35 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-05-12 | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | Completed
23-1989 | CONSTRUCTION OF ONE(1) STOREY-TWO CLASSROOM SCHOOL BUILDING WITH TOILET ATTACHED AT PANIBASAN NHS, MACO | PEO | No | Competitive Bidding | 2023-04-19 | 2023-05-08 |  | 2023-05-16 | 2023-05-30 | 2023-05-30 |  | 2023-05-30 | 2023-07-06 | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-20 | 2023-07-27 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 2802084.38 |  | 2802084.38 | 2771999.5 |  | 2771999.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-05-12 | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | Completed
23-1488 | UPGRADING OF HOSPITAL BUILDING FACILITIES AT DDOPH-MONTEVISTA | PEO | No | Competitive Bidding | 2023-02-21 | 2023-05-08 |  | 2023-05-16 | 2023-05-30 | 2023-05-30 |  | 2023-05-30 | 2023-07-06 | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-20 | 2023-07-21 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 859977.4 |  | 859977.4 | 855222.96 |  | 855222.96 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-05-12 | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | Completed
23-2207 | IMPROVEMENT OF WATER SYSTEM AT CABIDIANAN NHS, BRGY. CABIDIANAN, NABUNTURAN | PEO | No | Competitive Bidding | N/A | 2023-05-22 |  | N/A | 2023-05-30 | 2023-05-30 |  | 2023-05-30 | 2023-07-06 | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-20 | 2023-07-27 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 932786.54 |  | 932786.54 | 922782.44 |  | 922782.44 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-05-23 | 2023-05-23 | 2023-05-23 | N/A | N/A | Completed
23-C0500 | SUPPLY AND DELIVERY OF RICE WELL MILLED 50KG/SACK | PGO | No | Competitive Bidding | 2023-05-02 | 2023-06-12 |  | 2023-06-13 | 2023-06-27 | 2023-06-27 |  | 2023-06-27 | 2023-07-05 | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-27 | 2023-08-01 |  |  | 2023-08-14 | 2023-08-14 | Government of the Philippines (current year's budget) | 1140300 |  | 1140300 | 1139757 |  | 1139757 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-06-08 | 2023-06-26 | 2023-06-26 | 2023-06-26 | N/A | N/A | Completed
23-C0579 | SUPPLY AN DELIVERY OF CONSTRUCTION MATERIALS | PEO | No | Competitive Bidding | N/A | 2023-06-19 |  | N/A | 2023-06-27 | 2023-06-27 |  | 2023-06-27 | 2023-07-05 | 2023-07-20 |  |  |  | 2023-07-20 | 2023-08-02 | 2023-08-08 |  |  | 2023-08-18 | 2023-08-18 | Government of the Philippines (current year's budget) | 348981.6 | 348981.6 |  | 345738 | 345738 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-06-26 | 2023-06-26 | 2023-06-26 | N/A | N/A | Completed
23-2704 | SUPPLY AND DELIVERY CONSTRUCTION SUPPLIES | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-05-22 |  | N/A | N/A | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | 2023-07-20 | 2023-08-16 | 2023-08-22 |  |  | 2023-09-12 | 2023-09-12 | Government of the Philippines (current year's budget) | 80780.49 | 80780.49 |  | 77625.49 | 77625.49 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2716 | CONSTRUCTION SUPPLIES | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-05-22 |  | N/A | N/A | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | 2023-07-20 | 2023-08-14 | 2023-08-16 |  |  | 2023-09-12 | 2023-09-12 | Government of the Philippines (current year's budget) | 64327.49 | 64327.49 |  | 61800.49 | 61800.49 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4117 | MEALS AND SNACKS | PICTO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | N/A | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-14 | 2023-09-19 |  |  | 2023-12-14 | 2023-12-14 | Government of the Philippines (current year's budget) | 54437 | 54437 |  | 53734 | 53734 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2707 | CONSTRUCTION SUPPLIES | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-05-22 |  | N/A | N/A | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | 2023-07-20 | 2023-08-16 | 2023-08-17 |  |  | 2023-09-12 | 2023-09-12 | Government of the Philippines (current year's budget) | 78324.49 | 78324.49 |  | 75270.49 | 75270.49 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3095 | WATER | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-19 |  | N/A | N/A | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | N/A | 2023-07-31 | 2023-08-01 |  |  |  |  | Government of the Philippines (current year's budget) | 4551 | 4551 |  | 4440 | 4440 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3207 | ELECTRICAL SUPPLIES | VGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-20 |  | N/A | N/A | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | N/A | 2023-08-31 | 2023-09-04 |  |  | 2023-09-11 | 2023-09-11 | Government of the Philippines (current year's budget) | 12600 | 12600 |  | 12600 | 12600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3011 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-20 |  | N/A | N/A | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | 2023-07-28 | 2023-07-28 | 2023-08-01 |  |  | 2023-08-17 | 2023-08-17 | Government of the Philippines (current year's budget) | 55350 | 55350 |  | 54720 | 54720 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3336 | PLUMBING SUPPLIES | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-20 |  | N/A | N/A | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-09-05 | 2023-09-05 | Government of the Philippines (current year's budget) | 46418 | 46418 |  | 46347 | 46347 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3393 | PRINTING | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-23 |  | N/A | N/A | 2023-07-11 | 18 | N/A | N/A | 2023-07-20 |  | 9 | 27 | 2023-07-21 | 2023-07-31 | 2023-08-08 | 18 | 46 |  |  | Government of the Philippines (current year's budget) | 48900 | 48900 |  | 48360 | 48360 |  | 0.011043 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO | FALSE | FALSE
23-3247 | CONSTRUCTION SUPPLIES | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-23 |  | N/A | N/A | 2023-07-11 | 18 | N/A | N/A | 2023-07-20 |  | 9 | 27 | 2023-07-21 | 2023-08-16 | 2023-08-22 | 32 | 60 | 2023-09-05 | 2023-09-05 | Government of the Philippines (current year's budget) | 71242.51 | 71242.51 |  | 69214.85 | 69214.85 |  | 0.028461 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-2700 | JANITORIAL SUPPLIES | PACCO | No | NP-53.9 - Small Value Procurement | 4509700% | 4509900% |  | N/A | N/A | 4513200% |  | N/A | N/A | 4513500% |  |  |  | NA | 4515200% | 4515400% |  |  | 4516000% | 4516000% | Government of the Philippines (current year's budget) | 24289 | 24289 |  | 24172 | 24172 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-2999 | OTHER SUPPLIES | PACCO | No | NP-53.9 - Small Value Procurement | 2023-06-20 | 2023-06-23 | 3 | N/A | N/A | 2023-07-11 | 18 | N/A | N/A | 2023-07-20 |  | 9 | 27 | 2023-07-20 | 2023-07-28 | 2023-08-02 | 13 | 40 | 2023-08-09 | 2023-08-09 | Government of the Philippines (current year's budget) | 79605 | 79605 |  | 79315 | 79315 |  | 0.003643 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-3206 | GARMENTS | PGO | No | NP-53.9 - Small Value Procurement | 2023-06-20 | 2023-06-23 | 3 | N/A | N/A | 2023-07-11 | 18 | N/A | N/A | 2023-07-20 |  | 9 | 27 | 2023-07-20 | 2023-07-28 | 2023-08-02 | 13 | 40 | 2023-08-07 | 2023-08-07 | Government of the Philippines (current year's budget) | 7000 | 7000 |  | 7000 | 7000 |  | 0 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-3087 | PLAQUE | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-23 |  | N/A | N/A | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-28 | 2023-08-02 |  |  | 2023-09-08 | 2023-09-08 | Government of the Philippines (current year's budget) | 150650 | 150650 |  | 150650 | 150650 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3378 | PRINTING | PAO-PESD | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-23 |  | N/A | N/A | 2023-07-11 | 18 | N/A | N/A | 2023-07-20 |  | 9 | 27 | NA | NA | 2023-07-28 |  | 35 | 2023-08-02 | 2023-07-24 | Government of the Philippines (current year's budget) | 9996 | 9996 |  | 9282 | 9282 |  | 0.071429 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-3376 | WATER | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-23 |  | N/A | N/A | 2023-07-11 | 18 | N/A | N/A | 2023-07-20 |  | 9 | 27 | NA | 2023-07-28 | 2023-08-01 |  | 39 |  |  | Government of the Philippines (current year's budget) | 15375 | 15375 |  | 15000 | 15000 |  | 0.02439 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO | FALSE | FALSE
23-3391 | LUMBER | PEO | No | NP-53.9 - Small Value Procurement | 2023-06-27 | 2023-07-04 | 7 | N/A | N/A | 2023-07-11 | 7 | N/A | N/A | 2023-07-20 |  | 9 | 16 | NA | 2023-08-11 | 2023-08-16 |  | 43 | 2023-10-09 | 2023-10-09 | Government of the Philippines (current year's budget) | 10089.96 | 10089.96 |  | 10006.23 | 10006.23 |  | 0.0082983 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-2244 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | 2023-05-02 | 2023-07-04 | 63 | N/A | N/A | 2023-07-11 | 7 | N/A | N/A | 2023-07-20 |  | 9 | 16 | 2023-07-20 | 2023-07-28 | 2023-08-01 | 12 | 28 | 2023-09-06 | 2023-09-06 | Government of the Philippines (current year's budget) | 97500 | 97500 |  | 97500 | 97500 |  | 0 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-C0517 | OIL AND LUBRICANTS | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-05-22 |  | N/A | N/A | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | 2023-07-20 | 2023-08-10 | 2023-08-15 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 153759 | 153759 |  | 153269.5 | 153269.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2872 | SPAREPARTS | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-05-30 | 2023-06-02 |  | N/A | N/A | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | 2023-07-20 | 2023-08-02 | 2023-08-04 |  |  | 2023-08-07 | 2023-08-07 | Government of the Philippines (current year's budget) | 52440 | 52440 |  | 52377 | 52377 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3094 | FOOD/CATERIING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-23 |  | N/A | N/A | 2023-07-11 | 18 | N/A | N/A | 2023-07-20 |  | 9 | 27 | 2023-07-20 | 2023-07-28 | 2023-08-01 | 12 | 39 | 2023-08-13 | 2023-08-13 | Government of the Philippines (current year's budget) | 70600 | 70600 |  | 69600 | 69600 |  | 0.014164 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-C0601 | CONSTRUCTION SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-23 |  | N/A | N/A | 2023-07-11 | 18 | N/A | N/A | 2023-07-20 |  | 9 | 27 | 2023-07-20 | 2023-07-28 | 2023-08-02 | 13 | 40 | 2023-08-14 | 2023-08-14 | Government of the Philippines (current year's budget) | 152692 | 152692 |  | 151850 | 151850 |  | 0.0055144 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-2702 | OFFICE SUPPLIES | PACCO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-06-20 |  | N/A | N/A | 2023-07-11 | 21 | N/A | N/A | 2023-07-20 |  | 9 | 30 | 2023-07-20 | 2023-07-28 | 2023-08-01 | 12 | 42 | 2023-08-09 | 2023-08-09 | Government of the Philippines (current year's budget) | 114839 | 114839 |  | 112482 | 112482 |  | 0.020524 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-2701 | COMPUTER SUPPLIES | PACCO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-06-20 |  | N/A | N/A | 2023-07-11 | 21 | N/A | N/A | 2023-07-20 |  | 9 | 30 | 2023-07-20 | 2023-07-28 | 2023-08-01 | 12 | 42 | 2023-08-09 | 2023-08-09 | Government of the Philippines (current year's budget) | 42048 | 42048 |  | 41100 | 41100 |  | 0.022546 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-C0597 | OFFICE SUPPLIES | PIAO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-06-20 |  | N/A | N/A | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-28 | 2023-08-02 |  |  | 2023-08-16 | 2023-08-16 | Government of the Philippines (current year's budget) | 23319 | 23319 |  | 23099 | 23099 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-1655 | CONSTRUCTION SUPPLIES | PEO | No | NP-53.1 Two Failed Biddings | N/A | 2023-06-02 |  | N/A | N/A | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | 2023-07-20 | 2023-08-02 | 2023-08-08 |  |  | 2023-08-16 | 2023-08-16 | Government of the Philippines (current year's budget) | 311645 | 311645 |  | 310378.5 | 310378.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-1137 | SERVICES | PGO | No | NP-53.1 Two Failed Biddings | N/A | 2023-06-02 |  | N/A | N/A | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-28 | 2023-08-02 |  |  |  |  | Government of the Philippines (current year's budget) | 799750 | 799750 |  | 799750 | 799750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3079 | WATER | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2023-06-22 |  | N/A | 2023-07-11 | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | N/A | 2023-07-31 | 2023-08-01 |  |  | 2023-11-28 | 2023-11-28 | Government of the Philippines (current year's budget) | 17015 | 17015 |  | 16600 | 16600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0438 | LABORATORY SUPPLIES | PEEMO | No | Direct Contracting | N/A | 2023-06-19 |  | N/A | 2023-07-11 | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-28 | 2023-08-01 |  |  | 2023-08-02 | 2023-08-02 | Government of the Philippines (current year's budget) | 828222 | 828222 |  | 828222 | 828222 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0439 | LABORATORY SUPPLIES | PEEMO | No | Direct Contracting | N/A | 2023-06-13 |  | N/A | 2023-07-11 | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | 2023-07-20 | 2023-07-28 | 2023-07-31 |  |  | 2023-08-07 | 2023-08-07 | Government of the Philippines (current year's budget) | 1765998 | 1765998 |  | 860358 | 860358 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0528 | CONSTRUCTION SUPPLIES | PEO | No | Competitive Bidding | 2023-07-11 | 2023-07-17 |  | 2023-07-25 | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-18 | 2023-08-31 |  |  |  | 2023-09-01 | 2023-09-08 | 2023-09-11 |  |  | 2023-09-25 | 2023-09-25 | Government of the Philippines (current year's budget) | 1457009 | 1457009 |  | 1269456 | 1269456 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-07-19 | 2023-08-03 | 2023-08-03 | 2023-08-03 | N/A | N/A | Completed
23-2003 | 1 LOT CONSTRUCTION OF SLOPE PROTECTION AT BRGY. LAS ARENAS, PANTUKAN | PEO | No | Competitive Bidding | N/A | 2023-06-05 |  | N/A | 2023-06-13 | 2023-06-13 |  | 2023-06-13 | 2023-06-20 | 2023-07-28 |  |  |  | 2023-08-01 | 2023-08-03 | 2023-08-08 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 970245.77 |  | 970245.77 | 965061.55 |  | 965061.55 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-06-08 | 2023-06-08 | 2023-06-08 | N/A | N/A | Completed
23-1932 | IMPROVEMENT OF DAVAO DE ORO PROVINCIAL HOSPITAL-MONTEVISTA | PEO | No | Competitive Bidding | N/A | 2023-05-29 |  | 2023-06-06 | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-07-20 | 2023-07-28 |  |  |  | 2023-08-01 | 2023-08-03 | 2023-08-08 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 3271471.14 |  | 3271471.14 | 3267297.56 |  | 3267297.56 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-06-05 | 2023-06-16 | 2023-06-16 | 2023-06-16 | N/A | N/A | Completed
23-2002 | UPGRADING OF HOSPITAL BUILDING FACILITIES AT DDOPH-PANTUKAN | PEO | No | Competitive Bidding | 2023-04-19 | 2023-05-29 |  | 2023-06-06 | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-07-20 | 2023-07-28 |  |  |  | 2023-08-02 | 2023-08-03 | 2023-08-08 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 1167779.06 |  | 1167779.06 | 1147165.87 |  | 1147165.87 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-06-05 | 2023-06-16 | 2023-06-16 | 2023-06-16 | N/A | N/A | Completed
23-1998 | UPGRADING OF HOSPITAL BUILDING FACILITIES AT DDOPH-PANTUKAN | PEO | No | Competitive Bidding | N/A | 2023-05-29 |  | 2023-06-06 | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-07-20 | 2023-07-28 |  |  |  | 2023-08-02 | 2023-08-03 | 2023-08-08 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 3093997.35 |  | 3093997.35 | 3063656.1 |  | 3063656.1 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-06-05 | 2023-06-16 | 2023-06-16 | 2023-06-16 | N/A | N/A | Completed
23-2234 | CONSTRUCTION OF WATER SYSTEM AT (MIGUM-LOWER B), BRGY. CABUYUAN, MABINI | PEO | No | Competitive Bidding | N/A | 2023-05-29 |  | 2023-06-06 | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-07-20 | 2023-07-28 |  |  |  | 2023-08-01 | 2023-08-03 | 2023-08-08 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 1867751.96 |  | 1867751.96 | 1862663.66 |  | 1862663.66 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-06-05 | 2023-06-16 | 2023-06-16 | 2023-06-16 | N/A | N/A | Completed
23-2245 | LABORATORY SUPPLIES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-19 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-05 | 2023-08-14 | 2023-08-15 |  |  | 2023-08-23 | 2023-08-23 | Government of the Philippines (current year's budget) | 217500 | 217500 |  | 217500 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0527 | CONSTRUCTION SUPPLIES | PEO | No | Competitive Bidding | N/A | 2023-06-26 |  | N/A | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-21 | 2023-07-28 |  |  |  | 2023-08-03 | 2023-08-10 | 2023-08-11 |  |  | 2023-08-18 | 2023-08-18 | Government of the Philippines (current year's budget) | 862040 |  | 862040 | 731170 |  | 731170 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-07-07 | 2023-07-07 | 2023-07-07 | N/A | N/A | Completed
23-C0559 | SPARE PARTS (LIGHT VEHICLES) FUEL, OIL AND LUBRICANTS | PGSO | No | Competitive Bidding | 2023-06-13 | 2023-06-26 |  | N/A | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-21 | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-10 | 2023-08-15 |  |  | 2023-08-24 | 2023-08-24 | Government of the Philippines (current year's budget) | 360440 |  | 360440 |  |  | 294350 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-07-07 | 2023-07-07 | 2023-07-07 | N/A | N/A | Completed
23-2917 | CONSTRUCTION SUPPLIES | PEO | No | Competitive Bidding | N/A | 2023-06-19 |  | N/A | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-21 | 2023-07-28 |  |  |  | 2023-08-03 | 2023-08-23 | 2023-08-23 |  |  | 2023-09-12 | 2023-09-12 | Government of the Philippines (current year's budget) | 1269997 | 1269997 |  | 1269997 | 1269997 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-07-07 | 2023-07-07 | 2023-07-07 | N/A | N/A | Completed
23-C0505 | MEALS AND SNACKS | PDRRMO | No | Competitive Bidding | 2023-06-27 | 2023-07-03 |  | N/A | 2023-07-11 | 2023-07-11 |  | 2023-07-11 | 2023-07-21 | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-11 | 2023-08-29 |  |  | 2023-12-03 | 2023-12-03 | Government of the Philippines (current year's budget) | 890483 | 890483 |  | 780596 | 780596 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-07-07 | 2023-07-07 | 2023-07-07 | N/A | N/A | Completed
23-C0575 | OFFICE SUPPLIES | PAGRO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-06-27 | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-16 | 2023-08-23 |  |  | 2023-09-05 | 2023-09-05 | Government of the Philippines (current year's budget) | 132571 | 132571 |  | 132353 | 132353 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0547 | OFFICE SUPPLIES | VGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-06-27 | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-11 | 2023-08-14 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 14980 | 14980 |  | 14580 | 14580 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0609 | OFFICE SUPPLIES | PPDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-16 | 2023-08-17 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 32638 | 32638 |  | 32170 | 32170 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3416 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-05 | 2023-08-11 | 2023-08-11 |  |  | 2023-09-07 | 2023-09-07 | Government of the Philippines (current year's budget) | 153194 | 153194 |  | 150980 | 150980 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3340 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-07-11 | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-08 | 2023-08-09 |  |  | 2023-08-15 | 2023-08-15 | Government of the Philippines (current year's budget) | 7770 | 7770 |  | 7740 | 7740 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3622 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-07-11 | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-08 | 2023-08-09 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 19330 | 19330 |  | 18410 | 18410 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0616 | OFFICE SUPPLIES | PDRRMO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-07-11 | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-03 | 2023-08-11 | 2023-08-14 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 182745 | 182745 |  | 171455 | 171455 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0607 | OFFICE SUPPLIES | PENRO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-07-11 | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-10 | 2023-08-11 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 93433 | 93433 |  | 93433 | 93433 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0289 | SPAREPARTS | PICTO | No | NP-53.9 - Small Value Procurement | 2023-03-26 | 2023-05-22 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-16 | 2023-08-17 |  |  | 2023-09-04 | 2023-09-04 | Government of the Philippines (current year's budget) | 141220 | 141220 |  | 137410 | 137410 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0563 | FOOD/CATERING SERVICES | PHRMDO | No | NP-53.9 - Small Value Procurement | 2023-06-20 | 2023-06-22 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-05 | 2023-08-10 | 2023-08-11 |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 285772 | 285772 |  | 279990 | 279990 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2930 | PRINTED FORMS | PACCO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-20 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-16 | 2023-08-24 |  |  | 2023-09-21 | 2023-09-21 | Government of the Philippines (current year's budget) | 19500 | 19500 |  | 19200 | 19200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3258 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-20 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-11 | 2023-08-11 |  |  |  |  | Government of the Philippines (current year's budget) | 22000 | 22000 |  | 22000 | 22000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3100 | FOOD/CATERING SERVICES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-05 | 2023-08-11 | 2023-08-11 |  |  | 2023-08-25 | 2023-08-25 | Government of the Philippines (current year's budget) | 127300 | 127300 |  | 124800 | 124800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2873 | WATER | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-16 | 2023-08-17 |  |  |  |  | Government of the Philippines (current year's budget) | 3403 | 3403 |  | 3320 | 3320 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3379 | OFFICE EQUIPMENT | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-16 | 2023-08-23 |  |  | 2023-08-31 | 2023-08-31 | Government of the Philippines (current year's budget) | 15400 | 15400 |  | 15400 | 15400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3294 | ELECTRICAL SUPPLIES | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-10 | 2023-08-11 |  |  |  |  | Government of the Philippines (current year's budget) | 9470 | 9470 |  | 9445 | 9445 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3492 | CEMENT | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-10 | 2023-08-11 |  |  | 2023-08-18 | 2023-08-18 | Government of the Philippines (current year's budget) | 56511 | 56511 |  | 56322 | 56322 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2216 | PLUMBING SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-10 | 2023-08-11 |  |  | 2023-09-18 | 2023-09-18 | Government of the Philippines (current year's budget) | 13050 | 13050 |  | 12975 | 12975 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-1509 | OFFICE EQUIPMENT | VGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-11 | 2023-08-15 |  |  | 2023-08-18 | 2023-08-18 | Government of the Philippines (current year's budget) | 69640 | 69640 |  | 69634 | 69634 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2997 | COMPUTER SUPPLIES | PACCO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-03 | 2023-08-16 | 2023-08-22 |  |  | 2023-08-31 | 2023-08-31 | Government of the Philippines (current year's budget) | 104448 | 104448 |  | 100795 | 100795 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3431 | HARDWARE | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-27 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-16 | 2023-08-22 |  |  | 2023-10-09 | 2023-10-09 | Government of the Philippines (current year's budget) | 4212 | 4212 |  | 4142 | 4142 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3332 | JANITORIAL SUPPLIES | PIAO | No | NP-53.9 - Small Value Procurement | 2023-06-27 | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-11 | 2023-08-15 |  |  | 2023-08-31 | 2023-08-31 | Government of the Philippines (current year's budget) | 7717 | 7717 |  | 7680 | 7680 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3301 | CONSTRUCTION MATERIALS | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-10-09 | 2023-10-09 | Government of the Philippines (current year's budget) | 21801 | 21801 |  | 21701.5 | 21701.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0572 | JANITORIAL SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-16 | 2023-08-23 |  |  | 2023-09-05 | 2023-09-05 | Government of the Philippines (current year's budget) | 25390 | 25390 |  | 25301 | 25301 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0577 | JANITORIAL SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-03 | 2023-08-11 | 2023-08-14 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 69138 | 69138 |  | 68770 | 68770 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3044 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-22 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-10 | 2023-08-11 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 42360 | 42360 |  | 40200 | 40200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0418 | OIL | PGO | No | NP-53.9 - Small Value Procurement | 2023-04-16 | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-11 | 2023-08-15 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 39830 | 39830 |  | 39290 | 39290 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0512 | OFFICE EQUIPMENT | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-05 | 2023-08-16 | 2023-08-18 |  |  | 2023-08-30 | 2023-08-30 | Government of the Philippines (current year's budget) | 321370 |  | 321370 | 316870 |  | 316870 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0587 | COMPUTER SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-10 | 2023-08-11 |  |  | 2023-08-23 | 2023-08-23 | Government of the Philippines (current year's budget) | 100396 | 100396 |  | 100353 | 100353 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0386 | CONSTRUCTION SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-04-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-11 | 2023-08-16 |  |  | 2023-10-18 | 2023-10-18 | Government of the Philippines (current year's budget) | 230510 | 230510 |  | 230411 | 230411 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0099 | PLUMBING SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | 2023-05-02 | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-10 | 2023-08-11 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 47045 | 47045 |  | 45044 | 45044 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0485 | COMPUTER SUPPLIES | PAO | No | NP-53.9 - Small Value Procurement | 2023-05-02 | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-08 | 2023-08-09 |  |  | 2023-08-14 | 2023-08-14 | Government of the Philippines (current year's budget) | 47045 | 47045 |  | 45044 | 45044 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0606 | PRINTING | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-11 | 2023-08-15 |  |  |  |  | Government of the Philippines (current year's budget) | 149940 | 149940 |  | 139230 | 139230 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-2949 | CONSTRUCTION SUPPLIES | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-22 | 2023-08-23 |  |  | 2023-10-13 | 2023-10-13 | Government of the Philippines (current year's budget) | 87933.5 | 87933.5 |  | 87833.5 | 87833.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2946 | CONSTRUCTION SUPPLIES | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-22 | 2023-08-23 |  |  | 2023-10-13 | 2023-10-13 | Government of the Philippines (current year's budget) | 87933.5 | 87933.5 |  | 87833.5 | 87833.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2928 | CONSTRUCTION SUPPLIES | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-22 | 2023-08-23 |  |  | 2023-10-13 | 2023-10-13 | Government of the Philippines (current year's budget) | 87933.5 | 87933.5 |  | 87833.5 | 87833.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2945 | CONSTRUCTION SUPPLIES | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-22 | 2023-08-23 |  |  | 2023-10-13 | 2023-10-13 | Government of the Philippines (current year's budget) | 87933.5 | 87933.5 |  | 87833.5 | 87833.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3049 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-20 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-10 | 2023-08-11 |  |  | 2023-12-10 | 2023-12-10 | Government of the Philippines (current year's budget) | 25200 | 25200 |  | 25020 | 25020 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3104 | PRINTING | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-22 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-10 | 2023-08-11 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 19320 | 19320 |  | 18630 | 18630 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0578 | CONSTRUCTION SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-09 | 2023-08-16 | 2023-08-23 |  |  | 2023-12-11 | 2023-12-11 | Government of the Philippines (current year's budget) | 281300 | 281300 |  | 280569 | 280569 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3441 | PRINTING | PEO | No | NP-53.9 - Small Value Procurement | 2023-06-27 | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-11 | 2023-08-15 |  |  | 2023-08-16 | 2023-08-16 | Government of the Philippines (current year's budget) | 1792 | 1792 |  | 1664 | 1664 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3213 | OFFICE SUPPLIES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-16 | 2023-08-22 |  |  |  |  | Government of the Philippines (current year's budget) | 5600 | 5600 |  | 5560 | 5560 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3506 | PRINTING | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-09-19 | 2023-09-19 | Government of the Philippines (current year's budget) | 2800 | 2800 |  | 2600 | 2600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2250 | JOB ORDER (LABOR ONLY) | PHO | No | NP-53.9 - Small Value Procurement | 2023-04-18 | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-10 | 2023-08-11 |  |  | 2023-12-11 | 2023-12-11 | Government of the Philippines (current year's budget) | 9000 | 9000 |  | 9000 | 9000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3411 | JOB ORDER (LABOR ONLY) | PHO | No | NP-53.9 - Small Value Procurement | 2023-06-22 | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-11 | 2023-08-16 |  |  | 2023-12-11 | 2023-12-11 | Government of the Philippines (current year's budget) | 9000 | 9000 |  | 9000 | 9000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2944 | PRINTING | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-10 | 2023-08-11 |  |  | 2023-12-01 | 2023-12-01 | Government of the Philippines (current year's budget) | 56000 | 56000 |  | 52000 | 52000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3512 | PRINTED FORMS | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-11 | 2023-08-15 |  |  | 2023-10-04 | 2023-10-04 | Government of the Philippines (current year's budget) | 89600 | 89600 |  | 86400 | 86400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3719 | JANITORIAL SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-10 | 2023-08-11 |  |  | 2023-08-15 | 2023-08-15 | Government of the Philippines (current year's budget) | 15240 | 15240 |  | 14829 | 14829 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3655 | FOOD SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-08 | 2023-08-09 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 9258 | 9258 |  | 9251 | 9251 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3212 | AGRICULTURAL SUPPLIES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-14 | 2023-08-16 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 6000 | 6000 |  | 5994 | 5994 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0618 | JANITORIAL SUPPLIES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-14 | 2023-08-16 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 4625 | 4625 |  | 4625 | 4625 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3214 | FURNITURE AND FIXTURES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-16 | 2023-08-17 |  |  | 2023-08-24 | 2023-08-24 | Government of the Philippines (current year's budget) | 18000 | 18000 |  | 17800 | 17800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0595 | JANITORIAL SUPPLIES | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-10 | 2023-08-11 |  |  | 2023-08-15 | 2023-08-15 | Government of the Philippines (current year's budget) | 98950 | 98950 |  | 98341 | 98341 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0628 | ELECTRICAL SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-22 | 2023-08-23 |  |  | 2023-09-05 | 2023-09-05 | Government of the Philippines (current year's budget) | 225744 | 225744 |  | 225039 | 225039 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3175 | ELECTRICAL SUPPLIES | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-11 | 2023-08-14 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 15760 | 15760 |  | 15680 | 15680 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0614 | JANITORIAL SUPPLIES | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-11 | 2023-08-14 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 23626 | 23626 |  | 23061 | 23061 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2848 | COMPUTER SUPPLIES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-16 | 2023-08-17 |  |  | 2023-08-22 | 2023-08-22 | Government of the Philippines (current year's budget) | 3696 | 3696 |  | 3300 | 3300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3499 | JANITORIAL SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-03 | 2023-08-10 | 2023-08-11 |  |  | 2023-08-14 | 2023-08-14 | Government of the Philippines (current year's budget) | 64210 | 64210 |  | 64210 | 64210 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3346 | FOOD/CATERING SERVICES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | 2023-08-04 | 2023-08-11 | 2023-08-15 |  |  | 2023-11-24 | 2023-11-24 | Government of the Philippines (current year's budget) | 270000 | 270000 |  | 269250 | 269250 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0358 | DUPLICATING PRODUCTS/SPAREPARTS | PEEMO | No | Direct Contracting | N/A | 2023-06-22 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-22 | 2023-08-24 |  |  | 2023-10-02 | 2023-10-02 | Government of the Philippines (current year's budget) | 17053 | 17053 |  | 17053 | 17053 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2414 | OFFICE EQUIPMENT | SPO | No | Direct Contracting | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-10 | 2023-08-15 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 19000 | 19000 |  | 18000 | 18000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3271 | GAS | PEO | No | Direct Contracting | 2023-06-27 | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-10 | 2023-08-15 |  |  |  |  | Government of the Philippines (current year's budget) | 45075 | 45075 |  | 45075 | 45075 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3259 | GAS | PAGRO | No | Direct Contracting | 2023-06-27 | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-16 | 2023-08-17 |  |  | 2023-11-30 | 2023-11-30 | Government of the Philippines (current year's budget) | 39655 | 39655 |  | 21035 | 21035 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3001 | GAS | PAGRO | No | Direct Contracting | 2023-06-27 | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 3924 | 3924 |  | 3540 | 3540 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Cancelled
23-3454 | GAS | PDRRMO | No | Direct Contracting | 2023-06-27 | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-11 | 2023-08-15 |  |  |  |  | Government of the Philippines (current year's budget) | 21750 | 21750 |  | 13300 | 13300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0412 | GAS | PGSO | No | Direct Contracting | 2023-04-04 | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-22 | 2023-08-24 |  |  | 2023-09-28 | 2023-09-28 | Government of the Philippines (current year's budget) | 27592 | 27592 |  | 8165 | 8165 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3787 | GAS | PAGRO | No | Direct Contracting | N/A | 2023-07-04 |  | N/A | 2023-07-25 | 2023-07-25 |  | N/A | N/A | 2023-07-28 |  |  |  | N/A | 2023-08-22 | [5 empty] | Government of the Philippines (current year's budget) | 3924 | 3924 |  | 3540 | 3540 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-2811 | INSTALLATION OF STREETLIGHTS, POBLACION, MONTEVISTA | PEO | No | Competitive Bidding | 2023-07-25 | 2023-08-07 |  | 2023-08-22 | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-11-09 | 2023-11-21 |  |  |  | 2023-11-22 | 2023-11-23 | 2023-11-28 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 2985211.76 |  | 2985211.76 | 2979459.38 |  | 2979459.38 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3171 | CONSTRUCTION OF KIOKMAI SOCIAL HALL, KIOKMAI ES, BRGY. KIOKMAI, LAAK | PEO | No | Competitive Bidding | 2023-07-25 | 2023-08-07 |  | 2023-08-22 | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-11-09 | 2023-11-24 |  |  |  | 2023-11-22 | 2023-11-23 | 2023-11-28 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 1950688.46 |  | 1950688.46 | 1920777.81 |  | 1920777.81 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0590 | OFFICE SUPPLIES | PEO-MOTORPOOL | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-07-25 | 2023-07-31 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | 2023-11-22 | 2023-12-11 | 2023-12-18 |  |  | 2023-12-22 | 2023-12-22 | Government of the Philippines (current year's budget) | 54230 | 54230 |  | 54133.25 | 54133.25 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3385 | SPAREPARTS | PEO-MOTORPOOL | No | Direct Contracting | 2023-07-25 | 2023-07-31 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | N/A | 2023-10-26 | 2023-11-03 |  |  | 2023-11-10 | 2023-11-10 | Government of the Philippines (current year's budget) | 809504 | 809504 |  | 809504 | 809504 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3273 | OIL AND LUBRICANTS | PEO-MOTORPOOL | No | Competitive Bidding | 2023-07-25 | 2023-09-11 |  | 2023-09-19 | 2023-10-03 | 2023-10-03 |  | 2023-10-03 | 2023-10-06 | 2023-10-13 |  |  |  | 2023-10-17 | 2023-09-19 | 2023-09-20 |  |  | 2023-10-09 | 2023-10-09 | Government of the Philippines (current year's budget) | 4367830.5 | 4367830.5 |  | 2563900 | 2563900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3255 | TIRES | PEO-MOTORPOOL | No | Competitive Bidding | 2023-07-25 | 2023-07-31 |  | 2023-08-08 | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-25 | 2023-08-31 |  |  |  | 2023-09-08 | 2023-09-19 | 2023-09-20 |  |  | 2023-10-09 | 2023-10-09 | Government of the Philippines (current year's budget) | 3190400 | 3190400 |  | 2124000 | 2124000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-08-03 | 2023-08-18 | 2023-08-18 | 2023-08-18 | N/A | N/A | Completed
23-3826 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-13 | 2023-09-20 |  |  | 2023-09-20 | 2023-09-20 | Government of the Philippines (current year's budget) | 28480 | 28480 |  | 28480 | 28480 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3832 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-13 | 2023-09-14 |  |  | 2023-09-15 | 2023-09-15 | Government of the Philippines (current year's budget) | 900 | 900 |  | 900 | 900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3828 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-12 | 2023-09-14 |  |  | 2023-09-15 | 2023-09-15 | Government of the Philippines (current year's budget) | 162530 | 162530 |  | 162530 | 162530 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3827 | JOB OUT: WHEEL ALIGNMENT & BALANCING AND WIPER BLADE | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-13 | 2023-09-14 |  |  | 2023-09-15 | 2023-09-15 | Government of the Philippines (current year's budget) | 6500 | 6500 |  | 6500 | 6500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3846 | SPARE PARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-13 | 2023-09-14 |  |  | 2023-09-15 | 2023-09-15 | Government of the Philippines (current year's budget) | 6535 | 6535 |  | 6535 | 6535 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3895 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-14 | 2023-09-19 |  |  | 2023-09-19 | 2023-09-19 | Government of the Philippines (current year's budget) | 16350 | 16350 |  | 16350 | 16350 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3901 | STEERING SHAFT ASSY | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-14 | 2023-09-19 |  |  | 2023-09-20 | 2023-09-20 | Government of the Philippines (current year's budget) | 35000 | 35000 |  | 35000 | 35000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3885 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-13 | 2023-09-14 |  |  | 2023-09-15 | 2023-09-15 | Government of the Philippines (current year's budget) | 1650 | 1650 |  | 1650 | 1650 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0711 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-13 | 2023-09-14 |  |  | 2023-09-15 | 2023-09-15 | Government of the Philippines (current year's budget) | 5140 | 5140 |  | 5140 | 5140 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3866 | UPGRADING OF HOSPITAL BUILDING FACILITIES AT DDOPH-MARAGUSAN | PEO | No | Competitive Bidding | 2023-07-25 | 2023-08-05 |  | 2023-08-22 | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-11-09 | 2023-11-21 |  |  |  | 2023-11-22 | 2023-11-23 | 2023-11-28 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 1549654.01 | 1549654.01 |  | 1518903.01 | 1518903.01 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-08-18 | 2023-09-01 | 2023-09-01 | 2023-09-01 | N/A | N/A | Completed
23-4015 | WIPER BLADE (MITS STRADA) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-08 | 2023-09-12 |  |  | 2023-09-13 | 2023-09-13 | Government of the Philippines (current year's budget) | 1950 | 1950 |  | 1950 | 1950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0661 | SPARE PARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-06 | 2023-09-08 |  |  | 2023-09-11 | 2023-09-11 | Government of the Philippines (current year's budget) | 2880 | 2880 |  | 2880 | 2880 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3910 | SPAREPARTS | SPO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | 2023-09-01 | 2023-09-08 | 2023-09-13 |  |  | 2023-09-13 | 2023-09-13 | Government of the Philippines (current year's budget) | 91340 | 91340 |  | 91340 | 91340 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3911 | JOB OUT:DIAGNOSTIC ENGINE | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-06 | 2023-09-08 |  |  | 2023-09-08 | 2023-09-08 | Government of the Philippines (current year's budget) | 5400 | 5400 |  | 5400 | 5400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0562 | OFFICE SUPPLIES | SPO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-07-25 | 2023-07-31 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-20 |  |  |  | 2023-11-21 | 2023-12-01 | 2023-12-07 |  |  |  |  | Government of the Philippines (current year's budget) | 151866 | 151866 |  | 151866 | 151866 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0658 | CONSTRUCTION MATERIALS | PAGRO | No | Competitive Bidding | 2023-07-25 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-25 | 2023-09-04 |  |  |  | 2023-09-07 | 2023-09-14 | 2023-09-21 |  |  | 2023-10-09 | 2023-10-09 | Government of the Philippines (current year's budget) | 569777.93 | 569777.93 |  | 559575 | 559575 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-18 | 2023-08-18 | 2023-08-18 | N/A | N/A | Completed
23-3964 | SPARE PARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-30 |  |  |  | N/A | 2023-09-14 | 2023-09-19 |  |  | 2023-09-19 | 2023-09-19 | Government of the Philippines (current year's budget) | 12683 | 12683 |  | 12683 | 12683 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3830 | JOB ORDER | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-30 |  |  |  | N/A | 2023-09-13 | 2023-09-14 |  |  | 2023-09-15 | 2023-09-15 | Government of the Philippines (current year's budget) | 9000 | 9000 |  | 9000 | 9000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0630 | SPARE PARTS (HEAVY EQUIPMENT) | PGSO | No | Competitive Bidding | N/A | 2023-07-17 |  | N/A | 2023-07-25 | 2023-07-25 |  | 2023-07-25 | 2023-08-04 | 2023-08-10 |  |  |  | 2023-08-12 | 2023-08-24 | 2023-09-13 |  |  | 2023-09-22 | 2023-09-22 | Government of the Philippines (current year's budget) | 893275 | 893275 |  | 893275 | 893275 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-07-19 | 2023-07-19 | 2023-07-19 | N/A | N/A | Completed
23-3711 | FUEL, OIL AND LUBRICANTS | PGO | No | Competitive Bidding | N/A | 2023-07-10 |  | N/A | 2023-07-25 | 2023-07-25 |  | 2023-07-25 | 2023-08-04 | 2023-08-11 |  |  |  | 2023-08-15 | 2023-08-18 | 2023-08-22 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 243678 | 243678 |  | 243678 | 243678 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-07-19 | 2023-07-19 | 2023-07-19 | N/A | N/A | Completed
23-3338 | MONOBLOCK PLASTIC CHAIR | PGO | No | Competitive Bidding | N/A | 2023-07-10 |  | N/A | 2023-07-25 | 2023-07-25 |  | 2023-08-04 | 2023-08-04 | 2023-08-11 |  |  |  | 2023-08-15 | 2023-11-21 | 2023-11-30 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 267000 | 267000 |  | 267000 | 267000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-07-19 | 2023-07-19 | 2023-07-19 | N/A | N/A | Completed
23-2761 | DAO AND KAMAGONG SEEDLINGS | PDRRMO | No | Competitive Bidding | N/A | 2023-07-10 |  | N/A | 2023-07-25 | 2023-07-25 |  | 2023-07-25 | 2023-08-04 | 2023-08-11 |  |  |  | 2023-08-15 | 2023-08-22 | 2023-08-29 |  |  | 2023-09-18 | 2023-09-18 | Government of the Philippines (current year's budget) | 285000 | 285000 |  | 285000 | 285000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-07-19 | 2023-07-19 | 2023-07-19 | N/A | N/A | Completed
23-C0557 | PAINT (GLOSS LATEX-WHITE & QUICK DRY ENAMEL) | SEF | No | Competitive Bidding | N/A | 2023-06-26 |  | 2023-07-11 | 2023-07-25 | 2023-07-25 |  | 2023-07-25 | 2023-08-04 | 2023-08-11 |  |  |  | 2023-08-15 | 2023-08-22 | 2023-08-23 |  |  | 2023-09-07 | 2023-09-07 | Government of the Philippines (current year's budget) | 1899504 |  | 1899504 | 1899504 |  | 1899504 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-07-07 | 2023-07-19 | 2023-07-19 | 2023-07-19 | N/A | N/A | Completed
23-C0530 | CTNL (TROPONIN) AND HEMOGLOBIN | PEEMO | No | Competitive Bidding | 2023-07-13 | 2023-06-26 |  | N/A | 2023-07-25 | 2023-07-25 |  | 2023-07-25 | 2023-08-04 | 2023-08-11 |  |  |  | 2023-08-15 | 2023-08-22 | 2023-09-06 |  |  | 2023-09-25 | 2023-09-25 | Government of the Philippines (current year's budget) | 969608 | 969608 |  | 969608 | 969608 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-07-19 | 2023-07-19 | 2023-07-19 | N/A | N/A | Completed
23-2428 | VARIOUS SEEDLINGS | PDRRMO | No | Competitive Bidding | N/A | 2023-06-26 |  | N/A | 2023-07-25 | 2023-07-25 |  | 2023-07-25 | 2023-08-04 | 2023-08-11 |  |  |  | 2023-08-15 | 2023-08-22 | 2023-09-05 |  |  | 2023-10-13 | 2023-10-13 | Government of the Philippines (current year's budget) | 1276950 | 1276950 |  | 1276950 | 1276950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-07-19 | 2023-07-19 | 2023-07-19 | N/A | N/A | Completed
23-1927 | 1 LOT UPGRADING OF HOSPITAL BUILDING FACILITIES AT DDOPH-MONTEVISTA | PEO | No | Competitive Bidding | N/A | 2023-05-29 |  | 2023-06-06 | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-08-03 | 2023-08-11 |  |  |  | 2023-08-15 | 2023-08-18 | 2023-08-24 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 3321542.64 | 3321542.64 |  | 3317295.56 | 3317295.56 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-06-05 | 2023-06-16 | 2023-06-16 | 2023-06-16 | N/A | N/A | Completed
23-2629 | UPGRADING OH HOSPITAL BUILDING FACILITIES AT DDOPH-MONTEVISTA | PEO | No | Competitive Bidding | N/A | 2023-05-29 |  | 2023-06-06 | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-08-03 | 2023-08-11 |  |  |  | 2023-08-15 | 2023-08-18 | 2023-08-24 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 1805974.16 | 1805974.16 |  | 1801647.94 | 1801647.94 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-06-05 | 2023-06-16 | 2023-06-16 | 2023-06-16 | N/A | N/A | Completed
23-1928 | UPGRADING OF DAVAO DE ORO PROVINCIAL HOSPITAL-PANTUKAN | PEO | No | Competitive Bidding | N/A | 2023-05-29 |  | 2023-06-06 | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-08-03 | 2023-08-11 |  |  |  | 2023-08-12 | 2023-08-18 | 2023-08-24 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 1408940 |  | 1408940 | 1388810.65 |  | 1388810.65 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-06-05 | 2023-06-16 | 2023-06-16 | 2023-06-16 | N/A | N/A | Completed
23-1995 | CONSTRUCTION OF WATER SYSTEM LEVEL II, SITIO PONGPONG, BRGY. ANDAP, NEW BATAAN | PEO | No | Competitive Bidding | N/A | 2023-05-29 |  | 2023-06-06 | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-08-03 | 2023-08-10 |  |  |  | 2023-08-11 | 2023-08-18 | 2023-08-24 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 1001854.77 |  | 1001854.77 | 996654.66 |  | 996654.66 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-06-05 | 2023-06-16 | 2023-06-16 | 2023-06-16 | N/A | N/A | Completed
23-2519 | COMPLETION OF WATER SUPPLY SYSTEM AT PUROK 20 NURSERY, BARANGAY, NGAN, COMPOSTELA | PEO | No | Competitive Bidding | N/A | 2023-05-29 |  | 2023-06-06 | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-08-03 | 2023-08-10 |  |  |  | 2023-08-11 | 2023-08-18 | 2023-08-24 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 1872262.8 |  | 1872262.8 | 1866755.4 |  | 1866755.4 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-06-05 | 2023-06-16 | 2023-06-16 | 2023-06-16 | N/A | N/A | Completed
23-1830 | REHABILITATION OF DRAINAGE STRUCTURE AT ALEGRIA SECTION ALONG NABUNTURAN-GABI-COMPOSTELA ROAD | PEO | No | Competitive Bidding | 2023-03-21 | 2023-05-29 |  | 2023-06-06 | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-08-03 | 2023-08-10 |  |  |  | 2023-08-11 | 2023-08-18 | 2023-08-24 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 2268269.88 |  | 2268269.88 | 2218064.35 |  | 2218064.35 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-06-05 | 2023-06-16 | 2023-06-16 | 2023-06-16 | N/A | N/A | Completed
23-3331 | FOOD/CATERING SERVICES | PIAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-06-20 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-17 | 2023-08-18 |  |  | 2023-09-28 | 2023-09-28 | Government of the Philippines (current year's budget) | 15029 | 15029 |  | 14750 | 14750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-1924 | CONSTRUCTION SUPPLIES | PEO-GA | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-04 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-09-07 | 2023-09-07 | Government of the Philippines (current year's budget) | 39060 | 39060 |  | 38000 | 38000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0650 | CONSTRUCTION SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-22 | 2023-08-23 | 2023-08-29 |  |  | 2023-10-09 | 2023-10-09 | Government of the Philippines (current year's budget) | 90107.92 | 90107.92 |  | 90006.92 | 90006.92 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3753 | LUMBER | PAO-PRCSD | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-10-09 | 2023-10-09 | Government of the Philippines (current year's budget) | 19530 | 19530 |  | 19430.18 | 19430.18 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3056 | PAINTING MATERIALS | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-17 | 2023-08-22 |  |  | 2023-10-09 | 2023-10-09 | Government of the Philippines (current year's budget) | 2320 | 2320 |  | 2220 | 2220 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3601 | OFFICE EQUIPMENT | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-11 | 2023-08-22 | 2023-08-24 |  |  | 2023-08-31 | 2023-08-31 | Government of the Philippines (current year's budget) | 200000 | 200000 |  | 193800 | 193800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0662 | SPAREPARTS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-09-06 | 2023-09-06 | Government of the Philippines (current year's budget) | 44039.3 | 44039.3 |  | 44039.3 | 44039.3 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2899 | LUMBER | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-22 | 2023-08-22 | 2023-08-24 |  |  | 2023-08-31 | 2023-08-31 | Government of the Philippines (current year's budget) | 204842.59 | 204842.59 |  | 204743 | 204743 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3692 | LUMBER | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-10-19 | 2023-10-19 | Government of the Philippines (current year's budget) | 18032.02 | 18032.02 |  | 17932.27 | 17932.27 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3510 | LUMBER | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-10-19 | 2023-10-19 | Government of the Philippines (current year's budget) | 39495.98 | 39495.98 |  | 39395.14 | 39395.14 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3678 | JANITORIAL SUPPLIES | PICTO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-08-31 | 2023-08-31 | Government of the Philippines (current year's budget) | 33550 | 33550 |  | 33550 | 33550 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0615 | CONSTRUCTION SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-22 | 2023-08-22 | 2023-08-23 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 110240 | 110240 |  | 110148 | 110148 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3494 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-10-19 | 2023-10-19 | Government of the Philippines (current year's budget) | 13800 | 13800 |  | 13725 | 13725 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3656 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-18 | 2023-08-22 |  |  | 2023-10-06 | 2023-10-06 | Government of the Philippines (current year's budget) | 42780 | 42780 |  | 42780 | 42780 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3384 | SEEDS | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-18 | 2023-08-22 | 2023-09-05 |  |  | 2023-10-02 | 2023-10-02 | Government of the Philippines (current year's budget) | 121000 | 121000 |  | 120395 | 120395 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3051 | ELECTRICAL SUPPLIES | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-09-07 | 2023-09-07 | Government of the Philippines (current year's budget) | 960 | 960 |  | 946 | 946 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0644 | CONSTRUCTION SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 21036 | 21036 |  | 20973 | 20973 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0584 | CONSTRUCTION SUPPLIES | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-21 | 2023-08-22 | 2023-08-23 |  |  | 2023-09-07 | 2023-09-07 | Government of the Philippines (current year's budget) | 93545 | 93545 |  | 93440.5 | 93440.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0624 | PLUMBING SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-18 | 2023-08-18 | 2023-08-23 |  |  | 2023-09-07 | 2023-09-07 | Government of the Philippines (current year's budget) | 109509 | 109509 |  | 103396 | 103396 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3418 | CONSTRUCTION SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 49500 | 49500 |  | 49250 | 49250 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0621 | CONSTRUCTION SUPPLIES | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-09-07 | 2023-09-07 | Government of the Philippines (current year's budget) | 10120 | 10120 |  | 10069.5 | 10069.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0613 | AGRICIULTURAL SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-15 | 2023-08-22 | 2023-08-23 |  |  | 2023-09-04 | 2023-09-04 | Government of the Philippines (current year's budget) | 52294 | 52294 |  | 51440 | 51440 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0610 | OFFICE EQUIPMENT | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-11 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-18 | 2023-08-22 | 2023-08-23 |  |  | 2023-09-13 | 2023-09-13 | Government of the Philippines (current year's budget) | 196520 | 196520 |  | 196380 | 196380 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3486 | OTHER SUPPLIES/MATERIALS | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-07 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 14500 | 14500 |  | 14300 | 14300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0573 | AGRICULTURAL SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-21 | 2023-08-22 | 2023-08-23 |  |  | 2023-10-11 | 2023-10-11 | Government of the Philippines (current year's budget) | 398824 | 398824 |  | 394428 | 394428 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3025 | OTHER SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-09-01 | 2023-09-01 | Government of the Philippines (current year's budget) | 8400 | 8400 |  | 8393 | 8393 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2806 | DRUGS & MEDICINES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-10-20 | 2023-10-20 | Government of the Philippines (current year's budget) | 1900 | 1900 |  | 1896 | 1896 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0598 | SPAREPARTS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-15 | 2023-08-18 | 2023-08-22 |  |  | 2023-08-30 | 2023-08-30 | Government of the Philippines (current year's budget) | 77917 | 77917 |  | 77505 | 77505 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3680 | CONSTRUCTION EQUIPMENT | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 20000 | 20000 |  | 19900 | 19900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3335 | AGRICULTURAL SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-24 | 2023-08-29 |  |  | 2023-09-08 | 2023-09-08 | Government of the Philippines (current year's budget) | 26750 | 26750 |  | 26520 | 26520 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3661 | FOOD SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 20996 | 20996 |  | 20856 | 20856 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3174 | OIL AND LUBRICANTS | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-08-29 | 2023-08-29 | Government of the Philippines (current year's budget) | 13292.6 | 13292.6 |  | 12850 | 12850 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3189 | OIL AND LUBRICANTS | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-29 |  |  | 2023-08-30 | 2023-08-30 | Government of the Philippines (current year's budget) | 24524.4 | 24524.4 |  | 24000 | 24000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3603 | FIRE PROTECTION SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-09-07 | 2023-09-07 | Government of the Philippines (current year's budget) | 41140 | 41140 |  | 41100 | 41100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3491 | COMPUTER SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-23 |  |  | 2023-09-22 | 2023-09-22 | Government of the Philippines (current year's budget) | 22000 | 22000 |  | 21990 | 21990 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0533 | CONSTRUCTION SUPPLIES | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-23 | 2023-09-20 | 2023-09-29 |  |  | 2023-10-09 | 2023-10-09 | Government of the Philippines (current year's budget) | 80088.03 |  | 80088.03 | 79988.03 |  | 79988.03 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3470 | PRINTED FORMS | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-15 | 2023-08-22 | 2023-08-23 |  |  | 2023-10-06 | 2023-10-06 | Government of the Philippines (current year's budget) | 69720 | 69720 |  | 69720 | 69720 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3862 | FOOD/CATERING SERVICES | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | 2023-08-16 | 2023-08-16 | 2023-08-17 |  |  | 2023-08-20 | 2023-08-20 | Government of the Philippines (current year's budget) | 480000 | 480000 |  | 480000 | 480000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3646 | OFFICE SUPPLIES | PPDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-09-01 | 2023-09-04 |  |  | 2023-09-11 | 2023-09-11 | Government of the Philippines (current year's budget) | 46747.8 | 46747.8 |  | 45892 | 45892 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3536 | OFFICE SUPPLIES | PGSO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-07-17 |  | N/A | 2023-08-08 | 2023-08-08 |  | N/A | N/A | 2023-08-11 |  |  |  | N/A | 2023-08-22 | 2023-08-29 |  |  | 2023-09-26 | 2023-09-26 | Government of the Philippines (current year's budget) | 32340 | 32340 |  | 32200 | 32200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3171 | CONSTRUCTION OF KIOKMAI SOCIAL HALL, KIOKMAI ES, BRGY. KIOKMAI, LAAK | SEF | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | 2023-08-22 | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-09-11 | 2023-11-21 |  |  |  | 2023-11-22 | 2023-11-23 | 2023-11-28 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 1950688.46 |  | 1950688.46 | 1920777.81 |  | 1920777.81 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-08-18 | 2023-09-01 | 2023-09-01 | 2023-09-01 | N/A | N/A | Completed
23-3663 | 1 LOT CONSTRUCTION OF SAN JOSE-LEBANON ROAD SECTION, MONTEVISTA | PEO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | 2023-08-22 | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-09-11 | 2023-11-21 |  |  |  | 2023-11-22 | 2023-11-23 | 2023-11-28 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 14687275.25 |  | 14687275.25 | 14656814.06 |  | 14656814.06 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-08-18 | 2023-09-01 | 2023-09-01 | 2023-09-01 | N/A | N/A | Completed
23-3765 | 1 LOT CONCRETING OF ROAD AND CONSTRUCTION OF LINE CANAL AT SAN FRANCISCO ST. BRGY. KINGKING, PANTUKAN, DAVAO , DE ORO | PEO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | 2023-08-22 | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-09-11 | 2023-11-21 |  |  |  | 2023-11-22 | 2023-11-28 | 2023-11-28 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 7520117.89 |  | 7520117.89 | 7514927.34 |  | 7514927.34 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-08-18 | 2023-09-01 | 2023-09-01 | 2023-09-01 | N/A | N/A | Completed
23-4012 | MEDICAL KIT | SEF | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-11-12 | 2023-11-23 |  |  | 2023-12-14 | 2023-12-14 | Government of the Philippines (current year's budget) | 1925 | 1925 |  | 1924 | 1924 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2614 | JOB ORDER: REPAIR OF HEAVY EQUIPMENT | PEO-MOTORPOOL | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-09-14 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-11 | 2023-12-14 |  |  |  |  | Government of the Philippines (current year's budget) | 20000 | 20000 |  | 19700 | 19700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3866 | 1 LOT UPGRADING OF HOSPITAL BUILDING FACILITIES AT DDOPH-MARAGUSAN | PEO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | 2023-08-22 | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-09-11 | 2023-11-24 |  |  |  | 2023-11-22 | 2023-11-23 | 2023-11-28 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 2853622.33 | 2853622.33 |  | 2823624.73 | 2823624.73 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-08-18 | 2023-09-01 | 2023-09-01 | 2023-09-01 | N/A | N/A | Completed
23-3662 | 1 LOT CONSTRUCTION OF TRIBAL HALL BARANAGAY NEQ BARILI, MACO | PEO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | 2023-08-22 | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-09-11 | 2023-11-24 |  |  |  | 2023-11-22 | 2023-11-23 | 2023-11-28 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 1596975.09 |  | 1596975.09 | 1591994.57 |  | 1591994.57 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-08-18 | 2023-09-01 | 2023-09-01 | 2023-09-01 | N/A | N/A | Completed
23-3489 | 1 LOT REHABILITATION/IMPROVEMENT OF DAVAO DE ORO FARM, PASIAN, MONKAYO | PEO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | 2023-08-22 | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-11-09 | 2023-11-24 |  |  |  | 2023-11-22 | 2023-11-23 | 2023-11-28 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 4956202.58 |  | 4956202.58 | 4935795.26 |  | 4935795.26 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-08-18 | 2023-09-01 | 2023-09-01 | 2023-09-01 | N/A | N/A | Completed
23-3861 | 1 LOT CONSTRUCTION OF MULTIPURPOSE BUILDING AT CASOON ELEMENTARY SCHOOL, MONKAYO | PEO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | 2023-08-22 | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-11-09 | 2023-11-24 |  |  |  | 2023-11-22 | 2023-11-23 | 2023-11-28 |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 4920447.4 |  | 4920447.4 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-08-18 | 2023-09-01 | 2023-09-01 | 2023-09-01 | N/A | N/A | Completed
23-3050 | MICROSOFT 365 FAMILY ACCOUNT | PAO-INVESTMENT | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-14 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-26 | [5 empty] | Government of the Philippines (current year's budget) | 4699 | 4699 |  | 4699 | 4699 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0709 | OTHER SUPPLIES/MATERIALS | PAO | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-14 |  | N/A | 2023-09-05 | 2023-09-05 |  | N/A | N/A | 2023-09-08 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-10-12 | 2023-10-12 | Government of the Philippines (current year's budget) | 13514 | 13514 |  | 13308 | 13308 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3936 | ACETYLENE REFILL AND INDUSTRIAL OXYGEN REFILL | PAO | No | Direct Contracting | 2023-08-08 | 2023-08-14 |  | N/A | 2023-09-05 | 2023-09-05 |  | N/A | N/A | 2023-09-08 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-12-05 | 2023-12-05 | Government of the Philippines (current year's budget) | 4455 | 4455 |  | 2285 | 2285 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0699 | OFFICE SUPPLIES | PAO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-08-08 | 2023-09-06 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | 2023-10-13 | 2023-10-13 | 2023-10-18 |  |  | 2023-10-25 | 2023-10-25 | Government of the Philippines (current year's budget) | 83877 | 83877 |  | 81958 | 81958 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0719 | COMPUTER SUPPLIES/SPARE PARTS | PAO | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-14 |  | N/A | 2023-09-05 | 2023-09-05 |  | N/A | N/A | 2023-09-08 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-10-12 | 2023-10-12 | Government of the Philippines (current year's budget) | 12372 | 12372 |  | 12310 | 12310 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3599 | UPS W/ BUILT-IN AVR, 600 VA AND VOICE RECORDER 2GB BUILT-IN MEMORY AND MEMORY CARD | PGO-BAC | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-09-14 |  | N/A | 2023-07-11 | 2023-07-11 |  | N/A | N/A | 2023-07-20 |  |  |  | N/A | 2023-11-23 | 2023-11-28 |  |  | 2023-12-04 | 2023-12-04 | Government of the Philippines (current year's budget) | 7083 | 7083 |  | 5085 | 5085 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4056 | FOOD SUPPLIES | PGO | No | NP-53.5 Agency-to-Agency | 2023-08-08 | 2023-08-10 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-23 | 2023-08-29 | 2023-08-29 |  |  | 2023-09-20 | 2023-09-20 | Government of the Philippines (current year's budget) | 450000 | 450000 |  | 450000 | 450000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0725 | SPAREPARTS PLATE # 13008-CADS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-07-20 |  |  |  | N/A | 2023-12-13 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 25000 | 25000 |  | 25000 | 25000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4082 | GEMELINA LUMBER OR EQUIVALENT | PEO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-24 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-18 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 4700 | 4700 |  | 4700 | 4700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0676 | JANITORIAL SUPPLIES | PEEMO | No | Competitive Bidding | 2023-08-22 | 2023-08-29 |  | N/A | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-10-06 | 2023-10-13 |  |  |  | 2023-10-18 | 2023-10-26 | 2023-11-15 |  |  | 2023-12-04 | 2023-12-04 | Government of the Philippines (current year's budget) | 663166 | 663166 |  | 480869.05 | 480869.05 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0682 | CONSTRUCTION MATERIALS | PEEMO | No | Competitive Bidding | 2023-08-22 | 2023-08-29 |  | N/A | 2023-10-17 | 2023-10-17 |  | 2023-10-17 | 2023-11-20 | 2023-11-15 |  |  |  | 2023-11-17 | 2023-11-29 | 2023-11-30 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 375363 | 375363 |  | 374897 | 374897 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4198 | PRESSURE TANK 220 gals | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-24 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-17 |  |  | 2023-10-24 | 2023-10-24 | Government of the Philippines (current year's budget) | 25500 | 25500 |  | 25500 | 25500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3893 | ALUMINUM FOLDING LADDER- HEAVY DUTY | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 11000 | 11000 |  | 10500 | 10500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3920 | CLOTH SATIN-GOLD AND RED | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-24 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-18 |  |  | 2023-10-25 | 2023-10-25 | Government of the Philippines (current year's budget) | 4000 | 4000 |  | 4000 | 4000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4004 | DOCUMENT SCANNER | PBO | No | Competitive Bidding | 2023-08-22 | 2023-08-29 |  | N/A | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-10-12 | 2023-10-27 |  |  |  | 2023-10-27 | 2023-11-13 | 2023-11-30 |  |  |  |  | Government of the Philippines (current year's budget) | 200000 | 200000 |  | 194888 | 194888 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4006 | MEALS VIP AND SNACKS | PBO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-23 | 2023-10-24 |  |  | 2023-11-14 | 2023-11-14 | Government of the Philippines (current year's budget) | 29225 | 29225 |  | 28782 | 28782 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2736 | MEALS WITH ACCOMMODATION | PAO-IPRD | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-11-13 |  | N/A | 2023-12-05 | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 48300 | 48300 |  | 48195 | 48195 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Awarded with issued Notice of Award
23-4151 | AIRCONDITIONING UNIT | PAO | No | Competitive Bidding | 2023-08-22 | 2023-09-04 |  | N/A | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-10-12 | 2023-10-27 |  |  |  | 2023-11-08 | 2023-11-13 | 2023-11-16 |  |  | 2023-11-30 | 2023-11-30 | Government of the Philippines (current year's budget) | 304336 | 304336 |  | 237716 | 237716 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0716 | MINERAL WATER, 5 GAL | PGO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | 2023-10-17 | 2023-10-26 | 2023-11-07 |  |  |  |  | Government of the Philippines (current year's budget) | 119925 | 119925 |  | 117000 | 117000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3204 | BOARD WITH RING 4*4 | PGO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | 2023-11-21 | 2023-11-23 | 2023-11-28 |  |  | 2023-11-29 | 2023-11-29 | Government of the Philippines (current year's budget) | 97900 | 97900 |  | 97350 | 97350 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0543 | RICE (WELL MILLED) | PGO | No | Competitive Bidding | 2023-08-22 | 2023-08-28 |  | 2023-09-05 | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-10-12 | 2023-11-15 |  |  |  | 2023-11-21 | 2023-11-23 | 2023-12-20 |  |  | 2023-12-22 | 2023-12-22 | Government of the Philippines (current year's budget) | 1282500 | 1282500 |  | 1231200 | 1231200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-09-01 | 2023-09-22 | 2023-09-22 | 2023-09-22 | N/A | N/A | Completed
23-4047 | AIRCON WINDOW TYPE 2.0hp | PLO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | N/A | 2023-11-13 | 2023-11-16 |  |  | 2023-11-20 | 2023-11-20 | Government of the Philippines (current year's budget) | 49500 | 49500 |  | 44895 | 44895 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3940 | JOB ORDER(REHABILITATION OF 80 FT ANTENNA TOWER WITH SPECIFICATIONS | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-09-07 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-14 | 2023-12-27 | [5 empty] | Government of the Philippines (current year's budget) | 300000 | 300000 |  | 272000 | 272000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0581 | HEAVY SNACKS (VIP) (A) (B) | PHO | No | Competitive Bidding | 2023-08-22 | 2023-08-29 |  | N/A | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-09-29 | 2023-10-12 |  |  |  | 2023-10-13 | 2023-10-16 | 2023-10-24 |  |  | 2023-10-27 | 2023-10-27 | Government of the Philippines (current year's budget) | 352070 | 352070 |  | 347658 | 347658 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-09-22 | 2023-09-22 | 2023-09-22 | N/A | N/A | Completed
23-3804 | UNIFORM, ATHLETES | SEF | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | 2023-11-22 | [6 empty] | Government of the Philippines (current year's budget) | 300000 | 300000 |  | 299400 | 299400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0698 | BROCHURE, THREE FOLD-A4 SIZE AND MAGAZINE PRINTING | PAO | No | Competitive Bidding | 2023-08-22 | 2023-08-29 |  | N/A | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-09-29 | 2023-10-09 |  |  |  | 2023-10-09 | 2023-10-13 | 2023-10-24 |  |  | 2023-12-22 | 2023-12-22 | Government of the Philippines (current year's budget) | 352400 | 352400 |  | 261991.5 | 261991.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-09-22 | 2023-09-22 | 2023-09-22 | N/A | N/A | Completed
23-3987 | SERVER W/ COMPLETE ACCESSORIES | PICTO | No | Competitive Bidding | 2023-08-22 | 2023-08-29 |  | 2023-09-05 | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-10-12 | 2023-11-10 |  |  |  | 2023-11-10 | 2023-11-28 | 2023-11-29 |  |  |  |  | Government of the Philippines (current year's budget) | 1947956 | 1947956 |  | 1800000 | 1800000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-09-01 | 2023-09-22 | 2023-09-22 | 2023-09-22 | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4131 | CLOUD SERVER SUBSCRIPTION | PICTO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-20 |  |  |  | 2023-10-20 | 2023-11-21 | 2023-11-23 |  |  | 2023-12-20 | 2023-12-20 | Government of the Philippines (current year's budget) | 245000 | 245000 |  | 245000 | 245000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3366 | ELECTRICAL SUPPLIES | PGSO | No | Competitive Bidding | N/A | 2023-07-24 |  | N/A | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-09-01 | 2023-08-31 |  |  |  | 2023-09-05 | 2023-09-13 | 2023-09-25 |  |  | 2023-10-04 | 2023-10-04 | Government of the Philippines (current year's budget) | 304230 | 304230 |  | 251115 | 251115 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-03 | 2023-08-03 | 2023-08-03 | N/A | N/A | Completed
23-3690 | CONSTRUCTION SUPPLIES | PEO | No | Competitive Bidding | N/A | 2023-07-31 |  | N/A | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-18 | 2023-08-31 |  |  |  | 2023-09-01 | 2023-09-08 | 2023-09-11 |  |  | 2023-09-25 | 2023-09-25 | Government of the Philippines (current year's budget) | 557859.75 | 557859.75 |  | 510390 | 510390 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-03 | 2023-08-03 | 2023-08-03 | N/A | N/A | Completed
23-3477 | CONSTRUCTION SUPPLIES | PEO | No | Competitive Bidding | N/A | 2023-07-31 |  | N/A | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-18 | 2023-08-31 |  |  |  | 2023-09-01 | 2023-09-08 | 2023-09-11 |  |  | 2023-10-26 | 2023-10-26 | Government of the Philippines (current year's budget) | 895416.5 | 895416.5 |  | 738130 | 738130 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-03 | 2023-08-03 | 2023-08-03 | N/A | N/A | Completed
23-C0612 | COMPUTER DESKTOP (HIGH END) LAPTOP (MID RANGE) | PAGRO | No | Competitive Bidding | N/A | 2023-07-31 |  | N/A | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-18 | 2023-08-31 |  |  |  | 2023-09-01 | 2023-09-12 | 2023-09-14 |  |  | 2023-09-20 | 2023-09-20 | Government of the Philippines (current year's budget) | 334400 | 334400 |  | 326600 | 326600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-03 | 2023-08-03 | 2023-08-03 | N/A | N/A | Completed
23-3783 | GARMENTS | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-13 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-08 | 2023-09-11 |  |  | 2023-09-20 | 2023-09-20 | Government of the Philippines (current year's budget) | 40040 | 40040 |  | 39936 | 39936 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3750 | FOOD/CATERING SERVICES | PHRMDO | No | NP-53.9 - Small Value Procurement | 2023-08-15 | 2023-08-17 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | 2023-09-01 | 2023-09-08 | 2023-09-11 |  |  | 2023-09-22 | 2023-09-22 | Government of the Philippines (current year's budget) | 98725 | 98725 |  | 97075 | 97075 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3305 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-06-27 | 2023-07-04 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-13 | 2023-09-14 |  |  | 2023-09-15 | 2023-09-15 | Government of the Philippines (current year's budget) | 11700 | 11700 |  | 11700 | 11700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0593 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-06-20 | 2023-07-22 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-12 | 2023-09-14 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 5730 | 5730 |  | 5730 | 5730 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3805 | OFFICE SUPPLIES | SEF | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-08-03 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-10-13 | 2023-10-18 |  |  | 2023-11-10 | 2023-11-10 | Government of the Philippines (current year's budget) | 33890 | 33890 |  | 32576 | 32576 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3465 | JOB ORDER: LABOR, MATERIALS AND EQUIPMENT | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-06 | 2023-09-09 |  |  | 2023-09-12 | 2023-09-12 | Government of the Philippines (current year's budget) | 49500 | 49500 |  | 49457 | 49457 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3860 | OTHER SUPPLIES/MATERIALS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-13 | 2023-09-14 |  |  | 2023-09-22 | 2023-09-22 | Government of the Philippines (current year's budget) | 5610 | 5610 |  | 5604 | 5604 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3918 | PRINTING | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-08 | 2023-09-11 |  |  | 2023-09-11 | 2023-09-11 | Government of the Philippines (current year's budget) | 1792 | 1792 |  | 1664 | 1664 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4018 | PRINTING | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-10-11 | 2023-10-12 |  |  | 2023-10-23 | 2023-10-23 | Government of the Philippines (current year's budget) | 1792 | 1792 |  | 1664 | 1664 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3658 | JANITORIAL SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-07 | 2023-09-11 |  |  | 2023-09-13 | 2023-09-13 | Government of the Philippines (current year's budget) | 4800 | 4800 |  | 4750 | 4750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3158 | OTHER SUPPLIES/MATERIALS | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-10-16 | 2023-10-18 |  |  | 2023-11-28 | 2023-11-28 | Government of the Philippines (current year's budget) | 24000 | 24000 |  | 21600 | 21600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4120 | OTHER SUPPLIES/MATERIALS | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-08 | 2023-09-11 |  |  | 2023-09-20 | 2023-09-20 | Government of the Philippines (current year's budget) | 30300 | 30300 |  | 30300 | 30300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3865 | OTHER SUPPLIES/MATERIALS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-13 | 2023-09-14 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 10500 | 10500 |  | 8400 | 8400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0555 | FOOD/CATERING SERVICES | PGO | No | NP-53.1 Two Failed Biddings | N/A | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | 2023-09-01 | 2023-09-12 | 2023-09-14 |  |  | 2023-10-18 | 2023-10-18 | Government of the Philippines (current year's budget) | 508500 | 508500 |  | 505000 | 505000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0712 | DUPLICATING PRODUCTS | SPO | No | Direct Contracting | N/A | 2023-07-31 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | 2023-09-01 | 2023-09-08 | 2023-09-13 |  |  | 2023-10-02 | 2023-10-02 | Government of the Philippines (current year's budget) | 70702 | 70702 |  | 67622 | 67622 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3619 | FOOD/CATERING SERVICES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-19 | 2023-09-20 |  |  | 2023-11-22 | 2023-11-22 | Government of the Philippines (current year's budget) | 249900 | 249900 |  | 249900 | 249900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-0206 | OFFICE EQUIPMENT | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  |  |  | Government of the Philippines (current year's budget) | 12000 | 12000 |  | 11998 | 11998 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4071 | PRINTING | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-09-20 | 2023-09-20 | Government of the Philippines (current year's budget) | 5600 | 5600 |  | 5400 | 5400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3691 | PRINTING | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 1792 | 1792 |  | 1728 | 1728 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4011 | PRINTING | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-10-11 | 2023-10-12 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 1792 | 1792 |  | 1792 | 1792 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0710 | CONSTRUCTION SUPPLIES | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-14 | 2023-09-19 |  |  | 2023-12-27 | 2023-12-27 | Government of the Philippines (current year's budget) | 185500 | 185500 |  | 181796.5 | 181796.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0728 | PAINTING MATERIALS | PESO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-22 |  |  | 2023-10-10 | 2023-10-10 | Government of the Philippines (current year's budget) | 4419 | 4419 |  | 4330.7 | 4330.7 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0647 | CONSTRUCTION MATERIALS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-19 | 2023-09-20 |  |  | 2023-09-22 | 2023-09-22 | Government of the Philippines (current year's budget) | 268905.6 | 268905.6 |  | 199867 | 199867 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0727 | CONSTRUCTION SUPPLIES | PESO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-22 |  |  | 2023-10-10 | 2023-10-10 | Government of the Philippines (current year's budget) | 37806 | 37806 |  | 35537.1 | 35537.1 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4149 | OFFICE EQUIPMENT | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-17 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-14 | 2023-09-19 |  |  | 2023-10-02 | 2023-10-02 | Government of the Philippines (current year's budget) | 49500 | 49500 |  | 45495 | 45495 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3751 | PRINTING | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-19 | 2023-09-20 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 84000 | 84000 |  | 83700 | 83700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0684 | PRINTING | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  |  |  | Government of the Philippines (current year's budget) | 32200 | 32200 |  | 31050 | 31050 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3511 | PRINTING | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-20 | 2023-09-22 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 1792 | 1792 |  | 1728 | 1728 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2896 | PRINTING | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 1792 | 1792 |  | 1728 | 1728 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3834 | PRINTING | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-20 | 2023-09-22 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 3584 | 3584 |  | 3456 | 3456 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0726 | CONSTRUCTION SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-19 | 2023-09-22 |  |  | 2023-10-10 | 2023-10-10 | Government of the Philippines (current year's budget) | 186029 | 186029 |  | 182316.4 | 182316.4 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2751 | SPAREPARTS | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-28 | 2023-09-29 |  |  | 2023-10-04 | 2023-10-04 | Government of the Philippines (current year's budget) | 13060 | 13060 |  | 12680 | 12680 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3682 | JOB ORDER (LABOR & MATERIALS) | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-19 | 2023-09-20 |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 134500 | 134500 |  | 134500 | 134500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3915 | PRINTING | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 19600 | 19600 |  | 18900 | 18900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2918 | PRINTING | PEO | No | NP-53.9 - Small Value Procurement | 2023-07-25 | 2023-07-31 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-20 | 2023-09-22 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 1732 | 1732 |  | 1728 | 1728 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0633 | OFFICE EQUIPMENT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-19 | 2023-09-20 |  |  | 2023-10-16 | 2023-10-16 | Government of the Philippines (current year's budget) | 61500 | 61500 |  | 61300 | 61300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0542 | RESCUE TOOLS AND EQUIPMENT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-19 | 2023-09-20 |  |  | 2023-11-06 | 2023-11-06 | Government of the Philippines (current year's budget) | 84800 | 84800 |  | 84714 | 84714 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3847 | OFFICE EQUIPMENT | PPDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-15 | 2023-09-19 |  |  | 2023-10-13 | 2023-10-13 | Government of the Philippines (current year's budget) | 50000 | 50000 |  | 49900 | 49900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3967 | ELECTRICAL SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-15 | 2023-09-19 |  |  | 2023-10-04 | 2023-10-04 | Government of the Philippines (current year's budget) | 95000 | 95000 |  | 94000 | 94000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3952 | OTHER SUPPLIES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-19 | 2023-09-20 |  |  |  |  | Government of the Philippines (current year's budget) | 113400 | 113400 |  | 108000 | 108000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4102 | SPAREPARTS | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-14 | 2023-09-19 |  |  | 2023-10-17 | 2023-10-17 | Government of the Philippines (current year's budget) | 25800 | 25800 |  | 25600 | 25600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2146 | FEEDS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-10-11 | 2023-10-11 | Government of the Philippines (current year's budget) | 48300 | 48300 |  | 47800 | 47800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3837 | LUMBER | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-20 | 2023-09-22 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 23625.49 | 23625.49 |  | 23625.49 | 23625.49 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3050 | MICROSOFT 365 FAMILY ACCOUNT | PAO-INVESTMENT | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-14 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-10-26 | [5 empty] | Government of the Philippines (current year's budget) | 4699 | 4699 |  | 4699 | 4699 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4045 | INTERNET SUBSCRIPTION 4mbps | PAO | No | Direct Contracting | 2023-09-19 | 2023-10-06 |  | N/A | 2023-12-19 | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 233016 | 233016 |  | 219520 | 219520 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0709 | OTHER SUPPLIES/MATERIALS | PAO | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-14 |  | N/A | 2023-09-05 | 2023-09-05 |  | N/A | N/A | 2023-09-08 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-10-12 | 2023-10-12 | Government of the Philippines (current year's budget) | 13514 | 13514 |  | 13308 | 13308 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3936 | ACETYLENE REFILL AND INDUSTRIAL OXYGEN REFILL | PAO | No | Direct Contracting | 2023-08-08 | 2023-08-14 |  | N/A | 2023-09-05 | 2023-09-05 |  | N/A | N/A | 2023-09-08 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-12-05 | 2023-12-05 | Government of the Philippines (current year's budget) | 4455 | 4455 |  | 2285 | 2285 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0699 | OFFICE SUPPLIES | PAO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-08-08 | 2023-09-06 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | 2023-10-13 | 2023-10-13 | 2023-10-18 |  |  | 2023-10-25 | 2023-10-25 | Government of the Philippines (current year's budget) | 83877 | 83877 |  | 81958 | 81958 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0719 | COMPUTER SUPPLIES/SPARE PARTS | PAO | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-14 |  | N/A | 2023-09-05 | 2023-09-05 |  | N/A | N/A | 2023-09-08 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-10-12 | 2023-10-12 | Government of the Philippines (current year's budget) | 12372 | 12372 |  | 12310 | 12310 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3599 | UPS W/ BUILT-IN AVR, 600VAA AND VOICE RECORDER 2GB BUILT-IN MEMORY AND MEMORY CARD | PGO | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-09-14 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-23 | 2023-11-28 |  |  | 2023-12-04 | 2023-12-04 | Government of the Philippines (current year's budget) | 7083 | 7083 |  | 5085 | 5085 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4056 | RICE , NFA (50 KGS) | SEF | No | NP-53.5 Agency-to-Agency | 2023-08-08 | 2023-08-10 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-23 | 2023-08-29 | 2023-08-29 |  |  | 2023-09-20 | 2023-09-20 | Government of the Philippines (current year's budget) | 450000 | 450000 |  | 450000 | 450000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3156 | SOLAR LED LIGHTS (WATT : 300w, SOLAR PANEL:15w | PGO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | 2023-08-22 | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-09-29 | 2023-11-09 |  |  |  | 2023-11-09 | 2023-11-29 | 2023-12-12 |  |  |  |  | Government of the Philippines (current year's budget) | 3300000 | 3300000 |  | 2970000 | 2970000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-08-18 | 2023-09-01 | 2023-09-01 | 2023-09-01 | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4008 | COMPUTER WITH PRINTER & COMPLETE ACCESSORIES | PAO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-25 | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-19 | 2023-09-29 |  |  | 2023-10-13 |  | Government of the Philippines (current year's budget) | 493590 | 493590 |  | 454200 | 454200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-18 | 2023-08-18 | 2023-08-18 | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4005 | CCTV SYSTEM AT BAHAY PAG ASA AND PGSO WAREHOUSE | PICTO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-25 | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-14 | 2023-09-29 |  |  |  |  | Government of the Philippines (current year's budget) | 334418 | 334418 |  | 320858 | 320858 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-18 | 2023-08-18 | 2023-08-18 | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3446 | AIRCON SPLIT TYPE WALL MOUNTED 3.0 hp | PGO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-25 | 2023-09-04 |  |  |  | 2023-09-08 | 2023-10-03 | 2023-10-10 |  |  | 2023-10-17 | 2023-10-17 | Government of the Philippines (current year's budget) | 495000 | 495000 |  | 495000 | 495000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-18 | 2023-08-18 | 2023-08-18 | N/A | N/A | Completed
23-3807 | MEALS AND SNACKS WITH ACCOMMODATION A | SEF | No | NP-53.1 Two Failed Biddings | 2023-08-08 | 2023-09-28 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | 2023-10-24 | 2023-11-21 | 2023-12-11 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 598650 | 598650 |  | 597115 | 597115 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4044 | FURNITURE & FIXTURES | PLO | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-14 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | 2023-10-16 | 2023-10-16 | 2023-10-18 |  |  | 2023-11-16 | 2023-11-16 | Government of the Philippines (current year's budget) | 56686 | 56686 |  | 53910 | 53910 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4060 | BRAKE PAD, FOR N-URVN-YD25 1101-1010746 | DDOPH-MARAGUSAN | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-14 | 2023-09-19 |  |  | 2023-09-20 | 2023-09-20 | Government of the Philippines (current year's budget) | 5600 | 5600 |  | 5600 | 5600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4062 | BRAKE PAD 1101-544126 | DDOPH-MARAGUSAN | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-14 | 2023-09-19 |  |  | 2023-09-20 | 2023-09-20 | Government of the Philippines (current year's budget) | 5600 | 5600 |  | 5600 | 5600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4061 | BRAKE PAD 1312-440074 | DDOPH-MARAGUSAN | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-14 | 2023-09-19 |  |  | 2023-09-19 | 2023-09-19 | Government of the Philippines (current year's budget) | 5600 | 5600 |  | 5600 | 5600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3999 | BRAKE PAD AND BRAKE SHOE PLATE NO. 1101-1052101-CADS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-13 | 2023-09-14 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 900 | 900 |  | 900 | 900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0702 | CONSTRUCTION MATERIALS | PGSO | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-28 | 2023-09-29 |  |  | 2023-10-06 | 2023-10-06 | Government of the Philippines (current year's budget) | 171308 | 171308 |  | 126737 | 126737 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4051 | PUBLICATION AND ORDINANCE | SPO | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-14 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-09 |  |  |  | 2023-10-09 | 2023-11-16 | 2023-11-20 |  |  | 2023-12-11 | 2023-12-11 | Government of the Philippines (current year's budget) | 138000 | 138000 |  | 134987 | 134987 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4016 | SPARE PARTS FOR THE USE OF PLATE NO. 1101-366322 | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | 2023-09-01 | 2023-09-06 | 2023-09-08 |  |  | 2023-09-08 | 2023-09-08 | Government of the Philippines (current year's budget) | 56370 | 56370 |  | 56370 | 56370 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3951 | CRANKSHAFT PULLEY ASSAY (ISUZU FORWARD) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-06 | 2023-09-14 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 39000 | 39000 |  | 39000 | 39000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
[9 empty] | 0 | [30 empty] | Completed
23-C0622 | MEALS AND SNACKS A B WIHTOUT VENUE | PSWDO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-25 | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-19 | 2023-09-26 |  |  | 2023-10-17 | 2023-10-17 | Government of the Philippines (current year's budget) | 393641 | 393641 |  | 384248 | 384248 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4000 | SPARE PARTS FOR THE USE OF PLATE NO. 1101-130000 | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-14 | 2023-09-19 |  |  | 2023-09-19 | 2023-09-19 | Government of the Philippines (current year's budget) | 12800 | 12800 |  | 12800 | 12800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3998 | SPARE PARTS FOR THE USE OF PLATE NO 1101-395923 | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-14 | 2023-09-19 |  |  | 2023-09-19 | 2023-09-19 | Government of the Philippines (current year's budget) | 3000 | 3000 |  | 3000 | 3000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3994 | CCTV SYSTEM AT CAPITOL COMPOUND | PICTO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-25 | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-12 | 2023-09-29 |  |  |  |  | Government of the Philippines (current year's budget) | 991683 | 991683 |  | 909574 | 909574 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-31 | 2023-08-31 | 2023-08-31 | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3942 | LOT 1 IPPBX AND PUBLIC ADDRESS SYSTEM FOR CAPITOL BUILDING LOT 2 FOR PROVINCIAL HOSPITAL | PICTO | No | Competitive Bidding | 2023-08-08 | 2023-09-11 |  | 2023-09-19 | 2023-10-03 | 2023-10-03 |  | 2023-10-03 | 2023-10-12 | 2023-10-27 |  |  |  | 2023-11-10 | 2023-11-21 | 2023-12-14 |  |  |  |  | Government of the Philippines (current year's budget) | 1840000 | 1840000 |  | 1433610 | 1433610 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-09-22 | 2023-10-12 | 2023-10-12 | 2023-10-12 | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3980 | LED PANEL FOR BILLBOARD | PICTO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | N/A | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-09-08 | 2023-09-13 |  |  |  | 2023-09-13 | 2023-09-20 | 2023-09-22 |  |  | 2023-11-16 | 2023-11-16 | Government of the Philippines (current year's budget) | 2300000 | 2300000 |  | 2300000 | 2300000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-09-08 | 2023-09-08 | 2023-09-08 | N/A | N/A | Completed
23-4001 | SPARE PARTS FOR THE USE OF PLATE NO. 1101-1052183 | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-08 | 2023-08-17 |  | N/A | 2023-08-22 | 2023-08-22 |  | N/A | N/A | 2023-08-31 |  |  |  | N/A | 2023-09-12 | 2023-09-14 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 4710 | 4710 |  | 4710 | 4710 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3043 | FOOD SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-09-25 | 2023-09-25 | Government of the Philippines (current year's budget) | 26400 | 26400 |  | 25960 | 25960 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4122 | LUMBER, COCO OR EQUIVALENT | PHRMDO | No | NP-53.9 - Small Value Procurement | 2023-08-15 | 2023-08-17 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-12 | 2023-09-13 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 15964 | 15964 |  | 15257.9 | 15257.9 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0645 | VETERINARY DRUG AND BIOLOGICS | PVO | No | Competitive Bidding | N/A | 2023-07-10 |  | N/A | 2023-07-25 | 2023-07-25 |  | 2023-07-25 | 2023-08-11 | 2023-08-22 |  |  |  | 2023-08-25 | 2023-08-31 | 2023-09-11 |  |  | 2023-09-20 | 2023-09-20 | Government of the Philippines (current year's budget) | 663765 | 663765 |  | 589830 | 589830 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-07-28 | 2023-07-28 | 2023-07-28 | N/A | N/A | Completed
23-C0642 | FEEDS | PVO | No | Competitive Bidding | N/A | 2023-07-10 |  | 2023-07-25 | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-11 | 2023-08-22 |  |  |  | 2023-08-25 | 2023-08-31 | 2023-09-08 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 1171709 | 1171709 |  | 1070153 | 1070153 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-07-28 | 2023-08-11 | 2023-08-11 | 2023-08-11 | N/A | N/A | Completed
23-C0044 | CEMENT | PEO | No | NP-53.9 - Small Value Procurement | 2023-04-18 | 2023-07-04 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-09-01 | 2023-09-04 |  |  | 2023-11-08 | 2023-11-08 | Government of the Philippines (current year's budget) | 321126 | 321126 |  | 319783.5 | 319783.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0554 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | 2023-06-27 | 2023-07-17 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-29 | 2023-08-29 | 2023-09-01 |  |  | 2023-09-04 | 2023-09-04 | Government of the Philippines (current year's budget) | 156000 | 156000 |  | 154000 | 154000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0620 | WATER | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-09-05 | 2023-09-12 |  |  |  |  | Government of the Philippines (current year's budget) | 28905 | 28905 |  | 28200 | 28200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3452 | FOOD/CATERING SERVICES | PPDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-24 | 2023-08-24 | 2023-08-24 |  |  | 2023-08-31 | 2023-08-31 | Government of the Philippines (current year's budget) | 116720 | 116720 |  | 116000 | 116000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3420 | SAFETY GEARS & EQUIPMENT | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-09-01 | 2023-09-05 |  |  | 2023-09-26 | 2023-09-26 | Government of the Philippines (current year's budget) | 8570 | 8570 |  | 8570 | 8570 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0574 | AGRICULTURAL SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-07-11 | 2023-07-17 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-24 | 2023-08-31 | 2023-09-01 |  |  | 2023-09-13 | 2023-09-13 | Government of the Philippines (current year's budget) | 473275 | 473275 |  | 471952 | 471952 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3190 | VITAMINS/MEDICINES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-08-31 | 2023-09-05 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 800 | 800 |  | 750 | 750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3880 | CONSTRUCTION SUPPLIES | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-09-01 | 2023-09-04 |  |  | 2023-09-18 | 2023-09-18 | Government of the Philippines (current year's budget) | 15322.98 | 15322.98 |  | 15290 | 15290 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3699 | CONSTRUCTION SUPPLIES | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-09-08 | 2023-09-11 |  |  | 2023-09-20 | 2023-09-20 | Government of the Philippines (current year's budget) | 95246.14 | 95246.14 |  | 93998 | 93998 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3917 | CONSTRUCTION SUPPLIES | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-09-01 | 2023-09-04 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 82853 | 82853 |  | 80988 | 80988 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3368 | PLUMBING SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-09-06 | 2023-09-08 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 130065 | 130065 |  | 128367 | 128367 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0649 | PAINTING MATERIALS | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-09-06 | 2023-09-08 |  |  | 2023-09-18 | 2023-09-18 | Government of the Philippines (current year's budget) | 23438 | 23438 |  | 22432 | 22432 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3383 | VETERINARY DRUG AND BIOLOGICS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-24 | 2023-09-06 | 2023-09-13 |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 63144 | 63144 |  | 62375 | 62375 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0437 | CONSTRUCTION SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-09-04 | 2023-09-05 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 57124 | 57124 |  | 55979 | 55979 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0637 | CONSTRUCTION SUPPLIES | PICTO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-09-01 | 2023-09-04 |  |  | 2023-10-17 | 2023-10-17 | Government of the Philippines (current year's budget) | 36780 | 36780 |  | 36773.75 | 36773.75 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3613 | FURNITURES AND FIXTURES | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-09-01 | 2023-09-04 |  |  | 2023-09-26 | 2023-09-26 | Government of the Philippines (current year's budget) | 50000 | 50000 |  | 49941 | 49941 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3968 | ELECTRICAL SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-09-04 | 2023-09-05 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 5720 | 5720 |  | 5591 | 5591 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4017 | CONSTRUCTION SUPPLIES | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-09-08 | 2023-09-11 |  |  | 2023-09-20 | 2023-09-20 | Government of the Philippines (current year's budget) | 69377.52 | 69377.52 |  | 64954 | 64954 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3813 | FURNITURES AND FIXTURES | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-09-08 | 2023-09-11 |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 38700 | 38700 |  | 38430 | 38430 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0586 | FOOD/CATERING SERVICES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-25 | 2023-09-07 | 2023-09-08 |  |  | 2023-11-18 | 2023-11-18 | Government of the Philippines (current year's budget) | 281600 | 281600 |  | 281424 | 281424 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
|  |  |  | NP-53.9 - Small Value Procurement |  |  |  |  | 0 | [15 empty] | Government of the Philippines (current year's budget) | [7 empty] | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4070 | JANITORIAL SUPPLIES | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-08-31 | 2023-09-05 |  |  | 2023-09-19 | 2023-09-19 | Government of the Philippines (current year's budget) | 2500 | 2500 |  | 2405 | 2405 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3440 | FURNITURES AND FIXTURES | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-08-31 | 2023-09-04 |  |  | 2023-09-11 | 2023-09-11 | Government of the Philippines (current year's budget) | 13000 | 13000 |  | 12299 | 12299 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2923 | SAFETY GEARS & EQUIPMENT | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-09-01 | 2023-09-01 |  |  | 2023-09-07 | 2023-09-07 | Government of the Philippines (current year's budget) | 1925 | 1925 |  | 1924 | 1924 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0718 | OTHER SUPPLIES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-09-01 | 2023-09-04 |  |  | 2023-09-11 | 2023-09-11 | Government of the Philippines (current year's budget) | 29896 | 29896 |  | 29705 | 29705 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4039 | JANITORIAL SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-09-01 | 2023-09-04 |  |  | 2023-09-13 | 2023-09-13 | Government of the Philippines (current year's budget) | 25000 | 25000 |  | 24000 | 24000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2932 | SERVICES | PLO | No | Direct Contracting | N/A | 2023-08-03 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | N/A | 2023-08-29 | 2023-09-06 |  |  |  |  | Government of the Philippines (current year's budget) | 27828 | 27828 |  | 25000 | 25000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3509 | ACCOUNTABLE FORMS | PTO | No | NP-53.5 Agency-to-Agency | N/A | 2023-07-17 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-23 | 2023-09-01 | 2023-11-09 |  |  | 2023-10-19 | 2023-10-19 | Government of the Philippines (current year's budget) | 437500 | 437500 |  | 250250 | 250250 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3405 | PRINTED FORMS | PTO | No | NP-53.5 Agency-to-Agency | N/A | 2023-07-17 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-23 | 2023-09-01 | 2023-10-27 |  |  | 2023-11-06 | 2023-11-06 | Government of the Philippines (current year's budget) | 951925 | 951925 |  | 919900 | 919900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4056 | FOOD SUPPLIES | PGO | No | NP-53.5 Agency-to-Agency | 2023-08-08 | 2023-08-10 |  | N/A | 2023-08-15 | 2023-08-15 |  | N/A | N/A | 2023-08-22 |  |  |  | 2023-08-23 | 2023-08-29 | 2023-09-29 |  |  | 2023-08-20 | 2023-08-20 | Government of the Philippines (current year's budget) | 450000 | 450000 |  | 450000 | 450000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4090 | SPARE PARTS FOR THE USE OF PLATE # 1101-266030 CADS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 1617 | 1617 |  | 1617 | 1617 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4093 | SPARE PARTS FOR THE USE OF PLATE # 1101-266030 CADS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-13 | 2023-12-19 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 17050 | 17050 |  | 17050 | 17050 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4089 | SPAREPARTS PLATE # 1101-195969-PPDO | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 4500 | 4500 |  | 4500 | 4500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4088 | SPAREPARTS PLATE # 1101-225229 PGSO | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-14 |  |  | 2023-12-14 | 2023-12-14 | Government of the Philippines (current year's budget) | 35080 | 35080 |  | 35080 | 35080 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4095 | SPARE PARTS FOR THE USE OF PLATE #1101-1052165 | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 8400 | 8400 |  | 8400 | 8400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0723 | SPARE PARTS FOR THE USE OF PLATE #1101-278376 PAGRO | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-13 |  |  | 2023-12-14 | 2023-12-14 | Government of the Philippines (current year's budget) | 13800 | 13800 |  | 13800 | 13800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4099 | SPAREPARTS PLATE # 110-1052093 | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 5608 | 5608 |  | 5608 | 5608 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0725 | SPAREPARTS PLATE # 13008-CADS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-13 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 25000 | 25000 |  | 25000 | 25000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4082 | GEMELINA LUMBER OR EQUIVALENT | PEO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-18 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 4700 | 4700 |  | 4700 | 4700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0676 | JANITORIAL SUPPLIES | PEEMO | No | Competitive Bidding | 2023-08-22 | 2023-08-29 |  | N/A | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-10-06 | 2023-10-13 |  |  |  | 2023-10-18 | 2023-10-26 | 2023-11-15 |  |  | 2023-12-04 | 2023-12-04 | Government of the Philippines (current year's budget) | 663166 | 663166 |  | 480869.05 | 480869.05 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-09-22 | 2023-09-22 | 2023-09-22 | N/A | N/A | Completed
23-C0682 | CONSTRUCTION MATERIALS | PEEMO | No | Competitive Bidding | 2023-08-22 | 2023-10-03 |  | N/A | 2023-10-17 | 2023-10-17 |  | 2023-10-17 | 2023-10-20 | 2023-11-15 |  |  |  | 2023-11-17 | 2023-11-29 | 2023-11-30 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 375363 | 375363 |  | 374897 | 374897 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-10-27 | 2023-10-27 | 2023-10-27 | N/A | N/A | Completed
23-4198 | PRESSURE TANK 220 gals | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-24 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-17 |  |  | 2023-10-24 | 2023-10-24 | Government of the Philippines (current year's budget) | 25500 | 25500 |  | 25500 | 25500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3893 | ALUMINUM FOLDING LADDER- HEAVY DUTY | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-10-16 | 2023-10-18 |  |  | 2023-10-25 | 2023-10-25 | Government of the Philippines (current year's budget) | 11000 | 11000 |  | 10500 | 10500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3920 | CLOTH SATIN-GOLD AND RED | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-18 |  |  | 2023-10-25 | 2023-10-25 | Government of the Philippines (current year's budget) | 4000 | 4000 |  | 4000 | 4000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0687 | COMPUTER SPAREPARTS | PICTO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-20 | 2023-10-20 | Government of the Philippines (current year's budget) | 131526 | 131526 |  | 131526 | 131526 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
[9 empty] | 0 | [15 empty] | Government of the Philippines (current year's budget) |  | 200000 |  |  | 194888 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA |  |  |  |  | N/A | N/A
23-4006 | MEALS VIP AND SNACKS | PBO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-23 | 2023-10-24 |  |  | 2023-11-14 | 2023-11-14 | Government of the Philippines (current year's budget) | 29225 | 29225 |  | 28782 | 28782 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2736 | MEALS WITH ACCOMMODATION | PAO-IPRD | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-12-05 | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 48300 | 48300 |  | 48195 | 48195 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4151 23101129 | AIRCONDITIONING UNIT | PAO | No | Competitive Bidding | 2023-08-22 | 2023-09-04 |  | N/A | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-10-12 | 2023-10-13 |  |  |  | 2023-10-13 | 2023-11-16 | [5 empty] | Government of the Philippines (current year's budget) | 304336 | 304336 |  | 237716 | 237716 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-09-22 | 2023-09-22 | 2023-09-22 | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0716 | MINERAL WATER, 5 GAL | PGO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | 2023-10-17 | 2023-10-26 | 2023-11-07 |  |  |  |  | Government of the Philippines (current year's budget) | 119925 | 119925 |  | 117000 | 117000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3204 | BOARD WITH RING 4*4 | PGO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | 2023-11-21 | 2023-11-23 | 2023-11-28 |  |  | 2023-11-29 | 2023-11-29 | Government of the Philippines (current year's budget) | 97900 | 97900 |  | 97350 | 97350 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3940 | JOB ORDER(REHABILITATION OF 80 FT ANTENNA TOWER WITH SPECIFICATIONS | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-09-07 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-14 | 2023-12-27 | [5 empty] | Government of the Philippines (current year's budget) | 300000 | 300000 |  | 272000 | 272000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4066 | OTHER SUPPLIES | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-25 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 9700 | 9700 |  | 9396 | 9396 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4123 | OTHER SUPPLIES | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-09-25 | 2023-09-25 | Government of the Philippines (current year's budget) | 9100 | 9100 |  | 8750 | 8750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3693 | OFFICE EQUIPMENT | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-29 |  |  | 2023-10-19 | 2023-10-19 | Government of the Philippines (current year's budget) | 8408 | 8408 |  | 8408 | 8408 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3434 | JANITORIAL SUPPLIES | VGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-10-03 | 2023-10-03 | Government of the Philippines (current year's budget) | 36848 | 36848 |  | 36761 | 36761 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0629 | OFFICE EQUIPMENT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-25 | 2023-09-29 |  |  | 2023-10-26 | 2023-10-26 | Government of the Philippines (current year's budget) | 83420 | 83420 |  | 82500 | 82500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0611 | OFFICE SUPPLIES | PHRMDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-07-17 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-19 | 2023-09-20 |  |  | 2023-09-26 | 2023-09-26 | Government of the Philippines (current year's budget) | 89821.1 | 89821.1 |  | 88649 | 88649 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0635 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-07-31 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 10820 | 10820 |  | 10721 | 10721 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0643 | SPAREPARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2023-07-31 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | N/A | 2023-09-19 | 2023-09-25 |  |  | 2023-09-25 | 2023-09-25 | Government of the Philippines (current year's budget) | 2130 | 2130 |  | 2130 | 2130 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0538 | FOOD/CATERING SERVICES | PHO | No | NP-53.1 Two Failed Biddings | N/A | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-14 | 2023-09-19 |  |  | 2023-09-28 | 2023-09-28 | Government of the Philippines (current year's budget) | 2671500 |  | 2671500 | 2664650 |  | 2664650 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0599 | CONSTRUCTION MATERIALS | PEO-MOTORPOOL | No | Competitive Bidding | N/A | 2023-07-31 |  | N/A | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-25 | 2023-09-04 |  |  |  | 2023-09-07 | 2023-09-19 | 2023-09-21 |  |  | 2023-10-06 | 2023-10-06 | Government of the Philippines (current year's budget) | 957298 | 957298 |  | 897570 | 897570 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-03 | 2023-08-03 | 2023-08-03 | N/A | N/A | Completed
23-4003 | FIBER OPTIC FUSION MACHINE | PICTO | No | Competitive Bidding | N/A | 2023-07-31 |  | N/A | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-25 | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-14 | 2023-09-29 |  |  | 2023-12-15 | 2023-12-15 | Government of the Philippines (current year's budget) | 66000 | 66000 |  | 65898 | 65898 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-03 | 2023-08-03 | 2023-08-03 | N/A | N/A | Completed
23-C0605 | GARMENTS | PDRRMO | No | Competitive Bidding | N/A | 2023-07-31 |  | N/A | 2023-08-08 | 2023-08-08 |  | 2023-08-08 | 2023-08-25 | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-14 | 2023-11-07 |  |  |  |  | Government of the Philippines (current year's budget) | 477625 | 477625 |  | 360500 | 360500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-03 | 2023-08-03 | 2023-08-03 | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0631 | SPAREPARTS | PGSO | No | Competitive Bidding | N/A | 2023-07-31 |  | 2023-08-08 | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-25 | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-29 | 2023-09-29 |  |  | 2023-10-04 | 2023-10-04 | Government of the Philippines (current year's budget) | 2898075 | 2898075 |  | 1624735 | 1624735 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-08-03 | 2023-08-18 | 2023-08-18 | 2023-08-18 | N/A | N/A | Completed
23-4040 | CONSTRUCTION SUPPLY | SEF | No | Competitive Bidding | N/A | 2023-08-07 |  | N/A | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-25 | 2023-09-04 |  |  |  | 2023-09-08 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-26 | 2023-10-26 | Government of the Philippines (current year's budget) | 673902 | 673902 |  | 597150 | 597150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-18 | 2023-08-18 | 2023-08-18 | N/A | N/A | Completed
23-3835 | CONSTRUCTION SUPPLY | PEO | No | Competitive Bidding | N/A | 2023-08-08 |  | N/A | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-08-25 | 2023-09-04 |  |  |  | 2023-09-08 | 2023-09-19 | 2023-09-20 |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 464739 |  | 464739 | 413826.5 |  | 413826.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-18 | 2023-08-18 | 2023-08-18 | N/A | N/A | Completed
23-C0634 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Competitive Bidding | N/A | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-09-01 | 2023-09-08 |  |  |  | 2023-09-13 | 2023-09-28 | 2023-10-03 |  |  | 2023-10-04 | 2023-10-04 | Government of the Philippines (current year's budget) | 775508 | 775508 |  | 741828 | 741828 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-18 | 2023-08-18 | 2023-08-18 | N/A | N/A | Completed
23-C0629 | OFFICE EQUIPMENT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-09-05 | 2023-09-05 |  | N/A | N/A | 2023-09-08 |  |  |  | 2023-09-08 | 2023-09-25 | 2023-09-29 |  |  | 2023-10-26 | 2023-10-26 | Government of the Philippines (current year's budget) | 83420 | 83420 |  | 82500 | 82500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0636 | JOB ORDER (LABOR ONLY) | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-09-05 | 2023-09-05 |  | N/A | N/A | 2023-09-08 |  |  |  | 2023-09-05 | 2023-09-19 | 2023-09-20 |  |  | 2023-11-06 | 2023-11-06 | Government of the Philippines (current year's budget) | 52780 | 52780 |  | 47320 | 47320 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4013 | LUMBER | PGO-SEF | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-09-05 | 2023-09-05 |  | N/A | N/A | 2023-09-08 |  |  |  | N/A | 2023-10-13 | 2023-10-16 |  |  | 2023-11-06 | 2023-11-06 | Government of the Philippines (current year's budget) | 31834.51 | 31834.51 |  | 31157.18 | 31157.18 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4119 | SPORTS SUPPLIES | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-09-05 | 2023-09-05 |  | N/A | N/A | 2023-09-08 |  |  |  | N/A | 2023-09-19 | 2023-09-20 |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 7495 | 7495 |  | 7460 | 7460 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4212 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-26 |  | N/A | 2023-09-05 | 2023-09-05 |  | N/A | N/A | 2023-09-08 |  |  |  | 2023-09-14 | 2023-09-19 | 2023-09-20 |  |  | 2023-10-11 | 2023-10-11 | Government of the Philippines (current year's budget) | 150000 | 150000 |  | 150000 | 150000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4210 | FOOD SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-26 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-09-28 | 2023-10-06 |  |  | 2023-09-14 | 2023-09-14 | Government of the Philippines (current year's budget) | 35120 | 35120 |  | 32800 | 32800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0667 | AGRICULTURAL SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | 2023-09-13 | 2023-09-28 | 2023-09-29 |  |  | 2023-10-12 | 2023-10-12 | Government of the Philippines (current year's budget) | 96100 | 96100 |  | 93835 | 93835 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4083 | PRINTING | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-26 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-10-09 | 2023-10-10 |  |  | 2023-10-23 | 2023-10-23 | Government of the Philippines (current year's budget) | 1792 | 1792 |  | 1664 | 1664 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4284 | PRINTING | PPDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-09-29 | 2023-10-04 |  |  | 2023-11-21 | 2023-11-21 | Government of the Philippines (current year's budget) | 8400 | 8400 |  | 7800 | 7800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0742 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | 2023-09-14 | 2023-09-19 | 2023-09-20 |  |  | 2023-09-15 | 2023-09-15 | Government of the Philippines (current year's budget) | 367550 | 367550 |  | 367252 | 367252 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3363 | FEED INGREDIENTS | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | 2023-09-12 | 2023-09-28 | 2023-09-29 |  |  | 2023-11-22 | 2023-11-22 | Government of the Philippines (current year's budget) | 8000 | 8000 |  | 8000 | 8000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4215 | BAG | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-26 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-09-28 | 2023-09-29 |  |  | 2023-10-03 | 2023-10-03 | Government of the Philippines (current year's budget) | 28000 | 28000 |  | 27920 | 27920 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4245 | SPAREPARTS | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-10-03 | 2023-10-05 |  |  | 2023-10-05 | 2023-10-05 | Government of the Philippines (current year's budget) | 2500 | 2500 |  | 2500 | 2500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4207 | SPAREPARTS PLATE | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-09-28 | 2023-09-29 |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 1100 | 1100 |  | 1100 | 1100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0731 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-09-28 | 2023-09-29 |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 2950 | 2950 |  | 2950 | 2950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4139 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | 2023-09-12 | 2023-09-28 | 2023-09-29 |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 63840 | 63840 |  | 63840 | 63840 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4134 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | 2023-09-12 | 2023-09-28 | 2023-09-29 |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 62100 | 62100 |  | 62100 | 62100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4136 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-09-28 | 2023-09-29 |  |  | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 25315 | 25315 |  | 25315 | 25315 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4229 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | 2023-09-12 | 2023-10-02 | 2023-10-04 |  |  | 2023-10-05 | 2023-10-05 | Government of the Philippines (current year's budget) | 8345 | 8345 |  | 8345 | 8345 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4140 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-09-29 | 2023-10-09 |  |  | 2023-10-09 | 2023-10-09 | Government of the Philippines (current year's budget) | 23799 | 23799 |  | 23799 | 23799 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4292 | OIL FILTER (NAVARA) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-09-29 | 2023-10-10 |  |  | 2023-10-10 | 2023-10-10 | Government of the Philippines (current year's budget) | 380 | 380 |  | 380 | 380 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4227 | STAND -SIDE PLATE #1101-417658 | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-10-03 | 2023-10-04 |  |  | 2023-10-05 | 2023-10-05 | Government of the Philippines (current year's budget) | 600 | 600 |  | 600 | 600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4243 | SPAREPARTS PLATE # 1101-366178 | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-10-02 | 2023-10-04 |  |  | 2023-10-04 | 2023-10-04 | Government of the Philippines (current year's budget) | 3000 | 3000 |  | 3000 | 3000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4242 | PRESS IN & PRESS OUT LOWER ARM BUSHING, LH & RH | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-10-02 | 2023-10-04 |  |  | 2023-10-04 | 2023-10-04 | Government of the Philippines (current year's budget) | 700 | 700 |  | 700 | 700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4291 | SPARE PARTS PLATE # 31101-366171 | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-10-02 | 2023-10-04 |  |  | 2023-10-04 | 2023-10-04 | Government of the Philippines (current year's budget) | 37500 | 37500 |  | 37500 | 37500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4246 | JOB ORDER | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-28 | 2023-11-29 |  |  | 2023-11-29 | 2023-11-29 | Government of the Philippines (current year's budget) | 800 | 800 |  | 800 | 800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4244 | SPARE PARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-05 | 2023-09-07 |  | N/A | 2023-09-12 | 2023-09-12 |  | N/A | N/A | 2023-09-13 |  |  |  | N/A | 2023-10-03 | 2023-10-04 |  |  | 2023-10-05 | 2023-10-05 | Government of the Philippines (current year's budget) | 1650 | 1650 |  | 1650 | 1650 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0690 | MEALS AND SNACKS | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | 2023-09-05 | 2023-09-06 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | 2023-10-17 | 2023-10-26 | 2023-11-06 |  |  | 2023-11-09 | 2023-11-09 | Government of the Philippines (current year's budget) | 161640 | 161640 |  | 159408 | 159408 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0689 | COMPUTER SPAREPARTS | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-09-05 | 2023-09-06 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-17 |  |  | 2023-11-07 | 2023-11-07 | Government of the Philippines (current year's budget) | 31114 | 31114 |  | 30660 | 30660 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0641 | FOOD SUPPLIES | PGO | No | Competitive Bidding | N/A | 2023-08-14 |  | 2023-08-22 | 2023-09-05 | 2023-09-05 |  | 2023-09-05 | 2023-09-08 | 2023-09-13 |  |  |  | 2023-09-14 | 2023-09-19 | 2023-09-14 |  |  | 2023-10-31 | 2023-10-31 | Government of the Philippines (current year's budget) | 1961400 | 1961400 |  | 1954540 | 1954540 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-08-18 | 2023-09-01 | 2023-09-01 | 2023-09-01 | N/A | N/A | Completed
23-4288 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-12 | 2023-09-14 |  | N/A | 2023-09-19 | 2023-09-19 |  | N/A | N/A | 2023-09-22 |  |  |  | N/A | 2023-10-13 | 2023-10-18 |  |  | 2023-10-19 | 2023-10-19 | Government of the Philippines (current year's budget) | 9960 | 9960 |  | 9960 | 9960 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0743 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-12 | 2023-09-14 |  | N/A | 2023-09-19 | 2023-09-19 |  | N/A | N/A | 2023-09-22 |  |  |  | N/A | 2023-10-13 | 2023-10-18 |  |  | 2023-10-19 | 2023-10-19 | Government of the Philippines (current year's budget) | 24380 | 24380 |  | 24380 | 24380 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4323 | BRAKE PAD PLATE # 1101-9344969 | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-12 | 2023-09-14 |  | N/A | 2023-09-19 | 2023-09-19 |  | N/A | N/A | 2023-09-22 |  |  |  | N/A | 2023-10-09 | 2023-10-12 |  |  | 2023-10-12 | 2023-10-12 | Government of the Philippines (current year's budget) | 5600 | 5600 |  | 5600 | 5600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4287 | SPAREPARTS | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-12 | 2023-09-14 |  | N/A | 2023-09-19 | 2023-09-19 |  | N/A | N/A | 2023-09-22 |  |  |  | N/A | 2023-10-13 | 2023-10-19 |  |  | 2023-10-19 | 2023-10-19 | Government of the Philippines (current year's budget) | 49636 | 49636 |  | 49556 | 49556 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3599 | UPS W/ BUILT-IN AVR, 600 VA AND VOICE RECORDER 2GB BUILT-IN MEMORY AND MEMORY CARD | PGO-BAC | No | NP-53.9 - Small Value Procurement | 08.08.2023 | 2023-09-14 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-23 | 2023-11-28 |  |  | 2023-12-04 | 2023-12-04 | Government of the Philippines (current year's budget) | 7083 | 7083 |  | 5085 | 5085 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4328 | FURNITURES AND FIXTURES | PAO-ADMIN | No | Competitive Bidding | 2023-09-12 | 2023-09-18 |  | N/A | 2023-10-03 | 2023-10-03 |  | 2023-10-03 | 2023-10-06 | 2023-10-13 |  |  |  | 2023-10-17 | 2023-10-17 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 | Government of the Philippines (current year's budget) | 607646 | 607646 |  | 607646 | 607646 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4337 | BRAKE PAD (27294) PLATE # 1101-0048092 | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-09-12 | 2023-09-14 |  | N/A | 2023-09-19 | 2023-09-19 |  | N/A | N/A | 2023-09-22 |  |  |  | N/A | 2023-10-13 | 2023-10-18 |  |  | 2023-10-18 | 2023-10-18 | Government of the Philippines (current year's budget) | 5600 | 5600 |  | 5600 | 5600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4118 | FURNITURES AND FIXTURES | PDRRMO | No | Competitive Bidding | 2023-09-12 | 2023-09-25 |  | 2023-10-03 | 2023-10-17 | 2023-10-17 |  | 2023-10-17 | 2023-11-14 | 2023-11-24 |  |  |  | 2023-11-24 | 2023-12-12 | 2023-12-12 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 1201720 | 1201720 |  | 1188280 | 1188280 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4147 | MEALS AND SNACKS WITH ACCOMMODATION B | PLO | No | NP-53.9 - Small Value Procurement | 2023-09-12 | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | 2023-11-22 | 2023-11-29 | 2023-12-06 |  |  |  |  | Government of the Philippines (current year's budget) | 750000 | 750000 |  | 735000 | 735000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4340 | TIRES WITH INNER TUBE | PEO-MOTORPOOL | No | Competitive Bidding | 2023-09-12 | 2023-09-25 |  | 2023-10-03 | 2023-10-17 | 2023-10-17 |  | 2023-10-17 | 2023-11-10 | 2023-11-24 |  |  |  | 2023-11-21 | 2023-12-12 | [5 empty] | Government of the Philippines (current year's budget) | 3050000 | 3050000 |  | 1695500 | 1695500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-10-12 | 2023-10-27 | 2023-10-27 | 2023-10-27 | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4201 | JOB ORDER REPAIR OF 1 UNIT LN2 GENERATOR MODEL GN30i + UPM40W | PVO | No | Direct Contracting | 2023-09-12 | 2023-09-28 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | 2023-11-03 | 2023-11-21 | 2023-11-30 |  |  |  |  | Government of the Philippines (current year's budget) | 1800000 | 1800000 |  | 1788940 | 1788940 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4262 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-01 |  | N/A | 2023-09-19 | 2023-09-19 |  | N/A | N/A | 2023-09-22 |  |  |  | 2023-09-29 | 2023-10-09 | 2023-10-12 |  |  |  |  | Government of the Philippines (current year's budget) | 300000 | 300000 |  | 300000 | 300000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4028 | OFFICE EQUIPMENT | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-09-19 | 2023-09-19 |  | N/A | N/A | 2023-09-22 |  |  |  | N/A | 2023-10-13 | 2023-10-18 |  |  | 2023-10-25 | 2023-10-25 | Government of the Philippines (current year's budget) | 30000 | 30000 |  | 29500 | 29500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4258 | OFFICE EQUIPMENT | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-01 |  | N/A | 2023-09-19 | 2023-09-19 |  | N/A | N/A | 2023-09-22 |  |  |  | N/A | 2023-10-09 | 2023-10-20 |  |  | 2023-10-27 | 2023-10-27 | Government of the Philippines (current year's budget) | 44000 | 44000 |  | 43900 | 43900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4259 | OTHER SUPPLIES/MATERIALS | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-01 |  | N/A | 2023-09-19 | 2023-09-19 |  | N/A | N/A | 2023-09-22 |  |  |  | N/A | 2023-10-13 | 2023-10-18 |  |  | 2023-10-24 | 2023-10-24 | Government of the Philippines (current year's budget) | 15000 | 15000 |  | 14500 | 14500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4059 | AGRICULTURAL SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-25 |  | N/A | 2023-09-19 | 2023-09-19 |  | N/A | N/A | 2023-09-22 |  |  |  | N/A | 2023-10-13 | 2023-10-18 |  |  | 2023-10-20 | 2023-10-20 | Government of the Philippines (current year's budget) | 45000 | 45000 |  | 44994 | 44994 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4078 | SAFETY GEARS & EQUIPMENT | PEO | No | NP-53.9 - Small Value Procurement | 2023-08-22 | 2023-08-25 |  | N/A | 2023-09-19 | 2023-09-19 |  | N/A | N/A | 2023-09-22 |  |  |  | N/A | 2023-10-09 | 2023-10-18 |  |  | 2023-10-27 | 2023-10-27 | Government of the Philippines (current year's budget) | 1925 | 1925 |  | 1924 | 1924 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4132 | COMPUTER SUPPLIES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-01 |  | N/A | 2023-09-19 | 2023-09-19 |  | N/A | N/A | 2023-09-22 |  |  |  | N/A | 2023-10-13 | 2023-10-18 |  |  | 2023-10-27 | 2023-10-27 | Government of the Philippines (current year's budget) | 49119 | 49119 |  | 48690 | 48690 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0733 | MEDICAL SUPPLIES | PEEMO | No | Direct Contracting | N/A | 2023-09-14 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-23 | 2023-10-25 |  |  | 2023-11-29 | 2023-11-29 | Government of the Philippines (current year's budget) | 2088 | 2088 |  | 2088 | 2088 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0737 | DUPLICATING PRODUCTS | PEEMO | No | Direct Contracting | N/A | 2023-09-14 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-17 |  |  |  |  | Government of the Philippines (current year's budget) | 13984 | 13984 |  | 13984 | 13984 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0680 | LABORATORY SUPPLIES | PEEMO | No | Direct Contracting | N/A | 2023-09-14 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | 2023-10-03 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-20 | 2023-10-20 | Government of the Philippines (current year's budget) | 4025000 | 4025000 |  | 4025000 | 4025000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3600 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-09-06 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-05 |  |  |  | 2023-10-06 | 2023-10-13 | 2023-10-13 |  |  | 2023-10-17 | 2023-10-17 | Government of the Philippines (current year's budget) | 142912 | 142912 |  | 139762 | 139762 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3849 | CELLPHONE | PPDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | 2023-10-18 | 2023-10-23 | 2023-10-24 |  |  | 2023-11-14 | 2023-11-14 | Government of the Philippines (current year's budget) | 180000 | 180000 |  | 179400 | 179400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3211 | CELLPHONE | PPDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-17 |  |  | 2023-10-19 | 2023-10-19 | Government of the Philippines (current year's budget) | 8800 | 8800 |  | 8700 | 8700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3345 | FOOD/CATERING SERVICES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-26 | 2023-11-06 |  |  | 2023-12-04 | 2023-12-04 | Government of the Philippines (current year's budget) | 11625 | 11625 |  | 11250 | 11250 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0617 | CAMPING TENT | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-18 |  |  | 2023-11-08 | 2023-11-08 | Government of the Philippines (current year's budget) | 8000 | 8000 |  | 7100 | 7100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3223 | TABLE NAME HOLDER | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-17 |  |  | 2023-10-18 | 2023-10-18 | Government of the Philippines (current year's budget) | 8000 | 8000 |  | 8000 | 8000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3872 | PUBLICATION | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-09 |  |  |  | 2023-10-09 | 2023-10-16 | 2023-10-17 |  |  | 2023-11-13 | 2023-11-13 | Government of the Philippines (current year's budget) | 198000 | 198000 |  | 165000 | 165000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3188 | FOOD/CATERING SERVICES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-06 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | 2023-10-12 | 2023-10-16 | 2023-10-18 |  |  | 2023-11-28 | 2023-11-28 | Government of the Philippines (current year's budget) | 90000 | 90000 |  | 90000 | 90000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4268 | CONSTRUCTION SUPPLIES | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-30 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | 2023-10-17 | 2023-10-23 | 2023-10-24 |  |  | 2023-11-16 | 2023-11-16 | Government of the Philippines (current year's budget) | 292765.79 | 292765.79 |  | 292066.5 | 292066.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0740 | OTHER SUPPLIE/MATERIALS | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-30 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | 2023-10-17 | 2023-10-16 | 2023-10-17 |  |  | 2023-10-24 | 2023-10-24 | Government of the Philippines (current year's budget) | 199995 | 199995 |  | 199733.5 | 199733.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0717 | HEAVY DUTY VACUUM CLEANER, HEAVY DUTY WASHING MACHINE | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-24 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | 2023-10-17 | 2023-11-21 | 2023-11-23 |  |  |  |  | Government of the Philippines (current year's budget) | 98800 | 98800 |  | 98774 | 98774 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4014 | LUMBER | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-18 | 2023-10-20 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 2256 | 2256 |  | 2256 | 2256 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4041 | LUMBER | PGO-SEF | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-02 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-11-03 | 2023-11-06 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 10708.51 | 10708.51 |  | 10708.51 | 10708.51 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-2223 | LUMBER | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-30 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-18 | 2023-10-20 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 37506 | 37506 |  | 37506 | 37506 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0750 | FOOD/CATERING SERVICES | PPDO | No | NP-53.9 - Small Value Procurement | 2023-09-12 | 2023-09-28 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-06 |  |  |  | 2023-10-06 | 2023-10-11 | 2023-10-12 |  |  | 2023-10-20 | 2023-10-20 | Government of the Philippines (current year's budget) | 249930 | 249930 |  | 247695 | 247695 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0648 | VETERINARY SUPPLIES | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-18 |  |  | 2023-11-08 | 2023-11-08 | Government of the Philippines (current year's budget) | 16040 | 16040 |  | 14050 | 14050 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0721 | FRAME & PLAQUE | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-14 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-18 |  |  | 2023-11-08 | 2023-11-08 | Government of the Philippines (current year's budget) | 6700 | 6700 |  | 6550 | 6550 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0646 | FOOD/CATERING SERVICES | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-06 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | N/A | 2023-10-16 | 2023-10-17 |  |  | 2023-11-30 | 2023-11-30 | Government of the Philippines (current year's budget) | 21300 | 21300 |  | 21300 | 21300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0656 | FOOD/CATERING SERVICES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-06 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 51070 | 51070 |  | 51070 | 51070 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0317 | SERVICES | PICTO | No | NP-53.1 Two Failed Biddings | 2023-03-28 | 2023-05-05 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | 2023-10-18 | 2023-10-18 | 2023-11-07 |  |  |  |  | Government of the Philippines (current year's budget) | 105000 | 105000 |  | 103000 | 103000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3517 | TRAUMA BACK PACK | PDRRMO | No | NP-53.1 Two Failed Biddings | N/A | 2023-08-14 |  | N/A | 2023-10-03 | 2023-10-03 |  | N/A | N/A | 2023-10-12 |  |  |  | 2023-10-16 | 2023-10-16 | 2023-10-17 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 619800 | 619800 |  | 604500 | 604500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4406 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-03 | 2023-10-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-11-21 | 2023-11-23 |  |  | 2023-11-23 | 2023-11-23 | Government of the Philippines (current year's budget) | 4500 | 4500 |  | 4500 | 4500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4407 |  | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-03-10 | 2023-10-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-11-21 | 2023-11-23 |  |  | 2023-11-23 | 2023-11-23 | Government of the Philippines (current year's budget) | 6960 | 6960 |  | 6960 | 6960 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4409 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-03 | 2023-10-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-11-21 | 2023-11-29 |  |  | 2023-11-29 | 2023-11-29 | Government of the Philippines (current year's budget) | 13260 | 13260 |  | 13260 | 13260 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4408 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-03 | 2023-10-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-11-13 | 2023-11-16 |  |  | 2023-11-16 | 2023-11-16 | Government of the Philippines (current year's budget) | 16250 | 16250 |  | 16250 | 16250 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0694 | HEMATOLOGY ANALYZER | PEEMO | No | Direct Contracting | 2023-10-03 | 2023-10-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-11-08 | 2023-11-13 |  |  | 2023-11-17 | 2023-11-17 | Government of the Philippines (current year's budget) | 1352800 | 1352800 |  | 1352800 | 1352800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4417 | SPAREPARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-03 | 2023-10-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-11-21 | 2023-11-29 |  |  | 2023-11-29 | 2023-11-29 | Government of the Philippines (current year's budget) | 15000 | 15000 |  | 15000 | 15000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4416 | SPAREPARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-03 | 2023-10-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-11-14 | 2023-11-14 |  |  | 2023-11-14 | 2023-11-14 | Government of the Philippines (current year's budget) | 29730 | 29730 |  | 29730 | 29730 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4415 | BRAKE PAD, GEN (N-NAVARA) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-03 | 2023-10-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-11-21 |  |  |  |  | 0 | Government of the Philippines (current year's budget) | 13450 | 13450 |  | 13450 | 13450 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4413 | STABILIZER LINK KIT, REAR FOR N-NVR-YD25(27980) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-03 | 2023-10-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-11-14 | 2023-11-14 |  |  | 2023-11-14 | 2023-11-14 | Government of the Philippines (current year's budget) | 6476 | 6476 |  | 6476 | 6476 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4410 | BRAKE PAD FOR THE USE OF PLATE # 1101-361178 | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-03 | 2023-10-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-11-14 | 2023-11-14 |  |  | 2023-11-14 | 2023-11-14 | Government of the Philippines (current year's budget) | 13750 | 13750 |  | 13750 | 13750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4483 | SPAREPARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-03 | 2023-10-06 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-11-28 | 2023-11-29 |  |  | 2023-11-29 | 2023-11-29 | Government of the Philippines (current year's budget) | 18450 | 18450 |  | 18450 | 18450 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0755 | SPAREPARTS | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-03 | 2023-10-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-11-13 | 2023-11-16 |  |  | 2023-11-16 | 2023-11-16 | Government of the Philippines (current year's budget) | 17120 | 17120 |  | 17120 | 17120 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0769 | SPAREPARTS | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-10-03 | 2023-10-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | 2023-11-17 | 2023-11-28 | 2023-11-28 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 58353 | 58353 |  | 58353 | 58353 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0739 | CONSTRUCTION MATERIALS | PEO | No | NP-53.9 - Small Value Procurement | 2023-10-03 | 2023-10-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-12-11 | 2023-12-13 |  |  | 2023-12-22 | 2023-12-22 | Government of the Philippines (current year's budget) | 17791 | 17791 |  | 17650 | 17650 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0732 | CORE i5 COMPUTER DESKTOP | PICTO | No | Competitive Bidding | N/A | 2023-09-04 |  | 2023-09-19 | 2023-10-03 | 2023-10-03 |  | 2023-10-03 | 2023-10-06 | 2023-10-13 |  |  |  | 2023-10-17 | 2023-10-23 | 2023-10-24 |  |  | 2023-11-24 | 2023-11-24 | Government of the Philippines (current year's budget) | 1056400 | 1056400 |  | 851300 | 851300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-09-22 | 2023-10-12 | 2023-10-12 | 2023-10-12 | N/A | N/A | Completed
23-4200 | VETERINARY SUPPLIES | PVO | No | Competitive Bidding | N/A | 2023-09-18 |  | N/A | 2023-10-03 | 2023-10-03 |  | 2023-10-03 | 2023-10-06 | 2023-10-13 |  |  |  | 2023-10-20 | 2023-10-26 | 2023-11-03 |  |  | 2023-12-22 | 2023-12-22 | Government of the Philippines (current year's budget) | 527029 | 527029 |  | 476501 | 476501 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-10-12 | 2023-10-12 | 2023-10-12 | 2023-10-12 | N/A | N/A | Completed
23-4199 | VETERINARY DRUGS AND BIOLOGICS | PVO | No | Competitive Bidding | N/A | 2023-09-18 |  | N/A | 2023-10-03 | 2023-10-03 |  | 2023-10-03 | 2023-10-06 | 2023-10-13 |  |  |  | 2023-10-23 | 2023-10-26 | 2023-11-03 |  |  | 2023-12-06 | 2023-12-06 | Government of the Philippines (current year's budget) | 472956 | 472956 |  | 441086 | 441086 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-10-12 | 2023-10-12 | 2023-10-12 | 2023-10-12 | N/A | N/A | Completed
23-4300 | SPAREPARTS | PGO | No | Direct Contracting | N/A | 2023-09-07 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | N/A | 2023-10-26 | 2023-11-08 |  |  | 2023-11-15 | 2023-11-15 | Government of the Philippines (current year's budget) | 12046 | 12046 |  | 10950 | 10950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0576 | OFFICE SUPPLIES | PDRRMO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-07-11 | 2023-07-17 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | 2023-10-20 | 2023-10-27 | 2023-11-10 |  |  | 2023-11-20 | 2023-11-20 | Government of the Philippines (current year's budget) | 79876 | 79876 |  | 78357.5 | 78357.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0655 | OFFICE SUPPLIES | PDRRMO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-09-28 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | N/A | 2023-10-26 | 2023-11-06 |  |  | 2023-11-10 | 2023-11-10 | Government of the Philippines (current year's budget) | 21614 | 21614 |  | 20918 | 20918 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0552 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | 2023-07-25 | 2023-08-03 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | 2023-10-17 | 2023-10-23 | [5 empty] | Government of the Philippines (current year's budget) | 70000 | 70000 |  | 69080 | 69080 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3953 | KEYBOARD ORGAN | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-09 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | 2023-10-23 | 2023-10-27 | 2023-11-06 |  |  |  |  | Government of the Philippines (current year's budget) | 95000 | 95000 |  | 94999.5 | 94999.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3807 | FOOD/CATERING SERVICES | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-28 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | 2023-10-24 | 2023-11-21 | 2023-12-11 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 598650 | 598650 |  | 597115 | 597115 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0747 | PAINTING MATERIALS | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-28 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | 2023-10-20 | 2023-10-26 | 2023-11-06 |  |  | 2023-11-14 | 2023-11-14 | Government of the Philippines (current year's budget) | 64790 | 64790 |  | 64550 | 64550 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0659 | CONSTRUCTION SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | 2023-10-23 | 2023-10-26 | 2023-11-07 |  |  | 2023-11-30 | 2023-11-30 | Government of the Philippines (current year's budget) | 190988.7 | 190988.7 |  | 190810 | 190810 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4319 | SUPPLY AND INSTALLATION OF JALOUSIE | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-13 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | 2023-10-13 | 2023-10-26 | 2023-11-06 |  |  |  |  | Government of the Philippines (current year's budget) | 12740 | 12740 |  | 9555 | 9555 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4189 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-30 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | 2023-10-09 | 2023-10-26 | 2023-11-06 |  |  | 2023-12-29 | 2023-12-29 | Government of the Philippines (current year's budget) | 9000 | 9000 |  | 8880 | 8880 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4421 | DECORATION | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-28 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | N/A | 2023-10-26 | 2023-11-06 |  |  |  |  | Government of the Philippines (current year's budget) | 33630 | 33630 |  | 33100 | 33100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0525 | FOOD/CATERING SERVICES | PDRRMO | No | NP-53.1 Two Failed Biddings | 2023-06-27 | 2023-09-07 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | N/A | 2023-10-26 | 2023-11-03 |  |  | 2023-11-15 | 2023-11-15 | Government of the Philippines (current year's budget) | 33630 | 33630 |  | 33100 | 33100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0525 | FOOD/CATERING SERVICES | PDRRMO | No | NP-53.1 Two Failed Biddings | 2023-06-27 | 2023-09-07 |  | N/A | 2023-10-09 | 2023-10-09 |  | N/A | N/A | 2023-10-13 |  |  |  | 2023-10-20 | 2023-10-26 | 2023-11-03 |  |  | 2023-11-15 | 2023-11-15 | Government of the Philippines (current year's budget) | 3426800 | 3426800 |  | 3426800 | 3426800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4141 | SER VER WITH COMPLTE ACCESSORIES | SPO | No | Competitive Bidding | N/A | 2023-08-29 |  | N/A | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-09-29 | 2023-10-03 |  |  |  | 2023-10-18 | 2023-10-26 | 2023-11-16 |  |  |  |  | Government of the Philippines (current year's budget) | 486989 | 486989 |  | 479799 | 479799 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-09-22 | 2023-09-22 | 2023-09-22 | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0698 | BROCHURE AND MAGAZINE PRINTING | PAO | No | Competitive Bidding | N/A | 2023-08-29 |  | N/A | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-09-29 | 2023-10-09 |  |  |  | 2023-10-09 | 2023-10-13 | 2023-10-24 |  |  | 2023-12-22 | 2023-12-22 | Government of the Philippines (current year's budget) | 352400 | 352400 |  | 261991.5 | 261991.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-09-22 | 2023-09-22 | 2023-09-22 | N/A | N/A | Completed
23-C0581 | MEALS AND SNACKS | PHO | No | Competitive Bidding | N/A | 2023-08-29 |  | N/A | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-09-29 | 2023-10-12 |  |  |  | 2023-10-13 | 2023-10-16 | 2023-10-24 |  |  | 2023-10-27 | 2023-10-27 | Government of the Philippines (current year's budget) | 352070 | 352070 |  | 347658 | 347658 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-09-22 | 2023-09-22 | 2023-09-22 | N/A | N/A | Completed
23-4765 | UPS, WITH BUILT-IN AVR, 1000VA | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-06 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 9900 | 9900 |  | 9892 | 9892 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0773 | CONSTRUCTION MATERIALS | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-11 | 2023-12-27 | [5 empty] | Government of the Philippines (current year's budget) | 159023 |  | 159023 | 159023 |  | 159023 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4748 | BLIND CURTAINS 301.06 SQ. FT. | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  |  | 2023-11-30 | 2023-11-30 |  |  |  |  | Government of the Philippines (current year's budget) | 108850.5 | 108850.5 |  | 108835 | 108835 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4743 | 4*6 CLEAR GLASS WITH HANALOK FRAME FIXED GLASS WITH SNAP-ON | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-11-30 | 2023-12-04 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 8085 | 8085 |  | 8080 | 8080 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3303 | OIL FILTER (MITS. STRADA) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-28 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 385 | 385 |  | 385 | 385 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4659 | ENGINE OIL (MITS. STRADA) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-22 |  |  | 2023-12-22 | 2023-12-22 | Government of the Philippines (current year's budget) | 330 | 330 |  | 330 | 330 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4660 | FUEL FILTER AND OIL FILTER | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-30 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 660 | 660 |  | 660 | 660 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3302 | ENGINE OIL | PVGO | No | Direct Contracting | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-28 | 2023-12-06 |  |  | 2023-12-06 | 2023-12-06 | Government of the Philippines (current year's budget) | 1100 | 1100 |  | 1100 | 1100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4840 | OFFICE SUPPLIES | PAGRO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-07 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 6532 | 6532 |  | 6310 | 6310 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4806 | LPG GAS REFILL (50 KGS) | PAGRO | No | Direct Contracting | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | [5 empty] | Government of the Philippines (current year's budget) | 48840 | 48840 |  | 32960 | 32960 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0799 | OFFICE SUPPLIES | PAO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-22 |  |  |  | 2023-11-22 | 2023-11-30 | 2023-12-07 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 89500 | 89500 |  | 87885 | 87885 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0796 | JANITORIAL SUPPLIES | PAO-INVESTMENT | No | NP-53.9 - Small Value Procurement | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-11-30 | 2023-12-07 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 46654 | 46654 |  | 44792 | 44792 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4053 | COMPUTER SET i5 AND SDI VIDEO SWITCHER | PAO-IPRD | No | Competitive Bidding | 2023-10-17 | 2023-10-30 |  | N/A | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | 2023-11-14 | 2023-11-22 |  |  |  | 2023-11-22 | 2023-11-30 | 2023-12-05 |  |  |  |  | Government of the Philippines (current year's budget) | 200000 | 200000 |  | 179288 | 179288 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0782 | OFFICE SUPPLIES | PHO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-10-16 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-22 | 2023-11-30 |  |  | 2023-12-04 | 2023-12-04 | Government of the Philippines (current year's budget) | 6947 | 6947 |  | 6581 | 6581 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3945 | LIGHTNING PROTECTION SYSTEM | PDRRMO | No | Competitive Bidding | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-22 | 2023-08-22 |  | 2023-08-22 | 2023-10-12 | 2023-10-27 |  |  |  | 2023-11-06 | 2023-11-13 | [5 empty] | Government of the Philippines (current year's budget) | 500000 | 500000 |  | 498000 | 498000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-08-18 | 2023-08-18 | 2023-08-18 | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0734 | CONSTRUCTION MATERIALS | PGSO | No | Competitive Bidding | N/A | 2023-09-04 |  | N/A | 2023-09-19 | 2023-09-19 |  | 2023-09-19 | 2023-10-12 | 2023-10-27 |  |  |  | 2023-11-08 | 2023-11-21 | 2023-11-23 |  |  | 2023-12-05 | 2023-12-05 | Government of the Philippines (current year's budget) | 353915 | 353915 |  | 323009 | 323009 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-09-22 | 2023-09-22 | 2023-09-22 | N/A | N/A | Completed
23-C0749 | CONSTRUCTION MATERIALS | PVO | No | Competitive Bidding | N/A | 2023-09-18 |  | N/A | 2023-10-03 | 2023-10-03 |  | 2023-10-03 | 2023-10-12 | 2023-10-27 |  |  |  | 2023-11-08 | 2023-11-13 | 2023-11-16 |  |  | 2023-12-05 | 2023-12-05 | Government of the Philippines (current year's budget) | 236638.74 | 236638.74 |  | 226109.95 | 226109.95 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-10-12 | 2023-10-12 | 2023-10-12 | N/A | N/A | Completed
23-4049 | RADIO STATION EQUIPMENT | PDRRMO | No | Competitive Bidding | N/A | 2023-09-18 |  | N/A | 2023-10-03 | 2023-10-03 |  | 2023-10-03 | 2023-10-12 | 2023-10-27 |  |  |  | 2023-11-08 | 2023-11-21 | 2023-11-23 |  |  | 2023-12-20 | 2023-12-20 | Government of the Philippines (current year's budget) | 363420 | 363420 |  | 301650 | 301650 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2023-10-12 | 2023-10-12 | 2023-10-12 | N/A | N/A | Completed
23-C0668 | OFFICE SUPPLIES | PEEMO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-09-28 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | 2023-11-09 | 2023-11-21 | 2023-11-24 |  |  | 2023-12-05 | 2023-12-05 | Government of the Philippines (current year's budget) | 316889 | 316889 |  | 309640 | 309640 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0729 | COMPUTER SUPPLIES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-01 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | 2023-11-08 | 2023-11-13 | 2023-11-14 |  |  | 2023-11-20 | 2023-11-20 | Government of the Philippines (current year's budget) | 124664 | 124664 |  | 124313 | 124313 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4133 | JANITORIAL SUPPLIES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-06 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | 2023-11-09 | 2023-11-21 | 2023-11-24 |  |  | 2023-12-04 | 2023-12-04 | Government of the Philippines (current year's budget) | 100875 | 100875 |  | 99135 | 99135 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0708 | OFFICE EQUIPMENT | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-17 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-26 |  |  |  | 2023-10-27 | 2023-11-21 | 2023-11-23 |  |  | 2023-11-30 | 2023-11-30 | Government of the Philippines (current year's budget) | 227100 | 227100 |  | 213800 | 213800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0691 | PRIZES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-03 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | N/A | 2023-11-16 | 2023-11-29 |  |  | 2023-12-20 | 2023-12-20 | Government of the Philippines (current year's budget) | 26995 | 26995 |  | 26995 | 26995 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4327 | FURNITURES & FIXTURES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-01 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | 2023-10-30 | 2023-11-21 | 2023-11-28 |  |  | 2023-11-30 | 2023-11-30 | Government of the Philippines (current year's budget) | 144700 | 144700 |  | 144700 | 144700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3139 | CLOUD SERVER SUBSCRIPTION | PICTO | No | NP-53.1 Two Failed Biddings | N/A | 2023-09-01 |  | N/A | 2023-10-17 | 2023-10-17 |  | N/A | N/A | 2023-10-27 |  |  |  | 2023-10-27 | 2023-11-21 | [5 empty] | Government of the Philippines (current year's budget) | 513190.86 | 513190.86 |  | 513190.86 | 513190.86 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4768 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-07 | 2023-11-13 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-13 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 11350 | 11350 |  | 11350 | 11350 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4766 | SPARE PARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-07 | 2023-11-13 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-13 | 2023-12-18 |  |  | 2023-12-18 | 2023-12-18 | Government of the Philippines (current year's budget) | 40424 | 40424 |  | 40424 | 40424 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4997 | SPARE PARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-07 | 2023-11-13 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-12 | 2023-12-13 |  |  | 2023-12-14 | 2023-12-14 | Government of the Philippines (current year's budget) | 13100 | 13100 |  | 13100 | 13100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4946 | BRAKE PAD, FOR MITS STRADA | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-07 | 2023-11-13 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-12 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 4070 | 4070 |  | 4070 | 4070 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4996 | BRAKE PAD, FOR MITS STRADA | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-07 | 2023-11-13 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-12 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 4070 | 4070 |  | 4070 | 4070 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4945 | SPARE PARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-07 | 2023-11-13 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-12 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 28500 | 28500 |  | 28500 | 28500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4999 | SHOCK ABSORBER, REAR FOR ISUZU DMAX | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-07 | 2023-11-13 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-12 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 12500 | 12500 |  | 12500 | 12500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-5125 | SPARE PARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-07 | 2023-11-13 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 20375 | 20375 |  | 20375 | 20375 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4927 | MEALS AND SNACKS | PHO | No | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-12-07 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | 2023-11-24 | 2023-12-13 | 2023-12-18 |  |  |  |  | Government of the Philippines (current year's budget) | 216000 | 216000 |  | 212000 | 212000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0802 | MEALS AND SNACKS | PSWDO | No | Competitive Bidding | 2023-11-07 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-12 | [6 empty] | Government of the Philippines (current year's budget) | 390000 | 390000 |  | 385600 | 385600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4998 | SPARE PARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-07 | 2023-11-23 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-11-24 | [5 empty] | Government of the Philippines (current year's budget) | 12200 | 12200 |  | 12200 | 12200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0896 | CHRISTMAS DECORATION | PGSO | No | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-13 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | 2023-11-24 | 2023-12-13 | 2023-12-13 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 175642 | 175642 |  | 174328 | 174328 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0688 | LABORATORY SUPPLIES | PEEMO | No | Direct Contracting | N/A | 2023-09-28 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-28 | 2023-11-28 |  |  | 2023-11-30 | 2023-11-30 | Government of the Philippines (current year's budget) | 112000 | 112000 |  | 112000 | 112000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0686 | LABORATORY SUPPLIES | PEEMO | No | Direct Contracting | N/A | 2023-09-28 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-29 | 2023-11-29 |  |  | 2023-12-06 | 2023-12-06 | Government of the Philippines (current year's budget) | 649440 | 649440 |  | 649440 | 649440 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4090 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-12 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 1617 | 1617 |  | 1617 | 1617 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4093 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-13 | 2023-12-13 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 17050 | 17050 |  | 17050 | 17050 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4089 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-12 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 4500 | 4500 |  | 4500 | 4500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4088 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-12 |  |  | 2023-12-14 | 2023-12-14 | Government of the Philippines (current year's budget) | 35080 | 35080 |  | 35080 | 35080 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4095 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-12 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 8400 | 8400 |  | 8400 | 8400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4099 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-12 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 5608 | 5608 |  | 5608 | 5608 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0723 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-08-22 | 2023-08-25 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-12 |  |  | 2023-12-14 | 2023-12-14 | Government of the Philippines (current year's budget) | 13800 | 13800 |  | 13800 | 13800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4615 | SPAREPARTS | COA | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-09 | 2023-10-16 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-28 | 2023-11-28 |  |  | 2023-11-30 | 2023-11-30 | Government of the Philippines (current year's budget) | 8000 | 8000 |  | 8000 | 8000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4596 | SPAREPARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-09 | 2023-10-16 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-28 | 2023-11-28 |  |  | 2023-11-28 | 2023-11-28 | Government of the Philippines (current year's budget) | 62950 | 62950 |  | 62950 | 62950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4597 | SPAREPARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-09 | 2023-10-16 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-30 | 2023-11-30 |  |  | 2023-12-12 | 2023-12-12 | Government of the Philippines (current year's budget) | 10100 | 10100 |  | 10100 | 10100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4598 | SPAREPARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-09 | 2023-10-16 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-28 | 2023-11-28 |  |  | 2023-11-29 | 2023-11-29 | Government of the Philippines (current year's budget) | 9000 | 9000 |  | 9000 | 9000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4594 | SPAREPARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-09 | 2023-10-16 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-28 | 2023-11-28 |  |  | 2023-11-29 | 2023-11-29 | Government of the Philippines (current year's budget) | 33520 | 33520 |  | 33520 | 33520 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0772 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-09 | 2023-10-16 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-12 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 60280 | 60280 |  | 60280 | 60280 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4504 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-10-09 | 2023-10-16 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-13 | 2023-12-13 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 14150 | 14150 |  | 14150 | 14150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4230 | OFFICE SUPPLIES | SEF | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-09-07 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-28 | 2023-12-28 |  |  | 0 | 0 | Government of the Philippines (current year's budget) | 39466 | 39466 |  | 38820 | 38820 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4476 | OFFICE SUPPLIES | PTO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-10-16 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 3300 | 3300 |  | 3225 | 3225 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4683 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-10-16 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | 2023-11-17 | 2023-11-23 | 2023-11-23 |  |  | 2023-12-04 | 2023-12-04 | Government of the Philippines (current year's budget) | 55528 | 55528 |  | 54259 | 54259 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3623 | JOB ORDER:TRANSPARENCY BOARD | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-17 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-12-12 | 2023-12-12 |  |  | 2023-12-22 | 2023-12-22 | Government of the Philippines (current year's budget) | 45000 | 45000 |  | 44975 | 44975 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-1430 | GLOBAL POSITIONING SYSTEM | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-14 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | 2023-11-22 | 2023-11-28 | 2023-11-28 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 57500 | 57500 |  | 49500 | 49500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4515 | FURNITURE AND FIXTURES | PGSO | No | Competitive Bidding | N/A | 2023-10-30 |  | N/A | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | N/A | 2023-11-15 |  |  |  | 2023-11-24 | 2023-12-12 | 2023-12-12 |  |  |  |  | Government of the Philippines (current year's budget) | 995794 | 995794 |  | 990500 | 990500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3257 | SPAREPARTS | PEO | No | Direct Contracting | 2023-07-25 | 2023-07-31 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-12 | 2023-12-12 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 1999982 | 1999982 |  | 1700675.82 | 1700675.82 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0736 | OFFICE SUPPLIES | PAO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-09-01 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-11-30 | 2023-11-30 |  |  | 2023-12-14 | 2023-12-14 | Government of the Philippines (current year's budget) | 5700 | 5700 |  | 5700 | 5700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4682 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-10-09 | 2023-10-16 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  | 2023-12-12 | 2023-12-12 | Government of the Philippines (current year's budget) | 6910 | 6910 |  | 6884.5 | 6884.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3717 | EQUIPMENT LOGBOOK | PGO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2023-10-06 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-11 | 2023-12-11 |  |  |  |  | Government of the Philippines (current year's budget) | 3325 | 3325 |  | 3150 | 3150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4603 | TARPAULIN | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  |  |  | Government of the Philippines (current year's budget) | 6384 | 6384 |  | 6384 | 6384 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5051 | MEALS AND SNACKS WITH ACCOMMODATION | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-11-28 | 2023-11-28 |  |  |  |  | Government of the Philippines (current year's budget) | 112000 | 112000 |  | 98000 | 98000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3230 | OFFICE EQUIPMENT | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-16 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 20000 | 20000 |  | 19700 | 19700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4529 | LED SOLAR STREET LIGHT | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-16 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-11-30 | 2023-11-30 |  |  | 2023-12-06 | 2023-12-06 | Government of the Philippines (current year's budget) | 19000 | 19000 |  | 18900 | 18900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0790 | PAINTING MATERIALS | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-16 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  | 2023-12-15 | 2023-12-15 | Government of the Philippines (current year's budget) | 57320 | 57320 |  | 57073 | 57073 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0777 | PAINTING MATERIALS | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-16 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-01 | 2023-12-01 |  |  |  |  | Government of the Philippines (current year's budget) | 16838 |  | 16838 | 16777.5 |  | 16777.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0213 | MEALS AND SNACKS WITH ACCOMMODATION | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-22 |  |  |  | 2023-11-22 | 2023-12-04 | 2023-12-04 |  |  | 2023-11-29 | 2023-11-29 | Government of the Philippines (current year's budget) | 300000 | 300000 |  | 294000 | 294000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4440 | CONSTRUCTION MATERIALS | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-10-09 | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-22 |  |  |  | 2023-11-22 | [6 empty] | Government of the Philippines (current year's budget) | 213155 | 213155 |  | 210590 | 210590 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4453 | OIL AND LUBRICANTS | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-16 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  |  |  | Government of the Philippines (current year's budget) | 26199 | 26199 |  | 21000 | 21000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3933 | CROCODILE JACK | PEO | No | NP-53.9 - Small Value Procurement | 2023-10-09 | 2023-10-16 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | 2023-11-30 | 2023-12-11 | 2023-12-11 |  |  |  |  | Government of the Philippines (current year's budget) | 50000 | 50000 |  | 50000 | 50000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3925 | TRANSMISSION JACK HYDRAULIC | PEO | No | NP-53.9 - Small Value Procurement | 2023-10-09 | 2023-10-16 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | 2023-11-30 | 2023-12-11 | 2023-12-11 |  |  |  |  | Government of the Philippines (current year's budget) | 150000 | 150000 |  | 150000 | 150000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4454 | SPAREPARTS | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-16 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  |  |  | Government of the Philippines (current year's budget) | 13645 | 13645 |  | 13645 | 13645 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4583 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  |  |  | Government of the Philippines (current year's budget) | 25200 | 25200 |  | 24750 | 24750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4512 | FOOD/CATERING SERVICES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-11-23 | 2023-11-23 |  |  | 2023-12-21 | 2023-12-21 | Government of the Philippines (current year's budget) | 11600 | 11600 |  | 11136 | 11136 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0807 | LABORATORY SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-11-30 | 2023-11-30 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 43754 | 43754 |  | 43105 | 43105 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4581 | FOOD SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  | 2023-12-11 | 2023-12-11 | Government of the Philippines (current year's budget) | 6600 | 6600 |  | 6588 | 6588 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0805 | LABORATORY SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-11-30 | 2023-11-30 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 87595 | 87595 |  | 87059 | 87059 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4745 | BINDING MACHINE | PACCO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 30000 | 30000 |  | 29900 | 29900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0797 | WATER | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  |  |  | Government of the Philippines (current year's budget) | 27675 | 27675 |  | 27000 | 27000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0798 | OFFICE EQUIPMENT | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  |  |  | Government of the Philippines (current year's budget) | 34400 | 34400 |  | 34373.5 | 34373.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4756 | OFFICE EQUIPMENT | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-22 |  |  |  | 2023-11-22 | 2023-12-01 | 2023-12-01 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 83600 | 83600 |  | 83400 | 83400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4781 | GLASSES | PDRRMO | No | NP-53.9 - Small Value Procurement | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-01 | 2023-12-01 |  |  |  |  | Government of the Philippines (current year's budget) | 20436 | 20436 |  | 20314.5 | 20314.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5184 | T-SHIRT W/ PRINTING | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-11-30 | 2023-11-30 |  |  | 2023-11-11 | 2023-11-11 | Government of the Philippines (current year's budget) | 38500 | 38500 |  | 38500 | 38500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4933 | STICKER | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  | 2023-12-14 | 2023-12-14 | Government of the Philippines (current year's budget) | 22960 | 22960 |  | 22960 | 22960 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4584 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-16 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | 2023-12-12 | 2023-11-24 | 2023-11-24 |  |  | 2023-11-29 | 2023-11-29 | Government of the Philippines (current year's budget) | 80868 | 80868 |  | 79110 | 79110 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0874 | MEDALS/PLAQUES/TROPHY | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | 2023-11-30 | 2023-12-11 | 2023-12-11 |  |  | 2023-11-17 | 2023-11-17 | Government of the Philippines (current year's budget) | 154000 | 154000 |  | 154000 | 154000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0130 | OFFICE EQUIPMENT | PHO | No | NP-53.9 - Small Value Procurement | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | 2023-11-29 | 2023-12-22 | 2023-12-22 |  |  |  |  | Government of the Philippines (current year's budget) | 53144 | 53144 |  | 48925 | 48925 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0706 | SPAPREPARTS | PICTO | No | NP-53.1 Two Failed Biddings | N/A | 2023-09-01 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | 2023-11-24 | 2023-12-01 | 2023-12-01 |  |  |  |  | Government of the Philippines (current year's budget) | 359500 |  | 359500 | 333400 |  | 333400 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3981 | RICE | PGO | No | NP-53.1 Two Failed Biddings | N/A | 2023-10-23 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | 2023-11-22 | 2023-12-11 | 2023-12-11 |  |  | 2023-12-23 | 2023-12-23 | Government of the Philippines (current year's budget) | 2025000 | 2025000 |  | 1984500 | 1984500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3527 | CAPITAL OUTLAY/OTHER MACHINERIES & EQUIPMENT | PDRRMO | No | NP-53.1 Two Failed Biddings | N/A | 2023-08-14 |  | N/A | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-11-24 |  |  |  | 2023-11-30 | 2023-11-30 | 2023-11-30 |  |  |  |  | Government of the Philippines (current year's budget) | 438000 | 438000 |  | 437000 | 437000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4278 | OFFICE EQUIPMENT | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-14 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-29 | 2023-11-29 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 37000 | 37000 |  | 36800 | 36800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4279 | OFFICE EQUIPMENT | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-14 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | N/A | 2023-11-29 | 2023-11-29 |  |  |  |  | Government of the Philippines (current year's budget) | 8400 | 8400 |  | 8400 | 8400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4619 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | 2023-10-09 | 2023-10-16 |  | N/A | 2023-11-07 | 2023-11-07 |  | N/A | N/A | 2023-11-15 |  |  |  | 2023-11-17 | 2023-11-29 | 2023-11-29 |  |  |  |  | Government of the Philippines (current year's budget) | 185000 | 185000 |  | 184000 | 184000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4757 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | N/A | 2023-11-28 | 2023-11-28 |  |  | 2023-12-07 | 2023-12-07 | Government of the Philippines (current year's budget) | 35670 | 35670 |  | 35192 | 35192 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4938 | FOOD/CATERING SERVICES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | 2023-11-24 | 2023-12-04 | 2023-12-04 |  |  | 2023-12-22 | 2023-12-22 | Government of the Philippines (current year's budget) | 257600 | 257600 |  | 257040 | 257040 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4426 | FOOD/CATERING SERVICES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | N/A | 2023-12-12 | 2023-12-12 |  |  |  |  | Government of the Philippines (current year's budget) | 24300 | 24300 |  | 24300 | 24300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0812 | FOOD/CATERING SERVICES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | 2023-11-28 | 2023-11-29 | 2023-11-29 |  |  | 2023-12-06 | 2023-12-06 | Government of the Philippines (current year's budget) | 271580 | 271580 |  | 254080 | 254080 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0894 | FOOD/CATERING SERVICES | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-17 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | 2023-11-23 | 2023-12-12 | 2023-12-12 |  |  | 2023-12-06 | 2023-12-06 | Government of the Philippines (current year's budget) | 276730 | 276730 |  | 273432 | 273432 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4630 | FOOD SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-16 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  | 2023-12-12 | 2023-12-12 | Government of the Philippines (current year's budget) | 20840 | 20840 |  | 20640 | 20640 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4626 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | 2023-11-23 | 2023-12-04 | 2023-12-04 |  |  | 2023-12-18 | 2023-12-18 | Government of the Philippines (current year's budget) | 82000 | 82000 |  | 80200 | 80200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3864 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-07-31 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | 2023-11-23 | 2023-11-28 | 2023-11-28 |  |  | 2023-12-22 | 2023-12-22 | Government of the Philippines (current year's budget) | 139000 | 139000 |  | 135900 | 135900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0795 | FOOD/CATERING SERVICES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | 2023-11-23 | 2023-11-30 | 2023-11-30 |  |  | 2023-12-15 | 2023-12-15 | Government of the Philippines (current year's budget) | 224700 | 224700 |  | 221022 | 221022 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4196 | GRASS CUTTER | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | N/A | 2023-11-30 | 2023-11-30 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 30000 | 30000 |  | 29800 | 29800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-5009 | ALCOHOL | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | N/A | 2023-12-18 | 2023-12-18 |  |  | 2023-12-21 | 2023-12-21 | Government of the Philippines (current year's budget) | 1600 | 1600 |  | 1560 | 1560 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-5224 | EXTENSION WIRE | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | N/A | 2023-12-13 | 2023-12-13 |  |  |  |  | Government of the Philippines (current year's budget) | 1200 | 1200 |  | 1150 | 1150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5022 | JANITORIAL SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | N/A | 2023-12-11 | 2023-12-11 |  |  | 2023-12-19 | 2023-12-19 | Government of the Philippines (current year's budget) | 9775 | 9775 |  | 9675 | 9675 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4774 | VOICE RECORDER | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | N/A | 2023-12-04 | 2023-12-04 |  |  | 2023-12-13 | 2023-12-13 | Government of the Philippines (current year's budget) | 3300 | 3300 |  | 3100 | 3100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-5000 | UPS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | N/A | 2023-12-11 | 2023-12-11 |  |  | 2023-12-21 | 2023-12-21 | Government of the Philippines (current year's budget) | 39600 | 39600 |  | 38800 | 38800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4621 | UPS | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | N/A | 2023-12-11 | 2023-12-11 |  |  | 2023-12-21 | 2023-12-21 | Government of the Philippines (current year's budget) | 34548 | 34548 |  | 33300 | 33300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4103 | FOOD/CATERING SERVICES | PGO | No | NP-53.1 Two Failed Biddings | N/A | 2023-10-23 |  | N/A | 2023-11-21 | 2023-11-21 |  | N/A | N/A | 2023-11-23 |  |  |  | 2023-12-14 | 2023-12-19 | 2023-12-19 |  |  |  |  | Government of the Philippines (current year's budget) | 496800 | 496800 |  | 496800 | 496800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4674 | FUEL, OIL AND LUBRICANTS | PEO | No | Competitive Bidding | 2023-10-09 | 2023-10-30 |  | 2023-11-07 | 2023-11-15 | 2023-11-15 |  | 2023-11-15 | 2023-11-20 | 2023-11-23 |  |  |  | 2023-11-24 | 2023-12-13 | 2023-12-13 |  |  | 2023-12-18 | 2023-12-18 | Government of the Philippines (current year's budget) | 3002800 | 3002800 |  | 1716000 | 1716000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-07-07 |  |  |  | N/A | N/A | Completed
23-3924 | ON BOARD DIAGNOSTIC TOOLS, UNIVERSAL | PEO | No | Competitive Bidding | N/A | 2023-10-09 |  | N/A | 2023-10-17 | 2023-10-17 |  | 2023-10-17 | 2023-11-17 | 2023-11-23 |  |  |  | 2023-11-28 | 2023-12-11 | 2023-12-11 |  |  |  |  | Government of the Philippines (current year's budget) | 500000 | 500000 |  | 499000 | 499000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A |  |  |  | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0791 | FEEDS | PVO | No | Competitive Bidding | N/A | 2023-10-09 |  | 2023-10-17 | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | 2023-11-17 | 2023-11-23 |  |  |  | 2023-11-28 | 2023-12-01 | 2023-12-01 |  |  | 2023-12-11 | 2023-12-11 | Government of the Philippines (current year's budget) | 1168057 | 1168057 |  | 1162613 | 1162613 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA |  |  |  |  | N/A | N/A | Completed
23-C0763 | PDRRMO | PDRRMO | No | Competitive Bidding | N/A | 2023-10-09 |  | 2023-10-17 | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | 2023-11-17 | 2023-11-23 |  |  |  | 2023-11-30 | 2023-11-30 | 2023-11-30 |  |  |  |  | Government of the Philippines (current year's budget) | 1187900 |  | 1187900 | 679875 |  | 679875 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA |  |  |  |  | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3928 | CRIMPING MACHINE | PGO | No | Competitive Bidding | N/A | 2023-10-09 |  | 2023-10-17 | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | 2023-11-17 | 2023-11-23 |  |  |  | 2023-11-28 | 2023-12-13 | 2023-12-13 |  |  |  |  | Government of the Philippines (current year's budget) | 1100000 | 1100000 |  | 1080000 | 1080000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA |  |  |  |  | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4510 | FURNITURE & FIXTURES | PGSO | No | Competitive Bidding | N/A | 2023-10-30 |  | N/A | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | 2023-11-20 | 2023-11-23 |  |  |  | 2023-11-30 | 2023-12-12 | 2023-12-12 |  |  |  |  | Government of the Philippines (current year's budget) | 684266 | 684266 |  | 680910 | 680910 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA |  |  |  |  | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5382 | COMPUTER SET | PIAO | No | NP-53.9 - Small Value Procurement | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-18 | 2023-12-18 |  |  |  |  | Government of the Philippines (current year's budget) | 40000 | 40000 |  | 39900 | 39900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4686 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-12 | [6 empty] | Government of the Philippines (current year's budget) | 75000 | 75000 |  | 74400 | 74400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0907 | OTHER SUPPLIES/MATERIALS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-11 | [6 empty] | Government of the Philippines (current year's budget) | 51478 | 51478 |  | 50030 | 50030 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5283 | RICE | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-18 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 11479.44 | 11479.44 |  | 11436 | 11436 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5281 | OTHER SUPPLIES/MATERIALS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-18 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-11 | [6 empty] | Government of the Philippines (current year's budget) | 106993.7 | 106993.7 |  | 106815 | 106815 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0891 | FOOD/CATERING SERVICES | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-18 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-11 | [6 empty] | Government of the Philippines (current year's budget) | 340400 | 340400 |  | 340104 | 340104 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0853 | PLUMBING SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-13 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-22 | 2023-12-22 |  |  |  |  | Government of the Philippines (current year's budget) | 47280 | 47280 |  | 47015 | 47015 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0852 | ELECTRICAL SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-13 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-22 | 2023-12-22 |  |  |  |  | Government of the Philippines (current year's budget) | 34915 | 34915 |  | 34495 | 34495 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5384 | PLAQUES | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-27 | 2023-12-27 |  |  |  |  | Government of the Philippines (current year's budget) | 6000 | 6000 |  | 6000 | 6000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4179 | STEEL CASEMENT WINDOW | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-01 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-27 | 2023-12-27 |  |  |  |  | Government of the Philippines (current year's budget) | 38186.4 | 38186.4 |  | 38185 | 38185 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4174 | JALOUSIE WINDOW | PEO | No | NP-53.9 - Small Value Procurement | 2023-09-05 | 2023-09-07 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-22 | 2023-12-22 |  |  |  |  | Government of the Philippines (current year's budget) | 12740 | 12740 |  | 12739.5 | 12739.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4121 | STEEL CASEMENT WINDOW | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-08-25 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-22 | 2023-12-22 |  |  |  |  | Government of the Philippines (current year's budget) | 45570 | 45570 |  | 45569 | 45569 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4177 | JALOUSIE WINDOW | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-01 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-27 | 2023-12-27 |  |  |  |  | Government of the Philippines (current year's budget) | 12740 | 12740 |  | 12740 | 12740 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4191 | JALOUSIE WINDOW | PEO | No | NP-53.9 - Small Value Procurement | 2023-09-05 | 2023-09-07 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-22 | 2023-12-22 |  |  |  |  | Government of the Philippines (current year's budget) | 12740 | 12740 |  | 12740 | 12740 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4176 | JALOUSIE WINDOW | PEO | No | NP-53.9 - Small Value Procurement | 2023-09-05 | 2023-09-07 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-22 | 2023-12-22 |  |  |  |  | Government of the Philippines (current year's budget) | 12740 | 12740 |  | 12739.5 | 12739.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4175 | JALOUSIE WINDOW | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-01 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-22 | 2023-12-22 |  |  |  |  | Government of the Philippines (current year's budget) | 12740 | 12740 |  | 12739.5 | 12739.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4190 | JALOUSIE WINDOW | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2023-09-01 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-27 | 2023-12-27 |  |  |  |  | Government of the Philippines (current year's budget) | 12740 | 12740 |  | 12739.5 | 12739.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4561 | WALL PARTITION | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-12 | 2023-12-13 | 2023-12-13 |  |  | 2023-12-27 | 2023-12-27 | Government of the Philippines (current year's budget) | 79895.2 | 79895.2 |  | 79890 | 79890 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5306 | OFFICE EQUIPMENT | PGO | No | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-17 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-14 | 2023-12-19 | 2023-12-19 |  |  |  |  | Government of the Philippines (current year's budget) | 95000 | 95000 |  | 94800 | 94800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5163 | FOOD CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-07 | [6 empty] | Government of the Philippines (current year's budget) | 500000 | 500000 |  | 500000 | 500000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5265 | FOOD CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-11 | [6 empty] | Government of the Philippines (current year's budget) | 392550 | 392550 |  | 387316 | 387316 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3772 | BROOM STICK | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 4500 | 4500 |  | 4400 | 4400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4157 | FLASHLIGHT | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 17050 | 17050 |  | 16700 | 16700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5023 | FIRE EXTINGUISHER | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 8140 | 8140 |  | 8100 | 8100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4678 | MINERAL WATER | PVO | No | NP-53.9 - Small Value Procurement | 2023-10-09 | 2023-10-16 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 2460 | 2460 |  | 2400 | 2400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4617 | MINERAL WATER | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 15375 | 15375 |  | 15000 | 15000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5225 | PROJECTOR | PIAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-18 | 2023-12-18 |  |  |  |  | Government of the Philippines (current year's budget) | 49500 | 49500 |  | 48000 | 48000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0810 | OFFICE EQUIPMENT | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-14 | [6 empty] | Government of the Philippines (current year's budget) | 242379 | 242379 |  | 240700 | 240700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-3758 | LIQUID NITROGEN | PVO | No | NP-53.9 - Small Value Procurement | 2023-07-25 | 2023-07-31 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 19140 | 19140 |  | 19140 | 19140 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4870 | FOOD/CATERING SERVICES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-27 | 2023-12-27 | 2023-12-27 |  |  |  |  | Government of the Philippines (current year's budget) | 50490 | 50490 |  | 49572 | 49572 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4528 | AIRCON | PGSO | No | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-17 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-12 | [6 empty] | Government of the Philippines (current year's budget) | 100000 | 100000 |  | 99000 | 99000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0863 | FIRE EXTINGUISHER | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-22 | 2023-12-22 |  |  |  |  | Government of the Philippines (current year's budget) | 32780 | 32780 |  | 32570 | 32570 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5008 | JANITORIAL SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 20900 | 20900 |  | 20280 | 20280 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4902 | SAFETY GEARS & EQUIPMENT | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | 2023-12-11 | 2023-12-27 | 2023-12-27 |  |  |  |  | Government of the Philippines (current year's budget) | 104400 | 104400 |  | 103760 | 103760 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4487 | OFFICE SUPPLIES | PENRO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-10-09 | 2023-10-16 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-13 | 2023-12-13 |  |  | 2023-12-22 | 2023-12-22 | Government of the Philippines (current year's budget) | 15425 | 15425 |  | 15301.5 | 15301.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-5271 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 3500 | 3500 |  | 3500 | 3500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5354 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 23350 | 23350 |  | 23350 | 23350 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4772 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 36470 | 36470 |  | 36470 | 36470 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5349 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 26600 | 26600 |  | 26600 | 26600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5274 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-15 | 2023-11-18 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 35800 | 35800 |  | 35800 | 35800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5347 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 3500 | 3500 |  | 3500 | 3500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5346 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 51000 | 51000 |  | 51000 | 51000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5344 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 9850 | 9850 |  | 9850 | 9850 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5316 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 120000 | 120000 |  | 120000 | 120000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5342 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 11215 | 11215 |  | 11215 | 11215 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5350 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 42100 | 42100 |  | 42100 | 42100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4985 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-07 | 2023-11-13 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 9000 | 9000 |  | 9000 | 9000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5273 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 6500 | 6500 |  | 6500 | 6500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5272 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 5500 | 5500 |  | 5500 | 5500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0902 | SPAREPARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-27 | 2023-12-29 |  |  | 2023-12-29 | 2023-12-29 | Government of the Philippines (current year's budget) | 53900 | 53900 |  | 53900 | 53900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-5315 | SPAREPARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-27 | 2023-12-29 |  |  | 2023-12-29 | 2023-12-29 | Government of the Philippines (current year's budget) | 4000 | 4000 |  | 4000 | 4000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-5239 | SPAREPARTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-15 | 2023-11-17 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-22 | 2023-12-29 |  |  | 2023-12-29 | 2023-12-29 | Government of the Philippines (current year's budget) | 18950 | 18950 |  | 18950 | 18950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-5238 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-15 | 2023-11-17 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-27 |  |  |  | 2023-12-29 |  | Government of the Philippines (current year's budget) | 7497 | 7497 |  | 7497 | 7497 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4988 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-15 | 2023-11-18 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 13400 | 13400 |  | 13400 | 13400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4981 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-15 | 2023-11-18 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 7497 | 7497 |  | 7497 | 7497 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4878 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-15 | 2023-11-18 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 13400 | 13400 |  | 13400 | 13400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5351 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 3200 | 3200 |  | 3200 | 3200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5343 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 14500 | 14500 |  | 14500 | 14500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5348 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 4910 | 4910 |  | 4910 | 4910 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-5275 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | [6 empty] | Government of the Philippines (current year's budget) | 1800 | 1800 |  | 1800 | 1800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4662 | GAS | PEO | No | Direct Contracting | 2023-10-09 | 2023-10-23 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-22 | [5 empty] | Government of the Philippines (current year's budget) | 45075 | 45075 |  | 45075 | 45075 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-4613 | DUPLICATING PRODUCTS | VGO | No | Direct Contracting | 2023-10-17 | 2023-10-23 |  | N/A | 2023-11-29 | 2023-11-29 |  | N/A | N/A | 2023-12-07 |  |  |  | N/A | 2023-12-27 | [5 empty] | Government of the Philippines (current year's budget) | 5115 | 5115 |  | 5115 | 5115 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING RESTRICTED TO PACCO
23-C0660 | COMPUTER SUPPLIES | SEF | No | NP-53.9 - Small Value Procurement | 2023-08-08 | 2023-08-14 |  | N/A | 2023-08-30 | 2023-08-30 |  | N/A | N/A | 2023-09-04 |  |  |  | 2023-09-08 | 2023-10-09 | 2023-10-12 |  |  | 2023-10-20 | 2023-10-20 | Government of the Philippines (current year's budget) | 189891 | 189891 |  | 188220 | 188220 | [9 empty] | Completed
-
[25 empty] | Total Allotted Budget of Procurement Activities | 232417570.29 | 133225175.15 | 99392395.14 |  |  |  | 8.16%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 213451318.83 | 120511886.11 | 93211170.72
[25 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 18966251.46 | [14 empty] | 2023-06-30
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column42
ONGOING PROCUREMENT ACTIVITIES | [25 empty] | 0 | [5 empty] | -
23-C0820 | SEEDLINGS | PDRRMO | No | Competitive Bidding | 2023-11-07 | 2023-11-13 | 6 | N/A | 2023-11-21 | 2023-11-21 | 8 | 2023-11-21 | 2023-12-04 | 2023-12-13 | 13 | 22 | 30 | 2023-12-19 | [7 empty] | 556800 | 556800 |  | 385210 | 385210 |  | 0.30817 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Awarded with issued Notice of Award | 0
23-5126 | COMPUTER SYSTEM UNIT (AS PER SPECIFICATION) | PASSO | No | Competitive Bidding | 2023-11-15 | 2023-11-21 | 6 | N/A | 2023-11-29 | 2023-11-29 | 8 | 2023-11-29 | 2023-12-04 | 2023-12-13 | 5 | 14 | 22 | 2023-12-14 | [7 empty] | 313929 | 313929 |  | 301000 | 301000 |  | 4.118% | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Awarded with issued Notice of Award | 0
23-C0752 | MEALS AND SNACKS WITH ACCOMMODATION | PSWDO | No | Competitive Bidding | N/A | 2023-11-05 |  | 2023-11-15 | 2023-11-29 | 2023-11-29 |  | 2023-11-29 | 2023-12-04 | 2023-12-13 |  |  |  | 2023-12-19 | [7 empty] | 1092500 | 1092500 |  | 190125 | 190125 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Awarded with issued Notice of Award
23-C0883 | COMPUTER EQUIPMENT AND DEVICES | PICTO | No | Competitive Bidding | 2023-11-15 | 2023-11-21 |  | N/A | 2023-11-29 | 2023-11-29 |  | 2023-11-29 | 2023-12-04 | 2023-12-13 |  |  |  | 2023-12-14 | [7 empty] | 756753 | 756753 |  | 651400 | 651400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Awarded with issued Notice of Award
23-5254 | SPAREPARTS | COA | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 5700 | 5700 |  | 5700 | 5700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0889 | SPAREPARTS | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-29 | 2023-12-01 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 15220 | 15220 |  | 15220 | 15220 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5411 | SPAREPARTS | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-29 | 2023-12-01 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 13500 | 13500 |  | 13500 | 13500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5380 | SPAREPARTS | DDOPH-MARAGUSAN | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-29 | 2023-12-01 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 7300 | 7300 |  | 7300 | 7300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4348 | SPAREPARTS | DDOPH-PANTUKAN | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-29 | 2023-12-01 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 41774 | 41774 |  | 41774 | 41774 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4350 | SPAREPARTS | DDOPH-PANTUKAN | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2023-12-01 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 4680 | 4680 |  | 4680 | 4680 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4349 | SPAREPARTS | DDOPH-PANTUKAN | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-29 | 2023-12-01 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 45000 | 45000 |  | 45000 | 45000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5352 | SPAREPARTS | DDOPH-PANTUKAN | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-29 | 2023-12-01 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 5000 | 5000 |  | 5000 | 5000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0793 | DRUG AND MEDICINE | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 96700 | 96700 |  | 95600 | 95600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5025 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 43339 | 43339 |  | 41998 | 41998 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0844 | OFFICE SUPPLIES | PEEMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2023-11-17 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 33501 | 33501 |  | 33200 | 33200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-2736 | FOOD/CATERING SERVICES | PENRO | No | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 48300 | 48300 |  | 48195 | 48195 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4163 | AIRCON | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 35900 | 35900 |  | 35900 | 35900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5154 | OFFICE SUPPLIES | SPO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 32022 | 32022 |  | 31210 | 31210 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0860 | OFFICE SUPPLIES | PHO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-11-07 | 2023-11-13 | 6 | N/A | N/A | 2023-12-05 | 22 | N/A | N/A | 2023-12-13 |  | 8 | 30 | 2023-12-14 | [7 empty] | 67505 | 67505 |  | 63700 | 63700 |  | 5.637% | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process | -136
23-5015 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-11-07 | 2023-11-13 | 6 | N/A | N/A | 2023-12-05 | 22 | N/A | N/A | 2023-12-13 |  | 8 | 30 | N/A | [7 empty] | 33415 | 33415 |  | 32590 | 32590 |  | 0.02469 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process | -136
23-C0854 | CONSTRUCTION SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 7040 | 7040 |  | 6996 | 6996 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23- C0833 | RAINCOAT | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 9350 | 9350 |  | 9295 | 9295 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0814 | LABORATORY SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 24746 | 24746 |  | 24452 | 24452 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4578 | ELECTRICAL SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | 2023-12-18 | [7 empty] | 250500 | 250500 |  | 249408 | 249408 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4895 | TARPAULIN | PGO | No | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-15 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | N/A | [7 empty] | 32480 | 32480 |  | 32480 | 32480 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4579 | RICE | PGO | No | NP-53.1 Two Failed Biddings | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | 2023-12-11 | [7 empty] | 675000 | 675000 |  | 675000 | 675000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0670 | RICE | PEEMO | No | NP-53.1 Two Failed Biddings | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | 2023-12-11 | [7 empty] | 447500 | 447500 |  | 447500 | 447500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-3814 | TWO SEATER STUDENT TABLE AND CHAIR | SEF | No | NP-53.1 Two Failed Biddings | N/A | 2023-11-17 |  | N/A | N/A | 2023-12-05 |  | N/A | N/A | 2023-12-13 |  |  |  | 2023-12-14 | [7 empty] | 1200000 | 1200000 |  | 1200000 | 1200000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4347 | MOBILE SHOWER AND RESTROOM | PDRRMO | No | Competitive Bidding | N/A | 2023-11-05 |  | 2023-11-15 | 2023-11-29 | 2023-11-29 |  | 2023-11-29 | 2023-12-07 | 2023-12-14 |  |  |  | 2023-12-19 | [7 empty] | 1000000 | 1000000 |  | 998000 | 998000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-4422 | WATER MOBILE PURIFICATION UNIT, LMS | PDRRMO | No | Competitive Bidding | 2023-10-03 | 2023-11-05 |  | 2023-11-15 | 2023-11-29 | 2023-11-29 |  | 2023-11-29 | 2023-12-07 | 2023-12-14 |  |  |  | 2023-12-19 | [7 empty] | 2000000 | 2000000 |  | 1998000 | 1998000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-4050 | MACHINERIES AND EQUIPMENT | PDRRMO | No | Competitive Bidding | N/A | 2023-10-09 |  | 2023-10-17 | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | 2023-12-12 | 2023-12-14 |  |  |  | 2023-12-27 | [7 empty] | 1240000 | 1240000 |  | 1230000 | 1230000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-3932 | DELIVERY WELDING MACHINE | PEO | No | Competitive Bidding | N/A | 2023-11-13 |  | 2023-11-21 | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-12 | 2023-12-14 |  |  |  | 2023-12-27 | [7 empty] | 1300000 | 1300000 |  | 860000 | 860000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-4751 | SOLAR SET WITH SOLAR FLOODLIGHT AND BILLBOARD | PEO | No | Competitive Bidding | 2023-10-17 | 2023-11-27 |  | N/A | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-14 |  |  |  | 2023-12-18 | [7 empty] | 432435.54 | 432435.54 |  | 376218.91 | 376218.91 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-4752 | SOLAR SET WITH SOLAR FLOODLIGHT AND BILLBOARD | PEO | No | Competitive Bidding | 2023-10-17 | 2023-11-27 |  | N/A | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-14 |  |  |  | 2023-12-18 | [7 empty] | 291660.81 | 291660.81 |  | 253744.9 | 253744.9 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-4753 | SOLAR SET WITH SOLAR FLOODLIGHT AND BILLBOARD | PEO | No | Competitive Bidding | 2023-10-17 | 2023-11-27 | 41 | N/A | 2023-12-05 | 2023-12-05 | 8 | 2023-12-05 | 2023-12-11 | 2023-12-14 | 6 | 9 | 17 | 2023-12-18 | [7 empty] | 292706.2 | 292706.2 |  | 254654.39 | 254654.39 |  | 0.13 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process | -150
23-4754 | SOLAR SET WITH SOLAR FLOODLIGHT AND BILLBOARD | PEO | No | Competitive Bidding | 2023-10-17 | 2023-11-27 |  | N/A | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-14 |  |  |  | 2023-12-18 | [7 empty] | 292706.2 | 292706.2 |  | 254654.39 | 254654.39 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-4755 | SOLAR SET WITH SOLAR FLOODLIGHT AND BILLBOARD | PEO | No | Competitive Bidding | 2023-10-17 | 2023-11-27 |  | N/A | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-14 |  |  |  | 2023-12-18 | [7 empty] | 301229.82 | 301229.82 |  | 262069.94 | 262069.94 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-4517 | FURNITURE AND FIXTURES | PGSO | No | Competitive Bidding | N/A | 2023-11-05 |  | 2023-11-15 | 2023-11-29 | 2023-11-29 |  | 2023-11-29 | 2023-12-07 | 2023-12-14 |  |  |  | 2023-12-22 | [7 empty] | 1130244 | 1130244 |  | 1126140 | 1126140 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-C0849 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Competitive Bidding | N/A | 2023-11-13 |  | 2023-11-21 | 2023-12-12 | 2023-12-12 |  | 2023-12-12 | 2023-12-11 | 2023-12-14 |  |  |  | 2023-12-15 | [7 empty] | 1725660 | 1725660 |  | 1709080 | 1709080 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-5313 | SPAREPARTS (LIGHT VEHICLE) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | N/A | [7 empty] | 9075 | 9075 |  | 9075 | 9075 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5314 | SPAREPARTS (LIGHT VEHICLE) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-11-21 | 2023-11-24 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | N/A | [7 empty] | 3000 | 3000 |  | 3000 | 3000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0811 | LPG GAS REFILL | PAGRO | No | Direct Contracting | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | N/A | [7 empty] | 39028 | 39028 |  | 32680 | 32680 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4342 | ACCOUNTABLE FORMS | PTO | No | NP-53.5 Agency-to-Agency | N/A | 2023-10-16 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | 2023-12-27 | [7 empty] | 217800 | 217800 |  | 184800 | 184800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4142 | OTHER SUPPLIES/MATERIALS | PICTO | No | NP-53.9 - Small Value Procurement | 2023-09-05 | 2023-09-07 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | N/A | [7 empty] | 1540 | 1540 |  | 1480 | 1480 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4744 | COMPUTER SUPPLIES/SPAREPARTS | PBO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | N/A | [7 empty] | 1500 | 1500 |  | 1300 | 1300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0792 | MINERAL WATER | PGO | No | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | 2023-12-15 | [7 empty] | 77244 | 77244 |  | 75360 | 75360 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Awarded with issued Notice of Award
23-5088 | SPAREPARTS (LIGHT VEHICLES) | PGO | No | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | N/A | [7 empty] | 42600 | 42600 |  | 39600 | 39600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4741 | SPAREPARTS (LIGHT VEHICLES) | PGO | No | NP-53.9 - Small Value Procurement | 2023-10-17 | 2023-10-23 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | N/A | [7 empty] | 5060 | 5060 |  | 5060 | 5060 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5013 | FUEL, OIL, AND LUBRICANTS | PGO | No | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | N/A | [7 empty] | 7495 | 7495 |  | 6300 | 6300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5095 | FUEL, OIL, AND LUBRICANTS | PGO | No | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | N/A | [7 empty] | 11190 | 11190 |  | 10680 | 10680 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0780 | MEDICAL SUPPLIES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | N/A | [7 empty] | 29377 | 29377 |  | 29276.25 | 29276.25 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-3848 | PRINTER | PPDO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | N/A | [7 empty] | 13420 | 13420 |  | 13400 | 13400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5012 | OFFICE EQUIPMENT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | N/A | [7 empty] | 37000 | 37000 |  | 37000 | 37000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4855 | OFFICE EQUIPMENT | PAGRO | No | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | 2023-12-19 | [7 empty] | 188547 | 188547 |  | 187744 | 187744 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Awarded with issued Notice of Award
23-5513 | ASSORTED DECORATIONS | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2023-12-06 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | N/A | [7 empty] | 14900 | 14900 |  | 14850 | 14850 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-3457 | WATER SEPARATOR | PEO-MOTORPOOL | No | NP-53.9 - Small Value Procurement | 2023-07-25 | 2023-07-31 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | 2023-12-19 | [7 empty] | 222362 | 222362 |  | 222110 | 222110 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Awarded with issued Notice of Award
23-C0842 | MINERAL WATER | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-14 |  |  |  | 2023-12-15 | [7 empty] | 47191 | 47191 |  | 46040 | 46040 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Awarded with issued Notice of Award
23-C0892 | DUPLICATING PARTS | SPO | No | Direct Contracting | 2023-11-21 | 2023-11-24 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 12850 | 12850 |  | 12850 | 12850 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0914 | MEDICAL OXYGEN REFILL | PEEMO | No | Direct Contracting | 2023-12-12 | 2023-12-19 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 1066200 | 1066200 |  | 1066200 | 1066200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0837 | MEDICAL OXYGEN REFILL | PEEMO | No | Direct Contracting | N/A | 2023-11-24 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 1579800 | 1579800 |  | 1579800 | 1579800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4045 | INTERNET SUBSCRIPTION | PAO | No | Direct Contracting | 2023-09-19 | 2023-10-06 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 233016 | 233016 |  | 219500 | 219500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4712 | ACETYLENE & OXYGEN REFILL | PDRRMO | No | Direct Contracting | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 2900 | 2900 |  | 2285 | 2285 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0695 | ELECTROLYTES ANALYZER | PEEMO | No | Direct Contracting | 2023-10-03 | 2023-10-06 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 455592 | 455592 |  | 455592 | 455592 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0868 | DRUGS AND MEDICINES | PEEMO | No | Direct Contracting | N/A | 2023-11-24 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 105300 | 105300 |  | 105300 | 105300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0866 | ELECTROLYTES ANALYZER | PEEMO | No | Direct Contracting | 2023-11-29 | 2023-12-01 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 608850 | 608850 |  | 608850 | 608850 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5427 | SPAREPARTS | PGSO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-12 | 2023-12-14 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 3150 | 3150 |  | 3150 | 3150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5431 | SPAREPARTS | PGSO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-05 | 2023-12-12 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 32400 | 32400 |  | 32400 | 32400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5425 | SPAREPARTS | PGSO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-05 | 2023-12-12 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 36900 | 36900 |  | 36900 | 36900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0908 | SPAREPARTS | PDRRMO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-05 | 2023-12-12 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 10350 | 10350 |  | 10350 | 10350 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5426 | JOB OUT: AIRCON REPAIR | PGSO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-05 | 2023-12-12 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 8050 | 8050 |  | 8050 | 8050 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5407 | SPAREPARTS | PGSO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-05 | 2023-12-12 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 |  |  |  | N/A | [7 empty] | 3250 | 3250 |  | 3250 | 3250 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4588 | RAIN WATER COLLECTION STAINLESS | PDRRMO |  | NP-53.1 Two Failed Biddings | N/A | 2023-11-24 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 448800 | 448800 |  | 448305 | 448305 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0809 | FOOD SUPPLIES | PGO |  | NP-53.1 Two Failed Biddings | N/A | 2023-11-24 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 431336 | 431336 |  | 430930 | 430930 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4666 | ELECTRIC KILOWATT HOUR METER | PGO |  | NP-53.1 Two Failed Biddings | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 1200000 | 1200000 |  | 1200000 | 1200000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5090 | OFFICE SUPPLIES | PGO |  | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 3670 | 3670 |  | 3664 | 3664 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0832 | OFFICE SUPPLIES | PDRRMO |  | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 22845 | 22845 |  | 22697 | 22697 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4891 | OFFICE SUPPLIES | PASSO |  | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 7045 | 7045 |  | 7023 | 7023 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5005 | OFFICE SUPPLIES | PASSO |  | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 4950 | 4950 |  | 4950 | 4950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0876 | OFFICE SUPPLIES | PGO |  | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 8170 | 8170 |  | 8147 | 8147 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0671 | SPAREPARTS | PEEMO |  | NP-53.9 - Small Value Procurement | N/A | 2023-09-07 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 2120 | 2120 |  | 2090 | 2090 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4641 | OTHER SUPPLIES/MATERIALS | PICTO |  | NP-53.9 - Small Value Procurement | 2023-10-09 | 2023-10-16 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 89694 | 89694 |  | 89000 | 89000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0757 | COPPER TUBE | PGSO |  | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 211200 | 211200 |  | 202200 | 202200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5161 | ELECTRICAL SUPPLIES | PICTO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 3493 | 3493 |  | 3480 | 3480 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0826 | OTHER SUPPLIES/MATERIALS | PDRRMO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-17 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 16600 | 16600 |  | 16435 | 16435 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4798 | JANITORIAL SUPPLIES/HOUSEKEEPING | PPDO |  | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 6602 | 6602 |  | 6440 | 6440 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4623 | SPAREPARTS (AIRCONDITION) | PEO-GA |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 42650 | 42650 |  | 42648 | 42648 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0875 | TOKEN | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 90400 | 90400 |  | 90400 | 90400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4160 | OTHER SUPPLIES | PAO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 56100 | 56100 |  | 50400 | 50400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5227 | RICE | PHO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 357280 | 357280 |  | 313200 | 313200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5057 | SPAREPARTS | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 53500 | 53500 |  | 53375 | 53375 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5501 | CONSTRUCTION SUPPLIES | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-12-06 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 110349 | 110349 |  | 109225.5 | 109225.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0768 | CONSTRUCTION SUPPLIES | PDRRMO |  | NP-53.9 - Small Value Procurement | 2023-10-03 | 2023-10-06 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 246197 | 246197 |  | 244471.75 | 244471.75 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0888 | OFFICE EQUIPMENT | PTO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 297500 | 297500 |  | 295895 | 295895 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5004 | TIRES | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 35500 | 35500 |  | 35500 | 35500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5007 | OFFICE EQUIPMENT | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 34600 | 34600 |  | 34500 | 34500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5092 | OFFICE EQUIPMENT | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 50500 | 50500 |  | 50120 | 50120 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5096 | SPAREPARTS | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 4100 | 4100 |  | 4100 | 4100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0824 | JANITORIAL SUPPLIES | PDRRMO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 32285 | 32285 |  | 32255 | 32255 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4680 | LIQUID NITROGEN | PVO |  | NP-53.9 - Small Value Procurement | 2023-10-06 | 2023-10-16 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 38280 | 38280 |  | 38280 | 38280 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0899 | SOLAR LIGHT | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-21 | 2023-11-24 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 132600 | 132600 |  | 132600 | 132600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5263 | OFFICE EQUIPMENT | PAO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-24 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 186000 | 186000 |  | 182000 | 182000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0924 | OFFICE EQUIPMENT | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-12-06 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 35000 | 35000 |  | 32050 | 32050 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0890 | OFFICE EQUIPMENT | PSWDO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 59200 | 59200 |  | 42878 | 42878 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0898 | OFFICE EQUIPMENT | PICTO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-17 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 161400 | 161400 |  | 121743 | 121743 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0884 | OFFICE EQUIPMENT | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-17 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 75000 | 75000 |  | 61568 | 61568 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0815 | LABORATORY SUPPLIES | PAGRO |  | NP-53.9 - Small Value Procurement | N/A | 2023-12-01 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 427544 | 427544 |  | 423856 | 423856 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5242 | OTHER SUPPLIES/MATERIALS | PICTO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 16170 | 16170 |  | 16161 | 16161 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5241 | EMERGENCY LIGHT | PICTO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 7590 | 7590 |  | 7583.25 | 7583.25 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4162 | FREEZER | PAO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-17 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 26345 | 26345 |  | 26338 | 26338 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5146 | FLUORESCENT TUBE | PHO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 65000 | 65000 |  | 64750 | 64750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4992 | MEMORY CARD | PAO |  | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 7200 | 7200 |  | 7200 | 7200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0783 | CONSTRUCTION SUPPLIES | PGSO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 111687 | 111687 |  | 111070 | 111070 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0817 | LPG | PAGRO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 6970 | 6970 |  | 6970 | 6970 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0835 | WHISTLE | PENRO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 2520 | 2520 |  | 2520 | 2520 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0920 | OFFICE EQUIPMENT | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-12-06 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 523316 | 523316 |  | 512100 | 512100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5011 | FOOD SUPPLIES | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 42616 | 42616 |  | 41910 | 41910 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5500 | OFFICE EQUIPMENT | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-12-06 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 133600 | 133600 |  | 131800 | 131800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5499 | INK | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-12-06 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 14880 | 14880 |  | 14160 | 14160 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0900 | OFFICE EQUIPMENT | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-21 | 2023-11-24 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 100982 | 100982 |  | 99800 | 99800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4580 | FOOD CATERING SERVICES | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-10-23 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 49200 | 49200 |  | 48900 | 48900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5191 | FOOD CATERING SERVICES | PASSO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 6000 | 6000 |  | 5520 | 5520 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0765 | FOOD/CATERING SERVICES | PGO |  | NP-53.9 - Small Value Procurement | 2023-10-09 | 2023-10-16 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 100000 | 100000 |  | 98100 | 98100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5143 | FOOD/CATERING SERVICES | PASSO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 27500 | 27500 |  | 27500 | 27500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5058 | DOGFOOD | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 36630 | 36630 |  | 31500 | 31500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5086 | OFFICE EQUIPMENT | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 14913 | 14913 |  | 13535 | 13535 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5003 | WATER | PDRRMO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 14391 | 14391 |  | 14040 | 14040 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5155 | WATER | SPO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-17 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 32677 | 32677 |  | 31880 | 31880 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5246 | OFFICE EQUIPMENT | PICTO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 49200 | 49200 |  | 49173 | 49173 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4797 | OFFICE EQUIPMENT | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-17 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 87400 | 87400 |  | 87388 | 87388 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0843 | OFFICE EQUIPMENT | PEO-GA |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 71050 | 71050 |  | 71026 | 71026 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5081 | JANITORIAL SUPPLIES | PEO-GA |  | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 50227 | 50227 |  | 50172 | 50172 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0654 | GARDEN SUPPLIES | PGSO |  | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 32422 | 32422 |  | 32382 | 32382 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0873 | CONSTRUCTION SUPPLIES | PAO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 44900 | 44900 |  | 44830 | 44830 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4971 | MAGAZINE & POSTER | PAO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-17 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 270000 | 270000 |  | 267040 | 267040 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-3458 | FOOD/CATERING SERVICES | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-09-14 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 25200 | 25200 |  | 25020 | 25020 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4904 | GARMENTS | PDRRMO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 16000 | 16000 |  | 13500 | 13500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5257 | MUGS | PHO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 9000 | 9000 |  | 9000 | 9000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0827 | OFFICE EQUIPMENT | PDRRMO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 20699 | 20699 |  | 20699 | 20699 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0916 | LABORATORY SUPPLIES | PEEMO |  | NP-53.9 - Small Value Procurement | 2023-12-12 | 2023-12-14 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 283254 | 283254 |  | 279214 | 279214 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5097 | RICE COOKER | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 2100 | 2100 |  | 2100 | 2100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5098 | OFFICE EQUIPMENT | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 185210 | 185210 |  | 179600 | 179600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5006 | COFFEE MAKER | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 5128.65 | 5128.65 |  | 5120 | 5120 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4898 | RIBBON | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 2400 | 2400 |  | 2400 | 2400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5089 | INDUSTRIAL FAN | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 7000 | 7000 |  | 6980 | 6980 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5223 | POLO SHIRT | PSWDO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 18000 | 18000 |  | 18000 | 18000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4773 | TARPAULIN | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-17 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 56000 | 56000 |  | 56000 | 56000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4266 | TARPAULIN | PEO-GA |  | NP-53.9 - Small Value Procurement | 2023-10-03 | 2023-10-06 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 1792 | 1792 |  | 1792 | 1792 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5060 | FIRE EXTINGUISHER | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-19 |  | N/A | N/A | 2023-12-22 | [11 empty] | 41140 | 41140 |  | 41140 | 41140 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5197 | SPAREPARTS (HEAVY EQUIPMENT) | PEO-MOTORPOOL |  | Competitive Bidding | 2023-11-15 | 2023-11-21 |  | N/A | 2023-12-12 | 2023-12-12 |  | 2023-12-12 | 2023-12-18 | 2023-12-22 | [11 empty] | 752400 | 752400 |  | 424000 | 424000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-C0760 | SPARE PARTS (AIRCONDITION) | PGSO |  | Competitive Bidding | 2023-11-29 | 2023-12-04 |  | N/A | 2023-12-12 | 2023-12-12 |  | 2023-12-12 | 2023-12-18 | 2023-12-22 | [11 empty] | 443030 | 443030 |  | 377460 | 377460 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-5292 | INSTALLATION OF CCTV AT PRC | PRCSD |  | Competitive Bidding | 2023-11-29 | 2023-12-04 |  | N/A | 2023-12-12 | 2023-12-12 |  | 2023-12-12 | 2023-12-18 | 2023-12-22 | [11 empty] | 647117 | 647117 |  | 519000 | 519000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-C0872 | SPAREPARTS (LIGHT VEHICLES) | PGSO |  | Competitive Bidding | N/A | 2023-12-04 |  | N/A | 2023-12-12 | 2023-12-12 |  | 2023-12-12 | 2023-12-18 | 2023-12-22 | [11 empty] | 989947 | 989947 |  | 977950 | 977950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-C0862 | LABORATORY SUPPLIES | PEEMO |  | Competitive Bidding | N/A | 2023-11-27 |  | 2023-12-05 | 2023-12-19 | 2023-12-19 |  | 2023-12-19 | 2023-12-21 | 2023-12-27 | [11 empty] | 1086295.8 | 1086295.8 |  | 666324 | 666324 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-3984 | MINI INDOOR DATA CENTER | PICTO |  | Competitive Bidding | 2023-08-08 | 2023-11-27 |  | 2023-12-05 | 2023-12-19 | 2023-12-19 |  | 2023-12-19 | 2023-12-21 | 2023-12-27 | [11 empty] | 18499795 | 18499795 |  | 18480000 | 18480000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
23-5564 | SPAREPARTS (LIGHT VEHICLES) | SPO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-19 | 2023-12-21 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 8000 | 8000 |  | 8000 | 8000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5567 | SPAREPARTS (LIGHT VEHICLES) | SPO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-19 | 2023-12-21 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 27000 | 27000 |  | 27000 | 27000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5568 | SPAREPARTS (LIGHT VEHICLES) | SPO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-19 | 2023-12-21 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 64600 | 64600 |  | 64600 | 64600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5600 | SPAREPARTS (LIGHT VEHICLES) | SPO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-19 | 2023-12-21 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 9500 | 9500 |  | 9500 | 9500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5553 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-19 | 2023-12-21 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 14450 | 14450 |  | 14450 | 14450 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5599 | SPAREPARTS (LIGHT VEHICLES) | SPO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-19 | 2023-12-21 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 135400 | 135400 |  | 135400 | 135400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5551 | SPAREPARTS (HEAVY EQUIPMENT) | PDRRMO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-19 | 2023-12-21 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 2350 | 2350 |  | 2350 | 2350 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5559 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-19 | 2023-12-21 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 32500 | 32500 |  | 32500 | 32500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5558 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-19 | 2023-12-21 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 1500 | 1500 |  | 1500 | 1500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5552 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-19 | 2023-12-21 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 6500 | 6500 |  | 6500 | 6500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5557 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-19 | 2023-12-21 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 23100 | 23100 |  | 23100 | 23100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5550 | SPAREPARTS (LIGHT VEHICLES) | SPO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-19 | 2023-12-21 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 45270 | 45270 |  | 45270 | 45270 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5549 | SPAREPARTS (LIGHT VEHICLES) | SPO |  | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-19 | 2023-12-21 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 3500 | 3500 |  | 3500 | 3500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5001 | OFFICE SUPPLIES | PGO |  | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 20228 | 20228 |  | 19125 | 19125 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0804 | FOOD SUPPLIES | PAGRO |  | NP-53.1 Two Failed Biddings | N/A | 2023-11-24 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 414734 | 414734 |  | 400190 | 400190 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4915 | WHEEL BARROW | PDRRMO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 18480 | 18480 |  | 18300 | 18300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4837 | SAFETY GEARS & EQUIPMENT | PDRRMO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 223080 | 223080 |  | 220800 | 220800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4993 | OTHER | PDRRMO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 18480 | 18480 |  | 18300 | 18300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5450 | OTHER SUPPLIES/MATERIALS | SEF |  | NP-53.9 - Small Value Procurement | 2023-12-12 | 2023-12-14 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 18000 | 18000 |  | 16308 | 16308 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0784 | FOOD/CATERING SERVICES | PDRRMO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-24 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 38140 | 38140 |  | 38140 | 38140 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5400 | SPAREPARTS (MOTORCYCLE) | PGSO |  | NP-53.9 - Small Value Procurement | 2023-12-05 | 2023-12-12 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 1700 | 1700 |  | 1700 | 1700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0879 | CONSTRUCTION SUPPLIES | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-21 | 2023-11-24 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 58030 | 58030 |  | 57405 | 57405 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0921 | ELECTRICAL SUPPLIES | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-12-06 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 123118 | 123118 |  | 121755 | 121755 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0901 | LUMBER | PVO |  | NP-53.9 - Small Value Procurement | 2023-11-21 | 2023-11-24 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 7050 | 7050 |  | 6900 | 6900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0922 | CONSTRUCTION SUPPLIES | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-12-06 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 138414 | 138414 |  | 137440 | 137440 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0923 | CONSTRUCTION SUPPLIES | PGO |  | NP-53.9 - Small Value Procurement | 2023-12-05 | 2023-12-12 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 98544 | 98544 |  | 98544 | 98544 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5127 | OFFICE EQUIPMENT | PASSO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-03 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 21500 | 21500 |  | 19350 | 19350 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0877 | OFFICE EQUIPMENT | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 112500 | 112500 |  | 111450 | 111450 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0919 | OFFICE EQUIPMENT | PGSO |  | NP-53.9 - Small Value Procurement | N/A | 2023-12-01 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 186600 | 186600 |  | 184300 | 184300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0897 | AGRICULTURAL SUPPLIES | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-21 | 2023-11-24 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 36150 | 36150 |  | 34810 | 34810 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5014 | OTHER SUPPLIES/MATERIALS | PDRRMO |  | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 108000 | 108000 |  | 97848 | 97848 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0865 | OIL AND LUBRICANTS | SPO |  | NP-53.9 - Small Value Procurement | 2023-11-07 | 2023-11-13 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 207634 | 207634 |  | 199730 | 199730 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5455 | SPAREPARTS (LIGHT VEHICLES) | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2023-12-01 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 42000 | 42000 |  | 40000 | 40000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-3904 | OFFICE EQUIPMENT | PDRRMO |  | NP-53.9 - Small Value Procurement | N/A | 2023-11-13 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 30000 | 30000 |  | 29998 | 29998 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0885 | OFFICE EQUIPMENT | PGO |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 159347 | 159347 |  | 159100 | 159100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-3812 | OFFICE EQUIPMENT | SEF |  | NP-53.9 - Small Value Procurement | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 210000 | 210000 |  | 203000 | 203000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0909 | NEWBORN SCREENING TEST | PEEMO |  | Direct Contracting | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 1373750 | 1373750 |  | 1373750 | 1373750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-5296 | DUPLICATING PRODUCTS/SPAREPARTS | PTO |  | Direct Contracting | 2023-11-15 | 2023-11-18 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 6023 | 6023 |  | 5475 | 5475 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0917 | ELECTROLYTES REAGENT | PEEMO |  | Direct Contracting | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 82775 | 82775 |  | 51170 | 51170 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-3754 | DUPLICATING PRODUCTS/SPAREPARTS | PAO |  | Direct Contracting | N/A | 2023-07-17 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 11938 | 11938 |  | 11938 | 11938 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0861 | MEDICAL SUPPLIES | PEEMO |  | Direct Contracting | 2023-12-12 | 2023-12-14 |  | N/A | N/A | 2023-12-27 |  | N/A | N/A | 2023-12-29 | [11 empty] | 391400 | 391400 |  | 254325 | 254325 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-C0906 | HEMATOLOGY ANALYZER | PEEMO |  | Direct Contracting | N/A | 2023-12-12 |  | N/A | N/A | 2023-12-27 | 15 | N/A | N/A | 2023-12-29 |  | 2 | 17 | [8 empty] | 1010800 | 1010800 |  | 1010800 | 1010800 |  | 0 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process | -165
23-C0759 | CONTRUCTION MATERIALS | PGSO |  | Competitive Bidding | N/A | 2023-12-11 |  | 2023-12-19 | [17 empty] | 1606988.6 | 1606988.6 |  | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA |  |  |  |  | N/A | N/A | Ongoing Procurement Process
23-4586 | COMPLETION OF MULTIPURPOSE BUILDING | PGSO |  | Competitive Bidding | 2023-11-15 | 2023-12-11 |  | 2023-12-19 | [17 empty] | 6428465.39 | 6428465.39 |  | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA |  |  |  |  | N/A | N/A | Ongoing Procurement Process
23-3195 | IMPROVEMENT OF DAVAO DE ORO PROVINCIAL HOSPITAL, MONTEVISTA | PEO |  | Competitive Bidding | 2023-10-17 | 2023-12-04 |  | 2023-12-12 | [17 empty] | 2876379.83 | 2876379.83 |  | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. LATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA |  |  |  |  | N/A | N/A | Ongoing Procurement Process
0
0
[7 empty] | 13 | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 67502356.84 | 67502356.84 | 0 | 53252922.28 | 53252922.28 | 0 | 9.34%
| Prepared by: |  |  | Checked and Reviewed by: | [21 empty] | Recommended for Approval by:
| MELISSA N. SAMENTAR |  |  | JENES B. MIÑOZA, MPA | [21 empty] | ROLANDO S. SIMENE, DVM, MRDM
| Clerk II-BAC Secretariat | [6 empty] | Head-BAC Secretariat | [17 empty] | BAC Chairperson
Approved by:
Approved by:
GOV. DOROTHY P. MONTEJO-GONZAGA
Head of the Procuring Entity
Formulas:
Sub/ Open of Bids6 = Complete[[#This Row],[Eligibility Check5]]
Bid Evaluation7 = Complete[[#This Row],[Sub/ Open of Bids6]]
Inspection & Acceptance = Complete[[#This Row],[Delivery/ Completion]]
Eligibility Check = Complete[[#This Row],[Sub/Open of Bids]]
Ads/Post of IB = VLOOKUP((LEFT(Complete[[#This Row],[Code (PAP)]], FIND(CHAR(10), Complete[[#This Row],[Code (PAP)]],1)-1)),[1]PMR!$A:$AX,25,FALSE)
Pre-bid Conf = VLOOKUP((LEFT(Complete[[#This Row],[Code (PAP)]], FIND(CHAR(10), Complete[[#This Row],[Code (PAP)]],1)-1)),[1]PMR!$A:$AX,26,FALSE)
Sub/Open of Bids = VLOOKUP((LEFT(Complete[[#This Row],[Code (PAP)]], FIND(CHAR(10), Complete[[#This Row],[Code (PAP)]],1)-1)),[1]PMR!$A:$AX,28,FALSE)
Bid Evaluation = VLOOKUP((LEFT(Complete[[#This Row],[Code (PAP)]], FIND(CHAR(10), Complete[[#This Row],[Code (PAP)]],1)-1)),[1]PMR!$A:$AX,29,FALSE)
Post Qual = VLOOKUP((LEFT(Complete[[#This Row],[Code (PAP)]], FIND(CHAR(10), Complete[[#This Row],[Code (PAP)]],1)-1)),[1]PMR!$A:$AX,30,FALSE)
Contract Signing = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[2]Sheet1!$A2:B2590,2,FALSE)
Notice to Proceed = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[2]Sheet1!$A2:B2590,2,FALSE)
Delivery/ Completion = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[2]Sheet3!$A2:B2590,2,FALSE)

## Tool 1-Processing (hidden)
Summary of Information for Processing of IRPP
Indicator 1: % of Processed Procurement Activities vs Planned in terms of amount |  | #REF!
Formula | Value | Remarks
Total Amount of APP as updated | #REF!
Divide by: Total Amount of ABC of procurement activities started | #REF! | ABC of awarded + ABC of on-going procurement projects (less ABC of Failure of Bids)
Indicator 2: Average % of Variance Between Contract Amount vs Approved Budget for the Contract |  | #REF!
Particular | Value | Remarks
Total Amount of ABC of procurement activities started | #REF!
Total Contact Cost | 215208876.29
Total Variance for Each Awarded Procurement Project | #REF! | Column shall be hidden
Divide by Number of Awarded Procurement Projects | 326
Indicator 3. Timeliness on the Conduct of Procurement
|  | Indicator 3.1 Average No. of Days to commence procurement (Pre-Proc to Posting of IB) |  | Indicator 3.2: Average No. of Days to open bid proposals (Posting of IB/ to Opening of Bids) |  | Indicator 3.3: Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) |  | Indicator 3.4: Average Number of Days to Conclude Procurement (Posting of IB to Recommend Award) |  | Indicator 3.5: Average Number of Days to Issue Notice to Proceed (from Issuance of NOA to Issuance of NTP) |  | Indicator 3.6: Accumulated Number of Days for the Procurement Process (Posting of IB to NTP)
Mode of Procurement | Total No. of Activities under subject modality | Total No. of Days from PreProc to IB | Average Days from Pre-Proc to Posting of IB | Total No. of Days from IB to Opening | Average Days from Posting of IB to Opening of Bids | Total No. of Days Opening to Recommend Award) | Average Days from Opening of Bids to Recommend Award | Total No. of Days from Posting of IB to Recommend Award | Average Days from Posting of IB to Recommend Award | Total No. of Days from Issuance of NOA to Issue NTP | Average Days from NOA to NTP | Total No. of Days from Posting of IB to Issue NTP | Average Days from Posting of IB to NTP
Competitive Bidding | 128 | 56 | 0.4375 | 35 | 0.4375 | 69 | 0.53906 | 104 | 0.8125 | 0 | 0 | 0 | 0
Limited Source Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Direct Contracting | 44 | 0 | 0 | 15 | 0 | 2 | 0.045455 | 17 | 0.38636 | 0 | 0 | 0 | 0
Repeat Order | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(a) - Unforeseen Contingency | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 43 | 12 | 0.27907 | 86 | 0.27907 | 34 | 0.7907 | 120 | 2.7907 | 24 | 0.55814 | 0 | 0
NP-53.1 Two Failed Biddings | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP-53.2 Emergency Cases | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP-53.3 Take-Over of Contracts | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.5 Agency-to-Agency | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.7 Highly Technical Consultants | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.9 - Small Value Procurement | 476 | 76 | 0.15966 | 158 | 0.15966 | 90 | 0.18908 | 248 | 0.52101 | 113 | 0.23739 | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.11 NGO Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.12 Community Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Emergency Procurement under Bayanihan Act | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Alternative Method | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 868 | 6.2609 | 0.10953 | 12.7826 | 0.10953 | 8.4783 | 0.19554 | 21.2609 | 0.56382 | 5.9565 | 0.099442 | 0 | 0
*formula for days interval for each procurement activity for each indicator are embedded in the PMR.
Indicator 4. Percentage of Amount and Volume by Tender and Award of Procurement Activities per Mode of Procurement
Mode of Procurement | Total No. of Activities | Total Number of Awarded | Total ABC | Total Contract Cost | %Vol of Awarded | %ABC of Awarded | Total Number of Failed | ABC of Failed
Competitive Bidding | 131 | 121 | 182968695.84 | 164337476.01 | 92.37% | 89.82% | 0 | 0
Limited Source Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Direct Contracting | 44 | 5 | 8489922 | 7570142 | 11.36% | 89.17% | 0 | 0
Repeat Order | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(a) - Unforeseen Contingency | 149 | 4 | 190655 | 190655 | 2.685% | 100% | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 43 | 19 | 2049370.1 | 2008409.75 | 44.19% | 98% | 0 | 0
NP-53.1 Two Failed Biddings | 21 | 16 | 15196635.86 | 15098584.36 | 76.19% | 99.35% | 0 | 0
NP-53.2 Emergency Cases | 1 | 0 | 0 | 0 | 0% |  | 0 | 0
NP-53.3 Take-Over of Contracts | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.5 Agency-to-Agency | 6 | 6 | 2957225 | 2704950 | 100% | 91.47% | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.7 Highly Technical Consultants | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.9 - Small Value Procurement | 476 | 155 | 23754653.17 | 23298659.17 | 32.56% | 98.08% | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.11 NGO Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.12 Community Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 | 0 | 0 |  |  | 0 | 0
Emergency Procurement under Bayanihan Act | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Alternative Method | 0 | 0 | 0 | 0 |  |  | 0 | 0
Total | 871 | 326 | 235607156.97 | 235607156.97 | 44.92% | 95.13% | 0 | 0
Total for Alternative Mode of Procurement | 740 | 205 | 52638461.13 | 50871400.28 | 38.14% | 96.01% | 0 | 0
Indicator 5: Accumulated No. of Days for On-going Procurement Activities
Timeline | No. of Procurement Activities | %
Exceeds 180 days | 0 | 0%
Within 91 to 180 days | 0 | 0%
Within 45 to 90 days | 0 | 0%
Within 0 to 44 days | 0 | 0%
Total | 0 | 0%
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 6. Distribution of On-going, Awarded, and Failed procurement Activities
Status | No. of Procurement Activities | % by No. of Procurement of Activities | ABC Amount of Activities | % by ABC | Contract Cost | Contract/ABC | Variance
Awarded | 5 | 0.6944% | 3303626 | 1.284% | 2107184 | 0.8839% | 0.36216
Completed | 527 | 73.19% | 200683478.19 | 77.99% | 185084577.97 | 77.64% | 0.077729
Failed | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Ongoing | 188 | 26.11% | 53335197.02 | 20.73% | 51193933.28 | 21.48% | 0.040147
Total | 720 | 100% | 257322301.21 | 100% | 238385695.25 | 100% | 0.073591
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 7a: % of Number of Procurement activities conducted under early procurement |  |  | 0%
Indicator 7b: % of ABC of Procurement activities conducted under early procurement |  |  | 0%
Particular | No. of Procurement Activities | ABC Amount of Activities
Under EPA | 0 | 0
Regular Procurement | 736 | 253352503.86
Total | 736 | 253352503.86
Indicator 8a: Percentage of Number of Awarded Contracts under EPA |  |  | 0%
Indicator 8b: Percentage of Contract Cost of EPA against the total ABC under EPA |  |  | 0%
Formula | No. of Procurement Activities | Amount of ABC Procurement Activities | Contract Cost of Procurement Activities | Percentage Variance
Total Contracts Awarded under EPA* | 0 | 0 | 0 | 0%
Total Contracts Completed under EPA* | 0 | 0 | 0 | 0%
Total Failed Bid under EPA* | 0 | 0 | 0 | 0%
Total Ongoing Activities under EPA* | 0 | 0 | #VALUE! | #VALUE!
Total Procurement Activities under EPA | 0 | 0 | #VALUE!
To compute for the total, a separate sheet may be created of the PMO may simply filter the cells to capture the total number.
Indicator 9: Stages where failure of bidding are encountered
Particular | No. of Procurement Activities | Amount of ABC | Vol. % | Amount %
Invitation To Bid | 0 | 0 | 0% | 0%
Pre-bidding Conference | 0 | 0 | 0% | 0%
Opening of Bids | 0 | 0 | 0% | 0%
Bid Evaluation | 0 | 0 | 0% | 0%
Post-Qualification | 0 | 0 | 0% | 0%
BAC Resolution | 0 | 0 | 0% | 0%
Award | 0 | 0 | 0% | 0%
Cancelled | 1 | 0 | 100% | 0%
TOTAL | 1 | 0

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget)
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget)
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget)
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution
Failed under Section 35.1 (b) |  | BAC Resolution
Failed under Section 35.1 (c) |  | Award
Failed under Section 41 (b) |  | Cancelled
Failed under Section 41 (c)
Contract was extended
Contract was renewed
Cancelled
Others, please encode directly on the cell