## PMR
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (Provincial Government of Davao de Oro) Procurement Monitoring Report as of JANUARY-JUNE 2023
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Mode of Procurement | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
22-7334 | 1 LOT CONSTRUCTION OF 1 UNIT 2 | [19 empty] | PEO | PB | 09.27.2022 | 11.10.2022 | 11.15.2022 | 11.29.2022 | 11.29.2022 | 11.29.2022 | 01.07.2023 | 01.19.2023 | 02.08.2023 | 02.13.2023 |  |  | GF | 2399227.92 |  | 2399227.92 | 2279270.51 |  | 2279270.51 | Mr. Allan Rey N. Esmael | 11.10.2022 | n/a | 11.24.2022 | n/a | n/a
CW22-034 | CLASSROOM AT KILAGDING LAAK | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-4098 | 1 LOT CONSTRUCTION OF MULTIPURPOSE | [19 empty] | PGO-SEF | PB | 05.27.2022 | 10.07.2022 | 10.18.2022 | 11.18.2022 | 11.18.2022 | 11.18.2022 | 12.05.2022 | 12.06.2022 | 02.08.2023 | 02.14.2023 |  |  | GF | 1937753.2 |  | 1937753.2 | 1934245.57 |  | 1934245.57 | Mr. Allan Rey N. Esmael | 10.13.2022 | n/a | 11.11.2022 | n/a | n/a
CW22-033 | HALL AT BARABAT ELEMENTARY SCHOOL, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| CAGAN, BRGY. ANDAP, NEW BATAAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7122 | 1 LOT CONSTRUCTION OF GYM, PALOC | [19 empty] | PEO | PB | 11.22.2022 | 11.25.2022 | 12.06.2022 | 12.20.2022 | 01.26.2023 | 01.26.2023 | 02.08.2023 | 02.23.2023 | 03.16.2023 | 03.20.2023 |  |  | GF | 4954026.15 |  | 4954026.15 | 4093839.9 |  | 4093839.9 | Mr. Allan Rey N. Esmael | 10.13.2022 | n/a | 11.11.2022 | n/a | n/a
CW22-035 | NHS, BRGY PALOC, MARAGUSAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7790 | 1 LOT CONSTRUCTION OF GYM, PALOC | [19 empty] | PEO | PB | 11.22.2022 | 11.25.2022 | 12.06.2022 | 12.20.2022 | 12.20.2022 | 12.20.2022 | 02.08.2023 | 02.23.2023 | 03.16.2023 | 03.20.2023 |  |  | GF | 3751603.89 |  | 3751603.89 | 0 |  |  | Mr. Allan Rey N. Esmael | 10.13.2022 | n/a | 11.11.2022 | n/a | n/a
CW22-036 | NHS, BRGY PALOC, MARAGUSAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7331 | 1 LOT CONSTRUCTION OF MULTIPURPOSE | [19 empty] | PEO | PB | 12.20.2022 | 01.27.2023 | 02.07.2023 | 02.21.2023 | 02.21.2023 | 02.21.2023 | 03.16.2023 | 03.28.2023 | 04.14.2023 | 04.19.2023 |  |  | GF | 3965208.25 |  | 3965208.25 | 3945070.71 |  | 3945070.71 | Mr. Allan Rey N. Esmael | 10.13.2022 | n/a | 11.11.2022 | n/a | n/a
CW22-043 | BUILDING (CIDG) PPO COMPOUND, BRGY. | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| SANROQUE, NABUNTURAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-8860 | UPGRADING OF HOSPITAL BUILDING | [19 empty] | PEO | PB | 11.22.2022 | 01.27.2023 | 02.03.2023 | 02.07.2023 | 02.07.2023 | 02.21.2023 | 02.23.2023 | 03.28.2023 | 04.14.2023 | 04.19.2023 |  |  | GF | 1583224.96 |  | 1583224.96 | 1533241.65 |  | 1533241.65 | Mr. Allan Rey N. Esmael | 02.02.2023 | n/a | 02.21.2023 | n/a | n/a
CW22-042 | FACILITIES AT DDOPH-LAAK | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-8404 | SUPPLY AND DELIVERY OF RESCUE TOOLS | [19 empty] | PDRRMO | PB | n/a | 12.03.2022 | 12.13.2022 | 12.27.2023 | 12.27.2023 | 12.27.2023 | 01.05.2023 | 01.10.2023 | 02.09.2023 | 02.28.2023 |  |  | GF | 1029200 | 1029200 |  | 1029200 | 1029200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 12.22.2023 | n/a | n/a
2301001 | AND EQUIPMENT | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1338 | SUPPLY AND DELIVERY OF DRUGS AND | [19 empty] | PEEMO | PB | n/a | 12.3.2022 | 12.13.2022 | 12.27.2022 | 01.05.2023 | 01.05.2023 | 01.06.2023 | 01.20.2023 |  |  |  |  | GF | 18828107.57 | 18828107.57 |  | 666400 | 666400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 12.22.2023 | n/a | n/a |  | CONSIGNMENT
| MEDICINES FOR THE USE OF VARIOUS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| HOSPITAL (CONSIGNMENT) | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1338 | SUPPLY AND DELIVERY OF DRUGS AND | [19 empty] | PEEMO | PB | n/a | 12.3.2022 | 12.13.2022 | 12.27.2022 | 01.05.2023 | 01.05.2023 | 01.06.2023 | 01.20.2023 |  |  |  |  | GF | 18828107.57 | 18828107.57 |  | 659042 | 659042 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 12.22.2023 | n/a | n/a |  | CONSIGNMENT
| MEDICINES FOR THE USE OF VARIOUS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| HOSPITAL (CONSIGNMENT) | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1338 | SUPPLY AND DELIVERY OF DRUGS AND | [19 empty] | PEEMO | PB | n/a | 12.3.2022 | 12.13.2022 | 12.27.2022 | 01.05.2023 | 01.06.2023 | 01.06.2023 | 02.07.2023 |  |  |  |  | GF | 18828107.57 | 18828107.57 |  | 9750824 | 9750824 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 12.22.2023 | n/a | n/a |  | CONSIGNMENT
| MEDICINES FOR THE USE OF VARIOUS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| HOSPITAL (CONSIGNMENT) | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1338 | SUPPLY AND DELIVERY OF DRUGS AND | [19 empty] | PEEMO | PB | n/a | 12.3.2022 | 12.13.2022 | 12.27.2022 | 01.05.2023 | 01.06.2023 | 01.27.2023 | 02.17.2023 |  |  |  |  | GF | 18828107.57 | 18828107.57 |  | 2110970 | 2110970 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 12.22.2023 | n/a | n/a |  | CONSIGNMENT
| MEDICINES FOR THE USE OF VARIOUS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| HOSPITAL (CONSIGNMENT) | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-4200 | 1 LOT - CONSTRUCTION OF STAGE AND | [19 empty] | PGO | NP | 5.27.2022 | 12.22.20222 | n/a | n/a | 01.18.2023 | n/a | n/a | 1.26.2023 | 02.10.2023 | 02.23.2023 |  |  | GF | 2912879.05 |  | 2912879.05 | 2882860.9 |  | 2882860.9 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a
CW22-032 | BLEACHERS AT MELALE NHS, BRGY. | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| MELALE, LAAK, DAVAO DE ORO | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0216 | AIRCON MAINTENANCE | [19 empty] | SPO | NP | 1.26.2023 | 03.10.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.21.2023 |  |  |  |  | GF | 65000 | 65000 |  | 64500 | 64500 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23030110 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1760 | SUBMERSIBLE PUMP, 1HP SINGLE PHASE, | [19 empty] | PAGRO | SVP | n/a | 03.03.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.21.2023 |  |  |  |  | GF | 12000 | 12000 |  | 11500 | 11500 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23030116 | 60HZ, 220V | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0640 | SPORTS SUPPLIES AND GEARS | [19 empty] | PGO-SEF | SVP | n/a | 03.10.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.21.2023 | 03.29.2023 | 03.29.2023 | 05.03.2023 | 05.03.2023 | GF | 399038 | 399038 |  | 396698 | 396698 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23030117 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0080 | OIL AND LUBRICANTS | [19 empty] | PEO - | PB | 02.07.2023 | 02.10.2023 | 2.21.2023 | 03.07.2023 | 03.07.2023 | 03.07.2023 | 03.16.2023 | 03.28.2023 | 03.29.2023 | 03.29.2023 |  |  | GF | 3706042.5 | 3706042.5 |  | 3140312.5 | 3140312.5 |  | Mr. Allan Rey N. Esmael | 02.16.2023 | n/a | 02.27.2023 | n/a | n/a
23030146 | [20 empty] | MOTOR | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | POOL | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0431 | INTERNET SUBSCRIPTION | [19 empty] | SPO | DC | 02.07.2023 | 02.27.2023 | n/a | n/a | 04.19.2023 | n/a | n/a | 04.19.2023 | 05.08.2023 | 05.11.2023 |  |  | GF | 403200 | 403200 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0424 | INTERNET SUBSCRIPTION | [19 empty] | SPO | DC | 02.07.2023 | 02.27.2023 | n/a | n/a | 04.19.2023 | n/a | n/a | 04.19.2023 | 05.08.2023 | 05.11.2023 | 06.16.2023 | 06.16.2023 | GF | 360000 | 360000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040302 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0016 | PUBLICATION OF ORDINANCE | [19 empty] | SPO | PB | 02.07.2023 | 02.10.2023 | n/a | 02.21.2023 | 02.21.2023 | 02.21.2023 | 03.13.2023 | 03.25.2023 | 03.31.2023 | 05.02.2023 |  |  | GF | 240000 | 240000 |  | 180000 | 180000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 02.16.2023 | n/a | n/a
23-03-0137 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0102 | SANITARY/TOILETRIES | [19 empty] | PDRRMO | PB | n/a | 02.27.2023 | n/a | 03.07.2023 | 03.07.2023 | 03.07.2023 | 03.14.2023 | 03.27.2023 | 03.30.2023 | 04.12.2023 | 06.20.2023 | 06.20.2023 | GF | 676300 | 676300 |  | 675750 | 675750 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.02.2023 | n/a | n/a
23-03-0138 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C1294 | MEDIA BROADCASTING EQUIPMENT | [19 empty] | PGO-SEF | NP | n/a | 01.31.2023 | n/a | n/a | 02.07.2023 | n/a | n/a | 02.10.2023 | 03.29.2023 | 04.11.2023 | 04.18.2023 | 04.18.2023 | SOCIO CUL- | 1224950 | 1224950 |  | 1183950 | 1183950 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | TWO FAILED BIDDINGS
| AND ACCESSORIES | [33 empty] | TURAL AND | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | ARTS PROGRAM | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C1012 | AUTOMATED RAIN GAUGE STATION | [19 empty] | PDRRMO | NP | n/a | 01.31.2023 | n/a | n/a | 02.07.2023 | n/a | n/a | 02.10.2023 | 02.23.2023 | 02.28.2023 |  |  | SOCIO CUL- | 5000000 | 5000000 |  | 4992082 | 4992082 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | TWO FAILED BIDDINGS
| (WITH SPECIFICATIONS) | [33 empty] | TURAL AND | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | ARTS PROGRAM | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0237 | BOX FILE | [19 empty] | SPO | SVP | n/a | 01.31.2023 | n/a | n/a | 02.07.2023 | n/a | n/a | 02.07.2023 | 03.02.2023 | 03.03.2023 |  |  | SOCIO CUL- | 4836 | 4836 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[35 empty] | TURAL AND | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | ARTS PROGRAM | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C10101 | PLAQUE AND TOKEN | [19 empty] | SPO | SVP | n/a | 01.31.2023 | n/a | n/a | 02.07.2023 | n/a | n/a | 02.10.2023 | 02.23.2023 | 02.28.2023 |  |  | SOCIO CUL- | 4836 | 4836 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[35 empty] | TURAL AND | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | ARTS PROGRAM | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0415 | MEALS VIP AND HEAVY SNACKS | [19 empty] | SPO | SVP | n/a | 02.03.2023 | n/a | n/a | 02.07.2023 | n/a | n/a | 02.09.2023 | 03.02.2023 | 03.03.2023 | 06.15.2023 | 06.15.2023 | SOCIO CUL- | 4836 | 4836 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020009 | [34 empty] | TURAL AND | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | ARTS PROGRAM | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1166 | ELECTRONIC SUPPLIES AND | [19 empty] | PGO | SVP | n/a | 02.03.2023 | n/a | n/a | 02.07.2023 | n/a | n/a | 02.07.2023 | 02.22.2023 | 02.23.2023 |  |  | SOCIO CUL- | 4836 | 4836 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| ACCESSORIES | [33 empty] | TURAL AND | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | ARTS PROGRAM | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1183 | TARPAULIN-AS PER DESIGN | [19 empty] | PGO | SVP | n/a | 02.03.2023 | n/a | n/a | 02.07.2023 | n/a | n/a | 02.09.2023 | 02.23.2023 | 02.27.2023 |  |  | SOCIO CUL- | 4836 | 4836 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[35 empty] | TURAL AND | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | ARTS PROGRAM | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1196 | POLO SHIRT | [19 empty] | PGO | SVP | n/a | 02.03.2023 | n/a | n/a | 02.07.2023 | n/a | n/a | 02.07.2023 | 02.23.2023 | 02.27.2023 |  |  | SOCIO CUL- | 4836 | 4836 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[35 empty] | TURAL AND | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | ARTS PROGRAM | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0004 | MEALS AND SNACKS | [19 empty] | PGO | SVP | n/a | 02.03.2023 | n/a | n/a | 02.07.2023 | n/a | n/a | 02.07.2023 | 02.27.2023 | 03.01.2023 | 04.18.2023 | 04.18.2023 | SOCIO CUL- | 4836 | 4836 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[35 empty] | TURAL AND | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | ARTS PROGRAM | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0962 | BOTTLED WATER | [19 empty] | PGO | SVP | 02.07.2023 | [11 empty] | SOCIO CUL- | 4836 | 4836 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
[35 empty] | TURAL AND | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | ARTS PROGRAM | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1191 | FRESH FLOWER ASSORTED | [19 empty] | PGO | SA | 02.07.2023 | [11 empty] | GF | 15000 | 15000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1239 | ORGANIZER, DAILY PLANNER | [19 empty] | PGO-PS | SB | 02.07.2023 | [11 empty] | GF | 29000 | 29000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1160 | OFFICE SUPPLIES | [19 empty] | PGO-PS | SB | 02.07.2023 | [11 empty] | GF | 18409 | 18409 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0099 | JANITORIAL SUPPLIES | [19 empty] | PIAO | SVP | 02.07.2023 | [11 empty] | GF | 6197 | 6197 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0716 | STAMPS, MAILING | [19 empty] | PTO | AGENCY TO | 02.07.2023 | [11 empty] | GF | 3000 | 3000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
[22 empty] | AGENCY | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0905 | JANITORIAL SUPPLIES | [19 empty] | PTO | SVP | 02.07.2023 | [11 empty] | GF | 10465 | 10465 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0018 | JANITORIAL SUPPLIES | [19 empty] | PHRMDO | SVP | 02.07.2023 | [11 empty] | GF | 28678 | 28678 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0889 | MEALS WITHOUT VENUE AND SNACKS | [19 empty] | PBO | SVP | 02.07.2023 | [11 empty] | MAINTAINACE | 18550 | 18550 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| A & B (LIGHT) | [33 empty] | AND OPERA- | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | TION FUND | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0850 | LABOR AND MATERIALS FOR | [19 empty] | COA | SA | 02.07.2023 | [11 empty] | GF | 4000 | 4000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| LIGHT VEHICLES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0454 | LIGHT VEHICLE SPAREPARTS | [19 empty] | COA | SVP | 02.07.2023 | [11 empty] | GF | 4510 | 4510 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0456 | TIRES, TUBELESS (R17 & R16) | [19 empty] | COA | PB | 02.07.2023 | 02.10.2023 | n/a | 02.21.2023 | 02.21.2023 | 02.21.2023 | 03.16.2023 | 03.27.2023 | 04.03.2023 | 04.04.2023 |  |  | MOOE- | 103150 | 103150 |  | 57650 | 57650 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 02.16.2023 | n/a | n/a
23-03-0142 | [34 empty] | REGULAR | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-8167 | SUPPLY AND DELIVERY OF EMERGENCY | [19 empty] | PDRRMO | PB | n/a | 12.03.2022 | 12.13.2022 | 12.27.2023 | 12.27.2023 | 12.27.2023 | 01.27.2023 | 02.07.2023 |  |  |  |  | GF | 6500000 | 6500000 |  | 5589999 | 5589999 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 12.22.2023 | n/a | n/a
2302004 | RESPONSE VEHICLE USAR | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| (BRAND NEW/CUSTOMIZED) | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-8105 | SUPPLY AND INSTALLATION OF CCTV | [19 empty] | PDRRMO | PB | 11.15.2022 | 1.27.2023 | n/a | 2.07.2023 | 02.07.2023 | 02.07.2023 | 02.09.2023 | 03.01.2023 | 03.09.2023 | 03.10.2023 |  |  | GF | 160000 | 160000 |  | 119000 | 119000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 02.02.2023 | n/a | n/a
2302064 | CAMERA SYSTEM | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0963 | MEALS VIP/SNACKS | [19 empty] | PGO | PB | n/a | 02.06.2023 | n/a | 02.16.2023 | 02.16.2023 | 02.16.2023 | 02.17.2023 | 03.01.2023 | 03.09.2023 | 03.28.2023 |  |  | SOCIO CUL- | 189000 | 189000 |  | 173880 | 173880 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 02.23.2023 | n/a | n/a
23020065 | (FOR BULAWAN 2023 ACTIVCITIES) | [33 empty] | TURAL AND | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | ART PROGRAM | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0973 | MEALS WITHOUT VENUE AND SNACKS | [19 empty] | PGO | PB | n/a | 02.06.2023 | n/a | 2.16.2023 | 02.16.2023 | 02.16.2023 | 02.17.2023 | 03.01.2023 | 03.09.2023 | 03.28.2023 |  |  | SOCIO CUL- | 906157 | 906157 |  | 826228 | 826228 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 02.23.2023 | n/a | n/a
23020066 | (FOR BULAWAN 2023 ACTIVCITIES) | [33 empty] | TURAL AND | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | ART PROGRAM | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1248 | MEALS AND SNACKS | [19 empty] | PGO | SVP | n/a | 02.08.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.22.2023 | 02.28.2023 | 03.01.2023 | 06.19.2023 | 06.19.2023 | GF | 136000 | 136000 |  | 135500 | 135500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0931 | TONER FOR MP 2555SP-GESTETNER | [19 empty] | PBO | DC | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 6023 | 6023 |  | 6023 | 6023 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1218 | MAINTENANCE BOX FOR PHOTOCOPIER | [19 empty] | PGO | DC | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | MAINTAINACE | 9740 | 9740 |  | 9740 | 9740 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020059 | EPSON (WF-C878R) | [33 empty] | AND OPERATION | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | OF BAC | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0157 | PRINTING SUPPLIES | [19 empty] | PEEMO | DC | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 63812 | 63812 |  | 63812 | 63812 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020060 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0686 | TONER KIT BLACK TK-7220 | [19 empty] | PACCO | DC | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | MOOE-REG- | 16200 | 16200 |  | 16200 | 16200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020061 | [34 empty] | ULAR | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0174 | MEDICAL OXYGEN REFILL | [19 empty] | PEEMO | DC | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 2783700 | 2783700 |  | 2783700 | 2783700 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020063 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0184 | EXPANDED NEWBORN SCREENING KIT | [19 empty] | PEEMO | DC | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 4025000 | 4025000 |  | 4025000 | 4025000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020062 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0762 | PRINTER INK SUPPLIES | [19 empty] | PBO | SB | n/a | 02.16.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 4593 | 4593 |  | 4440 | 4440 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020056 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0006 | OFFICE SUPPLIES | [19 empty] | PGO | SB | n/a | 2.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 82855 | 82855 |  | 82755 | 82755 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020057 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0285 | PLAQUE - BIG RECTANGLE, AS PER DESIGN | [19 empty] | PAGRO | SVP | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | AGRICULTU- | 7200 | 7200 |  | 7170 | 7170 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020035 | [34 empty] | RAL INSTITU- | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[35 empty] | TIONAL PROGRAM | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0043 | TARPAULIN - AS PER DESIGN | [19 empty] | PAGRO | SVP | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 | 03.16.2023 | 06.30.2023 | 04.28.2023 | 04.28.2023 | GF | 16828 | 16828 |  | 15626 | 15626 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020036 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0104 | DIESEL ENGINE OIL | [19 empty] | PAGRO | SVP | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 16879.8 | 16879.8 |  | 16800 | 16800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020037 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0053 | BATTERY AND ENGINE OIL | [19 empty] | PAGRO | SVP | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 30240 | 30240 |  | 28917 | 28917 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020038 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0049 | TABLES AND CHAIRS | [19 empty] | PAGRO | SVP | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 28948 | 28948 |  | 28917 | 28917 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020039 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0107 | BROCHURE AND TARPAULIN | [19 empty] | PAGRO | SVP | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 | 03.15.2023 | 03.16.2023 | 05.23.2023 | 05.23.2023 | GF | 26472 | 26472 |  | 25652 | 25652 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020040 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0040 | AGRILCULTURAL SUPPLIES | [19 empty] | PAGRO | SVP | n/a | 2.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 172632 | 172632 |  | 171300 | 171300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020041 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0345 | STRAWBERRY SEEDLINGS | [19 empty] | PAGRO | SVP | n/a | 2.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 58564 | 58564 |  | 57596 | 57596 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020042 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0363 | FEEDS | [19 empty] | PAGRO | SVP | n/a | 2.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 103870 | 103870 |  | 102870 | 102870 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020043 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0166 | FUEL FILTER FOR GENSET | [19 empty] | PEEMO | SVP | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 8600 | 8600 |  | 8100 | 8100 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020044 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0168 | MOTORCYCLE SPAREPARTS | [19 empty] | PEEMO | SVP | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 6400 | 6400 |  | 6385 | 6385 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020045 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0919 | TARPAULIN - AS PER DESIGN | [19 empty] | PBO | SVP | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 4984 | 4984 |  | 4895 | 4895 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020046 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0228 | JOB ORDER (BOOKBINDING) - AS PER DESIGN | [19 empty] | SPO | SVP | n/a | 2.16.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 100000 | 100000 |  | 98000 | 98000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020047 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0192 | POWER TOOLS AND ACCESSORIES | [19 empty] | PGSO | SVP | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 41483 | 41483 |  | 41391 | 41391 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020048 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0042 | MEALS AND SNACKS | [19 empty] | PAGRO | SVP | n/a | 2.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 03.01.2023 | 03.13.2023 | 03.16.2023 | 05.30.2023 | 05.30.2023 | GF | 505479 | 505479 |  | 499855 | 499855 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020049 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0161 | MINERAL WATER, 5 GAL. | [19 empty] | PEEMO | SVP | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 47314 | 47314 |  | 46160 | 46160 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020050 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0170 | RAINCOAT, CLASS A | [19 empty] | PEEMO | SVP | n/a | 02.14.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 1320 | 1320 |  | 1315 | 1315 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020051 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0260 | PACKED MEALS AND SNACKS | [19 empty] | PASSO | SVP | n/a | 02.16.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 45870 | 45870 |  | 45375 | 45375 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020052 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1265 | GRASS CUTTER SPAREPARTS | [19 empty] | PGSO | SVP | n/a | 02.16.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 | 03.09.2023 | 05.10.2023 | 05.16.2023 | 05.16.2023 | GF | 13060 | 13060 |  | 12905 | 12905 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020053 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1222 | HEAVY SNACKS | [19 empty] | PGSO | SVP | n/a | 02.16.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 11625 | 11625 |  | 11250 | 11250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020054 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1573 | TAX CARD - AS PER SAMPLE | [19 empty] | PTO | SVP | n/a | 02.16.2023 | n/a | n/a | 02.16.2023 | n/a | n/a | 02.21.2023 |  |  |  |  | GF | 5500 | 5500 |  | 5250 | 5250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23020055 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda | 02.02.2023
22-6427 | SUPPLY AND DELIVERY OF SERVICE | [19 empty] | PAGRO | PB | n/a | 01.27.2023 | 02.07.2023 | 02.21.2023 | 02.21.2023 | 02.21.2023 | 02.22.2023 | 03.02.2023 | 03.13.2023 | 03.15.2023 |  |  | GF | 1550000 | 1550000 |  | 1549000 | 1549000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 02.16.2023 | n/a | n/a
2302066 | VEHICLE PICK-UP TYPE BRAND NEW 4*4, | [37 empty] | 0 |  |  | Ms. Leonarda M. Nator
| MANUAL TRANSMISSION | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0009 | SUPPLY AND DELIVERY OF ANIMAL | [19 empty] | PVO | PB |  | 02.06.2023 | 02.16.2023 | 02.28.2023 | 02.28.2023 | 02.28.2023 | 03.01.2023 | 03.09.2023 | 03.13.2023 | 03.28.2023 | 05.18.2023 | 05.23.2023 | GF | 1838827 | 1838827 |  | 1699067 | 1699067 |  | Mr. Allan Rey N. Esmael | 02.13.2023 | n/a | 02.23.2023 | n/a | n/a
23030081 | SUPPLIES | [37 empty] | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0209 | FOOD SUPPLIES | [19 empty] | PGSO | PB | n/a | 02.10.2023 | 02.21.202. | 03.07.2023 | 03.07.2023 | 03.07.2023 | 03.09.2023 | 03.10.2023 | 03.13.2023 | 03.14.2023 |  |  | GF | 1838827 | 1838827 |  | 1699067 | 1699067 |  | Mr. Allan Rey N. Esmael | 02.16.2023 | n/a | 03.02.2023 | n/a | n/a
23030107 | [38 empty] | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0194 | RICE (WELL MILLED) 50KG/SACK | [19 empty] | PGSO | PB | n/a | 02.10.2023 | 02.21.2023 | 03.07.2023 | 03.07.2023 | 03.07.2023 | 03.09.2023 | 03.10.2023 | 03.13.2023 | 03.14.2023 |  |  | GF | 1531087 | 1531087 |  | 1247416 | 1247416 |  | Mr. Allan Rey N. Esmael | 02.16.2023 | n/a | 03.02.2023 | n/a | n/a
23030108 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1541 | MEALS WITHOUT VENUE AND SNACKS | [19 empty] | PGSO | PB | n/a | 02.10.2023 | 02.21.2023 | 03.07.2023 | 03.07.2023 | 03.07.2023 | 03.09.2023 | 03.15.2023 | 03.16.2023 | 03.28.2023 | 06.22.2023 |  | GF | 1780000 | 1780000 |  | 1505000 | 1505000 |  | Mr. Allan Rey N. Esmael | 02.16.2023 | n/a | 03.02.2023 | n/a | n/a |  | FOR INSPECTION
23030109 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0090 | SPAREPARTS | [19 empty] | PEO- | SA | 02.21.2023 | [11 empty] | GF | 200000 | 200000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[21 empty] | MOTORPOOL | CASH ADVANCE | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0081 | ACETYLENE REFILL and OXYGEN, INDUSTRIAL | [19 empty] | PEO- | DC | 02.21.2023 | 02.27.2023 | n/a | n/a | 3.2.2023 | n/a | n/a | 03.10.2023 | 03.22.2023 | 03.29.2023 |  |  | GF | 45075 | 45075 |  | 45075 | 45075 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030094 | GAS-REFILL | [19 empty] | MOTORPOOL | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1481 | CONSTRUCTION OF MULTI-PURPOSE | [19 empty] | PEO | PB | 02.21.2023 | 04.21.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 06.15.2023 | 06.27.2023 |  |  |  |  | GF | 4989979.79 |  | 4989979.79 | 4844040.38 |  | 4844040.38 | Mr. Allan Rey N. Esmael | 04.26.2023 | n/a | 05.11.2023 | n/a | n/a |  | FOR CONTRACT
CW23-009 | BUILDING, TUBO-TUBO NHS, MONKAYO | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator | [6 empty] | SIGNING
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1487 | UPGRADING OF HOSPITAL BUILDING | [19 empty] | PEO | PB | 02.21.2023 | [11 empty] | GF | 1549654.01 |  | 1549654.01 | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
CW23-029 | FACILITIES AT DDOPH-MARAGUSAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1416 | CONSTRUCTION OF SLOPE PROTECTION AT | [19 empty] | PEO | PB | 02.21.2023 | 04.18.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 06.15.2023 | 06.29.2023 |  |  |  |  | GF | 1216901.49 |  | 1216901.49 | 1198171.05 |  | 1198171.05 | Mr. Allan Rey N. Esmael | 04.26.2023 | n/a | 05.11.2023 | n/a | n/a |  | FOR CONTRACT
CW23-010 | BUCANA-MAMBATANG FMR, MABINI | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator | [6 empty] | SIGNING
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1916 | CONSTRUCTION OF GYM WITH STAGE | [19 empty] | PEO | PB | n/a | 04.20.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 05.18.2023 | 06.02.2023 | 06.09.2023 | 06.14.2023 |  |  | GF | 4839332.08 |  | 4839332.08 | 4789339.41 |  | 4789339.41 | Mr. Allan Rey N. Esmael | 04.26.2023 | n/a | 05.11.2023 | n/a | n/a |  | FOR CONTRACT
CW23-010 | AGUINALDO, NATIONAL HIGH SCHOOL, BRGY. | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator | [6 empty] | SIGNING
| AGUINALDO LAAK | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1488 | UPGRADING OF HOSPITAL BUILDING | [19 empty] | PEO | PB | 02.21.2023 | 05.22.2023 |  | 05.30.2023 | 05.30.2023 | 05.30.2023 | [6 empty] | GF | 859977.4 |  | 859977.4 | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR POST-QUA
CW23-035 | FACILITIES AT DDOPH-MONTEVISTA | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1474 | CONSTRUCTION OF MULIT-PURPOSE | [19 empty] | PEO | PB | 02.21.2023 | 04.18.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 06.15.2023 | 06.29.2023 | 07.03.2023 |  |  |  | GF | 4983677.95 |  | 4983677.95 | 4933595.15 |  | 4933595.15 | Mr. Allan Rey N. Esmael | 04.26.2023 | n/a | 05.11.2023 | n/a | n/a |  | FOR NTP
CW23-008 | BUILDING, CONSUELO VALDERAMA, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| BRGY. NGAN, COMPOSTELA | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1361 | CONSTRUCTION OF WATER SYSTEM, | [19 empty] | PEO | PB | 02.21.2023 | 03.17.2023 | 03.28.2023 | 04.18.2023 | 04.18.2023 | 04.18.2023 | 04.21.2023 | 04.24.2023 | 05.04.2023 | 05.08.2023 |  |  | GF | 11325045.94 |  | 11325045.94 | 11291501.41 |  | 11291501.41 | Mr. Allan Rey N. Esmael | 03.23.2023 | n/a | 04.13.2023 | n/a | n/a
CW23-001 | BRGY. PASIAN, MONKAYO | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0239 | SPARE PARTS | [19 empty] | PGSO | PB | n/a | 02.27.2023 | 03.07.2023 | 03.21.2023 | 03.21.2023 | 03.21.2023 | 03.22.2023 | 03.27.2023 | 03.29.2023 | 03.29.2023 | 04.04.2023 | 04.04.2023 | GF | 3739970 | 3739970 |  | 2453165 | 2453165 |  | Mr. Allan Rey N. Esmael | 03.02.2023 | n/a | 03.16.2023 | n/a | n/a
23030171 | (LIGHT EQUIPMENT) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0097 | SPAREPARTS | [19 empty] | PEO | PB | 02.21.2023 | 03.07.2023 | 03.13.2023 | 03.21.2023 | 03.21.2023 | 03.21.2023 | 03.22.2023 | 03.30.2023 | 04.17.2023 | 04.18.2023 | 06.06.2023 | 06.06.2023 | GF | 5967036 | 5967036 |  | 5961543 | 5961543 |  | Mr. Allan Rey N. Esmael | 03.08.2023 | n/a | 03.16.2023 | n/a | n/a
23030173 | (HEAVY EQUIPMENT) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0154 | FOOD SUPPLIES | [19 empty] | PEEMO | SVP | 02.21.2023 | 02.27.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 03.14.2023 | 03.14.2023 |  |  | GF | 160940 | 160940 |  | 159862 | 159862 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030115 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0173 | ELECTRICAL SUPPLIES | [19 empty] | PEEMO | PB | 02.21.2023 | 02.27.2023 | n/a | 03.07.2023 | 03.07.2023 | 03.07.2023 | 03.14.2023 | 03.27.2023 | 04.03.2023 | 04.13.2023 |  |  | GF | 337902 | 337902 |  | 337396.77 | 337396.77 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.02.2023 | n/a | n/a
23030141 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0152 | JOB ORDER (REPAIR AND MAINTENANCE OF | [19 empty] | PEEMO | PB | 02.21.2023 | 02.27.2023 | n/a | 03.21.2023 | 03.21.2023 | 03.21.2023 | 03.22.2023 | 03.31.2023 | 04.13.2023 | 04.20.2023 |  |  | GF | 782000 | 782000 |  | 780000 | 780000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.16.2023 | n/a | n/a
23030181 | HOSPITAL EQUIPMENT | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0815 | FOOD SUPPLIES | [19 empty] | PDRRMO | PB | n/a | 02.27.2023 | n/a | 03.21.2023 | 03.21.2023 | 03.21.2023 | 03.22.2023 | 03.31.2023 | 04.17.2023 | 04.20.2023 |  |  | GF | 281370 | 281370 |  | 229680 | 229680 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.16.2023 | n/a | n/a
23030176 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0159 | JANITORIAL SUPPLIES | [19 empty] | PEEMO | PB | 02.21.2023 | 03.13.2023 | n/a | 03.21.2023 | 03.21.2023 | 03.21.2023 | 03.22.2023 | 04.03.2023 | 04.13.2023 | 04.14.2023 | 05.03.2023 | 05.03.2023 | GF | 838084 | 838084 |  | 837560.25 | 837560.25 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.16.2023 | n/a | n/a
23030180 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0264 | MEALS AND SNACKS (A) | [19 empty] | PDRRMO | PB | 03.07.2023 | 03.13.2023 | n/a | 03.21.2023 | 03.21.2023 | 03.21.2023 | 03.22.2023 | 03.31.2023 | 04.13.2023 | 04.18.2023 | 04.19.2023 | 04.19.2023 | GF | 800400 | 800400 |  | 783000 | 783000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.16.2023 | n/a | n/a
23030178 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0109 | MEALS WITH VENUE, WIHTOUT VENUE | [19 empty] | PAGRO | PB | 02.21.2023 | 02.27.2023 | n/a | 03.21.2023 | 03.21.2023 | 03.21.2023 | 03.22.2023 | 03.31.2023 | 04.13.2023 | 04.18.2023 | 05.26.2023 | 05.26.2023 | GF | 386094 | 386094 |  | 378085 | 378085 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.16.2023 | n/a | n/a
23-03-0179 | AND SNACKS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0069 | MEALS WITH VENUE, WITHOUT VENUE | [19 empty] | PHRMDO | PB | n/a | 02.27.2023 | n/a | 03.21.2023 | 03.21.2023 | 03.21.2023 | 03.22.2023 | 03.30.2023 | 04.14.2023 | 04.18.2023 | 06.01.2023 | 06.01.2023 | GF | 551583 | 551583 |  | 537675 | 537675 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.16.2023 | n/a | n/a
23030172 | AND SNACKS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0058 | GRASSCUTTER 4-STROKE ENGINE WITH | [19 empty] | PAGRO | PB | 02.21.2023 | 02.27.2023 | n/a | 03.07.2023 | 03.07.2023 | 03.07.2023 | 03.14.2023 | 03.29.2023 | 04.03.2023 | 04.11.2023 |  |  | GF | 90900 | 90900 |  | 89000 | 89000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.02.2023 | n/a | n/a
23030139 | COMPLETE ACCESSORIES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0084 | AGRICULTURAL SUPPLIES | [19 empty] | PAGRO | PB | 02.21.2023 | 02.27.2023 | n/a | 03.07.2023 | 03.07.2023 | 03.07.2023 | 03.14.2023 | 03.29.2023 | 04.03.2023 | 04.04.2023 | 05.24.2023 | 05.24.2023 | GF | 856256 | 856256 |  | 848590 | 848590 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.02.2023 | n/a | n/a
23030140 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0859 | HOSPITAL EQUIPMET FOR THE | [19 empty] | PSWDO | PB | n/a | 02.17.2023 | n/a | 02.28.2023 | 02.28.2023 | 02.28.2023 | 03.16.2023 | 03.28.2023 | 04.03.2023 | 04.14.2023 |  |  | GF | 580140 | 580140 |  | 399180 | 399180 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 02.23.2023 | n/a | n/a
23030143 | USE OF PWD WELFARE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| PROGRAM | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0172 | MEDICAL SUPPLIES FOR THE USE | [19 empty] | PEEMO | PB | n/a | 02.17.2023 | n/a | 02.28.2023 | 02.28.2023 | 02.28.2023 | 03.16.2023 | 03.28.32023 | 04.03.2023 | 04.04.2023 |  |  | GF | 245861 | 245861 |  | 160817 | 160817 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 02.23.2023 | n/a | n/a
23030144 | OF MOLECULAR LABORATORY | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0175 | MEDICAL SUPPLIES | [19 empty] | PEEMO | PB | n/a | 02.17.2023 | n/a | 02.28.2023 | 02.28.2023 | 02.28.2023 | 03.16.2023 | 03.28.2023 | 04.03.2023 | 04.12.2023 |  |  | GF | 290532 | 290532 |  | 237685 | 237685 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 02.23.2023 | n/a | n/a
23030145 | FOR THE USE OF VARIOUS HOSPITAL | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0158 | SUPPLY AND DELIVERY OF FLUIDS | [19 empty] | PEEMO | PB | n/a | 02.17.2023 | 02.28.2023 | 02.28.2023 | 02.28.2023 | 02.28.2023 | 03.22.2023 | 03.31.2023 | 04.12.2023 | 04.17.2023 |  |  | GF | 1709362 | 1709362 |  | 1150560 | 1150560 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 02.23.2023 | n/a | n/a
23030167 | FOR THE USE OF VARIOUS HOSPITALS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0176 | SUPPLY AND DELIVERY OF MEDICAL | [19 empty] | PEEMO | PB | n/a | 02.17.2023 | 02.28.2023 | 03.21.2023 | 03.21.2023 | 03.21.2023 | 03.22.2023 | 04.03.2023 | 04.13.2023 | 04.20.2023 | 05.26.2023 | 05.26.2023 | GF | 1456432.2 |  | 1456432.2 | 786615.9 | 786615.9 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.16.2023 | n/a | n/a
23030168 | SUPPLIIES\FOR THE USE OF | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| VARIOUS HOSPITALS | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0732 | SUPPLY AND DELIVERY OF | [19 empty] | PGSO | PB | n/a | 03.07.2023 | n/a | 03.21.2023 | 03.21.2023 | 03.21.2023 | 03.22.2023 | 03.24.2023 | 04.17.2023 | 05.04.2023 | 05.16.2023 | 05.16.2023 | GF | 799560 | 799560 |  | 720850 | 720850 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.16.2023 | n/a | n/a
23030168 | SPARE PARTS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| LIGHT VEHICLE | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1587 | SPAREPARTS | [19 empty] | PGSO | SA | 2.21.2023 | n/a | n/a | n/a | 2.28.2023 | n/a | n/a | 3.3.2023 |  |  |  |  | GF | 12600 | 12600 |  | 12600 | 12600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030090 | (HEAVY EQUIPMENT) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1602 | WHEEL ALIGNMENT & WHEEL BALANCING | [19 empty] | PGSO | SA | 2.21.2023 | n/a | n/a | n/a | 2.28.2023 | n/a | n/a | 3.3.2023 |  |  |  |  | GF | 4500 | 4500 |  | 4500 | 4500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030089 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0239 | SPAREPARTS | [19 empty] | PGSO | PB | 2.21.2023 |  | 3.7.2023 | [9 empty] | GF | 3739970 | 3739970 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| (LIGHT EQUIPMENT) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0253 | AGRICULTURAL SUPPLIES | [19 empty] | PVO | PB | 2.21.2023 | 02.27.2023 | n/a | 03.21.2023 | 03.21.2023 | 03.21.2023 | 03.22.2023 | 03.24.2023 | 04.13.2023 | 04.20.2023 | 05.24.2023 | 05.24.2023 | GF | 249985 | 249985 |  | 247700 | 247700 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.16.2023 | n/a | n/a
23030181 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[39 empty] | 0 |  |  | Engr. Michael C. Salarda
23-0123 | VOICE RECORDER, 2GB BUILT-IN MEMORY | [19 empty] | PIAO | SVP | 2.21.2023 | n/a | n/a | n/a | 3.2.2023 | n/a | n/a | 03.10.2023 | 03.21.2023 | 03.22.2023 |  |  | GF | 4204 | 4204 |  | 4200 |  | 4200 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
2303003 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0020 | OFFICE SUPPLIES | [19 empty] | SPO | SB | 2.21.2023 | 2.27.2023 | n/a | n/a | 2.28.2023 | n/a | n/a | 03.06.2023 | 03.16.2023 | 03.20.2023 |  |  | GF | 171862 | 171862 |  | 171498 |  | 171498 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030087 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0133 | OFFICE SUPPLIES | [19 empty] | COA | SB | 2.21.2023 | n/a | n/a | n/a | 3.2.2023 | n/a | n/a | 03.10.2023 | 03.22.2023 | 03.27.2023 |  |  | GF | 9191 | 9191 |  | 9119 |  | 9119 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030095 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0148 | OFFICE SUPPLIES | [19 empty] | PDRRMO | SB | 2.21.2023 | n/a | n/a | n/a | 2.28.2023 | n/a | n/a | 03.06.2023 | 03.21.2023 | 03.22.2023 |  |  | GF | 32530 | 32530 |  | 31730 |  | 31730 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030088 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1594 | OFFICE SUPPLIES | [19 empty] | PGO | SB | 2.21.2023 | 2.27.2023 | n/a | n/a | 2.28.2023 | n/a | n/a | 03.07.2023 | 03.23.2023 | 03.27.2023 | 50.29.2023 | 05.29.2023 | GF | 73418 | 73418 |  | 73419.5 |  | 73419.5 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030086 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1800 | MONOBLOCK CHAIR CLASSIC | [19 empty] | PGO | PB | 02.28.2023 | 03.07.2023 | n/a | 03.21.2023 | 03.21.2023 | 03.21.2023 | 03.22.2023 | 03.31.2023 | 03.28.2023 | 03.28.2023 |  |  | GF | 691645 | 691645 |  | 640866 |  | 640866 | Mr. Allan Rey N. Esmael | n/a | n/a | 03.16.2023 | n/a | n/a
23030169 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1801 | TOKEN | [19 empty] | PGO | SVP | 2.28.2023 | n/a | n/a | n/a | 3.2.2023 | n/a | n/a | 03.10.2023 | 03.16.2023 | 03.20.2023 |  |  | GF | 24000 | 24000 |  | 23880 |  | 23880 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030100 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1802 | SAMBULAYANG 6MX1M SATIN CLOTH | [19 empty] | PGO | SVP | 2.28.2023 | 3.2.2023 | n/a | n/a | 3.2.2023 | n/a | n/a | 03.15.2023 | 03.17.2023 | 03.20.2023 |  |  | GF | 84000 | 84000 |  | 83825 |  | 83825 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030101 | (ASSORTED COLOR WITH TAILBOARD) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1803 | LIGHTS AND SOUND SYSTEM | [19 empty] | PGO | SVP | 2.28.2023 | 3.2.2023 | n/a | n/a | 3.2.2023 | n/a | n/a | 03.15.2023 | 03.15.2023 | 03.15.2023 |  |  | GF | 525000 | 525000 |  | 523000 |  | 523000 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030102 | RENTAL PACKAGE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1810 | ENTERTAINMENT PACKAGE | [19 empty] | PGO | NP | 2.28.2023 | [11 empty] | GF | 1300000 | 1300000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | CANCELLED/
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator | [6 empty] | RETURNED TO R.O.
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0314 | MEALS AND SNACKS | [19 empty] | PSWDO | SVP | n/a | 2.20.2023 | n/a | n/a | 2.23.2023 | n/a | n/a | 03.01.2023 | 03.13.2023 | 03.16.2023 | 04.14.2023 | 04.14.2023 | GF | 453631 | 453631 |  | 442108 |  | 442108 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030064 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0191 | OFFICE SUPPLIES | [19 empty] | PGSO | SB | n/a | 2.16.2023 | n/a | n/a | 2.23.2023 | n/a | n/a | 03.02.2023 | 03.14.2023 | 03.15.2023 |  |  | GF | 99990.5 | 99990.5 |  | 99962 |  | 99962 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030065 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0009 | SUPPLY AND DELIVERY OF ANIMAL SUPPLIES | [19 empty] | PVO | PB | n/a | 2.6.2023 | 02.16.2023 | 2.28.2023 | 2.28.2023 | 3.1.2023 | 3.1.2023 | 03.09.2023 | 03.13.2023 | 03.28.2023 |  |  | GF | 1165923 | 1165923 |  | 1093370 |  | 1093370 | Mr. Allan Rey N. Esmael | 02.13.2023 | n/a | 02.23.2023 | n/a | n/a
23030081 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0114 | SUPPLY AND DELIVERY OF RICE | [19 empty] | PGO | PB | n/a | 02.06.2023 | n/a | 02.28.2023 | 02.28.2023 | 02.28.2023 | 03.01.2023 | 03.06.2023 | 03.06.2023 | 03.06.2023 |  |  | GF | 167423 | 167423 |  | 127590 |  | 127590 | Mr. Allan Rey N. Esmael | n/a | n/a | 02.23.2023 | n/a | n/a
23030082 | (WELL MILLED) 50kg/sack | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0235 | SUPPLY AND DELIVERY OF BATTERY FOR | [19 empty] | PEO- | PB | n/a | 02.20.2023 | n/a | 02.28.2023 | 02.28.2023 | 02.28.2023 | 03.01.2023 | 03.07.2023 | 03.21.2023 | 03.23.2023 |  |  | GF | 695600 | 695600 |  | 444000 |  | 444000 | Mr. Allan Rey N. Esmael | n/a | n/a | 02.23.2023 | n/a | n/a
23030083 | THE USE OF VARIOUS PROVINCIAL | [19 empty] | MOTORPOOL | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| EQUIPMENT | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0190 | SUPPLY AND DELIVERY OF SPARE PARTS | [19 empty] | PEO- | PB | n/a | 02.20.2023 | n/a | 02.28.2023 | 02.28.2023 | 02.28.2023 | 03.01.2023 | 03.07.2023 | 03.24.2023 | 03.24.2023 |  |  | GF | 673510 | 673510 |  | 417700 |  | 417700 | Mr. Allan Rey N. Esmael | n/a | n/a | 02.23.2023 | n/a | n/a
23030084 | FOR THE USE OF VARIOUS PROVINCIAL | [19 empty] | MOTORPOOL | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| EQUIPMENT | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0153 | SUPPLY AND DELIVERY OF RICE | [19 empty] | PEEMO | PB | n/a | 02.20.2023 | n/a | 2.28.2023 | 2.28.2023 | 02.28.2023 | 03.01.2023 | 03.06.2023 | 03.07.2023 | 03.09.2023 |  |  | GF | 678149 | 678149 |  | 618700 |  | 618700 | Mr. Allan Rey N. Esmael | n/a | n/a | 02.23.2023 | n/a | n/a
23030085 | (WELL MILLED) 50kg/sack FOR THE USE OF | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| VARIOUS HOSPITALS | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1282 | MONTHLY PREVENTIVE MAINTENANCE OF | [19 empty] | PGSO | DC | n/a | 02.16.2023 | n/a | n/a | 03.03.2023 | n/a | n/a | 03.08.2023 | 03.21.2023 | 03.22.2023 |  |  | GF | 25500 | 25500 |  | 25500 |  | 25500 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030091 | 1 UNIT MITSUBISHI ELEVATOR | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0156 | PRINTING SUPPLIES | [19 empty] | PEEMO | DC | 02.21.2023 | 02.27.2023 | n/a | n/a | 03.03.2023 | n/a | n/a | 03.08.2023 | 03.16.2023 | 03.17.2023 |  |  | GF | 18484 | 18484 |  | 18076 |  | 18076 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030092 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0231 | BLOOD CHEMISTRY SUPPLIES | [19 empty] | PEEMO | DC | 02.21.2023 | 02.27.2023 | n/a | n/a | 03.03.2023 | n/a | n/a | 03.08.2023 | 03.16.2023 | 03.17.2023 |  |  | GF | 796804 | 796804 |  | 796804 |  | 796804 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030093 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0124 | MEALS AND SNACKS | [19 empty] | PIAO | SVP | n/a | 02.06.2023 | n/a | n/a | 2.28.2023 | n/a | n/a | 03.08.2023 | 03.16.2023 | 03.17.2023 | 05.23.2023 | 05.23.2023 | GF | 17745 | 17745 |  | 17550 |  | 17550 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030067 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0751 | THERMOS JUG AND WATER HEATER | [19 empty] | PBO | SVP | n/a | 02.14.2023 | n/a | n/a | 2.28.2023 | n/a | n/a | 03.08.2023 | 03.15.2023 | 03.16.2023 |  |  | GF | 1532 | 1532 |  | 1532 |  | 1532 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030068 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0248 | MEALS AND SNACKS | [19 empty] | PICTO | SVP | n/a | 02.16.2023 | n/a | n/a | 2.28.2023 | n/a | n/a | 3.3.2023 | 03.16.2023 | 03.17.2023 | 06.28.2023 | 06.28.2023 | GF | 20691 | 20691 |  | 20472 |  | 20472 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030069 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0225 | TARPAULIN - AS PER DESIGN | [19 empty] | SPO | SVP | n/a | 02.16.2023 | n/a | n/a | 2.28.2023 | n/a | n/a | 3.3.2023 | 03.16.2023 | 03.17.2023 | 06.14.2023 | 06.14.2023 | GF | 11200 | 11200 |  | 11000 |  | 11000 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030070 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1598 | JANITORIAL SUPPLIES | [19 empty] | PGO | SVP | n/a | 02.20.2023 | n/a | n/a | 2.28.2023 | n/a | n/a | 3.3.2023 | 03.14.2023 | 03.15.2023 |  |  | GF | 28440 | 28440 |  | 28144 |  | 28144 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030071 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0965 | JANITORIAL SUPPLIES | [19 empty] | PLO | SVP | n/a | 02.20.2023 | n/a | n/a | 2.28.2023 | n/a | n/a | 3.3.2023 | 03.22.2023 | 03.24.2023 |  |  | GF | 14344 | 14344 |  | 14116 |  | 14116 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030072 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0262 | WOOD CHARCOAL, 20KG/SACK | [19 empty] | PAGRO | SVP | n/a | 02.14.2023 | n/a | n/a | 2.28.2023 | n/a | n/a | 3.3.2023 | 03.15.2023 | 03.16.2023 |  |  | GF | 10890 | 10890 |  | 10780 |  | 10780 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030073 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0096 | OFFICE TABLES AND CHAIRS | [19 empty] | PICTO | SVP | n/a | 02.16.2023 | n/a | n/a | 2.28.2023 | n/a | n/a | 3.3.2023 | 03.22.2023 | 04.03.2023 |  |  | GF | 49938 | 49938 |  | 49610 |  | 49610 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030074 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0477 | JANITORIAL SUPPLIES | [19 empty] | COA | SVP | 02.21.2023 | 02.27.2023 | n/a | n/a | 03.03.2023 | n/a | n/a | 03.03.2023 | 03.15.2023 | 03.16.2023 |  |  | GF | 25143 | 25143 |  | 24997 |  | 24997 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030075 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0721 | MEMO APDS | [19 empty] | PBO | SVP | 02.21.2023 | 02.27.2023 | n/a | n/a | 03.03.2023 | n/a | n/a | 03.03.2023 | 03.15.2023 | 03.16.2023 |  |  | GF | 1300 | 1300 |  | 1300 |  | 1300 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030076 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0509 | SCUBA DIVING BOOTS (2 PAIRS OF SIZE 10) | [19 empty] | PGO | SVP | n/a | 02.27.2023 | n/a | n/a | 03.03.2023 | n/a | n/a | 03.03.2023 | 03.14.2023 | 03.15.2023 |  |  | GF | 5000 | 5000 |  | 4400 |  | 4400 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030077 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0010 | MEALS WITH VENUE,VIP MEALS, AND | [19 empty] | PPDO | SVP | 02.21.2023 | 02.27.2023 | n/a | n/a | 03.03.2023 | n/a | n/a | 03.06.2023 | 03.06.2023 | 03.07.2023 | 06.20.2023 | 06.20.2023 | GF | 484925 | 484925 |  | 470135 |  | 470135 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030078 | LIGHT SNACKS A | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0110 | PACKED MEALS AND HEAVY & LIGHT SNACKS | [19 empty] | PHO | SVP | 02.21.2023 | 02.27.2023 | n/a | n/a | 03.03.2023 | n/a | n/a | 03.06.2023 | 03.06.2023 | 03.07.2023 | 06.26.2023 | 06.26.2023 | GF | 499416 | 499416 |  | 489205 |  | 489205 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030079 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0955 | MINERAL WATER 5 GAL. | [19 empty] | PDRRMO | SVP | n/a | 02.27.2023 | n/a | n/a | 03.03.2023 | n/a | n/a | 03.03.2023 | 03.07.2023 | 03.16.2023 |  |  | GF | 4551 | 4551 |  | 4440 |  | 4440 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030080 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0264 | MEALS AND SNACKS | [19 empty] | PDRRMO | PB | 03.07.2023 | [11 empty] | GF | 800400 | 800400 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1164 | VULCANIZING AND CHANGE TIRE | [19 empty] | PDRRMO | SA | 03.07.2023 | [11 empty] | GF | 25000 | 25000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0136 | AVR AND BARCODE SCANNER, HANDHELD | [19 empty] | PTO | SVP | 03.07.2023 | 03.10.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 03.30.2023 | 04.11.2023 | 05.16.2023 | 05.16.2023 | GF | 16693 | 16693 |  | 16680 | 16680 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030119 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0048 | PACKED MEALS AND SNACKS B (LIGHT) | [19 empty] | PGO | PB | 03.07.2023 | 03.13.2023 | n/a | 03.21.2023 | 03.21.2023 | 03.21.2023 | 03.22.2023 | 03.31.2023 | 04.25.2023 | 04.28.2023 |  |  | GF | 410886 | 410886 |  | 390180 | 390180 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.16.2023 | n/a | n/a
23030177 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0145 | SPARE PARTS (VEHICLE MAINTENANCE) | [19 empty] | COA | SVP | 03.07.2023 | 03.10.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.03.2023 | 04.03.2023 |  |  | GF | 92642 | 92642 |  | 91650 | 91650 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030118 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0233 | MINERAL WATER, 5 GAL. | [19 empty] | SPO | SVP | n/a | 02.16.2023 | n/a | n/a | 03.07.2023 | n/a | n/a | 03.10.2023 | 03.22.2023 | 03.24.2023 |  |  | GF | 27593 | 27593 |  | 26920 | 26920 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030096 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
Engr. Michael C. Salarda
23-C0276 | JANITORIAL SUPPLIES | [19 empty] | PBO | SVP | n/a | 02.16.2023 | n/a | n/a | 03.02.2023 | n/a | n/a | 03.10.2023 | 03.22.2023 | 03.24.2023 |  |  | GF | 6949 | 6949 |  | 6846.25 | 6846.25 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030097 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0129 | COMPUTER ACCESSORIES | [19 empty] | COA | SVP | 02.21.2023 | 02.27.2023 | n/a | n/a | 03.07.2023 | n/a | n/a | 03.10.2023 | 03.22.2023 | 03.24.2023 |  |  | GF | 7090 | 7090 |  | 7074 | 7074 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030098 | AND INK PRINTER SUPPLIES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0712 | JANITORIAL SUPPLIES | [19 empty] | PACCO | SVP | 02.21.2023 | 02.27.2023 | n/a | n/a | 03.02.2023 | n/a | n/a | 03.10.2023 | 03.16.2023 | 03.17.2023 | 03.24.2023 | 03.24.2023 | GF | 20072 | 20072 |  | 17390 | 17390 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030099 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1079 | MEALS AND SNACKS | [19 empty] | PGO | SVP | n/a | 03.03.2023 | n/a | n/a | 03.02.2023 | n/a | n/a | 03.15.2023 | 03.16.2023 | 03.17.2023 | 06.01.2023 | 06.01.2023 | GF | 141200 | 141200 |  | 134000 | 134000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030104 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0228 | DETERGENT POWDER | [19 empty] | PDRRMO | SVP | n/a | 02.27.2023 | n/a | n/a | 03.02.2023 | n/a | n/a | 03.10.2023 | 03.21.2023 | 03.22.2023 |  |  | GF | 9394 | 9394 |  | 9150 | 9150 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030105 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0165 | CONSTRUCTION SUPPLIES | [19 empty] | PEEMO | SVP | n/a | 03.03.2023 | n/a | n/a | 03.07.2023 | n/a | n/a | 03.13.2023 | 03.14.2023 | 03.15.2023 | 05.03.2023 | 05.03.2023 | GF | 270478 | 270478 |  | 267195 | 267195 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030106 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0200 | MEDICAL SUPPLIES | [19 empty] | PDRRMO | SVP | n/a | 03.03.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 | 06.26.2023 |  |  | GF | 103550 | 103550 |  | 103279 | 103279 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060641 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0236 | PROTECTIVE GEARS AND CLEANING SUPPLIES | [19 empty] | PENRO | SVP | n/a | n/a | n/a | n/a | 3.23.2023 | n/a | n/a | 04.01.2023 | 04.17.2023 | 04.18.2023 |  |  | GF | 26236 | 26236 |  | 26212 | 26212 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030181 | [38 empty] | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0526 | DIGITAL CAMERA (SPECS) | [19 empty] | PGO | SB | n/a | 02.27.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.03.2023 | 04.11.2023 |  |  | GF | 40000 | 40000 |  | 39800 | 39800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030114 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0026 | LEAVE CARD | [19 empty] | PHRMDO | SB | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.03.2023 | 04.04.2023 |  |  | GF | 7000 | 7000 |  | 7000 | 7000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030113 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0272 | OFFICE SUPPLIES | [19 empty] | PBO | SB | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.28.2023 | 04.03.2023 | 04.04.2023 |  |  | GF | 86666 | 86666 |  | 86561 | 86561 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030112 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0744 | OFFICE SUPPLIES | [19 empty] | PACCO | SB | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.28.2023 | 04.03.2023 | 04.04.2023 |  |  | GF | 112350 | 112350 |  | 111270 | 111270 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030111 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0244 | JANITORIAL SUPPLIES | [19 empty] | PVO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.03.2023 | 04.03.2023 | 04.25.2023 | 04.25.2023 | GF | 16420 | 16420 |  | 16282 | 16282 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030120 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0031 | DISTILLED WATER 6L/GAL (NO CPR) | [19 empty] | PAGRO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.03.2023 | 04.03.2023 |  |  | GF | 25894 | 25894 |  | 25680 | 25680 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030121 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0037 | JANITORIAL SUPPLIES | [19 empty] | PAGRO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.03.2023 | 04.04.2023 | 05.19.2023 | 05.19.2023 | GF | 27797 | 27797 |  | 27132 | 27132 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030123 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1408 | SHOVEL (HEAVY DUTY, 10 PCS) | [19 empty] | PDRRMO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.03.2023 | 04.11.2023 |  |  | GF | 5500 | 5500 |  | 5480 | 5480 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030122 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0051 | POLO SHIRT AND SPORTS UNIFORM | [19 empty] | PGO-SEF | SVP | n/a | 03.10.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.28.2023 | 03.29.2023 | 03.30.2023 |  |  | GF | 360000 | 360000 |  | 346050 | 346050 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030124 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1307 | FERTILIZER AND HERBICIDE | [19 empty] | PVO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.28.2023 | 03.29.2023 | 03.30.2023 |  |  | GF | 74955 | 74955 |  | 73970 | 73970 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030125 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0538 | ELECTRIC WELDING MACHINE (SPECS) | [19 empty] | PDRRMO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.03.2023 | 04.04.2023 |  |  | GF | 25000 | 25000 |  | 24500 | 24500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030126 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0463 | COLORED PRINTER 3-IN-1 AND EXTERNAL | [19 empty] | PAGRO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.03.2023 | 04.04.2023 |  |  | GF | 16600 | 16600 |  | 16580 | 16580 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030127 | HARD DRIVE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0639 | CELLCARD | [19 empty] | PGO-SEF | SVP | n/a | 03.10.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 03.29.2023 | 03.29.2023 | 05.05.2023 | 05.05.2023 | GF | 10000 | 10000 |  | 10000 | 10000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030128 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1207 | BINDER (AS PER SAMPLE, 80 PCS) | [19 empty] | PACCO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.03.2023 | 04.04.2023 |  |  | GF | 24000 | 24000 |  | 23840 | 23840 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030129 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0252 | DOG VACCINATION CERTIFICATE AND | [19 empty] | PVO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.13.2023 | 04.04.2023 | 05.08.2023 | 05.08.2023 | GF | 28960 | 28960 |  | 28653 | 28653 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030130 | TARPAULIN (AS PER DESIGN) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1614 | CHICK EMBRYO CELL (SPECS) | [19 empty] | PVO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.28.2023 | 04.03.2023 | 04.04.2023 |  |  | GF | 73600 | 73600 |  | 51570 | 51570 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030131 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0310 | RUBBER BOOTS AND RAINCOATS | [19 empty] | PDRRMO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.28.2023 | 04.03.2023 | 04.04.2023 |  |  | GF | 63579 | 63579 |  | 63170 | 63170 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030132 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1639 | PICTURE FRAME (AS PER DESIGN) | [19 empty] | SPO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.03.2023 | 04.04.2023 | 05.08.2023 | 05.08.2023 | GF | 16500 | 16500 |  | 16250 | 16250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030133 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0284 | TARPAULIN-AS PER DESIGN | [19 empty] | SPO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.04.2023 | 04.12.2023 |  |  | GF | 30660 | 30660 |  | 28470 | 28470 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030134 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0205 | OCCUPATIONAL SAFETY GEAR | [19 empty] | PDRRMO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.28.2023 | 04.03.2023 | 04.04.2023 |  |  | GF | 68900 | 68900 |  | 68500 | 68500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23033135 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1680 | OUTDOOR STICKER (AS PER SAMPLE) | [19 empty] | PTO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.21.2023 | n/a | n/a | 03.24.2023 | 04.03.2023 | 04.04.2023 |  |  | GF | 28500 | 28500 |  | 28000 | 28000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030136 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0255 | OFFICE SUPPLIES | [19 empty] | PTO | SB | n/a | 03.14.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 04.03.2023 | 04.13.2023 | 04.14.2023 | 05.08.2023 | 05.08.2023 | GF | 173522 | 173522 |  | 173224 | 173224 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030147 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1806 | STICKY NOTE/INDEX TAB (AS PER SAMPLE) | [19 empty] | PBO | SB | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.29.2023 | 04.13.2023 | 04.14.2023 | 06.27.2023 | 06.27.2023 | GF | 7000 | 7000 |  | 6800 | 6800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030148 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0274 | COMPUTER ACCESSORIES AND PRINTING | [19 empty] | PGO | SB | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.24.2023 | 04.20.2023 | 04.25.2023 | 05.05.2023 | 05.05.2023 | GF | 68924 | 68924 |  | 68860 | 68860 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030149 | SUPPLIES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1975 | FIRE EXTINGUISHER REFILL (10 LBS) | [19 empty] | PGO | SB | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.24.2023 | 04.20.2023 | 04.25.2023 |  |  | GF | 26741 | 26741 |  | 26000 | 26000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030160 | SUPPLIES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1071 | MINERAL WATER, 5 GAL | [19 empty] | PGO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.24.2023 | 04.25.2023 | 04.28.2023 |  |  | GF | 15375 | 15375 |  | 15000 | 15000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030161 | SUPPLIES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1161 | PRINTER INK SUPPLIES | [19 empty] | PGO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.24.2023 | 04.20.2023 | 04.25.2023 |  |  | GF | 20904 | 20904 |  | 20688 | 20688 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030162 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1172 | JANITORIAL SUPPLIES | [19 empty] | PGO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.24.2023 | 04.20.2023 | 04.25.2023 |  |  | GF | 8320 | 8320 |  | 8050 | 8050 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030163 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0243 | CABINET AND PLASTIC CHAIR AND PITCHER | [19 empty] | PVO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.24.2023 | 04.18.2023 | 04.19.2023 |  |  | GF | 15865 | 15865 |  | 15610 | 15610 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030164 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1761 | MEALS AND SNACKS | [19 empty] | PGO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.31.2023 | 04.20.2023 | 04.24.2023 | 06.13.2023 | 06.13.2023 | GF | 74520 | 74520 |  | 72900 | 72900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030165 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0157 | MEALS | [19 empty] | PGO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.29.2023 | 04.20.2023 | 04.24.2023 |  |  | GF | 9264 | 9264 |  | 9120 | 9120 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030166 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0275 | VETERINARY SUPPLIES | [19 empty] | PVO | SVP | n/a | 03.14.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.31.2023 | 04.20.2023 | 04.25.2023 | 05.05.2023 | 05.05.2023 | GF | 71848 | 71848 |  | 71847.55 | 71847.55 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030150 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0783 | MEALS VIP AND HEAVY SNACKS | [19 empty] | PVGO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 04.03.2023 | 04.19.2023 | 04.20.2023 |  |  | GF | 125000 | 125000 |  | 123500 | 123500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030151 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0261 | LABORATORY CHEMICALS | [19 empty] | PENRO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 04.17.2023 | 04.17.2023 | 04.20.2023 |  |  | GF | 21675 | 21675 |  | 21628 | 21628 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030152 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1512 | FOOD SUPPLIES-COFFEE, SUGAR, ETC | [19 empty] | PVGO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.29.2023 | 04.20.2023 | 04.25.2023 |  |  | GF | 7885 | 7885 |  | 7590 | 7590 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030153 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0123 | PRINTING AND BINDING OF BOOKS AND | [19 empty] | PHO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.29.2023 | 04.17.2023 | 04.18.2023 | 05.22.2023 | 05.22.2023 | GF | 22875 | 22875 |  | 22875 | 22875 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030154 | TRAINING MODULES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1040 | BOOK BINDING & PRINTING COVER | [19 empty] | PDRRMO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.29.2023 | 04.13.2023 | 04.14.2023 |  |  | GF | 10450 | 10450 |  | 10400 | 10400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030155 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0132 | JANITORIAL SUPPLIES | [19 empty] | PHO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.29.2023 | 04.17.2023 | 04.18.2023 |  |  | GF | 31467 | 31467 |  | 31367 | 31367 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030156 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1049 | TARPAULIN-AS PER DESIGN | [19 empty] | PDRRMO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.29.2023 | 04.13.2023 | 04.14.2023 | 06.27.2023 | 06.27.2023 |  | 8400 | 8400 |  | 8250 | 8250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030157 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0084 | MOBILE CABINET-3 DRAWERS (SPECS) | [19 empty] | PAO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.24.2023 | 04.20.2023 | 04.25.2023 |  |  | GF | 9900 | 9900 |  | 9890 | 9890 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030158 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1831 | PACKED MEALS AND SNACKS | [19 empty] | PGO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.24.2023 | n/a | n/a | 03.24.2023 | 04.20.2023 | 04.25.2023 |  |  | GF | 36900 | 36900 |  | 35250 | 35250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030159 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1898 | CONSTRUCTION OF WATER SYSTEM AT | [19 empty] | PEO | PB | 03.21.2023 | 05.18.2023 | 05.16.2023 | 05.30.2023 | 05.30.2023 | 05.30.2023 | [6 empty] | GF | 1446387.8 | 1446387.8 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR POST QUA
| CAMP 4, BRGY. PINDASAN, MABINI, DAVAO | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| DE ORO | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1896 | REHABILITATION OF FREEDOM | [19 empty] | PEO | PB | 03.21.2023 | [11 empty] | GF | 981386.05 | 981386.05 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| STAGE AT BRGY. OSMENA, COMPOSTELA | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1830 | REHABILITATION OFDRAINAGE | [19 empty] | PEO | PB | 03.21.2023 | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 2268269.88 | 2268269.88 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR POST QUA
| STRUCTURE AT ALEGRIA SECTION ALONG | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| NABUNTURAN-GABI-COMPOSTELA ROAD | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1833 | CONSTRUCTION OF COVERED COURT, | [19 empty] | PEO | PB | 03.21.2023 | [11 empty] | GF | 3751603.89 | 3751603.89 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| SITIO, MAG-ABAY, BRGY. MAGNAGA | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| NHS, BRGY. MAGNAGA, PANTUKAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1899 | CONSTRUCTION OF ONE (1) STOREY-TWO | [19 empty] | PEO | PB | 03.21.2023 | 04.21.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 05.18.2023 | 06.02.2023 | 06.09.2023 | 06.14.2023 |  |  | GF | 2975982.21 | 2975982.21 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| CLASSROOM SCHOO; BUILDING WITH TOILET | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| ATTACHED AT PANIBASAN NHS, MACO | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1625 | IMPROVEMENT OF DE ORO BAHAY PANGARAP | [19 empty] | PEO | PB | 03.21.2023 | 04.21.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 05.18.2023 | 06.02.2023 | 06.09.2023 | 06.14.2023 |  |  | GF | 1714912.26 |  | 1714912.26 | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| FACILITY, BRGYCABIDIANAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| NABUNTURAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1630 | CONSTRUCTION OF SLOPE PROTECTION | [19 empty] | PEO | PB | 03.21.2023 | 05.08.2023 | 05.16.2023 | 05.30.2023 | 05.30.2023 | 05.30.2023 | [6 empty] | GF | 1241109.13 |  | 1241109.13 | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR POST-QUA
| AT BRGY. PANANGAN, MACO | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1626 | CONSTRUCTION OF MULTIPURPOSE | [19 empty] | PEO | PB | 03.21.2023 | 04.21.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 06.15.2023 | 06.27.2023 |  |  |  |  | GF | 4778137.59 |  | 4778137.59 | 4727954 |  | 4727954 | Mr. Allan Rey N. Esmael | 04.26.2023 | n/a | 05.11.2023 | n/a | n/a
CW23-006 | BUILDING, CAMANSI NATIONAL HIGH | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| SCHOOL, MONTEVISTA | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1634 | CONSTRUCTION OF 1 UNIT 2 CLASSROOMS, | [19 empty] | PEO | PB | 03.21.2023 | 04.21.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 06.15.2023 | 06.27.2023 |  |  |  |  | GF | 2495161.76 |  | 2495161.76 | 2454983.84 |  | 2454983.84 | Mr. Allan Rey N. Esmael | 04.26.2023 | n/a | 05.11.2023 | n/a | n/a |  | FOR CONTRACT SIGNING
CW23-016 | MAGCAGONG NHS, BRGY. MAGCAGONG, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| MARAGUSAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1631 | CONSTRUCTION OF TUGOP, BRGY. | [19 empty] | PEO | PB | 03.21.2023 | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 2832670.36 |  | 2832670.36 | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR POST-QUA
CW23-053 | KINGKING, PANTUKAN, DAVAO DE ORO- | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1390 | CONSTRUCTION OF DRAINAGE | [19 empty] | PEO | PB | 03.21.2023 | 06.05.2023 | 06.13.2023 | 06.27.2023 | 06.27.2023 | 06.27.2023 | [6 empty] | GF | 4398193.31 |  | 4398193.31 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.07.2023 | n/a | 06.22.2023 | n/a | n/a |  | FOR POST-QUA
CW23-021 | MARAGUSAN, NATIONAL HIGH SCHOOL, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| MARAGUSAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1629 | CONSTRUCTION OF MULTIPURPOSE | [19 empty] | PEO | PB | 03.21.2023 | 05.08.2023 | 05.16.2023 | 05.30.2023 | 05.30.2023 | 05.30.2023 | [6 empty] | GF | 4891611.84 |  | 4891611.84 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.07.2023 | n/a | 05.25.2023 | n/a | n/a |  | FOR POST-QUA
CW23-021 | BUILDING, MAYAON NATIONAL HIGH | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| SCHOOL, MONTEVISTA | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1627 | CONSTRUCTION OF MULTIPURPOSE | [19 empty] | PEO | PB | 03.21.2023 | 04.21.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 06.15.2023 | 06.27.2023 |  |  |  |  | GF | 4874674.43 |  | 4874674.43 | 4844040.38 |  | 4844040.38 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
CW23-011 | SAN ISIDRO ELEMENTARY SCHOOL, BRGY. | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| SCHOOL, MONTEVISTA | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1551 | CONSTRUCTION OF MATERIALS | [19 empty] | PEO | PB | 03.21.2023 | [11 empty] | GF | 5582 | 5582 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| AND TARPAULIN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1352 | LIQUID NITROGEN | [19 empty] | PVO | PB | 03.21.2023 | [11 empty] | GF | 19200 | 19200 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| (REFILL) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1421 | CEILING SPEAKER AND PUBLIC | [19 empty] | PDRRMO | SVP | 03.21.2023 | [11 empty] | GF | 34500 | 34500 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| ADDRESS AMPLIFIER 250 WATTS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0266 | PORTABLE SOUND SYSTEM | [19 empty] | PENRO | NP-Two failed | 03.21.2023 | 05.31.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 200150 | 200150 |  | 197500 | 197500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 02.22.2023 | n/a | n/a
23060713 | [21 empty] | biddings | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0355 | PROFESSIONAL CAMERA STAND, | [19 empty] | PAO-ADMIN | SVP | 03.21.2023 | n/a | n/a | n/a |  | n/a | n/a | [5 empty] | GF | 3550 | 3550 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| TRIPOD WITH HEAD AND PLATE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1632 | WATER DISPENSER | [19 empty] | PACCO | SVP | 03.21.2023 | n/a | n/a | n/a |  | n/a | n/a | [5 empty] | GF | 5500 | 5500 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0120 | PHOTOCOPY OF DOCUMENTS | [19 empty] | PHO | SA | 03.21.2023 | n/a | n/a | n/a |  | n/a | n/a | [5 empty] | GF | 8466 | 8466 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1815 | SPARE PARTS | [19 empty] | PDRRMO | SA | 03.28.2023 | n/a | n/a | n/a | 04.18.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.11.2023 |  |  | GF | 16152 | 16152 |  | 16152 | 16152 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.10.2023 | n/a | n/a
23030234 | [26 empty] | . | [8 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1887 | FOOD SUPPL;IES | [19 empty] | PDRRMO | SVP | 3.28.2023 | 05.22.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 |  |  |  |  | GF | 99948 | 99948 |  | 99916 | 99916 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060642 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1420 | JANITORIAL SUPPLIES | [19 empty] | PDRRMO | SVP | 3.28.2023 | 03.30.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.08.2023 | 05.10.2023 | 05.17.2023 | 05.17.2023 | GF | 76420 | 76420 |  | 74970 | 74970 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040279 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1423 | OFFICE SUPPLIES | [19 empty] | PDRRMO | SB | 3.28.2023 | 03.30.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 177200 | 177200 |  | 172350 | 172350 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040252 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0032 | INDUSTRIAL OXYGEN REFILL | [19 empty] | PAGRO | DC | 3.28.2023 | [11 empty] | GF | 102715 | 102715 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| LPG REFILL AND ACETYLENE REFILL | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| (DC TO PRYCE GAS) | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0105 | OFFICE SUPPLIES | [19 empty] | PAGRO | SB | 3.28.2023 | 03.30.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.22.2023 | 06.05.2023 | 06.07.2023 | 06.21.2023 | 06.21.2023 | GF | 78961 |  | 78961 | 77834.75 |  | 77834.75 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050526 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2095 | BRAKE PAD | [19 empty] | DDOPH- | SA | 3.28.2023 | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 5600 | 5600 |  | 5600 | 5600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040233 | [20 empty] | Maragusan | [17 empty] | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2094 | BRAKE PAD | [19 empty] | DDOPH- | SA | 3.28.2023 | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 5600 | 5600 |  | 5600 | 5600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040232 | [20 empty] | Maragusan | [17 empty] | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1919 | SPARE PARTS | [19 empty] | PGSO | SA | 3.28.2023 | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.11.2023 |  |  | GF | 9960 | 9960 |  | 9960 | 9960 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040236 | (BRAKE PAD, BRAKE SHOE) | [37 empty] | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1921 | SPARE PARTS | [19 empty] | PGSO | SA | 3.28.2023 | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 |  |  |  |  | GF | 20110 | 20110 |  | 20110 | 20110 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040235 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0267 | OFFICE SUPPLIES | [19 empty] | PGO | SB | 3.28.2023 | 03.30.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.15.2023 | 05.18.2023 | 05.19.2023 | 05.19.2023 | GF | 155857 | 155857 |  | 154582.75 | 154582.75 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040251 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1607 | DOUBLE REVITS | [20 empty] | SVP | 3.28.2023 | 03.30.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.17.2022 | 05.22.2022 |  |  | GF | 36000 | 36000 |  | 34500 | 34500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050341 | INDUSTRIAL SHELVES | [19 empty] | PGO | [17 empty] | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1278 | COMPUTER SPARE PARTS | [19 empty] | PGO | SVP | 3.28.2023 | 03.30.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.17.2023 | 05.24.2023 | 05.30.2023 | 06.14.2023 | 06.14.2023 | GF | 102923 | 102923 |  | 102608 | 102608 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050395 | [20 empty] | (DILG) | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0784 | TRANSFORMERS, 15kva | [19 empty] | PGO | NP | 3.28.2023 | 05.05.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.07.2023 | 06.20.2023 | 06.23.2023 |  |  | TF | 181830 | 181830 |  | 179550 | 179550 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050549 | [20 empty] | (HPG) | TWO FAILED | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[22 empty] | BIDDINGS | [13 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0295 | OFFICE SUPPLIES & DEVICES | [19 empty] | PSWDO | SB | 3.28.2023 | 03.30.2023 | n/a | n/a | 05.11.2023 | 05.11.2023 | n/a | 05.19.2023 | 05.29.2023 | 05.30.2023 | 06.09.2023 | 06.09.2023 | GF | 168505 | 168505 |  | 165605 | 165605 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050371 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1509 | COLORED PRINTER | [19 empty] | VGO | PB | 3.28.2023 | 04.18.2023 | n/a | 04.19.2023 | 04.19.2023 | 04.19.2023 | n/a | n/a |  |  |  |  | GF | 69640 | 69640 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | CHANGE MODE TO SVP
| COMPUTER SET WITH | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| COMPLETE ACCESSORIES | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0233 | OFFICE SUPPLIES | [19 empty] | PENRO | SB | 3.28.2023 | 03.30.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.08.2023 | 05.10.2023 | 06.26.2023 | 06.26.2023 | GF | 290605 | 290605 |  | 122659 | 122659 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040250 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1825 | PROJECTOR AS PER SPECIFICATION | [19 empty] | PTO | SVP | 3.28.2023 | 03.30.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 | 06.27.2023 |  |  | GF | 49500 | 49500 |  | 45000 | 45000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR DELIVERY
23060643 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0346 | OFFICE SUPPLIES | [19 empty] | PASSO | NP | 3.28.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 06.01.2023 | 06.02.2023 | 06.21.2023 | 06.21.2023 | GF | 290605 | 290605 |  | 288752 | 288752 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050519 | [35 empty] | 0 | 0 |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0289 | ELECTRONIC SUPPLIES | [19 empty] | PICTO | SVP | 3.28.2023 |  | n/a | n/a |  | n/a | n/a | [5 empty] | GF | 141220 | 141220 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0229 | INTERNET SUBSCRIPTION | [19 empty] | PAO-ID | DC | 3.28.2023 | 03.30.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 166440 | 166440 |  | 166440 | 166440 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050613 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0852 | I LOT CLOUD SERVER | [19 empty] | PICTO | DC | 3.28.2023 | [11 empty] | TF | 344209 | 344209 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| ANNUAL SUBSCRIPTION | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0317 | CODE REPOSITORY AND | [19 empty] | PICTO | NP | 3.28.2023 | 05.05.2023 | n/a | 05.16.2023 | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 |  |  |  | GF | 105000 | 105000 |  | 103000 | 103000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050520 | WEB HOSTING PACKAGE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| WITH SPECIFICATION | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0211 | MEALS AND SNACKS | [19 empty] | PDRRMO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.28.2023 | n/a | n/a | 03.31.2023 | 04.13.2023 | 04.14.2023 | 06.06.2023 | 06.06.2023 | GF | 68764 | 68764 |  | 63220 | 63220 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030182 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1941 | VARIOUS TROPHIES | [19 empty] | PGO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.28.2023 | n/a | n/a | 04.01.2023 | 04.20.2023 | 04.25.2023 |  |  | GF | 11500 | 11500 |  | 11446 | 11446 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030183 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0338 | VETERINARY SUPPLIES | [19 empty] | PVO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.28.2023 | n/a | n/a | 04.01.2023 | 04.13.2023 | 04.20.2023 |  |  | GF | 18125 | 18125 |  | 18088 | 18088 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030184 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1201 | FOOD SUPPLIES-DRY GOODS | [19 empty] | PGO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.28.2023 | n/a | n/a | 04.01.2023 | 04.20.2023 | 04.25.2023 |  |  | GF | 20996 | 20996 |  | 20780 | 20780 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030185 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0229 | AGRICULTURAL SUPPLIES | [19 empty] | PDRRMO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.28.2023 | n/a | n/a | 04.01.2023 | 04.13.2023 | 04.14.2023 |  |  | GF | 19783 | 19783 |  | 19380 | 19380 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030186 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1574 | MEALS AND SNACKS | [19 empty] | PGO | SVP | n/a | 03.17.2023 | n/a | n/a | 03.28.2023 | n/a | n/a | 03.31.2023 | 04.13.2023 | 04.14.2023 | 06.09.2023 | 06.09.2023 | GF | 99625 | 99625 |  | 94250 | 94250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030187 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1755 | MEALS AND SNACKS | [19 empty] | PGO | SVP | n/a | 03.23.2023 | n/a | n/a | 03.28.2023 | n/a | n/a | 04.01.2023 | 04.20.2023 | 04.26.2023 |  |  | GF | 19695 | 19695 |  | 19532.5 | 19532.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030188 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1943 | MEALS AND SNACKS | [19 empty] | PGO | SVP | n/a | 03.23.2023 | n/a | n/a | 03.28.2023 | n/a | n/a | 04.01.2023 | 04.20.2023 | 04.26.2023 |  |  | GF | 39485 | 39485 |  | 39352.5 | 39352.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030189 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1940 | CERTIFICATE FRAME AND PAPER | [19 empty] | PGO | SVP | n/a | 03.23.2023 | n/a | n/a | 03.28.2023 | n/a | n/a | 04.01.2023 | 04.20.2023 | 04.26.2023 |  |  | GF | 3300 | 3300 |  | 2937 | 2937 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030190 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1973 | TARPAULIN-AS PER DESIGN | [19 empty] | PGO | SVP | n/a | 03.23.2023 | n/a | n/a | 03.28.2023 | n/a | n/a | 04.01.2023 | 04.20.2023 | 04.20.2023 |  |  | GF | 9996 | 9996 |  | 9817.5 | 9817.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030191 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1942 | SWEAT-SHIRT-FULL SUBLIMATION | [19 empty] | PGO | SVP | n/a | 03.23.2023 | n/a | n/a | 03.28.2023 | n/a | n/a | 03.28.2023 | 04.20.2023 | 04.25.2023 |  |  | GF | 15000 | 15000 |  | 14850 | 14850 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030192 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2174 | MEALS | [19 empty] | PGO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 03.28.2023 | n/a | n./a | 03.31.2023 | 04.20.2023 | 04.24.2023 |  |  | GF | 93956 | 93956 |  | 93480 | 93480 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030193 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1277 | MEALS AND SNACKS | [19 empty] | PGO | SVP | n/a | 03.24.2023 | n/a | n/a | 03.28.2023 | n/a | n/a | 03.31.2023 | 04.25.2023 | 04.28.2023 |  |  | GF | 137200 | 137200 |  | 134800 | 134800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23030194 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1467 | CONCRETING OF ROAD, | [19 empty] | PEO | PB | 04.04.2023 | 05.08.2023 | 05.16.2023 | 05.30.2023 | 05.30.2023 | 05.30.2023 | [6 empty] | GF | 9660453.88 |  | 9660453.88 | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR POST QUA
CW23-019 | BRGY. NABOC, MOKAYO | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2007 | CONSTRUCTION OF ONE (1) STOREY | [19 empty] | PEO | PB | 04.04.2023 | 04.21.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 05.18.2023 | 06.02.2023 | 06.09.2023 | 06.14.2023 |  |  | GF | 3789923.2 |  | 3789923.2 | 3739823.02 |  | 3739823.02 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
CW23-013 | TWO (2) CLASSROOMS SCHOOL BLDG. W/ | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| TOILET ATTACHED AT KILAGDING , LAAK | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1997 | CONSTRUCTION OF MULTIPURPOSE BLDG. | [19 empty] | PEO | PB | 04.04.2023 | 04.21.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 06.15.2023 | 06.27.2023 |  |  |  |  | GF | 4817791.76 |  | 4817791.76 | 4786961.94 |  | 4786961.94 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR CONTRACT SIGNING
CW23-015 | TANDAWAN INTEGRATED SCHOOL, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| NEW BATAAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1927 | UPGRADING OF HOSPITAL | [19 empty] | PEO | PB | 04.04.2023 | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 3321542.64 |  | 3321542.64 |  |  |  | Mr. Allan Rey N. Esmael | 05.30.2023 | n/a | 06.14.2023 | n/a | n/a |  | FOR POST-QUA
CW23-028 | FACILITIES AT DDOPH-MONTEVISTA | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1835 | JOB ORDER (REPAIR OF HEAVY | [19 empty] | PEO- | SVP | 04.04.2023 | [11 empty] | GF | 10000 | 10000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| EQUIPMENT | [19 empty] | Motorpool | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator | [6 empty] | FOR CONSOLIDATION
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1834 | JOB ORDER (REPAIR OF | [19 empty] | PEO- | SVP | 04.04.2023 | [11 empty] | GF | 10000 | 10000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| HEAVY EQUIPMENT) | [19 empty] | Motorpool | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator | [6 empty] | FOR CONSOLIDATION
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0412 | ACETYLENE, NITROGEN AND OXYGEN | [19 empty] | PGSO | DC | 04.04.2023 | [11 empty] | GF | 27592 | 27592 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| TANK (REFILL) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1675 | HIGHBAY LED LIGHTS, 200 | [19 empty] | PGSO | SVP | 04.04.2023 | 04.13.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 06.01.2023 | 06.05.2023 | 06.05.2023 | GF | 138000 | 138000 |  | 135900 | 135900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.06.2023 | n/a | n/a
23050427 | WATTS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2162 | CARBURATOR AND COIL IGNITION | [19 empty] | PGSO | SA | 04.04.2023 | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.11.2023 |  |  | GF | 14100 | 14100 |  | 14100 | 14100 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.08.2023 | n/a | n/a
23040237 | FOR GRASS CUTTER | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2160 | SPARE PARTS | [19 empty] | PGSO | SA | 04.04.2023 | 04.13.2023 | n/a | n/a | 04.18.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 20494 | 20494 |  | 20494 | 20494 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.08.2024 | n/a | n/a
23040239 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2159 | SPARE PARTS | [19 empty] | PGSO | SA | 04.04.2023 | 04.13.2023 | n/a | n/a | 04.18.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 7650 | 7650 |  | 7650 | 7650 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.08.2025 | n/a | n/a
23040239 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2129 | SPARE PARTS | [19 empty] | PGSO | SA | 04.04.2023 | 04.13.2023 | n/a | n/a | 04.18.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.11.2023 |  |  | GF | 148830 | 148830 |  | 148830 | 148830 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.08.2026 | n/a | n/a
23040240 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2130 | CATBURETOR ASSY | [19 empty] | PGSO | SA | 04.04.2023 | 04.13.2023 | n/a | n/a | 04.18.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 7890 | 7890 |  | 7890 | 7890 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.08.2027 | n/a | n/a
23040241 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1920 | SPARE PARTS | [19 empty] | PGSO | SA | 04.04.2023 | 04.13.2023 | n/a | n/a | 04.18.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 97550 | 97550 |  | 97550 | 97550 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.08.2028 | n/a | n/a
23040242 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2062 | SPARE PARTS | [19 empty] | PGSO | SA | 04.04.2023 | 04.13.2023 | n/a | n/a | 04.18.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.11.2023 |  |  | GF | 34430 | 34430 |  | 34430 | 34430 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.08.2029 | n/a | n/a
23040243 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0226 | MEALS AND SNACKS WITH | [19 empty] | PHO | SVP | 04.04.2023 | 04.13.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.26.2023 | 05.30.2023 |  |  | GF | 267150 | 267150 |  | 266879 | 266879 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.06.2023 | n/a | n/a
23050439 | ACCOMMODATION | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0388 | OFFICE SUPPLIES | [19 empty] | PGO | SB | 04.04.2023 | 05.05.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.06.2023 |  |  |  |  | GF | 198322 | 198322 |  | 195986 | 195986 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23050563 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0490 | OFFICE SUPPLIES | [19 empty] | PPDO | SB | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | 05.11.2023 | n/a | 05.19.2023 | 05.29.2023 | 05.30.2023 | 07.04.2023 | 07.04.2023 | GF | 336885 | 336885 |  | 332145 | 332145 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050377 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0469 | OFFICE SUPPLIES | [19 empty] | PHO | SB | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | 05.11.2023 | n/a | 05.11.2023 | 05.30.2023 | 06.02.2023 | 06.13.2023 | 06.13.2023 | GF | 8937 | 8937 |  | 8901 | 8901 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050376 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0448 | OFFICE SUPPLIES | [19 empty] | PHO | SB | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | 05.11.2023 | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 20468 | 20468 |  | 18398 | 18398 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050375 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0133 | OFFICE SUPPLIES | [19 empty] | PHO | SB | 04.04.2023 | 04.13.2023 | n/a | n/a | 05.11.2023 | 05.11.2023 | n/a | 05.19.2023 | 06.23.2023 | 06.26.2023 |  |  | GF | 225112.5 | 225112.5 |  | 218200 | 218200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050374 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2204 | BATTERY | [19 empty] | PDRRMO | SVP | 04.04.2023 | 04.13.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 06.02.2023 | 06.19.2023 | 06.19.2023 | GF | 10425 | 10425 |  | 10300 | 10300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050467 | (LK 1808605-GENSET) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2190 | SIGNAL LIGHT FLASHER | [19 empty] | PDRRMO | SA | 04.04.2023 | 04.13.2023 | n/a | n/a | 04.18.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.11.2023 |  |  | GF | 960 | 960 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040244 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0269 | MEALS AND SNACKS WITH VENUE | [19 empty] | PGO | SVP | 04.04.2023 | 04.13.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.23.2023 | 05.30.2023 | 06.02.2023 |  |  | GF | 208480 | 208480 |  | 198900 | 198900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050468 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0386 | CONSTRUCTION MATERIAL | [19 empty] | PEEMO | SVP | 04.04.2023 | [11 empty] | GF | 230510 | 230510 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0360 | MEALS AND SNACKS | [19 empty] | PSWDO | PB | 04.04.2023 | 05.22.2023 | n/a | 06.13.2023 | 06.13.2023 | 06.13.2023 | 06.15.2023 | 06.20.2023 |  |  |  |  | GF | 2136959 | 2136959 |  | 2089350 | 2089350 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 06.08.2023 | n/a | n/a |  | FOR PO APPROVAL
23060694 | WIHTOUT VENUE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2058 | WIRE, EXTENSION WITH HANDLE 15m | [19 empty] | PGO | SVP | 04.04.2023 | 04.13.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.24.2023 | 05.29.2023 | 06.29.2023 | 06.29.2023 | GF | 6600 | 6600 |  | 6590 | 6590 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050397 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1530 | OIL AND LUBRICANTS | [19 empty] | VGO | SVP | 04.04.2023 | 04.13.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.22.2023 | 06.23.2023 |  |  | GF | 37740 | 37740 |  | 36900 | 36900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050573 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0308 | MEDICAL OXYGEN | [19 empty] | PAGRO | DC | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.10.2023 | 04.27.2023 |  |  |  | GF | 1640 | 1640 |  | 1200 | 1200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040195 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0196 | OXYGEN GAS REFILL | [19 empty] | PDRRMO | DC | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.10.2023 | 05.09.2023 | 05.10.2023 | 06.22.2023 | 06.22.2023 | GF | 153780 | 153780 |  | 39600 | 39600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040196 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0672 | ACCOUNTABLE FORMS (#51, #55, #56, #57) | [19 empty] | PTO | NP | n/a | 02.06.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.04.2023 | 04.20.2023 |  |  |  | GF | 1011000 | 1011000 |  | 976000 | 976000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040197 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1922 | OFFICE SUPPLIES | [19 empty] | PBO | SB | n/a | 05.17.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.10.2023 | 04.20.2023 | 04.25.2023 |  |  | GF | 6984 | 6984 |  | 6565 | 6565 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040198 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0038 | OFFICE SUPPLIES | [19 empty] | PAGRO | SB | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.27.2023 | 05.03.2023 | 05.17.2023 | 05.17.2023 | GF | 128111 | 128111 |  | 127318 | 127318 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040199 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0285 | OFFICE SUPPLIES | [19 empty] | PVO | SB | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.19.2023 | 04.27.2023 | 05.11.2023 | 05.11.2023 | GF | 137097 | 137097 |  | 136588 | 136588 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040200 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0288 | OFFICE SUPPLIES AND DEVICES | [19 empty] | PICTO | SB | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.19.2023 | 04.27.2023 |  |  | GF | 54769 | 54769 |  | 54517 | 54517 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040201 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0326 | OFFICE SUPPLIES | [19 empty] | PLO | SB | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.25.2023 | 04.26.2023 | 05.04.2023 | 05.04.2023 | GF | 67002 | 67002 |  | 66538 | 66538 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040202 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0189 | OFFICE SUPPLIES | [19 empty] | PDRRMO | SB | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.27.2023 | 05.03.2023 | 05.16.2023 | 05.16.2023 | GF | 143517 | 143517 |  | 142607 | 142607 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040203 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1737 | AVR AND UPS | [19 empty] | PLO | SVP | n/a | n/a | n/a | n/a | 04.04.2023 | n/a | n/a | 04.10.2023 | 04.19.2023 | 04.27.2023 |  |  | GF | 4199 | 4199 |  | 4195 | 4195 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040204 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0242 | EMERGENCY LIGHT AND EXTENSION | [19 empty] | PENRO | SVP | n/a | 03.17.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.10.2023 | 04.20.2023 | 04.25.2023 | 05.09.2023 | 05.09.2023 | GF | 21840 | 21840 |  | 21800 | 21800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040205 | WIRE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0224 | CLEANING AND STORAGE SUPPLIES | [19 empty] | PGO | SVP | n/a | n/a | n/a | n/a | 04.04.2023 | n/a | n/a | 04.10.2023 | 04.20.2023 | 04.25.2023 | 05.29.2023 | 05.29.2023 | GF | 17240 | 17240 |  | 17221 | 17221 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040206 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1398 | STICKER, ORDINARY AND REFLECTORIZE- | [19 empty] | PDRRMO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.20.2023 | 04.20.2023 |  |  | GF | 121000 | 121000 |  | 119000 | 119000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040207 | AS PER SAMPLE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0911 | RICE (WELL MILLED) 50 KG/SACK | [19 empty] | PGO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.13.2023 | 04.13.2023 |  |  | GF | 665700 | 665700 |  | 662530 | 662530 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040208 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1780 | JANITORIAL SUPPLIES | [19 empty] | PPDO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.10.2023 | 04.19.2023 | 04.27.2023 | 05.02.2023 | 05.02.2023 | GF | 13635 | 13635 |  | 13581 | 13581 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040209 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1507 | JANITORIAL SUPPLIES | [19 empty] | PVGO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.10.2023 | 04.20.2023 | 04.25.2023 | 05.19.2023 | 05.19.2023 | GF | 39506 | 39506 |  | 39196 | 39196 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040210 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1638 | SPORTS SUPPLIES AND GEARS | [19 empty] | PGO-SEF | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.27.2023 | 05.02.2023 | 05.03.2023 | 05.03.2023 | GF | 399294 | 399294 |  | 396659 | 396659 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23040211 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1566 | ELECTRICAL SUPPLIES | [19 empty] | PEO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.27.2023 | 05.03.2023 | 06.22.2023 | 06.22.2023 | GF | 165918 | 165918 |  | 164997 | 164997 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040212 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1438 | CEMENT AND LUMBER | [19 empty] | PEO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.27.2023 | 05.03.2023 | 05.25.2023 | 05.25.2023 | GF | 179310.6 | 179310.6 |  | 178843.43 | 178843.43 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040213 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0486 | JANITORIAL SUPPLIES | [19 empty] | PEO-GA | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.10.2023 | 04.27.2023 | 05.03.2023 | 05.08.2023 | 05.08.2023 | GF | 28652 | 28652 |  | 28517 | 28517 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040214 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1554 | CONSTRUCTION SUPPLIES | [19 empty] | PEO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.27.2023 | 05.03.2023 | 05.15.2023 | 05.15.2023 | GF | 111615 | 111615 |  | 111457.5 | 111457.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040215 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0464 | KITCHEN SUPPLIES | [19 empty] | PDRRMO | NP | n/a | 04.11.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.11.2023 | 04.18.2023 | 04.27.2023 |  |  | GF | 153422.28 | 153422.28 |  | 153351 | 153351 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040222 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2408 | HOUSEKEEPING | [19 empty] | PDRRMO | NP | n/a | n/a | n/a | n/a | 04.04.2023 | n/a | n/a | 04.11.2023 | 04.18.2023 | 04.27.2023 |  |  | GF | 29218 | 29218 |  | 29170 | 29170 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040223 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0467 | FOOD SUPPLIES-WET MARKET | [19 empty] | PDRRMO | NP | n/a | 04.11.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.11.2023 | 04.13.2023 | 04.14.2023 | 05.31.2023 | 05.31.2023 | GF | 232190 | 232190 |  | 232190 | 232190 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040224 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2411 | FOOD SUPPLIES-DRY GOODS | [19 empty] | PDRRMO | NP | n/a | 04.11.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.11.2023 | 04.18.2023 | 04.27.2023 |  |  | GF | 2160 | 2160 |  | 2148 | 2148 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040225 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2467 | GEMELINA LUMBER OR EQUIVALENT | [19 empty] | PEO | SVP | n/a | 04.11.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.04.2023 | 04.27.2023 |  |  |  | GF | 2160 | 2160 |  | 2148 | 2148 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040300 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1548 | GEMELINA LUMBER OR EQUIVALENT | [19 empty] | PEO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.04.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 2160 | 2160 |  | 2148 | 2148 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040216 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0128 | AIR, FUEL, AND OIL FILTER | [19 empty] | PDRRMO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.25.2023 | 04.26.2023 | 04.27.2023 | 04.27.2023 | GF | 57930 | 57930 |  | 56980 | 56980 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040217 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0308 | CONSTRUCTION SUPPLIES | [19 empty] | VGO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.19.2023 | 04.27.2023 | 06.06.2023 | 06.06.2023 | GF | 289037 | 289037 |  | 287052 | 287052 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040218 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0050 | CONSTRUCTION SUPPLIES | [19 empty] | PAGRO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.19.2023 | 04.20.2023 | 05.29.2023 | 05.29.2023 | GF | 72763 | 72763 |  | 72453 | 72453 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040219 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0265 | CONSTRUCTION SUPPLIES | [19 empty] | PDRRMO | SVP | n/a | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.20.2023 | 04.25.2023 | 06.15.2023 | 06.15.2023 | GF | 163077 | 163077 |  | 162895 | 162895 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040220 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0315 | MEALS, VIP MEALS, AND SNACKS | [19 empty] | PAO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.04.2023 | n/a | n/a | 04.13.2023 | 04.20.2023 | 04.25.2023 | 06.15.2023 | 06.15.2023 | GF | 615308 | 615308 |  | 605102 | 605102 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040221 | (HEAVY AND LIGHT) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2249 | SOIL INVESTIGATION TEST | [19 empty] | PEO | PB | 04.18.2023 | 05.15.2023 |  | 05.30.2023 | 05.30.2023 | [7 empty] | GF | 260000 | 260000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | CHANGE MODE TO
| FOR DDOPH-MONTEVISTA | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator | [6 empty] | NEGOTIATED PROCUREMENT
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0044 | PORTLAND CEMENT | [19 empty] | PEO | SVP | 04.18.2023 | [11 empty] | GF | 321126 | 321126 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2347 | GEMELINA LUMBER OR EQUIVALENT | [19 empty] | PEO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.31.2023 | 06.05.2023 | 06.30.2023 | 06.30.2023 | GF | 88113.27 | 88113.27 |  | 85717.93 | 85717.93 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050443 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2291 | GEMELINA LUMBER OR | [19 empty] | PEO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 56943.57 | 56943.57 |  | 54894.57 | 54894.57 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050444 | EQUIVALENT | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0089 | OFFICE SUPPLIES | [19 empty] | PEO | PB | 04.18.2023 | 05.03.2023 | n/a | 05.11.2023 | 05.11.2023 | 05.11.2023 | 05.17.2023 | 06.06.2023 | 06.26.2023 | 06.27.2023 |  |  | GF | 304795 | 304795 |  | 250290.25 | 250290.25 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.08.2023 | n/a | n/a
23060622 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2122 | OIL AND LUBRICANTS | [19 empty] | PEO- | PB | 04.18.2023 | 05.08.2023 | 05.16.2023 | 05.30.2023 | 05.30.2023 | 05.30.2023 | 06.09.2023 | 06.21.2023 | 06.26.2023 | 06.27.2023 |  |  | GF | 3116990 | 3116990 |  | 2369900 | 2369900 |  | Mr. Allan Rey N. Esmael | 05.11.2023 | n/a | 05.25.2023 | n/a | n/a |  | FOR DELIVERY
23060659 | [20 empty] | Motorpool | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2333 | ACETYLENE REFILL, OXYGEN, | [19 empty] | PEO- | DC | 04.18.2023 | n/a | n/a | n/a | 05.02.2023 | 05.02.2023 | n/a | 05.02.2023 |  |  |  |  | GF | 45075 | 45075 |  | 45075 | 45075 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050317 | INDUSTRIAL GAS REFILL | [19 empty] | Motorpool | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2247 | SPAREPARTS (REPAIR | [19 empty] | PEO | SA | 04.18.2023 | [11 empty] | GF | 200000 | 200000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| AND MAINTAINANCE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0417 | MEALS AND SNACKS | [19 empty] | PSWDO | PB | 04.18.2023 | 05.03.2023 | n/a | 05.11.2023 | 05.11.2023 | 05.11.2023 | 05.17.2023 | 06.07.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 876086 | 876086 |  | 756236 | 756236 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.08.2023 | n/a | n/a
23060617 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0393 | OFFICE SUPPLIES | [19 empty] | PGO | SB | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.30.2023 | 06.02.2023 | 06.13.2023 | 06.13.2023 | GF | 6649 | 6649 |  | 6633 | 6633 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050379 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1129 | FAN, INDUSTRIAL | [19 empty] | PGO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.24.2023 | 05.29.2023 | 06.30.2023 | 06.30.2023 | GF | 19200 | 19200 |  | 19192 | 19192 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050413 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0429 | OFFICE SUPPLIES | [19 empty] | PGO | SB | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.31.2023 | 06.01.2023 | 06.15.2023 | 06.15.2023 | GF | 308479.4 | 308479.4 |  | 300885 | 300885 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050380 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0426 | KITCHENWARES AND UTENSILS | [19 empty] | PGO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.26.2023 | 05.30.2023 | 06.23.2023 | 06.23.2023 | GF | 40236.5 | 40236.5 |  | 39808 | 39808 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050422 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2085 | TARPAULIN-AS PER DESIGN | [19 empty] | PGO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.24.2023 | 05.30.2023 |  |  | GF | 28000 | 28000 |  | 26000 | 26000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050445 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0425 | CONSTRUCTION MATERIALS | [19 empty] | PGO | PB | 04.18.2023 | 05.03.2023 | n/a | 05.16.2023 | 05.16.2023 | 05.16.2023 | 05.17.2023 | 05.30.2023 | 06.15.2023 | 06.21.2023 | 06.30.2023 | 06.30.2023 | GF | 634552 | 634552 |  | 567800 | 567800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060633 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0450 | MEALS AND SNACKS WITH | [19 empty] | PGO | PB | 04.18.2023 | [11 empty] | GF | 1119300 | 1119300 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| ACCOMODATION | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0430 | JANITORIAL SUPPLIES | [19 empty] | PGO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.31.2023 | 06.01.2023 | 06.09.2023 | 06.09.2023 | GF | 162978 | 162978 |  | 160016 | 160016 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050423 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0428 | FURNITURE AND FIXTURES | [19 empty] | PGO | PB | 04.18.2023 | 05.03.2023 | n/a | 05.11.2023 | 05.11.2023 | 05.11.2023 | 05.17.2023 | 06.09.2023 | 06.15.2023 | 06.19.2023 | 06.22.2023 | 06.22.2023 | GF | 468787 | 468787 |  | 467784 | 467784 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060625 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1843 | MEALS AND SNACKS | [19 empty] | PBO | SVP | 04.18.2023 | 04.24.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.12.2023 | 05.17.2023 | 06.16.2023 | 06.16.2023 | GF | 20550 | 20550 |  | 20175 | 20175 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23-05-0353 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2497 | JOB ORDER (REPAIR OF MOTOR VEHICLE) | [19 empty] | SPO | SA | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | 05.11.2023 | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 05.31.2023 | 05.31.2023 | GF | 4500 | 4500 |  | 4500 | 4500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050367 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2448 | OFFICE SUPPLIES | [19 empty] | SPO | SB | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 06.05.2023 | 06.20.2023 | 06.20.2023 | GF | 30264 | 30264 |  | 29700 | 29700 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050378 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1414 | FUSER UNIT 220V | [19 empty] | SPO | DC | 04.18.2023 | [11 empty] | GF | 19000 | 19000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| (FUJI DCS2320) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0471 | SPAREPARTS | [19 empty] | SPO | PB | 04.18.2023 | 05.03.2023 | n/a | 05.11.2023 | 05.11.2023 | 05.11.2023 | 05.17.2023 | 06.06.2023 |  |  |  |  | GF | 346055 | 346055 |  | 328925 | 328925 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060623 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0369 | OFFICE SUPPLIES | [19 empty] | PAGRO | SB | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.29.2023 | 06.01.2023 | 06.05.2023 |  |  | GF | 84700 | 84700 |  | 83909 | 83909 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23050527 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0379 | AGRICULTURAL SUPPLIES | [19 empty] | PAGRO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.30.2023 | 06.02.2023 | 06.13.2023 | 06.13.2023 | GF | 42076 | 42076 |  | 42060 | 42060 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23050424 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0376 | OFFICE SUPPLIES | [19 empty] | PAGRO | SB | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.09.2023 | 06.09.2023 | GF | 57265 | 57265 |  | 55082 | 55082 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23050381 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1337 | UPS W/BUILT-IN AVR, 600VA | [19 empty] | PVO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 17274 | 17274 |  | 17220 | 17220 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23050414 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0343 | OFFICE SUPPLIES | [19 empty] | PAO-Admin | SB | 04.18.2023 | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 2023-06-19 | 2023-06-21 |  |  | GF | 218316 | 218316 |  | 189743 | 189743 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23050566 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2248 | UTILITY/PLASTIC BOX | [19 empty] | PACCO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.17.2023 | 05.29.2023 | 05.30.2023 | 06.09.2023 | 06.09.2023 | GF | 137250 | 137250 |  | 136250 | 136250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050415 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1689 | BRAKE PAD, FRONT & REAR FOR | [19 empty] | PGSO | SA | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.16.2023 | 05.19.2023 | 05.23.2023 | 05.23.2023 | GF | 33800 | 33800 |  | 33800 | 33800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050321 | TOYOTA FORTUNER 2019 | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0446 | MEALS AND SNACKS | [19 empty] | PHRMDO | PB | 04.18.2023 | 05.03.2023 | n/a | 05.11.2023 | 05.11.2023 | 05.11.2023 | 05.17.2023 | 06.06.2023 |  |  |  |  | GF | 460982 | 460982 |  | 456252 | 456252 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.08.2023 | n/a | n/a |  | FOR PO APPROVAL
23060618 | WITHOUT VENUE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0776 | STAMPS, MAILING | [19 empty] | PASSO | NP | 04.18.2023 | 05.22.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 |  |  |  | GF | 1950 | 1950 |  | 1950 | 1950 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060656 | PER DENOMINATION | [20 empty] | AGENCY-AGENCY | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2354 | TAX MAP BINDER BIG | [19 empty] | PASSO | SB | 04.18.2023 | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 45600 | 45600 |  | 45600 | 45600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050565 | (W/NUTS & BOLTS) MAROON | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0358 | DP BLACK INK, DA 14, MASTER | [19 empty] | PEEMO | DC | 04.18.2023 | [11 empty] | GF | 17880 | 17880 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| ROLL DRA 12 | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2323 | JANITORIAL SUPPLIES | [19 empty] | PTO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.09.2023 | 06.09.2023 | GF | 13471 | 13471 |  | 13025 | 13025 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050416 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2346 | JANITORIAL SUPPLIES | [19 empty] | PHRMDO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.23.2023 | 06.26.2023 |  |  | GF | 18894 | 18894 |  | 18331 | 18331 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23050472 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
MDLS 23-001 | MEDICAL AND DENTAL LABORATORIES | [19 empty] | PEEMO | PB | n/a | 03.06.2023 | 03.21.2023 | 03.28.2023 | 03.28.2023 | 03.28.2023 | 05.04.2023 | 05.11.2023 |  |  |  |  | GF | 4299812.8 | 4299812.8 |  | 1630742 | 1630742 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | CONSIGNMENT
| SUPPLIES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
DM 23-001 | DRUGS AND MEDICINES (CONSIGNMENT) | [19 empty] | PEEMO | PB | n/a | 03.06.2023 | 03.21.2023 | 03.28.2023 | 03.28.2023 | 03.28.2023 | 05.04.2023 | 05.11.2023 |  |  |  |  | GF | 49210120 | 49210120 |  | 15984538.6 | 1630742 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | CONSIGNMENT
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2152 | PHOTOCOPY OF DOCUMENTS | [19 empty] | PAO-Tourism | SA | 04.18.2023 | [11 empty] | GF | 1000 | 1000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2388 | AIR HOUSEWITH FITTINGS | [19 empty] | PDRRMO | SA | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.12.2023 | 05.15.2023 |  |  | GF | 12000 | 12000 |  | 12000 | 12000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050322 | AND UNIVERSAL CROSS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| JOINT (ISUZU SADDAM) | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2203 | SPARE PARTS | [19 empty] | PDRRMO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 151695 | 151695 |  | 151580 | 151580 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050417 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0363 | OFFICE SUPPLIES | [19 empty] | PEEMO | PB | 04.18.2023 | 05.03.2023 | n/a | 05.11.2023 | 05.11.2023 | 05.11.2023 | 05.17.2023 | 06.06.2023 |  |  |  |  | GF | 697287 | 697287 |  | 579600 | 579600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.08.2023 | n/a | n/a |  | FOR PO APPROVAL
23060621 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0377 | JANITORIAL SUPPLIES | [19 empty] | PEEMO | PB | 04.18.2023 | 05.03.2023 | n/a | 05.11.2023 | 05.11.2023 | 05.11.2023 | 05.17.2023 | 06.06.2023 | 06.23.2023 | 06.27.2023 |  |  | GF | 831425 | 831425 |  | 743046 | 743046 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.08.2023 | n/a | n/a
23060624 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2254 | LABORATORY SUPPLIES | [19 empty] | PHO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.07.2023 | 06.19.2023 | 06.21.2023 |  |  | GF | 135000 | 135000 |  | 134240 | 134240 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050578 | [35 empty] | 0 |  |  | - |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2250 | SEPTIC TANK CLEANING | [19 empty] | PHO | SVP | 04.18.2023 | [11 empty] | GF | 9000 | 9000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| AND SIPHONING | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0432 | PLAQUE AND TOKEN | [19 empty] | PGO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.26.2023 | 05.30.2023 |  |  | GF | 127350 | 127350 |  | 125525 | 125525 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050442 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2586 | MEDALS AND PLAQUE | [19 empty] | PSWDO | SVP | n/a | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 57564 | 57564 |  | 57060 | 57060 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050446 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2591 | VARIOUS WRENCHES | [19 empty] | PDRRMO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 4145 | 4145 |  | 3990 | 3990 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050441 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2505 | PLAQUE-AS PER DESIGN | [19 empty] | PDRRMO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 20000 | 20000 |  | 19900 | 19900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050440 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2068 | POLO SHIRT-AS PER DESIGN | [19 empty] | PAGRO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 20000 | 20000 |  | 19800 | 19800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050426 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0777 | PLAQUE-AS PER DESIGN | [19 empty] | PASSO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 18150 | 18150 |  | 17600 | 17600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050438 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2351 | BANDAGE GAUZE | [19 empty] | PDRRMO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 500 | 500 |  | 450 | 450 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR COMPLETION OF DELIVERY
23050437 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2273 | CONDOM | [19 empty] | PHO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 51000 | 51000 |  | 48960 | 48960 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050436 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1934 | FEEDS | [19 empty] | PAGRO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 75710 | 75710 |  | 75710 | 75710 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050435 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1570 | CONSTRUCTION MATERIALS | [19 empty] | PEO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.20.2023 | 06.20.2023 | GF | 15094 | 15094 |  | 14846 | 14846 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050434 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1118 | CONSTRUCTION MATERIALS | [19 empty] | PEO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.29.2023 | 06.29.2023 | GF | 30890.15 | 30890.15 |  | 30727.82 | 30727.82 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050433 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1659 | CONSTRUCTION MATERIALS | [19 empty] | PEO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.30.2023 | 05.31.2023 | 06.29.2023 | 06.29.2023 | GF | 49456 | 49456 |  | 49327 | 49327 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050432 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1656 | CONSTRUCTION MATERIALS | [19 empty] | PEO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.29.2023 | 06.29.2023 | GF | 49456 | 49456 |  | 49456 | 49456 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050431 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1550 | CONSTRUCTION MATERIALS | [19 empty] | PEO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.29.2023 | 06.29.2023 | GF | 49456 | 49456 |  | 49327 | 49327 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050430 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1556 | CONSTRUCTION MATERIALS | [19 empty] | PEO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.29.2023 | 05.30.2023 | 06.29.2023 | 06.29.2023 | GF | 161685 | 161685 |  | 161253 | 161253 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050429 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1249 | MEDALS AND TROPHIES | [19 empty] | PGO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.24.2023 | 05.30.2023 |  |  | GF | 24800 | 24800 |  | 24710 | 24710 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050428 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2034 | MEDALS (SPECS) | [19 empty] | PAGRO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.20.2023 | 06.20.2023 | GF | 3600 | 3600 |  | 3555 | 3555 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050425 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2147 | BEADS MAKING KIT | [19 empty] | PGO | SVP | n/a | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.24.2023 | 05.26.2023 | 06.05.2023 | 06.05.2023 | GF | 216100 | 216100 |  | 215912 | 215912 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050421 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2148 | BEAUTY AND HYGIENE SUPPLIES | [19 empty] | PGO | SVP | n/a | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.24.2023 | 05.26.2023 | 06.30.2023 | 06.30.2023 | GF | 216100 | 216100 |  | 215912 | 215912 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050420 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2150 | SNACKS | [19 empty] | PGO | SVP | n/a | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 06.13.2023 | 06.14.2023 |  |  | GF | 14000 | 14000 |  | 13720 | 13720 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050419 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2265 | FOOD SUPPLIES-DRY GOODS | [19 empty] | PENRO | SVP | n/a | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.24.2023 | 05.29.2023 | 06.09.2023 | 06.09.2023 | GF | 19556 | 19556 |  | 19348 | 19348 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050418 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0497 | LABORATORY SUPPLIES | [19 empty] | PENRO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.30.2023 | 05.31.2023 |  |  | GF | 28630 | 28630 |  | 28622 | 28622 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050411 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0495 | LABORATORY SUPPLIES | [19 empty] | PENRO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 28630 | 28630 |  | 28622 | 28622 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR DELIVERY COMPLETION
23050411 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0498 | JANITORIAL SUPPLIES | [19 empty] | PENRO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.30.2023 | 05.31.2023 | 06.09.2023 | 06.09.2023 | GF | 23042 | 23042 |  | 22770 | 22770 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050410 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0463 | TARPAULIN-AS PER DESIGN | [19 empty] | PDRRMO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 |  |  |  |  | GF | 20552 | 20552 |  | 19084 | 19084 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23050409 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0466 | JANITORIAL SUPPLIES | [19 empty] | PHO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 06.01.2023 | 06.02.2023 | 06.13.2023 | 06.13.2023 | GF | 2230 | 2230 |  | 2222 | 2222 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050408 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0045 | CONSTRUCTION SUPPLIES | [19 empty] | PEO-GA | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.17.2023 | 05.30.2023 | 05.31.2023 | 06.15.2023 | 06.15.2023 | GF | 74846 | 74846 |  | 74595 | 74595 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050407 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0378 | MEALS AND SNACKS, MEALS WITH VENUE | [19 empty] | PDRRMO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.15.2023 | 05.30.2023 | 06.02.2023 |  |  | GF | 288063 | 288063 |  | 282338 | 282338 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050406 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2604 | MICROPHONE LAPEL FOR CAMCORDER | [19 empty] | PHRMDO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.13.2023 | 06.13.2023 | GF | 1100 | 1100 |  | 1090 | 1090 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050405 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0497 | TARPAULIN-AS PER DESIGN | [19 empty] | PENRO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.30.2023 | 05.31.2023 |  |  | GF | 27580 | 27580 |  | 25610 | 25610 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050412 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2495 | SNACK PRODUCTS | [19 empty] | VGO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 06.14.2023 | 06.16.2023 | 06.22.2023 | 06.22.2023 | GF | 14820 | 14820 |  | 14760 | 14760 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050404 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2368 | RUBBING ALCOHOL | [19 empty] | PDRRMO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.13.2023 | 06.13.2023 | GF | 3129 | 3129 |  | 3087 | 3087 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050403 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2399 | LEAFLETS-AS PER SAMPLE | [19 empty] | PTO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 99400 | 99400 |  | 74900 | 74900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR COMPLETION OF DELIVERY
23050402 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1065 | JANITORIAL SUPPLIES | [19 empty] | PGO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 2780 | 2780 |  | 2740 | 2740 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050401 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1063 | FLASH DRIVE, 16 GB | [19 empty] | PGO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 |  |  |  |  | GF | 6160 | 6160 |  | 6125 | 6125 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23050400 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1048 | TARPAULIN-AS PER DESIGN | [19 empty] | PDRRMO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.13.2023 | 06.13.2023 | GF | 3000 | 3000 |  | 2990 | 2990 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050399 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1967 | TARPAULIN-AS PER DESIGN | [19 empty] | PDRRMO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 4200 | 4200 |  | 3900 | 3900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050398 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2397 | COMPUTER DEVICES | [19 empty] | PTO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.02.2023 | 06.02.2023 | GF | 13124 | 13124 |  | 13010 | 13010 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050396 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0364 | AGRICULTURAL SUPPLIES | [19 empty] | PAGRO | SVP | n/a | 03.28.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.07.2023 | 06.07.2023 | GF | 53016 | 53016 |  | 52892 | 52892 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050394 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1296 | PRINTER WITH SCANNER (3 IN 1) | [19 empty] | PENRO | SVP | n/a | 03.28.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.02.2023 | 06.02.2023 | GF | 26840 | 26840 |  | 26800 | 26800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050393 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1715 | COLORED PRINTER | [19 empty] | PASSO | SVP | n/a | 03.28.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.02.2023 | 06.02.2023 | GF | 12320 | 12320 |  | 12300 | 12300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050392 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0220 | MEALS AND S NACKS, MEALSWITH VENUE | [19 empty] | PGO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.15.2023 | 05.16.2023 | 05.19.2023 |  |  | GF | 423118 | 423118 |  | 413340 | 413340 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050391 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0462 | MEALS AND S NACKS | [19 empty] | PDRRMO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.17.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 355715 | 355715 |  | 352740 | 352740 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050390 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0283 | MEALS AND SNACKS, MEALS WITH | [19 empty] | PVO | SVP | 03.21.2023 | 04.11.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.17.2023 | 05.30.2023 | 06.05.2023 |  |  | GF | 200721 | 200721 |  | 199692.5 | 199692.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050389 | VENUE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0287 | ICT SUPPLIES | [19 empty] | PICTO | SVP | n/a | 03.30.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.19.2023 | 05.29.2023 | 06.01.2023 |  |  | GF | 310860 | 310860 |  | 310040 | 310040 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050388 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1011 | ELECTRIC POWER SPRAYER | [19 empty] | PDRRMO | SVP | 03.24.2023 | 03.28.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.07.2023 | 06.07.2023 | GF | 13000 | 13000 |  | 12890 | 12890 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050387 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1119 | CONSTRUCTION SUPPLIES | [19 empty] | PEO | SVP | n/a | 03.28.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.17.2023 | 05.29.2023 | 05.30.2023 | 06.15.2023 | 06.15.2023 | GF | 138837 | 138837 |  | 137760 | 137760 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050386 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0738 | SUBMERSIBLE UV LAMP 20W | [19 empty] | PGSO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.30.2023 | 06.30.2023 | GF | 34000 | 34000 |  | 33500 | 33500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050385 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0351 | OFFICE EQUIPMENT AND SUPPLIES | [19 empty] | PDRRMO | SVP | n/a | 03.28.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.30.2023 | 05.31.2023 | 06.09.2023 | 06.09.2023 | GF | 29750 | 29750 |  | 29725 | 29725 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050384 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0414 | HELMET, FULL FACED | [19 empty] | PVO | SVP | n/a | 03.28.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.30.2023 | 06.02.2023 | 06.16.2023 | 06.16.2023 | GF | 22000 | 22000 |  | 21960 | 21960 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050383 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0457 | OFFICE SUPPLIES | [19 empty] | PHO | SB | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.30.2023 | 06.02.2023 | 06.13.2023 | 06.13.2023 | GF | 15516 | 15516 |  | 15462 | 15462 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050382 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2288 | PHOTOCOPY OF DOCUMENT | [19 empty] | PHO | SA | 04.18.2023 | [11 empty] | GF | 7000 | 7000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0381 | CCTV AND TELEVISION | [19 empty] | PGO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.26.2023 | 05.30.2023 |  |  | GF | 68435 | 68435 |  | 68100 | 68100 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050348 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2394 | LIQUID NITROGEN | [19 empty] | PVO | DC | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 |  |  |  | GF | 19200 | 19200 |  | 19200 | 19200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050364 | (REFILL) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0461 | VETERINARY DRUGS AND BIOLOGICS | [19 empty] | PVO | SVP | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.29.2023 | 05.30.2023 |  |  | GF | 139348 | 139348 |  | 137410 | 137410 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR COMPLETION OF DELIVERY
23050447 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0474 | SPARE PARTS | [19 empty] | PGSO | SA | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.15.2023 | 05.17.2023 | 05.19.2023 | 05.19.2023 | GF | 21900 | 21900 |  | 21900 | 21900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050326 | (LIGHT VEHICLE) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2240 | BRAKE PAD | [19 empty] | PGSO | SA | 04.18.2023 | n/a | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.16.2023 | 05.18.2023 | 05.18.2023 | 05.18.2023 | GF | 5600 | 5600 |  | 5600 | 5600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050323 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2238 | BRAKE PAD | [19 empty] | PGSO | SA | 04.18.2023 | n/a | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.15.2023 | 05.18.2023 | 05.18.2023 | 05.18.2023 | GF | 5600 | 5600 |  | 5600 | 5600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050324 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0440 | DRIVE BELT (MITSUBISHI XPANDER) | [19 empty] | PGSO | SA | 04.18.2023 | n/a | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.15.2023 | 05.17.2023 | 05.17.2023 | 05.17.2023 | GF | 16700 | 16700 |  | 16700 | 16700 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050327 | AND JOB ORDER-WHEEL ALIGNMENT | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0475 | SPARE PARTS | [19 empty] | PGSO | SA | 04.18.2023 | 04.25.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.16.2023 | 05.17.2023 | 05.19.2023 | 05.19.2023 | GF | 88340 | 88340 |  | 88340 | 88340 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050328 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2477 | SPARE PARTS | [19 empty] | PGSO | SA | 04.18.2023 | n/a | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.15.2023 | 05.15.2023 |  |  | GF | 15420 | 15420 |  | 15420 | 15420 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050325 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0356 | MEDICAL OXYGEN REFILL | [19 empty] | PEEMO | DC | 03.24.2023 | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 2453700 | 2453700 |  | 2453700 | 2453700 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040245 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2171 | MONTHLY PREVENTIVE MAINTAINANCE | [19 empty] | PGSO | DC | n/a | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.11.2023 |  |  | GF | 25500 | 25500 |  | 25500 | 25500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040246 | OF 1 UNIT MITSUBISHI ELEVATOR | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0105 | EQUIPMENT PARTS AND SUPPLIES | [19 empty] | PEO- | NP | n/a | 03.23.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.08.2023 | 05.11.2023 | 05.30.2023 | 05.30.2023 | GF | 575153 | 575153 |  | 564992 | 564992 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040247 | [20 empty] | Motorpool | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1809 | INTERCOOLER HOSE FOR MITSUBISHI | [19 empty] | SPO | SA | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 12800 | 12800 |  | 12800 | 12800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040226 | STRADA WITH LABOR | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1695 | SPAREPARTS AND LABOR FOR | [19 empty] | PGSO | SA | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 28340 | 28340 |  | 28340 | 28340 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040227 | MITSUBISHI ADVENTURE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1694 | SPAREPARTS FOR MITSUBISHI | [19 empty] | PGSO | SA | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.11.2023 |  |  | GF | 36300 | 36300 |  | 36300 | 36300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040228 | EXPANDER | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1697 | UPPER SUSPENSION SHAFT KIT | [19 empty] | PGSO | SA | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 12400 | 12400 |  | 12400 | 12400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040229 | FIR MITSUBISHI L300 VAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1725 | BRAKE PAD AND BRAKE SHOE FOR | [19 empty] | PGSO | SA | n/a | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 9960 | 9960 |  | 9960 | 9960 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040230 | MITSUBISHI STRADA | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1726 | SPAREPARTS FOR MITSUBISHI | [19 empty] | PGSO | SA | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.04.2023 | 05.11.2023 | 05.16.2023 | 05.16.2023 | GF | 47191 | 47191 |  | 47191 | 47191 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040231 | STRADA | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1190 | TONER | [19 empty] | PAO | SB | n/a | 04.13.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 | 05.26.2023 | 05.26.2023 | GF | 18310 | 18310 |  | 16926 | 16926 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040248 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0225 | OFFICE SUPPLIES | [19 empty] | PDRRMO | SB | 03.21.2023 | 03.17.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 | 05.16.2023 | 05.16.2023 | GF | 23821 | 23821 |  | 23604 | 23604 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040249 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0134 | MINERAL WATER, (5GAL., 330ML) | [19 empty] | PGO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 139161 | 139161 |  | 135640 | 135640 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040253 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0920 | COMPUTER SET AND PRINTER | [19 empty] | PTO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 120800 | 120800 |  | 120580 | 120580 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040254 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1469 | TF WIRE TWISTED | [19 empty] | PDRRMO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 45000 | 45000 |  | 44955 | 44955 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040255 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0305 | CELLOPHANE | [19 empty] | PSWDO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.11.2023 | 05.18.2023 | 05.26.2023 | 05.26.2023 | GF | 116000 | 116000 |  | 114400 | 114400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040256 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0302 | TARPAULIN-AS PER DESIGN | [19 empty] | PDRRMO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.24.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 74900 | 74900 |  | 73562.5 | 73562.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040257 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0249 | SPAREPARTS FOR REPAIR AND | [19 empty] | PVO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.02.2023 | 05.03.2023 | 05.23.2023 | 05.23.2023 | GF | 17532 | 17532 |  | 17518 | 17518 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040258 | MAINTAINANCE OF FEED MILL AND | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| GRASS CHOPPER | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0193 | GARDEN TOOLS AND SUPPLIES | [19 empty] | PGSO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.08.2023 | 05.10.2023 | 05.29.2023 | 05.29.2023 | GF | 125413 | 125413 |  | 121965 | 121965 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040259 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0273 | JANITORIAL SUPPLIES | [19 empty] | PGO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.11.2023 | 05.18.2023 | 06.26.2023 | 06.26.2023 | GF | 8169 | 8169 |  | 8019 | 8019 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040260 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0241 | CONSTRUCTION SUPPLIES | [19 empty] | PENRO | SVP | n/a | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.08.2023 | 05.10.2023 | 06.13.2023 | 06.13.2023 | GF | 52675 | 52675 |  | 52660 | 52660 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040261 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0046 | ELECTRICAL SUPPLIES | [19 empty] | PEO-GA | SVP | n/a | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.08.2023 | 05.10.2023 | 06.07.2023 | 06.07.2023 | GF | 68179 | 68179 |  | 67604 | 67604 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040262 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0271 | GARDEN TOOLS AND SUPPLIES | [19 empty] | PVO | SVP | n/a | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.02.2023 | 05.03.2023 | 05.16.2023 | 05.16.2023 | GF | 63762 | 63762 |  | 63705 | 63705 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040263 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1883 | OFFICE DEVICES AND EQUIPMENT | [19 empty] | PDRRMO | SVP | n/a | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.27.2023 | 05.08.2023 | 05.10.2023 | 05.22.2023 | 05.22.2023 | GF | 156600 | 156600 |  | 156516 | 156516 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23040264 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0739 | EXTENSION WIRES | [19 empty] | PASSO | SVP | n/a | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 | 06.02.2023 | 06.02.2023 | GF | 920 | 920 |  | 916 | 916 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23040265 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1497 | ROOFING MATERIALS | [19 empty] | PEO-GA | SVP | n/a | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.08.2023 | 05.10.2023 | 05.26.2023 | 05.26.2023 | GF | 143587 | 143587 |  | 143555 | 143555 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23040266 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1568 | CONSTRUCTION SUPPLIES | [19 empty] | SEF | SVP | n/a | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.27.2023 | 05.17.2023 | 05.18.2023 |  |  | GF | 131870 | 131870 |  | 131559.5 | 131559.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040265 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1558 | CONSTRUCTION EQUIPMENT | [19 empty] | PEO | SVP | n/a | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.09.2023 | 05.10.2023 | 06.15.2023 | 06.15.2023 | GF | 111615 | 111615 |  | 111560 | 111560 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23040268 | AND SUPPLIES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1441 | CEMENT AND ROOFING MATERIALS | [19 empty] | PEO | SVP | n/a | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.08.2023 | 05.10.2023 | 06.06.2023 | 06.06.2023 | GF | 138837 | 138837 |  | 138813 | 138813 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040269 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1563 | CONSTRUCTION EQUIPMENT | [19 empty] | PEO | SVP | n/a | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.09.2023 | 05.10.2023 | 06.13.2023 | 06.13.2023 | GF | 111615 | 111615 |  | 111560 | 111560 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23040270 | AND SUPPLIES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1654 | ELECTRICAL SUPPLIES | [19 empty] | PEO | SVP | n/a | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.02.2023 | 05.03.2023 | 06.22.2023 | 06.22.2023 | GF | 142052 | 142052 |  | 141622 | 141622 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23040271 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1569 | CONSTRUCTION SUPPLIES | [19 empty] | PEO | SVP | n/a | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.02.2023 | 05.03.2023 | 05.17.2023 | 05.17.2023 | GF | 93631 | 93631 |  | 93434 | 93434 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040272 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1117 | CEMENT AND ROOFING MATERIALS | [19 empty] | PEO | SVP | n/a | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.27.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 138837 | 138837 |  | 138399 | 138399 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040273 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1116 | CEMENT AND ROOFING MATERIALS | [19 empty] | PEO | SVP | n/a | 03.28.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.27.2023 | 05.02.2023 | 05.03.2023 |  |  | GF | 143517 | 143517 |  | 143100 | 143100 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040274 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2072 | INK PRINTER, ALL-IN-ONE ECO TANK | [19 empty] | PDRRMO | SVP | n/a | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 15400 | 15400 |  | 15200 | 15200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040275 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0928 | FIRE EXTINGUISHER (10 LBS) | [19 empty] | PENRO | SVP | n/a | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.02.2023 | 05.03.2023 | 05.08.2023 | 05.08.2023 | GF | 4070 | 4070 |  | 4000 | 4000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040276 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0385 | PLUMBING SUPPLIES | [19 empty] | PEEMO | SVP | 03.24.2023 | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.08.2023 | 05.10.2023 | 06.13.2023 | 06.13.2023 | GF | 79310 | 79310 |  | 79235 | 79235 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040277 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1495 | CONSTRUCTION TOOLS AND SUPPLIES | [19 empty] | PEO | SVP | n/a | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.02.2023 | 05.03.2023 | 05.23.2023 | 05.23.2023 | GF | 269316 | 269316 |  | 269210 | 269210 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23040278 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1889 | RICE COOKER, 12 CUPS | [19 empty] | PDRRMO | SVP | n/a | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 |  |  | GF | 5666 | 5666 |  | 5660 | 5660 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23040280 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0131 | EXTENSION WIRES | [19 empty] | PHO | SVP | 03.21.2023 | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 | 06.13.2023 | 06.13.2023 | GF | 13434 | 13434 |  | 12970 | 12970 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040281 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1009 | FLOATING CHLORINE TABLET DISPENSER | [19 empty] | PDRRMO | SVP | 03.24.2023 | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 | 05.23.2023 | 05.23.2023 | GF | 19435 | 19435 |  | 19389 | 19389 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a
23040282 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0278 | OFFICE DEVICES AND ACCESSORIES | [19 empty] | PACCO | SVP | 03.21.2023 | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.25.2023 | 05.02.2023 | 05.04.2023 | 05.31.2023 | 05.31.2023 | GF | 52568 | 52568 |  | 52476 | 52476 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040283 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1954 | MINERAL WATER, (5GAL) | [19 empty] | PGO | SVP | n/a | 03.24.2023 | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.02.2023 | 05.04.2023 |  |  | GF | 2050 | 2050 |  | 2000 | 2000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040284 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2092 | EXECUTIVE SWIVEL MESH CHAIR | [19 empty] | PBO | SVP | n/a | n/a | n/a | n/a | 04.13.2023 | n/a | n/a | 04.18.2023 | 05.08.2023 | 05.10.2023 | 05.26.2023 | 05.26.2023 | GF | 15000 | 15000 |  | 14800 | 14800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23040285 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1989 | INSTALLATION OF GABIONS AT SECURED | [19 empty] | PEO | PB | 04.19.2023 | 05.08.2023 | 05.16.2023 | 05.30.2023 | 05.30.2023 | 05.30.2023 | [6 empty] | GF | 2802084.38 |  | 2802084.38 | 0 |  |  | Mr. Allan Rey N. Esmael | 05.11.2023 | n/a | 05.25.2023 | n/a | n/a |  | FOR POST QUA
CW23-027 | ROAD SHOULDER-ALONG STO. NINO- | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| CROSSING PANAG COGONON | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2520 | CONSTRUCTION OF WATER SUPPLY | [19 empty] | PEO | PB | 04.19.2023 | 05.08.2023 | 05.16.2023 | 05.30.2023 | 05.30.2023 | 05.30.2023 | [6 empty] | GF | 3198096 |  | 3198096 | 0 |  |  | Mr. Allan Rey N. Esmael | 05.11.2023 | n/a | 05.25.2023 | n/a | n/a |  | FOR POST QUA
CW23-026 | SYSTEM, BRGY SAN JOSE, MONKAYO | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2521 | CONSTRUCTION OF STAGE WITH | [19 empty] | PEO | PB | 04.19.2023 | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 2883242.63 |  | 2883242.63 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-025 | BLEACHERS AT ARAIBO, PANTUKAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2522 | CONSTRUCTION OF WATER SUPPLY | [19 empty] | PEO | PB | 04.19.2023 | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 3212845.86 |  | 3212845.86 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-051 | SYSTEM AT BRGY. PAMINTARAN, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| MARAGUSAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2545 | CONSTRUCTION OF ONE (1) STOREY- | [19 empty] | PEO | PB | 04.19.2023 | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 3789812.7 |  | 3789812.7 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-038 | TWO-CLASSROOMS BUILDING WITH | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| TOILET ATTACHED AT MAGCAGONG | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2002 | UPGRADING OF HOSPITAL BUILDING | [19 empty] | PEO | PB | 04.19.2023 | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 3789812.7 |  | 3789812.7 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-036 | FACILITIES AT DDOPH-PANTUKAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1995 | CONSTRUCTION OF WATER SYSTEM | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 1001854.77 |  | 1001854.77 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-040 | LEVEL II, SITIO PONGPONG, BRGY. ANDAP | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| NEW BATAAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1536 | REHABILITATION OF DRAINAGE STRUCTURE | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 1430589.79 |  | 1430589.79 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-045 | SLONG AMOR-CRUZ BAGONG SILANG | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| ROAD, LAAK | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2003 | CONSTRUCTION OF SLOPE PROTECTION | [19 empty] | PEO | PB | n/a | 06.05.2023 | n/a | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 970245.77 |  | 970245.77 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-054 | BRGY. LAS ARENAS, PANTUKAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| ROAD, LAAK | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1928 | UPGRADING OF DAVAO DE ORO | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 1408940 |  | 1408940 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-037 | PROVINCIAL HOSPITAL-PANTUKAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| ROAD, LAAK | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2207 | IMPROVEMENT OF WATER SYSTEM AT | [19 empty] | PEO | PB | n/a | 05.22.2023 | n/a | 05.30.2023 | 05.30.2023 | 05.30.2023 | [6 empty] | GF | 932786.54 |  | 932786.54 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-044 | CABIDIANAN NHS, BRGY. CABIDIANAN, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| NABUNTURAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1932 | IMPROVEMENT OFDAVAO DE ORO | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 3271471.14 |  | 3271471.14 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-030 | PROVINCIAL HOSPITAL-MONTEVISTA | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1998 | UPGRADING OF HOSPITAL BUILDING | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 3093997.35 |  | 3093997.35 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-039 | FACILITIES AT DDOPH-PANTUKAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2234 | CONSTRUCTION OF WATER SYSTEM | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 1867751.96 |  | 1867751.96 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-046 | AT (MIGUM-LOWER B) BRGY. CABUYUAN, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| MABINI | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2519 | COMPLETION OF WATER SYSTEM AT PUROK | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 1867751.96 |  | 1867751.96 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-042 | 20 NURSERY, BARANGAY NGAN, COMPOS- | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| TELA | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2629 | UPGRADING OF HOSPITAL FACILITIES AT | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 1805974.16 |  | 1805974.16 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-031 | DDOPH-MONTEVISTA | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| TELA | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1897 | SLOPE PROTECTION AT TUGOP, BRGY. | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 1883872.34 |  | 1883872.34 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-032 | KINGKING, PANTUKAN. DDO | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| TELA | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2698 | CONSTRUCTION OF MULTIPURPOSE | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 4931657.94 |  | 4931657.94 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-033 | BUILDING, COGONON ELEMENTARY SCHOOL | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| TELA | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2630 | UPGRADING OF HOSPITAL BUILDING | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 2939925.87 |  | 2939925.87 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-034 | FACILITIES AT DDOPH-MARAGUSAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2717 | CAPITOL SITE DEVELOPMENT | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 1224647.75 |  | 1224647.75 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-043 | WATER SYSTEM | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1628 | CONSTRUCTION OF HOSPITAL WASTE | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 14217212.67 |  | 14217212.67 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-047 | AND TREATMENT FACILITIES AT DDOPH- | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| PANTUKAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2541 | CONSTRUCTION OF HOSPITAL WASTE | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 13692971.23 |  | 13692971.23 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-048 | AND TREATMENT FACILITIES AT DDOPH- | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| MONTEVISTA | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2539 | CONSTRUCTION OF HOSPITAL WASTE | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 12007095.66 |  | 12007095.66 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-049 | AND TREATMENT FACILITIES AT DDOPH- | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| LAAK | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2539 | CONSTRUCTION OF HOSPITAL WASTE | [19 empty] | PEO | PB | n/a | 05.29.2023 | 06.06.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | [6 empty] | GF | 11840617.67 |  | 11840617.67 | 0 |  |  | Mr. Allan Rey N. Esmael | 06.01.2023 | n/a | 06.15.2023 | n/a | n/a |  | FOR POST QUA
CW23-049 | AND TREATMENT FACILITIES AT DDOPH- | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| MARAGUSAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2556 | SPARE PARTS | [19 empty] | PGSO | SA | 04.19.2023 | 04.26.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.16.2023 | 05.18.2023 | 05.22.2023 | 05.22.2023 | GF | 8350 | 8350 |  | 8350 | 8350 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050333 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2566 | BRAKE PAD AND BRAKE SHOE | [19 empty] | PGSO | SA | 04.19.2023 | 04.26.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.15.2023 | 05.18.2023 | 05.18.2023 | 05.18.2023 | GF | 14830 | 14830 |  | 14830 | 14830 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050332 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2563 | SPARE PARTS | [19 empty] | PGSO | SA | 04.19.2023 | n/a | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.16.2023 | 05.19.2023 | 05.22.2023 | 05.22.2023 | GF | 20000 | 20000 |  | 20000 | 20000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050331 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2547 | SPARE PARTS | [19 empty] | PGSO | SA | 04.19.2023 | 04.26.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.15.2023 | 05.18.2023 | 05.18.2023 | 05.18.2023 | GF | 34925 | 34925 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050330 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2600 | ICD-UX5700F DIGITAL VOICE RECORDER | [19 empty] | PHRMDO | SA | 04.19.2023 | 04.26.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 7400 | 7400 |  | 7400 | 7400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050579 | UX SERIES 4GB WITH RADIO | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2601 | EXTERNAL HDD 3.5"ITB S AND USB | [19 empty] | PHRMDO | SVP | 04.19.2023 | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 4602 | 4602 |  | 4598 | 4598 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR COMPLETION OF DELIVERY
23050602 | EXTENSION, 3m | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2468 | FREEZER 7cu, (CHEST TYPE) | [19 empty] | PAO- | SVP | 04.19.2023 | 04.26.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 05.31.2023 | 06.08.2023 | 06.08.2023 | GF | 26345 | 26345 |  | 26000 | 26000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050480 | [20 empty] | Admin | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0481 | OFFICE SUPPLIES | [19 empty] | PAO- | SB | 04.19.2023 | 04.26.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 06.01.2023 | 06.05.2023 | 06.23.2023 | 06.23.2023 | GF | 61198 | 61198 |  | 59689 | 59689 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050461 | [20 empty] | Admin | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0478 | POSTER, CALENDAR-AS PER SAMPLE | [19 empty] | PAO- | SVP | 04.19.2023 | 04.26.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 05.30.2023 | 05.31.2023 | 06.02.2023 | 06.02.2023 | GF | 71538 | 71538 |  | 67931.4 | 67931.4 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050477 | AND TARPAULIN | [19 empty] | Admin | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0487 | COMPUTER SPARE PARTS | [19 empty] | PAO- | SVP | 04.19.2023 | 04.26.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 05.30.2023 | 05.31.2023 | 06.16.2023 | 06.16.2023 | GF | 109511 | 109511 |  | 107901 | 107901 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050479 | [20 empty] | Admin | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0479 | JOB ORDER (BOOKBINDING)-AS PER | [19 empty] | PAO- | PB | 04.19.2023 | 05.03.2023 | n/a | 05.11.2023 | 05.11.2023 | 05.11.2023 | 05.17.2023 | 06.06.2023 | 06.22.2023 | 06.27.2023 |  |  | GF | 299732.8 | 299732.8 |  | 224575 | 224575 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.08.2023 | n/a | n/a
23060626 | DESIGN AND MAGAZINE 4 COLORS, | [19 empty] | Admin | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| PRINTING | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2602 | SHIRT, POLO W/ EMBROIDERY | [19 empty] | PAO- | SVP | 04.19.2023 | 04.26.2023 | n/a | 05.16.2023 | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 05.31.2023 |  |  | GF | 11740 | 11740 |  | 11100 | 11100 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050474 | [20 empty] | Admin | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2490 | SAFETY GEARS | [19 empty] | PAO- | SVP | 04.19.2023 | 04.26.2023 | n/a | 05.16.2023 | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 05.31.2023 | 06.15.2023 | 06.15.2023 | GF | 24660 | 24660 |  | 24270 | 24270 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050475 | [20 empty] | Admin | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2603 | COLORED PRINTER W/ SCANNER | [19 empty] | PHRMDO | SVP | 04.19.2023 | [11 empty] | GF | 10450 | 10450 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| 3 IN 1 TANK TYPE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2400 | JANITORIAL SUPPLIES | [19 empty] | VGO | SVP | 04.19.2023 | 04.26.2023 | n/a | 05.16.2023 | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.05.2023 | 06.13.2023 | 06.13.2023 | GF | 25860 | 25860 |  | 25298 | 25298 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050476 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0418 | OIL 4T, DIESEL ENGINE AND TIRE | [19 empty] | PGO | SVP | 04.19.2023 | [11 empty] | GF | 39830 | 39830 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| TUBELESS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0480 | JOB ORDER REPAIR (WHEEL ALIGNMENT) | [19 empty] | SPO | SA | 04.19.2023 | 04.26.2023 | n/a | n/a | 05.11.2023 | 05.11.2023 | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 05.31.2023 | 05.31.2023 | GF | 21400 | 21400 |  | 21400 | 21400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050368 | LOWER AND UPPER BALL JOINT | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2578 | BRAKE PAD | [19 empty] | SPO | SA | 04.19.2023 | 04.26.2023 | n/a | 05.02.2023 |  | 05.02.2023 | n/a | 05.02.2023 | 05.12.2023 | 05.18.2023 | 05.18.2023 | 05.18.2023 | GF | 5600 | 5600 |  | 5600 | 5600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050336 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0451 | COLORED PRINTER W/ SCANNER AND | [19 empty] | VGO | SVP | 04.19.2023 | [11 empty] | GF | 29050 | 29050 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| L360, PRINTER | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0496 | OFFICE SUPPLIES | [19 empty] | PENRO | SB | 04.19.2023 | 04.26.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 06.01.2023 | 06.05.2023 | 06.16.2023 | 06.16.2023 | GF | 76033 | 76033 |  | 74167 |  | 74167 | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050460 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0499 | COMPUTER DESKTOP, FAN, STAND | [19 empty] | PENRO | PB | 04.19.2023 | 05.03.2023 | n/a | 05.11.2023 | 05.11.2023 | 05.11.2023 | 05.17.2023 | 06.06.2023 | 06.19.2023 | 06.21.2023 | 06.27.2023 |  | GF | 251235 | 251235 |  | 223700 |  | 223700 | Mr. Allan Rey N. Esmael | n/a | n/a | 05.08.2023 | n/a | n/a |  | FOR INSPECTION
23060620 | AND PRINTER WITH SCANNER | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0453 | MEALS WITHOUT VENUE, PACKED | [19 empty] | PHO | PB | 04.19.2023 | 05.03.2023 | n/a | 05.11.20213 | 05.11.2023 | 05.11.2023 | 05.17.2023 | 06.07.2023 | 06.23.2023 | 06.29.2023 |  |  | GF | 415671 | 415671 |  | 370086 |  | 370086 | Mr. Allan Rey N. Esmael | n/a | n/a | 05.08.2023 | n/a | n/a
23060615 | MEAL, HEAVY SNACKS (A) (B) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0160 | SUPPLY AND DELIVERY OF FIRE | [19 empty] | PHO | PB | n/a | n/a | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.14.2023 | 04.25.2023 | 05.08.2023 | 05.11.2023 | 05.26.2023 | 05.26.2023 | GF | 236060 | 236060 |  | 87000 | 87000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040306 | EXTINGUISHER 10LBS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0129 | SUPPLY AND DELIVERY OF SPARE PARTS | [19 empty] | PDRRMO | PB | n/a | 03.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.14.2023 | 04.25.2023 | 05.08.2023 | 05.10.2023 | 05.26.2023 | 05.26.2023 | GF | 660847 | 660847 |  | 659660 | 659660 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040307 | FOR HEAVY EQUIPMENT | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0309 | SUPPLY AND DELIVERY OF SPARE PARTS | [19 empty] | VGO | PB | n/a | 03.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.14.2023 | 04.25.2023 | 05.09.2023 | 05.10.2023 | 05.26.2023 | 05.26.2023 | GF | 329370 | 329370 |  | 325810 | 325810 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040308 | FOR LIGHT VEHICLE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1658 | SUPPLY AND DELIVERY OF CONSTRUC- | [19 empty] | PEO | PB | n/a | 03.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.14.2023 | 04.25.2023 | 05.17.2023 | 05.18.2023 | 06.09.2023 | 06.09.2023 | GF | 213899.3 | 213899.3 |  | 211760.31 | 211760.31 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040309 | TION MATERIALS FOR THE CONSTRUCTION | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| OF SLOPE AT BRGY. PROSPERIDAD | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1115 | SUPPLY AND DELIVERY OF GEMELINA | [19 empty] | PEO | PB | n/a | 03.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.14.2023 | 04.25.2023 |  |  |  |  | GF | 983489.85 | 983489.85 |  | 980935.85 | 980935.85 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a |  | FOR PO APPROVAL
23040310 | LUMBER AND PORTLAND CEMENT FOR | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| THE CONCRETING ROAD, NABUNTURAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1653 | SUPPLY AND DELIVERY OF CONSTRUCTION | [19 empty] | PEO | PB | n/a | 03.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.14.2023 | 04.25.2023 | 05.11.2023 | 05.18.2023 | 05.29.2023 | 05.29.2023 | GF | 671992.7 | 671992.7 |  | 669932.06 | 669932.06 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040311 | MATERIALS FOR THE CONSTRUCTION | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| OF DRAINAGE, MARAGUSAN NHS | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1496 | SUPPLY AND DELIVERY OF CONSTRUC- | [19 empty] | PEO | PB | n/a | 03.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.14.2023 | 04.25.2023 | 05.17.2023 | 05.18.2023 | 06.09.2023 | 06.09.2023 | GF | 957420.55 | 957420.55 |  | 954850.4 | 954850.4 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040312 | TION AND ELECTRICAL MATERIALS FOR | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| THE IMPROVEMENT OF GYM | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1562 | SUPPLY AND DELIVERY OF ELECTRICAL | [19 empty] | PEO | PB | n/a | 03.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.14.2023 | 04.25.2023 | 05.08.2023 | 05.10.2023 | 06.09.2023 | 06.09.2023 | GF | 534665 | 534665 |  | 531783.59 | 531783.59 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040313 | MATERIALS FOR THE CONSTRUCTION | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| OF TEACHERS COTTAGE, BORINGOT IS | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1652 | SUPPLY AND DELIVERY OF CONSTRUCTION | [19 empty] | PEO | PB | n/a | 03.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.14.2023 | 04.25.2023 | 05.11.2023 | 05.19.2023 | 06.09.2023 | 06.09.2023 | GF | 658913 | 658913 |  | 656467.21 | 656467.21 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040314 | AND ELECTRICAL MATERIALS FOR THE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| CONSTRUCTION OF TEACHERS COTTAGE | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0307 | FABRICATION AND INSTALLATION OF | [19 empty] | PEO | PB | 03.21.2023 | 03.24.2023 | n/a | 04.04.2023 | 04.04.2023 | 04.04.2023 | 04.14.2023 | 04.24.2023 | 05.08.2023 | 06.16.2023 |  |  | GF | 321750 | 321750 |  | 273000 | 273000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.30.2023 | n/a | n/a
| BILLBOARD, LABOR, MATERIALS, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| SIZE 4*8 SQ FT | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0195 | SUPPLY AND DELIVERY OF DRUGS | [19 empty] | PGO | PB | n/a | 05.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.13.2023 | 04.25.2023 | 05.08.2023 | 05.17.2023 | 06.20.2023 | 06.20.2023 | GF | 897213 | 897213 |  | 451220 | 451220 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040286 | AND MEDICINES | [19 empty] | for the use of | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | PVO | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2142 | LANDRACE HYBRID PIGLET, FEMALE | [19 empty] | PGO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.29.2023 |  |  |  | GF | 288000 | 288000 |  | 287760 | 287760 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060645 | 18-20kgs, 35-40 DAYS OLD | [19 empty] | for the use of | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | PVO | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2456 | HELMET, FULL PACED, WITH BUILT IN | [19 empty] | PGO for the | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 | 06.26.2023 | 06.26.2023 | GF | 16500 | 16500 |  | 16140 | 16140 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050589 | GOGGLES, HEAVY DUTY | [19 empty] | use of PVO | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2145 | MEALS AND SNACKS WITH VENUE | [19 empty] | PGO for the | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.02.2023 |  |  | GF | 16750 | 16750 |  | 15100 | 15100 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050512 | [20 empty] | use of PVO | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2459 | ALCOHOL, RUBBING, 70%, 500ml | [19 empty] | PGO for the | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.02.2023 | 06.13.2023 | 06.13.2023 | GF | 2235 | 2235 |  | 2205 | 2205 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050513 | [20 empty] | use of PVO | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2415 | FLASHDRIVE, 32GB | [19 empty] | PGO for the | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 3200 | 3200 |  | 3200 | 3200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050585 | [20 empty] | use of PVO | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2460 | PREMIUM PRE-STARTTER HOG PELLETS | [19 empty] | PGO for the | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.05.2023 |  |  | GF | 36250 | 36250 |  | 35810 | 35810 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050514 | WITH LEAN PLUS TECHNOLOGY (25kl/sacl) | [19 empty] | use of PVO | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2449 | MEALS AND SNACKS WITH VENUE | [19 empty] | PGO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.15.2023 | 06.16.2023 |  |  | GF | 160000 | 160000 |  | 155000 | 155000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050586 | [20 empty] | for PPOC | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0500 | RICE (WELL MILLED) 50kgs/sack | [19 empty] | PGO | PB | 05.02.2023 | 06.12.2023 | 06.13.2023 | 06.27.2023 | 06.27.2023 | 06.27.2023 | [6 empty] | GF | 1140300 | 1140300 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR POST QUA
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2543 | OFFICE SUPPLIES | [19 empty] | PGO | SB | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | 05.16.2023 | n/a | 05.16.2023 | 05.30.2023 | 06.02.2023 | 06.13.2023 | 06.13.2023 | GF | 8155 | 8155 |  | 7990 | 7990 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050458 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2175 | MEALS VIP AND SNACKS | [19 empty] | PGO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.23.2023 | 05.29.2023 | 06.08.2023 |  |  | GF | 98409 | 98409 |  | 97140 | 97140 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050511 | [20 empty] | for the use | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | of PENRO | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0441 | PROTECTIVE GEAR As per sample | [19 empty] | PGO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 06.06.2023 | 06.08.2023 | 06.19.2023 | 06.19.2023 | GF | 153376 | 153376 |  | 150720 | 150720 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050510 | [20 empty] | for the use | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | of PENRO | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2561 | GLOVES, SURGICAL STERILE with CPR | [19 empty] | PGO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 |  |  |  |  | GF | 30866 | 30866 |  | 22660 | 22660 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23050509 | [20 empty] | for the use | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | of PHO | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2568 | DRUG TEST KITS AND SCREW CAP | [19 empty] | PGO | SVP | 05.02.2023 | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.15.2023 | 06.19.2023 |  |  | GF | 115000 | 115000 |  | 54000 | 54000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050597 | URINE CONTAINER | [19 empty] | for the use | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | of PHO | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0223 | MEDICAL SUPPLIES | [19 empty] | PGO | SVP | 05.02.2023 | [11 empty] | GF | 436762 | 436762 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[21 empty] | for the use | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | of PHO | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0485 | COMPUTER SPARE PARTS | [19 empty] | PAO- | SVP | 05.02.2023 | [11 empty] | GF | 47045 | 47045 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[21 empty] | Investment | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0476 | MEALS VIP AND SNACKS | [19 empty] | PAO- | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 05.31.2023 | 06.01.2023 |  |  | GF | 208025 | 208025 |  | 204984 | 204984 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050508 | [20 empty] | Investment | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0449 | JANITORIAL SUPPLIES | [19 empty] | PIAO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 06.02.2023 | 06.13.2023 | 06.13.2023 | GF | 8940 | 8940 |  | 8881 | 8881 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050507 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2326 | CABINET, STEEL FILLING W/ SAFE | [19 empty] | PTO | SVP | 05.02.2023 | [11 empty] | GF | 39000 | 39000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| 4 SOREYS (4 DRAWERS AND 1 SAFE) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2082 | MEDAL WITH DESIGN "2" | [19 empty] | PGO for | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.05.2023 |  |  | GF | 10000 | 10000 |  | 9750 | 9750 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050506 | [20 empty] | the use of | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | PSWDO | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0486 | STAND FAN, WALL FAN AND PORTABLE | [19 empty] | PGO for | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.23.2023 | 05.30.2023 | 06.02.2023 | 06.13.2023 | 06.13.2023 | GF | 97439 | 97439 |  | 97391 | 97391 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050505 | SOUND SYSTEM | [19 empty] | the use of | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | BAHAY-Pag-Asa | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2239 | LEVER, HAND BRAKE | [19 empty] | PGSO | SA | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.11.2023 | 05.11.2023 | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 05.31.2023 | 05.31.2023 | GF | 1245 | 1245 |  | 1245 | 1245 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050369 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1561 | CONSTRUCTION MATERIALS FOR THE | [19 empty] | PEO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 06.07.2023 | 06.09.2023 |  |  | GF | 269316 | 269316 |  | 269210 | 269210 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050504 | USE OF WATER SYSTEM AT NAPNAPAN, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| PANTUKAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0458 | GEMELINA LUMBER, NAILS AND | [19 empty] | PEO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.19.2023 | 06.20.2023 | 06.30.2023 | 06.30.2023 | GF | 28160 | 28160 |  | 27904 | 27904 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050503 | ORDIANRY PLYWOOD | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0459 | TARPAULIN AS PER DESIGN | [19 empty] | PEO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.22.2023 | 06.23.2023 |  |  | GF | 25088 | 25088 |  | 23296 | 23296 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR DELIVERY COMPLETION
23050502 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2632 | CONSTRUCTION MATERIALS FOR | [19 empty] | PEO | PB | 05.02.2023 | 05.08.2023 | n/a | 05.16.2023 | 05.16.2023 | 05.16.2023 | 05.17.2023 | 06.07.2023 | 06.22.2023 | 06.23.2023 |  |  | GF | 554630 | 554630 |  | 553610 |  | 553610 | Mr. Allan Rey N. Esmael | n/a | n/a | 05.11.2023 | n/a | n/a
23060632 | THE USE OF WATER SYSTEM, AT BRGY. | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| SAN ISIDRO, MONKAYO | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0465 | MEDICAL KIT FOR THE USE OF VARIOUS | [19 empty] | PEO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.07.2023 | 06.09.2023 |  |  | GF | 7700 | 7700 |  | 2240 | 2240 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050496 | PROJECTS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2633 | MEDICAL KIT FOR THE USE OF WATER | [19 empty] | PEO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.31.2023 | 06.06.2023 |  |  | GF | 1925 | 1925 |  | 560 | 560 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050497 | SUPPLY SYSTEM AT BRGY. SAN ISIDRO, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| MONKAYO | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2432 | MEDICAL KIT FOR THE USE OF WATER | [19 empty] | PEO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.06.2023 |  |  | GF | 1925 | 1925 |  | 560 | 560 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050498 | SYSTEM AT BRGY. NEW ATURIAS, MACO | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2634 | TARPAULIN AS PER DESIGN | [19 empty] | PEO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.05.2023 |  |  | GF | 1792 | 1792 |  | 1664 | 1664 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050499 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0454 | DRUG AND MEDICINE | [19 empty] | PHO | SVP | 05.02.2023 | n/a | n/a | n/a | 05.30.2023 | n/a | n/a | 06.06.2023 |  |  |  |  | GF | 122550 | 122550 |  | 114630 | 114630 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23050584 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2655 | SPARE PARTS FOR THE USE OF KIA K2700 | [19 empty] | PDRRMO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 35340 | 35340 |  | 34300 | 34300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060681 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0422 | MINERAL WATER, 5 GAL. | [19 empty] | PGO-BAC | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.07.2023 | 06.13.2023 |  |  | GF | 153996 | 153996 |  | 150240 | 150240 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050500 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2638 | MEALS AND SNACKS | [19 empty] | PBO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 06.02.2023 |  |  | GF | 15800 | 15800 |  | 15250 | 15250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050501 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2282 | OFFICE SUPPLIES | [19 empty] | PICTO | SB | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 | 06.26.2023 | 06.26.2023 | GF | 11300 | 11300 |  | 9930 | 9930 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050569 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2244 | MEALS WITH ACCOMMODATION AND | [19 empty] | PGO | SVP | 05.02.2023 | [11 empty] | GF | 88000 | 88000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O
| VENUE B | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0473 | BARCODE SCANNER, HANDHELD AND | [19 empty] | PTO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 05.31.2023 | 06.13.2023 | 06.13.2023 | GF | 29642 | 29642 |  | 29600 | 29600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050495 | MONEY COUNTER | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2191 | SPARE PARTS | [19 empty] | DDOPH- | SA | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.30.2023 | 05.31.2023 | 06.02.2023 | 06.02.2023 | GF | 11200 | 11200 |  | 11200 | 11200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050370 | [20 empty] | Maragusan | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0438 | LABORATORY SUPPLIES | [19 empty] | PEEMO | DC | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 |  |  |  |  | GF | 828265.21 | 828265.21 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23050518 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1688 | SPARE PARTS FOR THE USE OF | [19 empty] | PASSO | DC | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.16.2023 | 05.16.2023 | n/a | 05.16.2023 | 05.30.2023 | 05.31.2023 | 06.23.2023 | 06.23.2023 | GF | 85650 | 85650 |  | 85650 | 85650 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050517 | GESTETNER PHOTOCOPIER | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2176 | SWEATSHIRT-FULL SUBLIMATION | [19 empty] | PGO | SVP | 05.02.2023 | 05.05.2023 | n/a | 05.16.2023 | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.05.2023 | 06.06.2023 |  |  | GF | 6500 | 6500 |  | 6370 | 6370 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050494 | [20 empty] | for the use | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | PENRO | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2725 | OIL & LUBRICANTS | [19 empty] | PGO | PB | 05.02.2023 | 05.08.2023 | 05.16.2023 | 05.30.2023 | 05.30.2023 | 05.30.2023 | 06.09.2023 | 06.21.2023 | 06.22.2023 | 06.27.2023 |  |  | GF | 1183166.18 | 1183166.18 |  | 1183166.18 | 1183166.18 |  | Mr. Allan Rey N. Esmael | 05.11.2023 | n/a | 05.25.2023 | n/a | n/a
23060660 | [20 empty] | for the use | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | PENRO | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0281 | SUPPLY AND DELIVERY OF GARMENTS | [19 empty] | DEPED | PB | n/a | 04.11.2023 | n/a | 04.19.2023 | 04.19.2023 | 04.19.2023 | 04.20.2023 | 04.26.2023 | 05.15.2023 | 05.22.2023 |  |  | GF | 900000 | 900000 |  | 897960 | 897960 |  | Mr. Allan Rey N. Esmael | 04.05.2023 | n/a | 04.14.2023 | n/a | n/a
23040304 | FOR DAVRAA MEET 2023 | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0201 | SUPPLY AND DELIVERY OF SPARE PARTS, | [19 empty] | SPO | PB | 03.21.2023 | 03.25.2023 | 04.04.2023 | 04.18.2023 | 04.18.2023 | 04.18.2022 | 04.20.2023 | 05.03.2023 | 05.08.2023 | 05.11.2023 | 06.09.2023 | 06.09.2023 | GF | 1244072 | 1244072 |  | 1192869 | 1192869 |  | Mr. Allan Rey N. Esmael | 03.17.2023 | n/a | 04.13.2023 | n/a | n/a
23040305 | OIL AND LUBRICANTS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1360 | 1 LOT CONSTRUCTION OF WATER SYSTEM | [19 empty] | PEO | PB | 03.07.2023 | 03.24.2023 | 03.28.2023 | 04.18.2023 | 04.18.2023 | 04.18.2023 | 04.21.2023 | 04.24.2023 | 05.04.2023 | 05.08.2023 |  |  | GF | 2623799.14 | 2623799.14 |  | 2607542.28 | 2607542.28 |  | Mr. Allan Rey N. Esmael | 03.23.2023 | n/a | 04.19.2023 | n/a | n/a
CW23-002 | BRGY. PASIAN, MONKAYO | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2158 | 1 LOT IMPROVEMENT OF "GININTUANG | [19 empty] | PEO | PB | 03.21.2023 | 03.24.2023 | 04.04.2023 | 04.18.2023 | 04.18.2023 | 04.18.2023 | 04.21.2023 | 04.25.2023 | 05.04.2023 | 05.08.2023 |  |  | GF | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a
CW23-004 | PARAISO | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0251 | SUPPLY AND DELIVERY OF VETERINARY | [19 empty] | PVO | PB | n/a | 03.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.13.2023 | 04.25.2023 | 05.02.2023 | 05.11.2023 | 06.29.2023 | 06.29.2023 | GF | 997938 | 997938 |  | 969963 | 969963 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040287 | DRUGS AND BIOLOGICS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1396 | SUPPLY AND DELIVERY OF C2S UV | [19 empty] | PDRRMO | PB | n/a | 03.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.13.2023 | 04.25.2023 | 05.12.2023 | 05.30.2023 |  |  | GF | 500000 | 500000 |  | 396875 | 396875 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040288 | PROCESSED MAGAZINE PRINITNG | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0257 | SUPPLY AND DELIVERY OF FRUIT | [19 empty] | PENRO | PB | n/a | 03.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.13.2023 | 04.20.2023 | 05.08.2023 | 05.16.2023 |  |  | GF | 399990 | 399990 |  | 237129 | 237129 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040289 | TREES SEEDLINGS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0915 | SUPPLY AND DELIVERY OF SEEDLINGS | [19 empty] | PDRRMO | PB | n/a | 03.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.13.2023 | 04.20.2023 | 05.08.2023 | 05.16.2023 |  |  | GF | 300000 | 300000 |  | 214500 | 214500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040290 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0222 | SUPPLY AND DELIVERY OF DRUGS AND | [19 empty] | PGO | PB | n/a | 03.20.2023 | n/a | 03.28.2023 | 03.28.2023 | 03.28.2023 | 04.13.2023 | 04.25.2023 | 05.11.2023 | 05.17.2023 | 06.20.2023 | 06.20.2023 | GF | 797013 | 797013 |  | 323367.8 | 323367.8 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040291 | MEDICINES FOR THE USE OF PHO | [19 empty] | for the use | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | of PHO | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0188 | SUPPLY AND DELIVERY OF MEDICAL | [19 empty] | PDRRMO | PB | 03.21.2023 | 03.24.2023 | n/a | 04.04.2023 | 04.04.2023 | 04.04.2023 | 04.13.2023 | 04.25.2023 | 05.08.2023 | 05.11.2023 | 05.16.2023 | 05.16.2023 | GF | 346608 | 346608 |  | 213259 | 213259 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.23.2023 | n/a | n/a
23040292 | SUPPLIES | [19 empty] | for the use | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | of PHO | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0074 | SUPPLY AND DELIVERY OF OFFICE | [19 empty] | PHRMDO | PB | 03.21.2023 | 03.24.2023 | n/a | 04.04.2023 | 04.04.2023 | 04.04.2023 | 04.13.2023 | 04.25.2023 | 05.08.2023 | 05.15.2023 | 05.26.2023 | 05.26.2023 | GF | 329632 | 329632 |  | 327799 | 327799 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.30.2023 | n/a | n/a
23040293 | SUPPLIES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0162 | SUPPLY AND DELIVERY OF OFFICE | [19 empty] | PEEMO | PB | 03.21.2023 | 03.24.2023 | n/a | 04.04.2023 | 04.04.2023 | 04.04.2023 | 04.13.2023 | 04.25.2023 | 05.08.2023 | 05.10.2023 | 05.26.2023 | 05.26.2023 | GF | 931654 | 931654 |  | 930883.05 | 930883.05 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.30.2023 | n/a | n/a
23040294 | SUPPLIES FOR THE USE OF PEEMO AND | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| VARIOUS HOSPITALS | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0151 | SUPPLY AND DELIVERY OF PHOTOCOPIER | [19 empty] | PEEMO | PB | 03.21.2023 | 03.24.2023 | n/a | 04.04.2023 | 04.04.2023 | 04.04.2023 | 04.13.2023 | 04.24.2023 | 05.08.2023 | 05.11.2023 | 05.16.2023 | 05.16.2023 | GF | 150000 | 150000 |  | 89000 | 89000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.30.2023 | n/a | n/a
23040295 | AS PER SPECIFICATION FOR THE USE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| OF PEEMO | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0034 | SUPPLY AND DELIIVERY OF FERTILIZERS, | [19 empty] | PAGRO | PB | 03.21.2023 | 03.24.2023 | n/a | 04.04.2023 | 04.04.2023 | 04.04.2023 | 04.13.2023 | 04.25.2023 | 06.01.2023 | 06.02.2023 |  |  | GF | 150311 | 150311 |  | 132728 | 132728 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.30.2023 | n/a | n/a
23040296 | PESTICIDES AND ROOT HORMONES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0218 | SUPPLY AND DELIVERY OF FOOD | [19 empty] | PENRO | PB | 03.21.2023 | 03.24.2023 | n/a | 04.04.2023 | 04.04.2023 | 04.04.2023 | 04.13.2023 | 04.25.2023 | 05.08.2023 | 05.25.2023 |  |  | GF | 399872 | 399872 |  | 353096 | 353096 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.30.2023 | n/a | n/a
23040297 | SUPPLIES (MEALS AND SNACKS) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0113 | SUPPLY AND DELIVERY OF FOOD | [19 empty] | PENRO | PB | 03.21.2023 | 03.24.2023 | n/a | 04.04.2023 | 04.04.2023 | 04.04.2023 | 04.13.2023 | 04.25.2023 | 05.08.2023 | 05.25.2023 |  |  | GF | 150311 | 150311 |  | 132728 | 132728 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.30.2023 | n/a | n/a
23040298 | SUPPLIES (MEALS AND SNACKS) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0349 | SUPPLY AND DELIVERY OF ELECTRO- | [19 empty] | PEEMO | PB | n/a | 03.24.2023 | n/a | 04.04.2023 | 04.04.2023 | 04.04.2023 | 04.13.2023 | 04.24.2023 | 05.08.2023 | 05.17.2023 |  |  | GF | 796016 | 796016 |  | 550056 | 550056 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 03.30.2023 | n/a | n/a
23040299 | LYTES ANALYZER (SODIUM, POTASSIUM, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| CHLORIDE, CALCIUM) | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1698 | SUPPLY AND DELIVERY OF TIRES FOR | [19 empty] | PEO- | PB | 03.21.2023 | 03.25.2023 | 04.04.2023 | 04.18.2023 | 04.18.2023 | 04.18.2023 | 04.26.2023 | 05.11.2023 | 05.18.2023 | 05.22.2023 | 05.26.2023 | 05.26.2023 | GF | 8440000 | 8440000 |  | 4987000 | 4987000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.13.2023 | n/a | n/a
23050357 | HEAVY EQUIPMENT | [19 empty] | Motorpool | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0391 | SUPPLY AND DELIVERY OF PHOTOCOPIER | [19 empty] | PEEMO | PB | n/a | 04.11.2023 | n/a | 04.19.2023 | 04.19.2023 | 04.19.2023 | 04.26.2023 | 05.09.2023 | 05.15.2023 | 05.16.2023 | 05.23.2023 | 05.23.2023 | GF | 100000 | 100000 |  | 85800 | 85800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.14.2023 | n/a | n/a
23050358 | FOR THE USE OF DDOPH-MARAGUSAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2106 | SUPPLY AND DELIVERY OF MONOBLOCK | [19 empty] | PGO | PB | n/a | 04.11.2023 | n/a | 04.19.2023 | 04.19.2023 | 04.19.2023 | 04.26.2023 | 05.11.2023 | 05.17.2023 | 05.19.2023 | 05.22.2023 | 05.22.2023 | GF | 534000 | 534000 |  | 375000 | 375000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.14.2023 | n/a | n/a
23050359 | PLASTIC CHAIR FOR THE USE OF OPLAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| PAGBABAGO-ELCAC | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0392 | SUPPLY AND DELIVERY OF MEDICAL | [19 empty] | PEEMO | PB | 03.24.2023 | 04.11.2023 | n/a | 04.19.2023 | 04.19.2023 | 04.19.2023 | 04.26.2023 | 05.11.2023 | 05.16.2023 | 05.25.2023 | 06.14.2023 | 06.14.2023 | GF | 408924 | 408924 |  | 243087.4 | 243087.4 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.14.2023 | n/a | n/a
23050360 | DENTAL AND LABORATORY SUPPLIES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| FOR THE USE OF VARIOUS HOSPITALS | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0373 | SUPPLY AND DELIVERY OF MEDICAL | [19 empty] | PEEMO | PB | n/a | 04.11.2023 | n/a | 04.19.2023 | 04.19.2023 | 04.19.2023 | 04.26.2023 | 05.11.2023 | 05.16.2023 | 05.25.2023 | 06.06.2023 | 06.06.2023 | GF | 994168.4 | 994168.4 |  | 731506 | 731506 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.14.2023 | n/a | n/a
23050361 | SUPPLIES FOR THE USE VARIOUS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| HOSPITALS | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1676 | SUPPLY AND DELIVERY OF ELECTRICAL | [19 empty] | PGSO | PB | n/a | 04.11.2023 | n/a | 04.19.2023 | 04.19.2023 | 04.19.2023 | 04.26.2023 | 05.11.2023 | 05.16.2023 | 05.19.2023 | 05.29.2023 | 05.29.2023 | GF | 652110 | 652110 |  | 650018 | 650018 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.14.2023 | n/a | n/a
23050362 | SUPPLIES FOR THE USE OF CAPITOL | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| BUILDING MAINTAINANCE | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0660 | PRINT CARTRIDGE (PHOTOCOPIER) | [19 empty] | PASSO | DC | n/a | 03.28.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.18.2023 | 06.29.2023 | 06.29.2023 | 06.29.2023 | GF | 49533 | 49533 |  | 42873 | 42873 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050316 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0506 | BLOOD CHEMISTRY SUPPLIES | [19 empty] | PEEMO | DC | n/a | n/a | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.18.2023 | 05.23.2023 | 05.31.2023 | 05.31.2023 | GF | 135900 | 135900 |  | 135900 | 135900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050318 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2575 | PLASTIC CANVASS | [19 empty] | PDRRMO | NP | n/a | 04.24.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.11.2023 | 05.12.2023 | 05.18.2023 | 05.24.2023 | 05.24.2023 | GF | 364500 | 364500 |  | 364500 | 364500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050319 | [21 empty] | (EMERGENCY | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[22 empty] | CASES) | [13 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2576 | VARIOUS HDPE PIPES | [19 empty] | PDRRMO | NP | n/a | 04.24.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.12.2023 | 05.12.2023 | 06.21.2023 | 06.15.2023 | 05.16.2023 | GF | 301872 | 301872 |  | 301872 | 301872 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050320 | [21 empty] | (EMERGENCY | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[22 empty] | CASES) | [13 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2222 | SPAREPARTS | [19 empty] | SPO | SA | n/a | 04.25.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.12.2023 | 05.15.2023 |  |  | GF | 3913 | 3913 |  | 3913 | 3913 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050329 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0781 | COMVAL CAPITOL MULTI-PURPOSE | [19 empty] | PGO | SVP | n/a | 03.28.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.17.2023 | 05.18.2023 |  |  | GF | 12500 | 12500 |  | 12300 | 12300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050337 | COOPERATIVE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0259 | FUEL AND OIL FILTER | [19 empty] | PENRO | SVP | n/a | 03.28.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.16.2023 | 05.19.2023 |  |  | GF | 3500 | 3500 |  | 3487 | 3487 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050338 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0411 | BULB | [19 empty] | PVO | SVP | n/a | 03.28.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.16.2023 | 05.19.2023 |  |  | GF | 7550 | 7550 |  | 7495 | 7495 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050339 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2135 | EARLY WARNING DEVICE (SPECS) | [19 empty] | PDRRMO | SVP | 03.28.2023 | 03.30.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.12.2023 | 05.18.2023 | 06.23.2023 | 06.23.2023 | GF | 13200 | 13200 |  | 12600 | 12600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050340 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0232 | TARPAULIN-AS PER DESIGN | [19 empty] | PENRO | SVP | n/a | 03.30.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.16.2023 | 05.18.2023 |  |  | GF | 36400 | 36400 |  | 35880 | 35880 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050342 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0219 | TARPAULIN-AS PER DESIGN | [19 empty] | PENRO | SVP | n/a | 05.30.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.16.2023 | 05.18.2023 |  |  | GF | 20160 | 20160 |  | 19872 | 19872 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050343 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1719 | BARCODE SCANNER | [19 empty] | PBO | SVP | n/a | 04.11.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.12.2023 | 05.15.2023 | 05.16.2023 | 05.16.2023 | GF | 20160 | 20160 |  | 19872 | 19872 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050343 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0354 | FOOD SUPPLIES-DRY GOODS | [19 empty] | PEEMO | SVP | n/a | 04.11.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.11.2023 | 05.17.2023 | 05.18.2023 | 06.05.2023 | 06.05.2023 | GF | 153330 | 153330 |  | 147603 | 147603 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050345 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0106 | AGRICULTURAL SUPPLIES AND SAFETY GEAR | [19 empty] | PAGRO | SVP | 03.21.2023 | 04.11.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.11.2023 | 05.17.2023 | 05.18.2023 | 06.05.2023 | 06.05.2023 | GF | 262068 | 262068 |  | 257770 | 257770 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050346 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2131 | HEAVY SNACKS | [19 empty] | PGSO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.16.2023 | 05.17.2023 |  |  | GF | 11625 | 11625 |  | 11187.5 | 11187.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050347 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2331 | MEALS AND SNACKS | [19 empty] | PGO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.10.2023 | 05.17.2023 | 05.19.2023 | 06.15.2023 | 06.15.2023 | GF | 55350 | 55350 |  | 54360 | 54360 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050348 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0455 | SAFETY GEARS | [19 empty] | PTO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.11.2023 | 05.12.2023 | 05.18.2023 | 05.26.2023 | 05.26.2023 | GF | 58080 | 58080 |  | 57440 | 57440 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050349 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0367 | MEALS AND SNACKS | [19 empty] | PAGRO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.11.2023 | 05.12.2023 | 05.18.2023 |  |  | GF | 411807 | 411807 |  | 409215 | 409215 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050350 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0361 | JANITORIAL SUPPLIES | [19 empty] | PAGRO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.16.2023 | 05.18.2023 | 06.13.2023 | 06.13.2023 | GF | 18398 | 18398 |  | 17920 | 17920 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050351 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2325 | MEALS AND SNACKS | [19 empty] | PIAO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.12.2023 | 05.15.2023 |  |  | GF | 17745 | 17745 |  | 17420 | 17420 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050352 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2596 | MEALS AND SNACKS | [19 empty] | PGO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.17.2023 | 05.19.2023 |  |  | GF | 13800 | 13800 |  | 13300 | 13300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050354 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2607 | MEALS WITH VENUE | [19 empty] | PGO | SVP | n/a | 04.25.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.17.2023 | 05.19.2023 |  |  | GF | 33000 | 33000 |  | 32250 | 32250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050355 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2126 | MEALS WITHOUT VENUE | [19 empty] | PGO | SVP | n/a | 04.25.2023 | n/a | n/a | 05.02.2023 | n/a | n/a | 05.02.2023 | 05.26.2023 | 05.29.2023 |  |  | GF | 9264 | 9264 |  | 9072 | 9072 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050356 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0456 | OFFICE SUPPLIES | [19 empty] | PTO | SB | n/a | 04.13.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.19.2023 | 05.30.2023 | 05.31.2023 | 06.16.2023 | 06.16.2023 | GF | 180185 | 180185 |  | 176493 | 176493 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050373 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0452 | OFFICE SUPPLIES | [19 empty] | PHRMDO | SB | n/a | 04.13.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.30.2023 | 06.09.2023 | 06.09.2023 | GF | 48098 | 48098 |  | 47368 | 47368 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050372 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2483 | HYPO-CHLORINATOR | [19 empty] | PDRRMO | NP-EMERGENCY | n/a | 0.28.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.15.2023 | 05.29.2023 | 05.31.2023 |  |  | GF | 61600 | 61600 |  | 57700 | 57700 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050365 | [21 empty] | CASES | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2485 | CHLORINE COMPARATOR | [19 empty] | PDRRMO | NP-EMERGENCY | n/a | 03.28.2023 | n/a | n/a | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.29.2023 | 05.31.2023 | 06.29.2023 | 06.29.2023 | GF | 30000 | 30000 |  | 27860 | 27860 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050365 | [21 empty] | CASES | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0405 | EXPANDED NEW BORN SCREENING TEST | [19 empty] | PEEMO | DC | 03.24.2023 | 03.28.2023 | n/a | 05.11.2023 | 05.11.2023 | n/a | n/a | 05.11.2023 | 05.30.2023 | 06.01.2023 | 06.05.2023 | 06.05.2023 | GF | 3823750 | 3823750 |  | 3823750 | 3823750 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050363 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0350 | HEMATOLOGY ANALYZER (COMPLETE BLOOD | [19 empty] | PEEMO | PB | n/a | 03.25.2023 | 04.04.2023 | 04.18.2023 | 04.18.2023 | 04.18.2023 | 04.26.2023 | 05.17.2023 | 05.15.2023 | 05.18.2023 |  |  | GF | 1642914 | 1642914 |  | 800394 | 800394 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.13.2023 | n/a | n/a
23050451 | COUNT) FOR THE USE OF VARIOUS HOSPITALS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1470 | LAND SURVEY INSTRUMENT | [19 empty] | PEO | PB | 03.21.2023 | 03.25.2023 | 04.04.2023 | 04.18.2023 | 04.18.2023 | 04.18.2023 | 04.26.2023 | 05.11.2023 |  |  |  |  | GF | 1800000 | 1800000 |  | 988000 | 988000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.13.2023 | n/a | n/a
23050450 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0352 | RICE (WELL MILLED) 50kg/sack | [19 empty] | PEEMO | PB | n/a | 04.11.2023 | n/a | 04.19.2023 | 04.19.2023 | 04.19.2023 | 05.04.2023 | 05.16.2023 | 06.22.2023 | 06.30.2023 | 06.30.2023 | 06.30.2023 | GF | 569746 | 569746 |  | 565000 | 565000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.12.2023 | n/a | n/a
23050452 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1923 | VARIOUS CONSTRUCTION SUPPLY | [19 empty] | PEO- | PB | n/a | 04.11.2023 | 04.18.2023 | 05.02.2023 | 05.02.2023 | 05.02.2023 | 05.04.2023 | 05.16.2023 | 06.05.2023 | 06.09.2023 | 06.29.2023 | 06.29.2023 | GF | 1459602.15 | 1459602.15 |  | 1328418.15 | 1328418.15 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.26.2023 | n/a | n/a
23050453 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2322 | FUIL, OIL AND LUBRICANTS | [19 empty] | PDRRMO | PB | na/ | 04.11.2023 | n/a | 05.02.2023 | 05.02.2023 | 05.02.2023 | 05.04.2023 | 05.16.2023 | 05.29.2023 | 05.30.2023 | 06.08.2023 | 06.08.2023 | GF | 337509 | 337509 |  | 336917 | 336917 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.27.2023 | n/a | n/a
23050457 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0155 | FLUIDS FOR THE USE VARIOUS HOSPITALS | [19 empty] | PEEMO | PB | 03.21.2023 | 04.11.2023 | n/a | 05.02.2023 | 05.02.2023 | 05.02.2023 | 05.04.2023 | 05.16.2023 | 05.30.2023 | 05.31.2023 | 06.07.2023 | 06.07.2023 | GF | 1284852 | 1284852 |  | 805272 | 805272 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.27.2023 | n/a | n/a
23050456 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0355 | FLUIDS FOR THE USE VARIOUS HOSPITALS | [19 empty] | PEEMO | PB | 03.24.2023 | 04.11.2023 | 04.18.2023 | 05.02.2023 | 05.02.2023 | 05.02.2023 | 05.04.2023 | 05.16.2023 | 05.30.2023 | 05.31.2023 | 06.19.2023 | 06.19.2023 | GF | 1284852 | 1284852 |  | 805272 | 805272 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.27.2023 | n/a | n/a
23050455 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0286 | RESCUE TOOLS AND EQUIPMENT | [19 empty] | PDRRMO | PB | n/a | 04.11.2023 | 04.18.2023 | 05.02.2023 | 05.02.2023 | 05.02.2023 | 05.04.2023 | 05.16.2023 | 05.30.2023 | 06.01.2023 |  |  | GF | 1392784 | 1392784 |  | 1298000 | 1298000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.27.2023 | n/a | n/a
23050454 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0147 | DRUGS AND MEDICINES | [19 empty] | PHO | PB | 03.21.2023 | 03.25.2023 | 04.04.2023 | 04.18.2023 | 04.18.2023 | 04.18.2023 | 04.26.2023 | 05.16.2023 | 06.01.2023 | 06.05.2023 | 06.23.2023 | 06.23.2023 | GF | 1268285 | 1268285 |  | 1199029.2 | 1199029.2 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.13.2023 | n/a | n/a
23050449 | SUBSCRIPTION A | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0854 | SUPPLY AND DELIVERY OF INTERNET | [19 empty] | PICTO | PB | n/a | 04.11.2023 | 04.18.2023 | 05.02.2023 | 05.02.2023 | 05.02.2023 | 05.05.2023 | 05.19.2023 | 06.01.2023 | 06.21.2023 |  |  | GF | 1938000 | 1938000 |  | 1228000.08 | 1228000.08 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.26.2023 | n/a | n/a
23050528 | SUBSCRIPTION A | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1677 | SUPPLY AND DELIVERY OF INTERNET | [19 empty] | PICTO | PB | n/a | 04.11.2023 | 04.18.2023 | 05.02.2023 | 05.02.2023 | 05.02.2023 | 05.05.2023 | 05.22.2023 | 05.30.2023 | 06.01.2023 |  |  | GF | 1198400.04 | 1198400.04 |  | 568068 | 568068 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 04.26.2023 | n/a | n/a
23050529 | SUBSCRIPTION B | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0371 | ELECTROLYTES ANALYZER | [19 empty] | PEEMO | DC | 03.24.2023 | 04.11.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 06.01.2023 | 06.21.2023 |  |  | GF | 747066 | 747066 |  | 747066 | 747066 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050516 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0210 | CONSTRUCTION SUPPLIES AND TOOLS | [19 empty] | PEEMO | NP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 06.01.2023 | 06.05.2023 |  |  | GF | 111615 | 111615 |  | 111390 | 111390 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050521 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0951 | MEALS VIP AND HEAVY SNACKS | [19 empty] | PDRRMO | NP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 06.01.2023 | 06.05.2023 | 06.20.2023 | 06.20.2023 | GF | 194400 | 194400 |  | 188000 | 188000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050522 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2482 | MEDICAL SUPPLIES | [19 empty] | PDRRMO | NP-EMERGENCY | n/a | 04.13.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 05.31.2023 | 06.30.2023 | 06.30.2023 | GF | 33783 | 33783 |  | 33025 | 33025 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050523 | [21 empty] | CASES | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0472 | DRUGS AND MEDICINES | [19 empty] | PDRRMO | NP-EMERGECY | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.23.2023 | 05.31.2023 | 06.06.2023 |  |  | GF | 558016.02 | 558016.02 |  | 316100.76 | 316100.76 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050524 | [21 empty] | CASES | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2599 | OFFICE SUPPLIES | [19 empty] | PGO | SB | 05.16.2023 | [11 empty] | GF | 36315 | 36315 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0521 | OFFICE SUPPLIES | [19 empty] | PHO | SB | 05.16.2023 | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.06.2023 | 06.19.2023 | 06.21.2023 |  |  | GF | 128653 | 128653 |  | 128653 | 128653 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR DELIVERY
23050567 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2763 | SPARE PARTS (LIGHT VEHICLE) | [19 empty] | PGSO | SA | 05.16.2023 | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | GF | 19215 | 19215 |  | 19215 | 19215 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2715 | INTERNET FIREWALL | [19 empty] | PGSO | PB | 05.16.2023 | 05.19.2023 | n/a | 05.30.2023 | 05.30.2023 | 05.30.2023 | 06.09.2023 | 06.29.2023 |  |  |  |  | GF | 800000 | 800000 |  | 799112 | 799112 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.25.2023 | n/a | n/a |  | FOR PO APPROVAL
23060693 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2840 | MEALS VIP (3 VIANDS) 3 MAIN DISH 1 SOUP | [19 empty] | PGO | SVP | 05.16.2023 | 05.26.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.06.2023 | 06.07.2023 | 06.22.2023 | 06.22.2023 | GF | 117900 | 117900 |  | 115200 | 115200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050612 | WITH FRUITS OR DESSERTS, SOFTDRINKS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| OR JUICE | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2785 | OIL PRESSURE SENDER (GENERATOR SET) | [19 empty] | PDRRMO | SVP | 05.16.2023 | [11 empty] | GF | 2900 | 2900 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | REFER SIR RANDY
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1511 | OFFICE SUPPLIES | [19 empty] | PVGO | SB | n/a | 03.28.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.07.2023 | 06.08.2023 | 06.08.2023 | GF | 96762 | 96762 |  | 95647.25 | 95647.25 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050525 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0419 | OFFICE SUPPLIES | [19 empty] | PGO | SB | n/a | 04.24.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 05.30.2023 | 06.01.2023 | 06.08.2023 | 06.08.2023 | GF | 129950 | 129950 |  | 123125 | 123125 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050459 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0507 | OFFICE SUPPLIES | [19 empty] | VGO | SB | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 06.01.2023 | 06.05.2023 | 06.16.2023 | 06.16.2023 | GF | 86779 | 86779 |  | 80958 | 80958 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050462 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0410 | ELECTRICAL SUPPLIES | [19 empty] | PDRRMO | SVP | n/a | 03.28.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 05.31.2023 |  |  | GF | 7848 | 7848 |  | 7827 | 7827 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050463 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1964 | BATTERY 12V 13 PLATES, N70-MAINTAINACE | [19 empty] | PAGRO | SVP | n/a | 03.28.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.05.2023 |  |  | GF | 19000 | 19000 |  | 18240 | 18240 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050464 | FREE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2143 | VETERINARY SUPPLIES | [19 empty] | PGO | SVP | 03.24.2023 | 03.28.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.06.2023 | 06.29.2023 | 06.29.2023 | GF | 49250 | 49250 |  | 48665 | 48665 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050465 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1718 | SIGNAGE, MIRRORIZED WITH BRONZE | [19 empty] | PBO | SVP | n/a | 04.11.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 05.31.2023 |  |  | GF | 7200 | 7200 |  | 7000 | 7000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050466 | BACKGROUND (SAMPLE/DESIGN) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2413 | FREON | [19 empty] | SPO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.31.2023 | 06.06.2023 | 06.19.2023 | 06.19.2023 | GF | 9300 | 9300 |  | 9100 | 9100 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050469 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2412 | PICTURE FRAME (AS PER DESIGN) | [19 empty] | SPO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.05.2023 |  |  | GF | 3300 | 3300 |  | 3280 | 3280 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050470 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2229 | POLYETHYLENE GAS | [19 empty] | PDRRMO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 05.31.2023 | 06.06.2023 | 06.06.2023 | GF | 44250 | 44250 |  | 43375 | 43375 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050471 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1609 | GAVEL | [19 empty] | PGO | SVP | n/a | 04.25.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 05.31.2023 | 06.15.2023 | 06.15.2023 | GF | 6000 | 6000 |  | 5990 | 5990 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050473 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0447 | UPS WITH AVR | [19 empty] | PEO-GA | SVP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.05.2023 | 06.16.2023 | 06.16.2023 | GF | 28437 | 28437 |  | 28150 | 28150 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050478 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2289 | PRINTING AND BINDING OF TRAINING | [19 empty] | PHO | SVP | n/a | 04.26.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.05.2023 |  |  | GF | 7650 | 7650 |  | 7650 | 7650 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050481 | MODULES | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2215 | AGRICULTURAL SUPPLIES AND TOOLS | [19 empty] | PDRRMO | SVP | n/a | 04.26.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 05.30.2023 | 05.31.2023 | 06.05.2023 | 06.05.2023 | GF | 72787 | 72787 |  | 71840 | 71840 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050482 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2280 | ORAL MEDICAL SUPPLY | [19 empty] | PHO | SVP | n/a | 04.26.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 06.01.2023 | 06.14.2023 | 06.14.2023 | GF | 25000 | 25000 |  | 20000 | 20000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050483 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2425 | PACKED MEALS AND SNACKS | [19 empty] | PHO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 06.01.2023 |  |  | GF | 42390 | 42390 |  | 40060 | 40060 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050484 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2224 | TARPAULIN-AS PER DESIGN | [19 empty] | PEO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.07.2023 | 06.09.2023 |  |  | GF | 1792 | 1792 |  | 1664 | 1664 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR COMPLETION OF DELIVERY
23050485 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1136 | SINGLET | [19 empty] | PGO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 05.31.2023 |  |  | GF | 30000 | 30000 |  | 29600 | 29600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050486 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1138 | OFFICE TABLES AND CHAIRS | [19 empty] | PGO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 05.30.2023 | 05.31.2023 | 06.16.2023 | 06.16.2023 | GF | 90600 | 90600 |  | 89592 | 89592 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050487 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1270 | PLAQUE-AS PER DESIGN | [19 empty] | PGO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 05.31.2023 |  |  | GF | 18150 | 18150 |  | 17600 | 17600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050488 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2535 | MINERAL WATER, (330 ML AND 5GAL.) | [19 empty] | PGO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 06.02.2023 |  |  | GF | 8145 | 8145 |  | 7862 | 7862 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050489 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2532 | JANITORIAL SUPPLIES | [19 empty] | PGO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 06.02.2023 | 06.06.2023 | 06.06.2023 | GF | 18860 | 18860 |  | 18510 | 18510 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050490 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2664 | MEALS AND SNACKS (VENUE) | [19 empty] | PGO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 05.30.2023 | 06.02.2023 |  |  | GF | 24920 | 24920 |  | 24560 | 24560 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050491 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2685 | TARPAULIN-AS PER DESIGN | [19 empty] | PGO-SEF | SVP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 1792 | 1792 |  | 1664 | 1664 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR COMPLETION OF DELIVERY
23050492 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0370 | AGRICULTURAL SUPPLIES | [19 empty] | PAGRO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.19.2023 | 06.01.2023 | 06.05.2023 |  |  | GF | 90960 | 90960 |  | 90040 | 90040 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
. | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1795 | MEALS WITH VENUE | [19 empty] | PGO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.16.2023 | n/a | n/a | 05.16.2023 | 06.01.2023 | 06.02.2023 |  |  | GF | 22000 | 22000 |  | 22000 | 22000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050515 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3042 | RICE (WELL MILLED) | [19 empty] | PGO-PRC | PB | 05.30.2023 | 06.12.2023 | n/a | 06.20.2023 | 06.20.2023 | n/a | [6 empty] | GF | 589500 | 589500 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | Change mode to SVP
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0538 | MEALS AND SNAKS | [19 empty] | PHO | PB | 05.30.2023 | [11 empty] | GF | 2671500 | 2671500 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | RETURNED TO RO
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0539 | MEALS AND SNAKS | [19 empty] | PHO | PB | 05.30.2023 | 06.05.2023 | n/a | 06.13.2023 | 06.13.2023 | 06.13.2023 | 06.15.2023 | 06.30.2023 |  |  |  |  | GF | 711620 | 711620 |  | 694025 | 694025 |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | FOR PO APPROVAL
23060696 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2830 | JOB ORDER-REPAIR AND MAINTANANCE | [19 empty] | PDRRMO | SVP | 05.30.2023 | 06.02.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 134773 | 134773 |  | 134742 | 134742 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060686 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2835 | SPARE PARTS FOR THE USE OF KIA 2700 | [19 empty] | PDRRMO | SA | 05.30.2023 | 06.02.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 | 06.27.2023 | 06.26.2023 | 06.26.2023 | GF | 52580 | 52580 |  | 52580 | 52580 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060634 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2838 | BRAKE PAD AND BRAKE SHOE FOR | [19 empty] | PDRRMO | SA | 05.30.2023 | 06.02.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 | 06.26.2023 | 06.26.2023 | 06.26.2023 | GF | 23600 | 23600 |  | 23600 | 23600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060635 | THE USE N-NAVARA | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2872 | SPAREPARTS FOR VARIOUS | [19 empty] | PDRRMO | SVP | 05.30.2023 | [11 empty] | GF | 52440 | 52440 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| VEHICLE | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0522 | INK, TONER FOR PHOTOCOPIER | [19 empty] | PEO | SB | 05.30.2023 | 06.02.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.26.2023 | 06.27.2023 |  |  | GF | 180845 | 180845 |  | 179100 | 179100 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR COMPLETION OF DELIVERY
23060640 | AND TONER FOR HP LASERJET | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2660 | OFFICE SUPPLIES | [19 empty] | PEO | SB | 05.30.2023 | [11 empty] | GF | 98477 | 98477 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060697 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0442 | COMPUTER DESKTOP, DIGITAL CAMERA | [19 empty] | PGO for | PB | n/a | 05.03.2023 | n/a | 05.11.2023 | 05.11.2023 | 05.11.2023 | 05.17.2023 | 06.05.2023 | 06.19.2023 | 06.21.2023 | 06.27.2023 |  | GF | 251235 | 251235 |  | 223700 | 223700 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.08.2023 | n/a | n/a |  | FOR INSPECTION
23060619 | DSLR, LAPTOP AND PRINTER | [19 empty] | use of PENRO | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1367 | SPARE PARTS | [19 empty] | PEO- | PB | 03.21.2023 | 04.24.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 05.17.2023 | 06.06.2023 | 06.23.2023 | 06.27.2023 |  |  | GF | 1795645 | 1795645 |  | 1227045 | 1227045 |  | Mr. Allan Rey N. Esmael | 04.26.2023 | n/a | 05.08.2023 | n/a | n/a
23060627 | [20 empty] | Motorpool | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0227 | RICEV (WELL MILLED) 50 KG/SACK | [19 empty] | PGO for the | PB | n/a | 04.24.2023 | n/a | 05.16.2023 | 05.16.2023 | 05.16.2023 | 05.17.2023 | 06.07.2023 |  |  |  |  | GF | 420000 | 420000 |  | 419400 | 419400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.11.2023 | n/a | n/a |  | FOR PO APPROVAL
23060628 | [20 empty] | use of PHO | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0416 | RICEV (WELL MILLED) 50 KG/SACK | [19 empty] | PGO | PB | n/a | 04.24.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 05.17.2023 | 06.07.2023 | 06.22.2023 | 06.30.2023 |  |  | GF | 2658600 | 2658600 |  | 2658600 | 2658600 |  | Mr. Allan Rey N. Esmael | 04.26.2023 | n/a | 05.08.2023 | n/a | n/a |  | FOR DELIVERY COMPLETION
23060629 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0460 | FEEDS | [19 empty] | PVO | PB | n/a | 04.24.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 05.17.2023 | 06.09.2023 | 06.14.2023 | 06.19.2023 |  |  | GF | 1165743 | 1165743 |  | 1085470 | 1085470 |  | Mr. Allan Rey N. Esmael | 04.26.2023 | n/a | 05.08.2023 | n/a | n/a |  | FOR DELIVERY COMPLETION
23060630 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1549 | CONSTRUCTION SUPPLIES | [19 empty] | PEO | PB | n/a | 05.08.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 05.17.2023 | 06.06.2023 | 06.22.2023 |  |  |  | GF | 1163438 | 1163438 |  | 1107001 | 1107001 |  | Mr. Allan Rey N. Esmael | 04.26.2023 | n/a | 05.08.2023 | n/a | n/a
23060631 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0488 | OFFICE EQUIPMENT | [19 empty] | PGO | PB | n/a | 05.15.2023 | n/a | 05.30.2023 | 05.30.2023 | 05.30.2023 | 06.09.2023 | 06.19.2023 | 06.26.2023 | 06.29.2023 |  |  | GF | 810504 | 810504 |  | 689500 | 689500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.25.2023 | n/a | n/a
23060661 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0270 | OFFICE EQUIPMENT | [19 empty] | PGO | PB | n/a | 05.15.2023 | n/a | 05.30.2023 | 05.30.2023 | 05.30.2023 | 06.09.2023 | 06.26.2023 | 06.29.2023 |  |  |  | GF | 220620 | 220620 |  | 196500 | 196500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.25.2023 | n/a | n/a |  | FOR SERVE
23060662 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0516 | TIRES TUBELESS | [19 empty] | PEEMO | PB | n/a | 05.15.2023 | n/a | 05.30.2023 | 05.30.2023 | 05.30.2023 | 06.09.2023 | 06.13.2023 | 06.23.2023 | 06.23.2023 |  |  | GF | 334344 | 334344 |  | 284200 | 284200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.25.2023 | n/a | n/a |  | FOR DELIVERY
23060663 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
Engr. Michael C. Salarda
23-C0523 | HYGIENE SUPPLIES | [19 empty] | PDRRMO | PB | n/a | 05.19.2023 | n/a | 05.30.2023 | 05.30.2023 | 05.30.2023 | 06.09.2023 | 06.22.2023 | 06.23.2023 | 07.04.2023 |  |  | GF | 659800 | 659800 |  | 590250 | 590250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 05.25.2023 | n/a | n/a
23060664 | [41 empty] | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0439 | HEMATOLOGY ANALYZER | [19 empty] | PEEMO | DC | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.15.2023 | 06.20.2023 |  |  | GF | 1765998 | 1765998 |  | 1539588 | 1539588 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23050614 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1547 | MEALS AND SNACKS WITH | [19 empty] | PGO | NP | n/a | 05.05.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.07.2023 | 06.15.2023 | 06.20.2023 |  |  | GF | 181830 | 181830 |  | 179550 | 179550 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050548 | ACCOMMODATIION WITHIN TAGUM CITY | [20 empty] | TWO FAILED | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[22 empty] | BIDDINGS | [13 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0125 | MEALS WITH ACCOMMODATION AND | [19 empty] | PDRRMO | NP | 03.21.2023 | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.06.2023 |  |  |  |  | GF | 2284480 | 2284480 |  | 2206600 | 2206600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23050550 | VENUE B (WITHIN DAVAO CITY) | [20 empty] | TWO FAILED | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[22 empty] | BIDDINGS | [13 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2976 | BEDDINGS | [19 empty] | PDRRMO | NP EMERGENCY | n/a | 05.26.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.06.2023 | 06.19.2023 | 06.20.2023 | 06.27.2023 | 06.27.2023 | GF | 51950 | 51950 |  | 51500 | 51500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050551 | [21 empty] | CASES | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0510 | PORTABLE SHOWER AND TOILET | [19 empty] | PDRRMO | NP EMERGENCY | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.06.2023 | 06.19.2023 |  |  |  | GF | 679368 | 679368 |  | 679368 | 679368 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR SERVE
23050552 | AND PLATIC SEPTIC TANK | [20 empty] | CASES | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2721 | MEALS AND SNACKS | [19 empty] | PDRRMO | SA | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 |  |  |  |  | GF | 197818 | 197818 |  | 197818 | 197818 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | REIMBURSEMENT
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2785 | OIL PRESSURE SENDER (GENERATOR SET) | [19 empty] | PDRRMO | SA | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 2900 | 2900 |  | 2900 | 2900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | REIMBURSEMENT
23050553 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2681 | SPAREPARTS | [19 empty] | PGSO | SA | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 | 06.22.2023 | 06.22.2023 | GF | 7736 | 7736 |  | 7736 | 7736 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050555 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0508 | SPAREPARTS | [19 empty] | PGSO | SA | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.22.2023 | 06.22.2023 | 06.22.2023 | GF | 19200 | 19200 |  | 19200 | 19200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050556 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2682 | SPAREPARTS | [19 empty] | PGSO | SA | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 | 06.20.2023 | 06.20.2023 | GF | 7443 | 7443 |  | 7443 | 7443 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050557 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2668 | SPAREPARTS | [19 empty] | PGSO | SA | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.22.2023 | 06.23.2023 | 06.23.2023 | GF | 8650 | 8650 |  | 8650 | 8650 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050558 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2683 | SPAREPARTS | [19 empty] | PGSO | SA | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.22.2023 | 06.23.2023 | 06.23.2023 | GF | 1150 | 1150 |  | 1150 | 1150 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050559 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2722 | BRAKE PAD AND BRAKE SHOE | [19 empty] | PGSO | SA | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.22.2023 | 06.23.2023 | 06.23.2023 | GF | 8570 | 8570 |  | 8570 | 8570 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050560 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2720 | BRAKE PAD | [19 empty] | PGSO | SA | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.22.2023 | 06.23.2023 | 06.23.2023 | GF | 4070 | 4070 |  | 4070 | 4070 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050561 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2559 | OFFICE SUPPLIES | [19 empty] | PGO | SB | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 |  |  |  |  | GF | 36315 | 36315 |  | 36165 | 36165 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23050564 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2565 | OFFICE SUPPLIES | [19 empty] | PGO | SB | n/a | 04.26.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 | 06.26.2023 | 06.26.2023 | GF | 10000 | 10000 |  | 10000 | 10000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050568 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0892 | LABORATORY SUPPLIES | [19 empty] | PENRO | SVP | n/a | 03.28.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.21.2023 |  |  |  | 58960 | 58960 |  | 58310 | 58310 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050570 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0400 | LABOTATORY SUPPLIES | [19 empty] | PENRO | SVP | n/a | 03.28.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.21.2023 |  |  |  | 71807 | 71807 |  | 71350 | 71350 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050571 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0312 | JANITORIAL SUPPLIWA | [19 empty] | PGSO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.13.2023 | 06.19.2023 |  |  |  |  | 244184 | 244184 |  | 243868 | 243868 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR SERVE
23050572 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0221 | REPAIRS AND MAINTAIANCE-MACHINERY | [19 empty] | SPO | SVP | n/a | 04.13.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 |  |  |  | 40394 | 40394 |  | 39990 | 39990 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050574 | AND EQUIPMENT | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2582 | LABORATORY SUPPLIES | [19 empty] | PENRO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 |  |  |  | 39748 | 39748 |  | 39645 | 39645 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050575 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0088 | OFFICE SUPPLIES | [19 empty] | PEO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.30.2023 | n/.a | n/a | 06.07.2023 | 06.19.2023 | 06.20.2023 | 06.30.2023 | 06.30.2023 |  | 280485 | 280485 |  | 278287 | 278287 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050576 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0435 | OTHER MACHINERIES AND EQUIPMENT | [19 empty] | PGSO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.06.2023 | 06.19.2023 | 06.20.2023 | 06.29.2023 | 06.29.2023 |  | 243361 | 243361 |  | 241406 | 241406 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050577 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0483 | OFFICE SUPPLIES | [19 empty] | PAO | SVP | n/a | 04.26.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.15.2023 | 06.20.2023 | 06.26.2023 | 06.26.2023 |  | 22000 | 22000 |  | 22000 | 22000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050580 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0380 | MEALS AND SNACKS | [19 empty] | PGO | SVP | n/a | 04.26.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.15.2023 | 06.20.2023 |  |  |  | 53620 | 53620 |  | 49046 | 49046 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050581 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1134 | MINERAL WATER | [19 empty] | PGO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.15.2023 | 06.20.2023 |  |  |  | 6150 | 6150 |  | 6000 | 6000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050582 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2487 | MINERAL WATER | [19 empty] | PGO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 |  |  |  | 15375 | 15375 |  | 15000 | 15000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050583 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0501 | VETERINARY SUPPLIES | [19 empty] | PDRRMO | SVP | n/a | 04.24.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.21.2023 |  |  | GF | 21410 | 21410 |  | 21200 | 21200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050587 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0468 | MEALS AND SNACKS WITHOUT VENUE | [19 empty] | PDRRMO | SVP | 05.02.2023 | 05.05.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 50684 | 50684 |  | 49415 | 49415 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050588 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2684 | CONSTRUCTION SUPPLIES | [19 empty] | SEF | SVP | n/a | 05.05.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.23.2023 | 06.30.2023 |  |  | GF | 80740.49 | 80740.49 |  | 80703.49 | 80703.49 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050590 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
Engr. Michael C. Salarda
23-C0223 | MEDICAL SUPPLIES | [19 empty] | PGO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 |  |  |  |  | GF | 436762 | 436762 |  | 427925 | 427925 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23050591 | [41 empty] | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0397 | FUEL FILTERS | [19 empty] | PEEMO | SVP | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.06.2023 | 06.23.2023 | 06.27.2023 |  |  | GF | 119221 | 119221 |  | 118350 | 118350 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR DELIVERY
23050592 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2457 | GARMENTS | [19 empty] | PGO | SVP | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 14000 | 14000 |  | 13972 | 13972 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050593 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2008 | PRINTING | [19 empty] | PAO | SVP | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 1400 | 1400 |  | 1337.5 | 1337.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050594 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2569 | SINGLET | [19 empty] | PGO | SVP | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 |  |  |  |  | GF | 30000 | 30000 |  | 30000 | 30000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23050595 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2762 | MEALS WITH SNACKS | [19 empty] | PGO | SVP | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.15.2023 | 06.16.2023 |  |  | GF | 346500 | 346500 |  | 340000 | 340000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050596 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 | [5 empty] | Engr. Michael C. Salarda
23-C0384 | ELECTRICAL SUPPLIES | [19 empty] | PEEMO | SVP | 03.24.2023 | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.06.2023 | 06.19.2023 | 06.20.2023 | 06.13.2023 | 06.13.2023 | GF | 187834 | 187834 |  | 186130 | 186130 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050598 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 | [5 empty] | Engr. Michael C. Salarda
23-C0398 | JANITORIAL SUPPLIES | [19 empty] | PASSO | SVP | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.06.2023 | 06.19.2023 | 06.20.2023 | 06.30.2023 | 06.30.2023 | GF | 21945 | 21945 |  | 21666 | 21666 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050599 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0493 | PLAQUE AND TOKEN | [19 empty] | PAO | SVP | 04.19.2023 | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 06.06.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 54100 | 54100 |  | 53110 | 53110 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050600 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1735 | OFFICE SUPPLIES | [19 empty] | PASSO | SVP | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 |  |  | GF | 49200 | 49200 |  | 48000 | 48000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050601 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0477 | MINERAL WATER | [19 empty] | PAO | SVP | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.15.2023 | 06.19.2023 |  |  | GF | 3280 | 3280 |  | 3200 | 3200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050603 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0518 | SPAREPARTS | [19 empty] | PEEMO | SVP | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 | 06.26.2023 | 06.26.2023 | GF | 36300 | 36300 |  | 35920 | 35920 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050604 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2558 | JANITORIAL SUPPLIES | [19 empty] | PGO | SVP | n/a | 04.26.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 |  |  |  |  | GF | 2430 | 2430 |  | 2400 | 2400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23050605 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0396 | PRINTING | [19 empty] | PGO | SVP | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 |  |  |  |  | GF | 29680 | 29680 |  | 28090 | 28090 |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | FOR PO APPROVAL
23050606 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0515 | PRINTING | [19 empty] | PEO | SVP | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.23.2023 | 06.26.2023 |  |  | GF | 5376 | 5376 |  | 5088 | 5088 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR COMPLETION OF DELIVERY
23050607 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2493 | SPAREPARTS | [19 empty] | PICTO | SVP | n/a | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.22.2023 |  |  | GF | 28500 | 28500 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050608 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2656 | JANITORIAL SUPPLIES | [19 empty] | PDRRMO | SVP | 05.02.2023 | 05.22.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 | 06.26.2023 | 06.26.2023 | GF | 5950 | 5950 |  | 5950 | 5950 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050609 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0504 | JANITORIAL SUPPLIES | [19 empty] | PBO | SVP | n/a | 05.05.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.19.2023 | 06.20.2023 | 06.26.2023 | 06.26.2023 | GF | 7558 | 7558 |  | 7522 | 7522 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23050610 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0531 | OFFICE EQUIPMENT | [19 empty] | PAO | SVP | n/a | 05.26.2023 | n/a | n/a | 05.30.2023 | n/a | n/a | 05.30.2023 | 06.06.2023 | 06.07.2023 |  |  | GF | 78040 | 78040 |  | 78010 | 78010 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR COMPLETION OF DELIVERY
23050611 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3097 | OFFICE SUPPLIES | [19 empty] | PVGO | SB | 06.13.2023 | [11 empty] | GF | 10000 | 10000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3008 | BRAKE PAD, FOR MITS, STRADA (GLS 2.4) | [19 empty] | SPO | SA | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 4070 | 4070 |  | 4070 | 4070 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060679 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0541 | BRAKE PAD | [19 empty] | SPO | SA | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 1700 | 1700 |  | 1700 | 1700 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060678 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2807 | SPARE PARTS | [19 empty] | PGSO | SA | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 82300 | 82300 |  | 82300 | 82300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060677 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0534 | CONSTRUCTION MATERIALS | [19 empty] | PGSO | SVP | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 234203 | 234203 |  | 233864 | 233864 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060707 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1588 | CONSTRUCTION MATERIALS | [19 empty] | PGSO | SVP | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 212596 | 212596 |  | 212596 | 212596 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060706 | (PLUMBING SUPPLIES) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2737 | ELECTRICAL SUPPLIES | [19 empty] | PGSO | SVP | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 112900 | 112900 |  | 112180 | 112180 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060705 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2960 | PHOTOCOPY OF DOCUMENTS | [19 empty] | PHO | SA | 06.13.2023 | [11 empty] | GF | 14710 | 14710 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3157 | COMPUTER SUPPLIES | [19 empty] | PBO | SVP | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 11991 | 11991 |  | 11970 | 11970 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060704 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3040 | OFFICE SUPPLIES FOR THE USE OF | [19 empty] | PEO- | SB | 06.13.2023 | [11 empty] | GF | 14004 | 14004 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060700 | MOTORPOOL | [19 empty] | Motorpool | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0420 | ADBLUE, 20 ltr/s | [19 empty] | PEO- | SVP | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 282875 | 282875 |  | 279750 | 279750 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060711 | [20 empty] | Motorpool | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3039 | CONTINOUS INK SUPPLY SYSTEM | [19 empty] | PEO- | SB | 06.13.2023 | [11 empty] | GF | 5696 | 5696 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060699 | [20 empty] | Motorpool | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3101 | WHEEL ALIGNMENT AND WHEEL | [19 empty] | PGSO | SA | 06.13.2023 | 06.19.2023 | n/a | n/;a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 4500 | 4500 |  | 4500 | 4500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060676 | BALANCING | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3021 | JOB ORDER | [19 empty] | PGSO | SA | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 10500 | 10500 |  | 10500 | 10500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060675 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3019 | SPARE PARTS | [19 empty] | PGSO | SA | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 78500 | 78500 |  | 78500 | 78500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060674 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3018 | BRAKE PAD, FOR MITS, STRADA | [19 empty] | PGSO | SA | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 4070 | 4070 |  | 4070 | 4070 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060673 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0544 | SPARE PARTS FOR LIGHT VEHICLE | [19 empty] | PGSO | SA | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 52995 | 52995 |  | 52995 | 52995 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060672 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3023 | WHEEL HUB BEARING ASSY. | [19 empty] | PGSO | SA | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 9600 | 9600 |  | 9600 | 9600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | CASH ADVANCE
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3020 | JOB OUT | [19 empty] | PGSO | SA | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 700 | 700 |  | 700 | 700 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3015 | BEARINGS, HUB (FRONT & REAR), BRAKE | [19 empty] | PGSO | SA | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 3350 | 3350 |  | 3350 | 3350 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060670 | SHOE (XRM 125) AND SWITCH, FOOT | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| BRAKE | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3014 | SPARE PARTS FOR LIGHT VEHICLE | [19 empty] | PGSO | SA | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 10002 | 10002 |  | 10002 | 10002 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060668 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3022 | WIPER BLADE FOR STRD | [19 empty] | PGSO | SA | 06.13.2023 | 06.19.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 850 | 850 |  | 850 | 850 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060667 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3013 | MEDAL | [19 empty] | PGSO | SVP | 06.13.2023 | 06.23.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 399000 | 399000 |  | 399000 | 399000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060717 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0556 | OFFICE SUPPLIES | [19 empty] | PBO | SB | n/a | 06.13.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 399000 | 399000 |  | 399000 | 399000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060698 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0559 | FUEL, OIL AND LUBRICANTS | [19 empty] | SPO | PB | 06.13.2023 | [11 empty] | GF | 360440 | 360440 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0438 | LABORATORY SUPPLIES/REAGENT | [19 empty] | PEEMO | DC | 06.13.2023 | [11 empty] | GF | 828222 | 828222 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0530 | CTNL (TROPONIN) AND HEMOGLOBIN | [19 empty] | PEEMO | PB | 06.13.2023 | [11 empty] | GF | 969608 | 969608 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| A1C | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3118 | JOB ORDER: FURNISHING LABOR AND | [19 empty] | PGO | SVP | 06.13.2023 | [11 empty] | GF | 180000 | 180000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO RO
| MATERIALS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2967 | SPARE PARTS FOR THE USE OF PNP | [19 empty] | PGO | SVP | 06.13.2023 | [11 empty] | GF | 9093 | 9093 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| PERSONNEL | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2966 | DIAGNOSE TRANSMISSION MALFUNCTION | [19 empty] | PGO | SVP | 06.13.2023 | [11 empty] | GF | 25000 | 25000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | ENDORSE TO PGSO
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator | [6 empty] | FOR FURTHER
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda | [6 empty] | EVALUATION
23-C0470 | OFFICE SUPPLIES | [19 empty] | PDRRMO | SB | n/a | 05.22.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 | 06.29.2023 |  |  | GF | 26977 | 26977 |  | 26937 | 26937 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060636 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0513 | OFFICE SUPPLIES | [19 empty] | PICTO | SB | n/a | 05.22.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 | 06.29.2023 |  |  | GF | 7840 | 7840 |  | 7825 | 7825 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060637 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0484 | OFFICE SUPPLIES | [19 empty] | PGO | SB | n/a | 05.22.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.22.2023 | 06.23.2023 | 06.30.2023 | 06.30.2023 | GF | 36544 | 36544 |  | 36262 | 36262 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060638 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0537 | OFFICE SUPPLIES | [19 empty] | PHO | SB | n/a | 06.02.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 | 06.27.2023 |  |  | GF | 91401 | 91401 |  | 90791 | 90791 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR COMPLETION OF DELIVERY
23060639 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0118 | PRINTING | [19 empty] | PHO | SVP | n/a | 05.05.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.21.2023 | 06.22.2023 | 06.23.2023 |  | GF | 55916 | 55916 |  | 51922 | 51922 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060644 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2714 | JANITORIAL SUPPLIES | [19 empty] | PICTO | SVP | n/a | 05.22.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 | 06.29.2023 |  |  | GF | 10150 | 10150 |  | 10140 | 10140 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060646 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2798 | PRINTED FORMS | [19 empty] | PPDO | SVP | n/a | 05.22.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 | 06.26.2023 |  |  | GF | 20900 | 20900 |  | 20900 | 20900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060647 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2711 | ELECTRICAL SUPPLIES | [19 empty] | PICTO | SVP | n/a | 05.22.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 | 06.26.2023 |  |  | GF | 7590 | 7590 |  | 7584 | 7584 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060648 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0375 | AGRICULTURAL SUPPLIES | [19 empty] | PDRRMO | SVP | n/a | 05.22.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 | 06.27.2023 |  |  | GF | 272716 | 272716 |  | 269970 | 269970 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060649 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1535 | LUMBER/CEMENT | [19 empty] | PEO | SVP | n/a | 05.22.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.26.2023 | 06.27.2023 |  |  | GF | 110447.85 | 110447.85 |  | 110053.18 | 110053.18 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060650 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1557 | LUMBER/CEMENT | [19 empty] | PEO | SVP | n/a | 05.22.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.21.2023 | 06.26.2023 | 06.27.2023 |  |  | GF | 101805 | 101805 |  | 101462.5 | 101462.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060651 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1679 | CONSTRUCTION SUPPLIES | [19 empty] | PEO | SVP | n/a | 05.22.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 |  |  |  |  | GF | 30300 | 30300 |  | 29900 | 29900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060652 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2579 | LABORATORY SUPPLIES | [19 empty] | PENRO | SVP | n/a | 06.02.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.21.2023 | 06.23.2023 |  |  | GF | 30300 | 30300 |  | 29900 | 29900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060653 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2996 | FOOD SUPPLIES | [19 empty] | PHO | SVP | n/a | 06.02.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 | 06.27.2023 |  |  | GF | 50010 | 50010 |  | 48343 | 48343 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
23060665 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2965 | FURNITURES & FIXTURES | [19 empty] | PGO | SVP | n/a | 06.02.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.20.2023 | 06.29.2023 |  |  |  | GF | 133500 | 133500 |  | 132000 | 132000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR SERVE
23060655 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2978 | OTHER SUPPLIES/MATERIALS | [19 empty] | PGO | SVP | n/a | 06.02.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.20.2023 | 06.22.2023 | 06.26.2023 | 06.26.2023 | 06.26.2023 | GF | 133500 | 133500 |  | 132000 | 132000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR SERVE
23060666 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2975 | FOOD/CATERING SERVICES | [19 empty] | PGO | SVP | n/a | 06.02.2023 | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.21.2023 | 06.22.2023 |  |  | GF | 133500 | 133500 |  | 132000 | 132000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR SERVE
23060658 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0545 | PLUMBING SUPPLIES | [19 empty] | PDRRMO | NP-Emergency | n/a | n/a | n/a | n/a | 06.13.2023 | n/a | n/a | 06.13.2023 | 06.23.2023 |  |  |  | GF | 70631 | 70631 |  | 39068 | 39068 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR SERVE
23060656 | [21 empty] | cases | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
Engr. Michael C. Salarda
23-C0563 | MEALS AND SNACKS (LIGHT) WITH | [19 empty] | PHRMO | SVP | 06.20.2023 | [11 empty] | GF | 285772 | 285772 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| VENUE | [40 empty] | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3206 | T-SHIRT JERSEY SUBLIMATION | [19 empty] | PGO-PS | SVP | 06.20.2023 | [11 empty] | GF | 7000 | 7000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[21 empty] | SPORTS | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[21 empty] | DIVISION | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3156 | 100W SOLAR LIGHT OUTDOOR WATER- | [19 empty] | PGO-PS | PB | 06.20.2023 | [11 empty] | GF | 3300000 | 3300000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a
| PROOF LED | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0543 | RICE (WELL MILLED) 50kg/sack | [19 empty] | PGO | PB | 06.20.2023 | [11 empty] | GF | 1007300 | 1007300 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0358 | DP BLACK INK, DA 14, INK, BLACK DA14 | [19 empty] | PEEMO | DC | 06.20.2023 | [11 empty] | GF | 17053 | 17053 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| 600 ml AND MASTER ROLL DRA 12 | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2999 | UTILITY/PLASTIC BOX (20 ltrs.) | [19 empty] | PACCO | SVP | 06.20.2023 | [11 empty] | GF | 79605 | 79605 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2700 | JANITORIAL SUPPLIES | [19 empty] | PACCO | SVP | 06.20.2023 | [11 empty] | GF | 24289 | 24289 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3289 | TARPAULIN-AS PER DESIGN | [19 empty] | PEO | NP | 06.20.2023 | n/a | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 1792 | 1792 |  | 1664 | 1664 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060714 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3248 | TARPAULIN-AS PER DESIGN | [19 empty] | PEO | SVP | 06.20.2023 | 06.23.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 1792 | 1792 |  | 1664 | 1664 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060712 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3247 | GEMELINA LUMBER OR EQUIVALENT | [19 empty] | PEO | SVP | 06.20.2023 | [11 empty] | GF | 71242.51 | 71242.51 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3129 | PROVISION AND INSTALLATION OF SOLAR | [19 empty] | PEO | PB | 06.20.2023 | [11 empty] | GF | 296539.37 | 296539.37 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a
| POWER AT MABUGNAO ES, MARAGUSAN | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3151 | PROVISION AND INSTALLATION OF SOLAR | [19 empty] | PEO | PB | 06.20.2023 | [11 empty] | GF | 296539.37 | 296539.37 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a
| POWER AT SINGANAN PS, MACO | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3130 | PROVISION AND INSTALLATION OF SOLAR | [19 empty] | PEO | PB | 06.20.2023 | [11 empty] | GF | 296539.37 | 296539.37 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a
| POWER POWER AT SAN ISIDRO IS, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| MONKAYO | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2995 | RICE 50kg (WITH IRON FORTIFIED) | [19 empty] | PHO | PB | 06.20.2023 | [11 empty] | GF | 360000 | 360000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1824 | JOB ORDER: LABOR AND INSTALLATION | [19 empty] | PAO-IPRD | PB | 06.20.2023 | [11 empty] | GF | 3655000 | 3655000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | RETURN TO RO FOR THE
| OF RADIO STATION (PHASE 1) | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator | [6 empty] | EVALUATION OF TERMS &
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda | [6 empty] | CONDITION
23-C0526 | SUPPLY AND DELIVERY OF TIRES | [19 empty] | PDRRMO | PB | n/a | 06.05.2023 | n/a | 06.13.2023 | 06.13.2023 | 06.13.2023 | 06.15.2023 | 06.21.2023 |  |  |  |  | GF | 451976 | 451976 |  | 330400 | 330400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 06.08.2023 | n/a | n/a |  | FOR PO APPROVAL
23060695 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2536 | COMPUTER SUPPLIES | [19 empty] | PGO | SB | n/a | 05.22.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 3125 | 3125 |  | 3125 | 3125 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060680 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2713 | OTHER SUPPLIES | [19 empty] | PICTO | SVP | n/a | 05.22.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 13200 | 13200 |  | 12000 | 12000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060682 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2524 | OTHER SUPPLIES | [19 empty] | PGO | SVP | n/a | 05.22.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 18000 | 18000 |  | 18000 | 18000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060683 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2492 | COMPUTER SUPPLIES | [19 empty] | PICTO | SVP | n/a | 05.22.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 21120 | 21120 |  | 21120 | 21120 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060684 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0144 | SPAREPARTS | [19 empty] | PHO | SVP | n/a | 05.22.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 49461.25 | 49461.25 |  | 49304 | 49304 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060685 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0382 | WATER | [19 empty] | PEEMO | SVP | n/a | 06.02.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 45100 | 45100 |  | 44000 | 44000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060687 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2758 | FOOD SUPPLIES | [19 empty] | PDRRMO | SVP | n/a | 06.02.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 280430 | 280430 |  | 279931.04 | 279931.04 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060688 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0540 | PRINTING | [19 empty] | PEO | SVP | n/a | 06.02.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 8960 | 8960 |  | 8640 | 8640 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060689 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3119 | FOOD/CATERING SERVICES | [19 empty] | PGO | SVP | n/a | 06.02.2023 | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 74520 | 74520 |  | 72900 | 72900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060690 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0589 | PLUMBING SUPPLIES | [19 empty] | PEO | NP-Emergency | n/a | n/a | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 567438.51 | 567438.51 |  | 560696.51 | 560696.51 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060691 | [21 empty] | Cases | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2760 | FOOD/CATERING SERVICES | [19 empty] | PDRRMO | NP-Emergency | n/a | n/a | n/a | n/a | 06.20.2023 | n/a | n/a | 06.20.2023 |  |  |  |  | GF | 457860 | 457860 |  | 451530 | 451530 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060692 | [21 empty] | Cases | [13 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1623 | 1 LOT CONSTRUCTION OF GYM WITH | [19 empty] | PEO | PB | 03.21.2023 | 04.18.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 06.15.2023 | 06.29.2023 | 07.03.2023 |  |  |  | GF | 1897678.28 | 1897678.28 |  | 1872753.19 | 1872753.19 |  | Mr. Allan Rey N. Esmael | 04.26.2023 | n/a | 05.11.2023 | n/a | n/a |  | FOR NTP
CW23-007 | BLEACHER AT PUROK 2, CONCEPCION, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| MACO | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1837 | 1 LOT CONSTRUCTION OF MULTIPURPOSE | [19 empty] | PEO | PB | 03.21.2023 | 04.18.2023 | 05.12.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 06.15.2023 | 06.20.2023 |  |  |  |  | GF | 1394873.65 | 1394873.65 |  | 1394583.49 | 1394583.49 |  | Mr. Allan Rey N. Esmael | 05.05.2023 | n/a | 05.11.2023 | n/a | n/a |  | FOR CONTRACT SIGNING
CW23-014 | HALL, MAGNAGA NHS, BRGY. MAGNAGA, | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| PANTUKAN | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-1984 | 1 LOT CONSTRUCTION OF 1 STOREY 4 | [19 empty] | PEO | PB | 04.04.2023 | 04.18.2023 | 05.02.2023 | 05.16.2023 | 05.16.2023 | 05.16.2023 | 06.15.2023 | 06.29.2023 |  |  |  |  | GF | 3901087.09 | 3901087.09 |  | 3860799.32 | 3860799.32 |  | Mr. Allan Rey N. Esmael | 04.26.2023 | n/a | 05.11.2023 | n/a | n/a |  | FOR CONTRACT SIGNING
CW23-017 | CLASSROOM BLDG. WITH COMFORT ROOM | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| ATTACHED | [34 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2901 | DUBLICATING PRODUCTS | [19 empty] | PACCO | DC | n/a | 06.20.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 16200 | 16200 |  | 16200 | 16200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060715 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3012 | JOB ORDER (LABOR & MATERIALS) | [19 empty] | PGO | DC | n/a | 06.20.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 9740 | 9740 |  | 9740 | 9740 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060716 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2228 | OFFICE EQUIPMENT | [19 empty] | PHO | SVP | n/a | 06.13.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 28500 | 28500 |  | 28200 | 28200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060701 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3099 | OFFICE EQUIPMENT | [19 empty] | PBO | SVP | n/a | 06.13.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 15400 | 15400 |  | 15200 | 15200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060702 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3041 | JANITORIAL SUPPLIES | [19 empty] | PEO | SVP | n/a | 06.13.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 9062 | 9062 |  | 8770 | 8770 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060703 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3203 | FOOD SUPPLIES | [19 empty] | SPO | SVP | n/a | 06.19.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 7809 | 7809 |  | 7744.5 | 7744.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060708 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-0846 | OTHER SUPPLIES/MATERIALS | [19 empty] | PHO | SVP | n/a | 06.19.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 6000 | 6000 |  | 5800 | 5800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060709 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3250 | OFFICE EQUIPMENT | [19 empty] | PGO | SVP | n/a | 06.19.2023 | n/a | n/a | 06.27.2023 | n/a | n/a | 06.27.2023 |  |  |  |  | GF | 12300 | 12300 |  | 12200 | 12200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR PO APPROVAL
23060710 | [35 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3416 | OFFICE SUPPLIES | [19 empty] | PGO | SB | 06.27.2023 | [11 empty] | GF | 153194 | 153194 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0554 | MEALS AND SNACKS WITH VENUE | [19 empty] | PGO | SVP | 06.27.2023 | [11 empty] | GF | 156000 | 156000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0555 | MEALS AND SNACKS WITH VENUE | [19 empty] | PGO | PB | 06.27.2023 | [11 empty] | GF | 508500 | 508500 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | FOR POSTING
| AND ACCOMMODATION | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-2244 | MEALS AND SNACKS WITH ACCOMMO- | [19 empty] | PGO | SVP | 06.27.2023 | [11 empty] | GF | 97500 | 97500 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR POSTING
| DATION A | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0547 | OFFICE SUPPLIES | [19 empty] | PVGO | SB | 06.27.2023 | [11 empty] | GF | 14980 | 14980 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR POSTING
[39 empty] | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0580 | CONSIGNMENT OF DRUGS AND MEDICINE | [19 empty] | PEEMO | PB | 06.27.2023 | [11 empty] | GF | 6197937.4 | 6197937.4 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | FOR POSTING
| (SLOW MOVING DRUGS | [34 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0585 | CONSIGNMENT OF DRUGS AND MEDICINE | [19 empty] | PEEMO | NP | 06.27.2023 | [11 empty] | GF | 3494681.2 | 3494681.2 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-C0593 | SPARE PARTS | [19 empty] | PGSO | SA | 06.27.2023 | [11 empty] | GF | 5730 | 5730 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[36 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
23-3305 | SPARE PARTS | [19 empty] | PGSO | SA | 06.27.2023 | [11 empty] | GF | 11700 | 11700 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3391 | GEMELINA LUMBER OR EQUIVALENT | [19 empty] | PEO(SEF) | SVP | 06.27.2023 | [11 empty] | TF | 10089.96 | 10089.96 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3301 | CONSTRUCTION MATERIALS | [19 empty] | PEO(SEF) | SVP | 06.27.2023 | [11 empty] | GF | 21801.5 | 21801.5 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3273 | OIL AND LUBRICANTS | [19 empty] | PEO(SEF) | PB | 06.27.2023 | [11 empty] | GF | 4367830.5 | 4367830.5 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3272 | SPAREPARTS (REPAIR AND MAIN- | [19 empty] | PEO- | SA | 06.27.2023 | [11 empty] | GF | 200000 | 200000 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
| TAINACE | [19 empty] | Motorpool | [14 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3271 | ACETYLENE REFILL AND OXYGEN | [19 empty] | PEO- | DC | 06.27.2023 | [11 empty] | GF | 45075 | 45075 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[21 empty] | Motorpool | [14 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-C0525 | MEALS AND SNACKS WITH | [19 empty] | PDRRMO | PB | 06.27.2023 | [11 empty] | GF | 3281000 | 3281000 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
| ACCOMMODATION | [34 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-C0505 | MEALS AND SNAKS | [19 empty] | PDRRMO | PB | 06.27.2023 | [11 empty] | GF | 890483 | 890483 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3346 | MEALS AND SNACKS WITH | [19 empty] | PDRRMO | SVP | 06.27.2023 | [11 empty] | GF | 270000 | 270000 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
| ACCOMMODATION | [34 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-1430 | GLOBAL POSITIONING SYSTEM | [19 empty] | PDRRMO | SVP | 06.27.2023 | [11 empty] | GF | 57500 | 57500 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3259 | ACETYLENE REFILL AND INDUSTRIAL | [19 empty] | PAGRO | DC | 06.27.2023 | [11 empty] | GF | 39655 | 39655 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
| OXYGEN REFILL | [34 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-C0575 | OFFICE SUPPLIES | [19 empty] | PAGRO | SB | 06.27.2023 | [11 empty] | GF | 132571 | 132571 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3001 | LPG GAS REFILL | [19 empty] | PAGRO | DC | 06.27.2023 | [11 empty] | GF | 3924 | 3924 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3139 | CLOUD SERVER SUBSCRIPTION | [19 empty] | PICTO | PB | 06.27.2023 | [11 empty] | GF | 513190.86 | 513190.86 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-2705 | SPARE PARTS OF COMMUNICATION | [19 empty] | PDRRMO | PB | 06.27.2023 | [11 empty] | GF | 688750 | 688750 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3332 | JANITORIAL SUPPLIES | [19 empty] | PIAO | SVP | 06.27.2023 | [11 empty] | GF | 7717 | 7717 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3172 | AIRCON COMPRESSOR 3TR MODEL | [19 empty] | PENRO | SVP | 06.27.2023 | [11 empty] | GF | 35000 | 35000 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3411 | SEPTIC TANK CLEANING AND | [19 empty] | PHO | SVP | 06.27.2023 | [11 empty] | GF | 9000 | 9000 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
| SILPHONING | [34 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3441 | TARPAULIN-AS PER DESIGN | [19 empty] | PEO | SVP | 06.27.2023 | [11 empty] | GF | 1792 | 1792 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
23-3431 | CWN NAILS, GEMELINA LUMBER OR | [19 empty] | PEO | SVP | 06.27.2023 | [11 empty] | GF | 4212 | 4212 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
| EQUIVALENT AND ORDINARY PLYWOOD | [34 empty] | 0 |  |  | 0
| TYPE II | [34 empty] | 0 |  |  | 0
23-3454 | MEDICAL OXYGEN REFILL | [19 empty] | PDRRMO | DC | 06.27.2023 | [11 empty] | GF | 21750 | 21750 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | FOR POSTING
[36 empty] | 0 |  |  | 0
[36 empty] | 0 |  |  | 0
Total Alloted Budget of Procurement Activities | [35 empty] | Php 249, 992, 237.53
Total Contract Price of Procurement Activities Conducted | [35 empty] | Php 226, 831, 471.22
Total Savings(Total Alloted Budget-Total Contract Price) | [35 empty] | Php 23, 160, 766.31
Prepared by: | [23 empty] | Checked by: | [7 empty] | Recommended for Approval by : | [7 empty] | Approved by:
MELISSA N. SAMENTAR | [23 empty] | JENES B. MIÑOZA, MPA | [7 empty] | ROLANDO S. SIMENE, DVM, MRDM | [6 empty] | GOV. DOROTHY P. MONTEJO-GONZAGA
CLERK II | [23 empty] | HEAD BAC SECRETARIAT | [8 empty] | BAC CHAIRPERSON | [6 empty] | HEAD OF THE PROCURING ENTITY

## Sheet3
[6 empty] | 2399227.92 |  | 2279270.51
2399227.92 |  |  |  |  | 2279270.51 | 1937753.2 |  | 1934245.57
1937753.2 |  |  |  |  | 1934245.57 | 4954026.15 |  | 4093839.9
4954026.15 |  |  |  |  | 4093839.9 | 4954026.15 |  | 4093839.9
4954026.15 |  |  |  |  | 4093839.9 | 3695208.25 |  | 3945070.71
3695208.25 |  |  |  |  | 3945070.71 | 1583224.96 |  | 1533241.65
1583224.96 |  |  |  |  | 1533241.65
1029200 |  |  |  | 1029200 |  | 1029200 |  | 1029200
18828107.57 |  |  | 666400 | 666400
18828107.57 | 18828107.57 |  | 659042 | 659042 |  | 18828107.57 |  | 20827090
18828107.57 | 18828107.57 |  | 9750824 | 9750824 |  | 2912879.05 |  | 2882860.9
18828107.57 | 18828107.57 |  | 9750824 | 9750824 |  | 65000 |  |  | 64500
2912879.05 |  | 2912879.05 | 2882860.9 |  | 2882860.9 | 12000 |  |  | 11500
65000 | 65000 |  | 64500 | 64500 |  | 399038 |  |  | 396698
12000 | 12000 |  | 11500 | 11500 |  | 3706042.5 |  |  | 3140312.5
399038 | 399038 |  | 396698 | 396698 |  | 240000 |  |  | 180000
3706042.5 | 3706042.5 |  | 3140312.5 | 3140312.5 |  | 676300 |  |  | 675750
403200 | 403200 |  | 0 |  |  | 1224950 |  |  | 1183950
360000 | 360000 |  | 0 |  | 20827090 | 5000000 |  |  | 4992082
240000 |  |  |  | 180000 |  | 103150 |  |  | 57650
676300 |  |  |  | 675750 |  | 6500000 |  |  | 5589999
1224950 |  |  |  | 1183950 |  | 160000 |  |  | 119000
5000000 |  |  |  | 4992082 |  | 189000 |  |  | 173880
4836 | 4836 |  | 0 |  |  | 906157 |  |  | 826228
4836 | 4836 |  | 0 |  |  | 6023 |  |  | 6023
4836 | 4836 |  | 0 |  |  | 9740 |  |  | 9740
4836 | 4836 |  | 0 |  |  | 63812 |  |  | 63812
4836 | 4836 |  | 0 |  |  | 16200 |  |  | 16200
4836 | 4836 |  | 0 |  |  | 2783700 |  |  | 2783700
4836 | 4836 |  | 0 |  |  | 4025000 |  |  | 4025000
4836 | 4836 |  | 0 |  |  | 4593 |  |  | 4440
15000 | 15000 |  | 0 |  |  | 82855 |  |  | 82755
29000 | 29000 |  | 0 |  |  | 7200 |  |  | 7170
18409 | 18409 |  | 0 |  |  | 16828 |  |  | 15626
6197 | 6197 |  | 0 |  |  | 16879.8 |  |  | 16800
3000 | 3000 |  | 0 |  |  | 30240 |  |  | 28917
0 |  |  | 0 |  |  | 28948 |  |  | 28917
10465 | 10465 |  | 0 |  |  | 26472 |  |  | 25652
28678 | 28678 |  | 0 |  |  | 172632 |  |  | 171300
18550 | 18550 |  | 0 |  |  | 58564 |  |  | 57596
4000 | 4000 |  | 0 |  |  | 103870 |  |  | 102870
4510 | 4510 |  | 0 |  |  | 8600 |  |  | 8100
103150 |  |  |  | 57650 |  | 6400 |  |  | 6385
6500000 |  |  |  | 5589999 |  | 4984 |  |  | 4895
160000 |  |  |  | 119000 |  | 100000 |  |  | 98000
189000 |  |  |  | 173880 |  | 41483 |  |  | 41391
906157 |  |  |  | 826228 |  | 505479 |  |  | 499855
6023 |  |  |  | 6023 |  | 47314 |  |  | 46160
9740 |  |  |  | 9740 |  | 1320 |  |  | 1315
63812 |  |  |  | 63812 |  | 45870 |  |  | 45375
16200 |  |  |  | 16200 |  | 13060 |  |  | 12905
2783700 |  |  |  | 2783700 |  | 11625 |  |  | 11250
4025000 |  |  |  | 4025000 |  | 5500 |  |  | 5250
4593 |  |  |  | 4440 |  | 1550000 |  |  | 1549000
82855 |  |  |  | 82755 |  | 1838827 |  |  | 1699067
7200 |  |  |  | 7170 |  | 1838827 |  |  | 1699067
16828 |  |  |  | 15626 |  | 1531087 |  |  | 1247416
16879.8 |  |  |  | 16800 |  | 1780000 |  |  | 1505000
30240 |  |  |  | 28917 |  | 200000 |  |  | 0
28948 |  |  |  | 28917 |  |  |  |  | 0
26472 |  |  |  | 25652 |  | 45075 |  |  | 45075
172632 |  |  |  | 171300 |  |  | 4989979.79 |  | 4844040.38
58564 |  |  |  | 57596 |  |  | 1549654.01 |  | 0
103870 |  |  |  | 102870 |  |  | 1216901.49 |  | 1198171.05
8600 |  |  |  | 8100 |  |  | 4839332.08 |  | 4789339.41
6400 |  |  |  | 6385 |  |  | 859977.4 |  | 0
4984 |  |  |  | 4895 |  |  | 4983677.95 |  | 4933595.15
100000 |  |  |  | 98000 |  |  | 11325045.94 |  | 11291501.41
41483 |  |  |  | 41391 |  | 3739970 |  |  | 2453165
505479 |  |  |  | 499855 |  | 5967036 |  |  | 5961543
47314 |  |  |  | 46160 |  | 160940 |  |  | 159862
1320 |  |  |  | 1315 |  | 337902 |  |  | 337396.77
45870 |  |  |  | 45375 |  | 782000 |  |  | 780000
13060 |  |  |  | 12905 |  | 281370 |  |  | 229680
11625 |  |  |  | 11250 |  | 838084 |  |  | 837560.25
5500 |  |  |  | 5250 |  | 800400 |  |  | 783000
1550000 |  |  |  | 1549000 |  | 386094 |  |  | 378085
1838827 |  |  |  | 1699067 |  | 551583 |  |  | 537675
1838827 |  |  |  | 1699067 |  | 90900 |  |  | 89000
1531087 |  |  |  | 1247416 |  | 856256 |  |  | 848590
1780000 |  |  |  | 1505000 |  | 580140 |  |  | 399180
200000 | [5 empty] | 245861 |  |  | 160817
0 | [5 empty] | 290532 |  |  | 237685
45075 |  |  |  | 45075 |  | 1709362 |  |  | 1150560
4989979.79 |  |  |  |  | 4844040.38 |  | 1456432.2 |  | 786615.9
1549654.01 | [5 empty] | 799560 |  |  | 720850
1216901.49 |  |  |  |  | 1198171.05 | 12600 |  |  | 12600
4839332.08 |  |  |  |  | 4789339.41 | 4500 |  |  | 4500
859977.4 | [5 empty] | 3739970 |  |  | 0
4983677.95 |  |  |  |  | 4933595.15 | 249985 |  |  | 247700
11325045.94 |  |  |  |  | 11291501.41 | 4204 |  |  | 4200
3739970 |  |  |  | 2453165 |  | 171862 |  |  | 171498
5967036 |  |  |  | 5961543 |  | 9191 |  |  | 9119
160940 |  |  |  | 159862 |  | 32530 |  |  | 31730
337902 |  |  |  | 337396.77 |  | 73418 |  |  | 73419.5
782000 |  |  |  | 780000 |  | 691645 |  |  | 640866
281370 |  |  |  | 229680 |  | 24000 |  |  | 23880
838084 |  |  |  | 837560.25 |  | 84000 |  |  | 83825
800400 |  |  |  | 783000 |  | 525000 |  |  | 523000
386094 |  |  |  | 378085 |  | 1300000 |  |  | 0
551583 |  |  |  | 537675 |  | 453631 |  |  | 442108
90900 |  |  |  | 89000 |  | 99990.5 |  |  | 99962
856256 |  |  |  | 848590 |  | 1165923 |  |  | 1093370
580140 |  |  |  | 399180 |  | 167423 |  |  | 1279590
245861 |  |  |  | 160817 |  | 695600 |  |  | 444000
290532 |  |  |  | 237685 |  | 673510 |  |  | 417700
1709362 |  |  |  | 1150560 |  | 678149 |  |  | 618700
1456432.2 |  |  |  | 786615.9 |  | 25500 |  |  | 25500
799560 |  |  |  | 720850 |  | 18484 |  |  | 18076
12600 |  |  |  | 12600 |  | 796804 |  |  | 796804
4500 |  |  |  | 4500 |  | 17745 |  |  | 17550
3739970 | [5 empty] | 1532 |  |  | 1532
249985 |  |  |  | 247700 |  | 20691 |  |  | 20472
4204 |  |  |  |  | 4200 | 11200 |  |  | 11000
171862 |  |  |  |  | 171498 | 28440 |  |  | 28144
9191 |  |  |  |  | 9119 | 14344 |  |  | 14116
32530 |  |  |  |  | 31730 | 10890 |  |  | 10780
73418 |  |  |  |  | 73419.5 | 49938 |  |  | 49610
691645 |  |  |  |  | 640866 | 25143 |  |  | 24997
24000 |  |  |  |  | 23880 | 1300 |  |  | 1300
84000 |  |  |  |  | 83825 | 5000 |  |  | 4400
525000 |  |  |  |  | 523000 | 484925 |  |  | 470135
1300000 | [5 empty] | 499416 |  |  | 489205
453631 |  |  |  |  | 442108 | 4551 |  |  | 4440
99990.5 |  |  |  |  | 99962 | 800400 |  |  | 0
1165923 |  |  |  |  | 1093370 | 25000 |  |  | 0
167423 |  |  |  |  | 1279590 | 16693 |  |  | 16680
695600 |  |  |  |  | 444000 | 410886 |  |  | 390180
673510 |  |  |  |  | 417700 | 92642 |  |  | 91650
678149 |  |  |  |  | 618700 | 27593 |  |  | 26920
25500 |  |  |  |  | 25500 | 6949 |  |  | 6846.25
18484 |  |  |  |  | 18076 | 7090 |  |  | 7074
796804 |  |  |  |  | 796804 | 20072 |  |  | 17390
17745 |  |  |  |  | 17550 | 141200 |  |  | 134000
1532 |  |  |  |  | 1532 | 9394 |  |  | 9150
20691 |  |  |  |  | 20472 | 270478 |  |  | 267195
11200 |  |  |  |  | 11000 | 103550 |  |  | 103279
28440 |  |  |  |  | 28144 | 26236 |  |  | 26212
14344 |  |  |  |  | 14116 | 40000 |  |  | 39800
10890 |  |  |  |  | 10780 | 7000 |  |  | 7000
49938 |  |  |  |  | 49610 | 86666 |  |  | 86561
25143 |  |  |  |  | 24997 | 112350 |  |  | 111270
1300 |  |  |  |  | 1300 | 16420 |  |  | 16282
5000 |  |  |  |  | 4400 | 25894 |  |  | 25680
484925 |  |  |  |  | 470135 | 27797 |  |  | 27132
499416 |  |  |  |  | 489205 | 5500 |  |  | 5480
4551 |  |  |  |  | 4440 | 360000 |  |  | 346050
800400 | [5 empty] | 74955 |  |  | 73970
25000 | [5 empty] | 25000 |  |  | 24500
16693 |  |  |  | 16680 |  | 16600 |  |  | 16580
410886 |  |  |  | 390180 |  | 10000 |  |  | 10000
92642 |  |  |  | 91650 |  | 24000 |  |  | 23840
27593 |  |  |  | 26920 |  | 28960 |  |  | 28653
6949 |  |  |  | 6846.25 |  | 73600 |  |  | 51570
7090 |  |  |  | 7074 |  | 63579 |  |  | 63170
20072 |  |  |  | 17390 |  | 16500 |  |  | 16250
141200 |  |  |  | 134000 |  | 30660 |  |  | 28470
9394 |  |  |  | 9150 |  | 68900 |  |  | 68500
270478 |  |  |  | 267195 |  | 28500 |  |  | 28000
103550 |  |  |  | 103279 |  | 173522 |  |  | 173224
26236 |  |  |  | 26212 |  | 7000 |  |  | 6800
40000 |  |  |  | 39800 |  | 68924 |  |  | 68860
7000 |  |  |  | 7000 |  | 26741 |  |  | 26000
86666 |  |  |  | 86561 |  | 15375 |  |  | 15000
112350 |  |  |  | 111270 |  | 20904 |  |  | 20688
16420 |  |  |  | 16282 |  | 8320 |  |  | 8050
25894 |  |  |  | 25680 |  | 15865 |  |  | 15610
27797 |  |  |  | 27132 |  | 74520 |  |  | 72900
5500 |  |  |  | 5480 |  | 9264 |  |  | 9120
360000 |  |  |  | 346050 |  | 71848 |  |  | 71847.55
74955 |  |  |  | 73970 |  | 125000 |  |  | 123500
25000 |  |  |  | 24500 |  | 21675 |  |  | 21628
16600 |  |  |  | 16580 |  | 7885 |  |  | 7590
10000 |  |  |  | 10000 |  | 22875 |  |  | 22875
24000 |  |  |  | 23840 |  | 10450 |  |  | 10400
28960 |  |  |  | 28653 |  | 31467 |  |  | 31367
73600 |  |  |  | 51570 |  | 8400 |  |  | 8250
63579 |  |  |  | 63170 |  | 9900 |  |  | 9890
16500 |  |  |  | 16250 |  | 36900 |  |  | 35250
30660 |  |  |  | 28470 |  | 4778137.59 |  |  | 4727954
68900 |  |  |  | 68500 |  | 2495161.76 |  |  | 2454983.84
28500 |  |  |  | 28000 |  | 4874674.43 |  | 4844040.38
173522 |  |  |  | 173224 |  | 200150 |  |  | 197500
7000 |  |  |  | 6800
68924 |  |  |  | 68860
26741 |  |  |  | 26000
15375 |  |  |  | 15000
20904 |  |  |  | 20688
8320 |  |  |  | 8050
15865 |  |  |  | 15610
74520 |  |  |  | 72900
9264 |  |  |  | 9120
71848 |  |  |  | 71847.55
125000 |  |  |  | 123500
21675 |  |  |  | 21628
7885 |  |  |  | 7590
22875 |  |  |  | 22875
10450 |  |  |  | 10400
31467 |  |  |  | 31367
8400 |  |  |  | 8250
9900 |  |  |  | 9890
36900 |  |  |  | 35250
1446387.8 | 1446387.8 |  | 0
981386.05 | 981386.05 |  | 0
2268269.88 | 2268269.88 |  | 0
3751603.89 | 3751603.89 |  | 0
2975982.21 | 2975982.21 |  | 0
1714912.26 |  | 1714912.26 | 0
1241109.13 |  | 1241109.13 | 0
4778137.59 |  |  |  |  | 4727954
2495161.76 |  |  |  |  | 2454983.84
2832670.36 |  | 2832670.36 | 0
4398193.31 |  | 4398193.31 | 0
4891611.84 |  | 4891611.84 | 0
4874674.43 |  |  |  |  | 4844040.38
5582 | 5582 |  | 0
19200 | 19200 |  | 0
34500 | 34500 |  | 0
200150 |  |  |  | 197500
0 |  |  | 0
3550 | 3550 |  | 0
5500 | 5500 |  | 0
8466 | 8466 |  | 0
16152 | 16152 |  | 16152 | 16152
99948 | 99948 |  | 99916 | 99916
76420 | 76420 |  | 74970 | 74970
177200 | 177200 |  | 172350 | 172350
102715 | 102715 |  | 0
78961 |  | 78961 | 77834.75 |  | 77834.75
5600 | 5600 |  | 5600 | 5600
5600 | 5600 |  | 5600 | 5600
9960 | 9960 |  | 9960 | 9960
20110 | 20110 |  | 20110 | 20110
155857 | 155857 |  | 154582.75 | 154582.75
36000 | 36000 |  | 34500 | 34500
102923 | 102923 |  | 102608 | 102608
181830 | 181830 |  | 179550 | 179550
0 |  |  | 0
0 |  |  | 0
168505 | 168505 |  | 165605 | 165605
69640 | 69640 |  | 0
290605 | 290605 |  | 122659 | 122659
49500 | 49500 |  | 45000 | 45000
290605 | 290605 |  | 288752 | 288752
141220 | 141220 |  | 0
166440 | 166440 |  | 166440 | 166440
344209 | 344209 |  | 0
105000 | 105000 |  | 103000 | 103000
68764 | 68764 |  | 63220 | 63220
11500 | 11500 |  | 11446 | 11446
18125 | 18125 |  | 18088 | 18088
20996 | 20996 |  | 20780 | 20780
19783 | 19783 |  | 19380 | 19380
99625 | 99625 |  | 94250 | 94250
19695 | 19695 |  | 19532.5 | 19532.5
39485 | 39485 |  | 39352.5 | 39352.5
3300 | 3300 |  | 2937 | 2937
9996 | 9996 |  | 9817.5 | 9817.5
15000 | 15000 |  | 14850 | 14850
93956 | 93956 |  | 93480 | 93480
137200 | 137200 |  | 134800 | 134800
9660453.88 |  | 9660453.88 | 0
3789923.2 |  | 3789923.2 | 3739823.02 |  | 3739823.02
4817791.76 |  | 4817791.76 | 4786961.94 |  | 4786961.94
3321542.64 |  | 3321542.64
10000 | 10000 |  | 0
10000 | 10000 |  | 0
27592 | 27592 |  | 0
138000 | 138000 |  | 135900 | 135900
14100 | 14100 |  | 14100 | 14100
20494 | 20494 |  | 20494 | 20494
7650 | 7650 |  | 7650 | 7650
148830 | 148830 |  | 148830 | 148830
7890 | 7890 |  | 7890 | 7890
97550 | 97550 |  | 97550 | 97550
34430 | 34430 |  | 34430 | 34430
267150 | 267150 |  | 266879 | 266879
198322 | 198322 |  | 195986 | 195986
336885 | 336885 |  | 332145 | 332145
8937 | 8937 |  | 8901 | 8901
20468 | 20468 |  | 18398 | 18398
225112.5 | 225112.5 |  | 218200 | 218200
10425 | 10425 |  | 10300 | 10300
960 | 960 |  | 0
208480 | 208480 |  | 198900 | 198900
230510 | 230510 |  | 0
2136959 | 2136959 |  | 2089350 | 2089350
6600 | 6600 |  | 6590 | 6590
37740 | 37740 |  | 36900 | 36900
1640 | 1640 |  | 1200 | 1200
153780 | 153780 |  | 39600 | 39600
1011000 | 1011000 |  | 976000 | 976000
6984 | 6984 |  | 6565 | 6565
128111 | 128111 |  | 127318 | 127318
137097 | 137097 |  | 136588 | 136588
54769 | 54769 |  | 54517 | 54517
67002 | 67002 |  | 66538 | 66538
143517 | 143517 |  | 142607 | 142607
4199 | 4199 |  | 4195 | 4195
21840 | 21840 |  | 21800 | 21800
17240 | 17240 |  | 17221 | 17221
121000 | 121000 |  | 119000 | 119000
665700 | 665700 |  | 662530 | 662530
13635 | 13635 |  | 13581 | 13581
39506 | 39506 |  | 39196 | 39196
399294 | 399294 |  | 396659 | 396659
165918 | 165918 |  | 164997 | 164997
179310.6 | 179310.6 |  | 178843.43 | 178843.43
28652 | 28652 |  | 28517 | 28517
111615 | 111615 |  | 111457.5 | 111457.5
153422.28 | 153422.28 |  | 153351 | 153351
29218 | 29218 |  | 29170 | 29170
232190 | 232190 |  | 232190 | 232190
2160 | 2160 |  | 2148 | 2148
2160 | 2160 |  | 2148 | 2148
2160 | 2160 |  | 2148 | 2148
57930 | 57930 |  | 56980 | 56980
289037 | 289037 |  | 287052 | 287052
72763 | 72763 |  | 72453 | 72453
163077 | 163077 |  | 162895 | 162895
615308 | 615308 |  | 605102 | 605102
260000 | 260000 |  | 0
321126 | 321126 |  | 0
88113.27 | 88113.27 |  | 85717.93 | 85717.93
56943.57 | 56943.57 |  | 54894.57 | 54894.57
304795 | 304795 |  | 250290.25 | 250290.25
3116990 | 3116990 |  | 2369900 | 2369900
45075 | 45075 |  | 45075 | 45075
200000 | 200000 |  | 0
876086 | 876086 |  | 756236 | 756236
6649 | 6649 |  | 6633 | 6633
19200 | 19200 |  | 19192 | 19192
308479.4 | 308479.4 |  | 300885 | 300885
40236.5 | 40236.5 |  | 39808 | 39808
28000 | 28000 |  | 26000 | 26000
634552 | 634552 |  | 567800 | 567800
1119300 | 1119300 |  | 0
162978 | 162978 |  | 160016 | 160016
468787 | 468787 |  | 467784 | 467784
20550 | 20550 |  | 20175 | 20175
4500 | 4500 |  | 4500 | 4500
30264 | 30264 |  | 29700 | 29700
19000 | 19000 |  | 0
346055 | 346055 |  | 328925 | 328925
84700 | 84700 |  | 83909 | 83909
42076 | 42076 |  | 42060 | 42060
57265 | 57265 |  | 55082 | 55082
17274 | 17274 |  | 17220 | 17220
218316 | 218316 |  | 189743 | 189743
137250 | 137250 |  | 136250 | 136250
33800 | 33800 |  | 33800 | 33800
460982 | 460982 |  | 456252 | 456252
1950 | 1950 |  | 1950 | 1950
0 |  |  | 0
40700 | 40700 |  | 45600 | 45600
17880 | 17880 |  | 0
13471 | 13471 |  | 13025 | 13025
18894 | 18894 |  | 18331 | 18331
1000 | 1000 |  | 0
12000 | 12000 |  | 12000 | 12000
151695 | 151695 |  | 151580 | 151580
697287 | 697287 |  | 579600 | 579600
831425 | 831425 |  | 743046 | 743046
135000 | 135000 |  | 134240 | 134240
9000 | 9000 |  | 0
127350 | 127350 |  | 125525 | 125525
57564 | 57564 |  | 57060 | 57060
4145 | 4145 |  | 3990 | 3990
20000 | 20000 |  | 19900 | 19900
20000 | 20000 |  | 19800 | 19800
18150 | 18150 |  | 17600 | 17600
500 | 500 |  | 450 | 450
51000 | 51000 |  | 48960 | 48960
75710 | 75710 |  | 75710 | 75710
15094 | 15094 |  | 14846 | 14846
30890.15 | 30890.15 |  | 30727.82 | 30727.82
49456 | 49456 |  | 49327 | 49327
49456 | 49456 |  | 49456 | 49456
49456 | 49456 |  | 49327 | 49327
161685 | 161685 |  | 161253 | 161253
24800 | 24800 |  | 24710 | 24710
3600 | 3600 |  | 3555 | 3555
216100 | 216100 |  | 215912 | 215912
216100 | 216100 |  | 215912 | 215912
14000 | 14000 |  | 13720 | 13720
19556 | 19556 |  | 19348 | 19348
28630 | 28630 |  | 28622 | 28622
28630 | 28630 |  | 28622 | 28622
23042 | 23042 |  | 22770 | 22770
20552 | 20552 |  | 19084 | 19084
2230 | 2230 |  | 2222 | 2222
74846 | 74846 |  | 74595 | 74595
288063 | 288063 |  | 282338 | 282338
1100 | 1100 |  | 1090 | 1090
27580 | 27580 |  | 25610 | 25610
14820 | 14820 |  | 14760 | 14760
3129 | 3129 |  | 3087 | 3087
99400 | 99400 |  | 74900 | 74900
2780 | 2780 |  | 2740 | 2740
6160 | 6160 |  | 6125 | 6125
3000 | 3000 |  | 2990 | 2990
4200 | 4200 |  | 3900 | 3900
13124 | 13124 |  | 13010 | 13010
53016 | 53016 |  | 52892 | 52892
26840 | 26840 |  | 26800 | 26800
12320 | 12320 |  | 12300 | 12300
423118 | 423118 |  | 413340 | 413340
355715 | 355715 |  | 352740 | 352740
200721 | 200721 |  | 199692.5 | 199692.5
310860 | 310860 |  | 310040 | 310040
13000 | 13000 |  | 12890 | 12890
138837 | 138837 |  | 137760 | 137760
34000 | 34000 |  | 33500 | 33500
29750 | 29750 |  | 29725 | 29725
22000 | 22000 |  | 21960 | 21960
15516 | 15516 |  | 15462 | 15462
7000 | 7000 |  | 0
68435 | 68435 |  | 68100 | 68100
19200 | 19200 |  | 19200 | 19200
139348 | 139348 |  | 137410 | 137410
21900 | 21900 |  | 21900 | 21900
5600 | 5600 |  | 5600 | 5600
5600 | 5600 |  | 5600 | 5600
16700 | 16700 |  | 16700 | 16700
88340 | 88340 |  | 88340 | 88340
15420 | 15420 |  | 15420 | 15420
2453700 | 2453700 |  | 2453700 | 2453700
25500 | 25500 |  | 25500 | 25500
575153 | 575153 |  | 564992 | 564992
12800 | 12800 |  | 12800 | 12800
28340 | 28340 |  | 28340 | 28340
36300 | 36300 |  | 36300 | 36300
12400 | 12400 |  | 12400 | 12400
9960 | 9960 |  | 9960 | 9960
47191 | 47191 |  | 47191 | 47191
18310 | 18310 |  | 16926 | 16926
23821 | 23821 |  | 23604 | 23604
139161 | 139161 |  | 135640 | 135640
120800 | 120800 |  | 120580 | 120580
45000 | 45000 |  | 44955 | 44955
116000 | 116000 |  | 114400 | 114400
74900 | 74900 |  | 73562.5 | 73562.5
17532 | 17532 |  | 17518 | 17518
125413 | 125413 |  | 121965 | 121965
8169 | 8169 |  | 8019 | 8019
52675 | 52675 |  | 52660 | 52660
68179 | 68179 |  | 67604 | 67604
63762 | 63762 |  | 63705 | 63705
156600 | 156600 |  | 156516 | 156516
920 | 920 |  | 916 | 916
143587 | 143587 |  | 143555 | 143555
131870 | 131870 |  | 131559.5 | 131559.5
111615 | 111615 |  | 111560 | 111560
138837 | 138837 |  | 138813 | 138813
111615 | 111615 |  | 111560 | 111560
142052 | 142052 |  | 141622 | 141622
93631 | 93631 |  | 93434 | 93434
138837 | 138837 |  | 138399 | 138399
143517 | 143517 |  | 143100 | 143100
15400 | 15400 |  | 15200 | 15200
4070 | 4070 |  | 4000 | 4000
79310 | 79310 |  | 79235 | 79235
269316 | 269316 |  | 269210 | 269210
5666 | 5666 |  | 5660 | 5660
13434 | 13434 |  | 12970 | 12970
19435 | 19435 |  | 19389 | 19389
52568 | 52568 |  | 52476 | 52476
2050 | 2050 |  | 2000 | 2000
15000 | 15000 |  | 14800 | 14800
2802084.38 |  | 2802084.38 | 0
3198096 |  | 3198096 | 0
2883242.63 |  | 2883242.63 | 0
3212845.86 |  | 3212845.86 | 0
3789812.7 |  | 3789812.7 | 0
3789812.7 |  | 3789812.7 | 0
1001854.77 |  | 1001854.77 | 0
1430589.79 |  | 1430589.79 | 0
970245.77 |  | 970245.77 | 0
1408940 |  | 1408940 | 0
932786.54 |  | 932786.54 | 0
3271471.14 |  | 3271471.14 | 0
3093997.35 |  | 3093997.35 | 0
1867751.96 |  | 1867751.96 | 0
1867751.96 |  | 1867751.96 | 0
1805974.16 |  | 1805974.16 | 0
1883872.34 |  | 1883872.34 | 0
4931657.94 |  | 4931657.94 | 0
2939925.87 |  | 2939925.87 | 0
1224647.75 |  | 1224647.75 | 0
14217212.67 |  | 14217212.67 | 0
13692971.23 |  | 13692971.23 | 0
12007095.66 |  | 12007095.66 | 0
11840617.67 |  | 11840617.67 | 0
8350 | 8350 |  | 8350 | 8350
14830 | 14830 |  | 14830 | 14830
20000 | 20000 |  | 20000 | 20000
34925 | 34925 |  | 0
7400 | 7400 |  | 7400 | 7400
4602 | 4602 |  | 4598 | 4598
26345 | 26345 |  | 26000 | 26000
61198 | 61198 |  | 59689 | 59689
71538 | 71538 |  | 67931.4 | 67931.4
109511 | 109511 |  | 107901 | 107901
299732.8 | 299732.8 |  | 224575 | 224575
11740 | 11740 |  | 11100 | 11100
24660 | 24660 |  | 24270 | 24270
10450 | 10450 |  | 0
25860 | 25860 |  | 25298 | 25298
39830 | 39830 |  | 0
21400 | 21400 |  | 21400 | 21400
5600 | 5600 |  | 5600 | 5600
29050 | 29050 |  | 0
76033 | 76033 |  | 74167 |  | 74167
251235 | 251235 |  | 223700 |  | 223700
415671 | 415671 |  | 370086 |  | 370086
236060 | 236060 |  | 87000 | 87000
660847 | 660847 |  | 659660 | 659660
329370 | 329370 |  | 325810 | 325810
213899.3 | 213899.3 |  | 211760.31 | 211760.31
983489.85 | 983489.85 |  | 980935.85 | 980935.85
671992.7 | 671992.7 |  | 669932.06 | 669932.06
957420.55 | 957420.55 |  | 954850.4 | 954850.4
534665 | 534665 |  | 531783.59 | 531783.59
658913 | 658913 |  | 656467.21 | 656467.21
321750 | 321750 |  | 273000 | 273000
897213 | 897213 |  | 451220 | 451220
288000 | 288000 |  | 287760 | 287760
16500 | 16500 |  | 16140 | 16140
16750 | 16750 |  | 15100 | 15100
2235 | 2235 |  | 2205 | 2205
3200 | 3200 |  | 3200 | 3200
36250 | 36250 |  | 35810 | 35810
160000 | 160000 |  | 155000 | 155000
1140300 | 1140300 |  | 0
8155 | 8155 |  | 7990 | 7990
98409 | 98409 |  | 97140 | 97140
153376 | 153376 |  | 150720 | 150720
30866 | 30866 |  | 22660 | 22660
115000 | 115000 |  | 54000 | 54000
436762 | 436762 |  | 0
47045 | 47045 |  | 0
208025 | 208025 |  | 204984 | 204984
8940 | 8940 |  | 8881 | 8881
39000 | 39000 |  | 0
10000 | 10000 |  | 9750 | 9750
97439 | 97439 |  | 97391 | 97391
1245 | 1245 |  | 1245 | 1245
269316 | 269316 |  | 269210 | 269210
28160 | 28160 |  | 27904 | 27904
25088 | 25088 |  | 23296 | 23296
0 |  |  | 553610 |  | 553610
7700 | 7700 |  | 2240 | 2240
1925 | 1925 |  | 560 | 560
1925 | 1925 |  | 560 | 560
1792 | 1792 |  | 1664 | 1664
122550 | 122550 |  | 114630 | 114630
35340 | 35340 |  | 34300 | 34300
153996 | 153996 |  | 150240 | 150240
15800 | 15800 |  | 15250 | 15250
11300 | 11300 |  | 9930 | 9930
88000 | 88000 |  | 0
29642 | 29642 |  | 29600 | 29600
11200 | 11200 |  | 11200 | 11200
828265.21 | 828265.21 |  | 0
85560 | 85560 |  | 85650 | 85650
6500 | 6500 |  | 6370 | 6370
1183166 | 1183166 |  | 1183166.18 | 1183166.18
900000 | 900000 |  | 897960 | 897960
1244072 | 1244072 |  | 1192869 | 1192869
2623799.14 | 2623799.14 |  | 2607542.28 | 2607542.28
0 |  |  | 0
997938 | 997938 |  | 969963 | 969963
500000 | 500000 |  | 396875 | 396875
399990 | 399990 |  | 237129 | 237129
300000 | 300000 |  | 214500 | 214500
797013 | 797013 |  | 323367.8 | 323367.8
346608 | 346608 |  | 213259 | 213259
329632 | 329632 |  | 327799 | 327799
931654 | 931654 |  | 930883.05 | 930883.05
150000 | 150000 |  | 89000 | 89000
150311 | 150311 |  | 132728 | 132728
399872 | 399872 |  | 353096 | 353096
150311 | 150311 |  | 132728 | 132728
796016 | 796016 |  | 550056 | 550056
8440000 | 8440000 |  | 4987000 | 4987000
100000 | 100000 |  | 85800 | 85800
534000 | 534000 |  | 375000 | 375000
408924 | 408924 |  | 243087.4 | 243087.4
994168.4 | 994168.4 |  | 731506 | 731506
652110 | 652110 |  | 650018 | 650018
49533 | 49533 |  | 42873 | 42873
135900 | 135900 |  | 135900 | 135900
364500 | 364500 |  | 364500 | 364500
0 |  |  | 0
0 |  |  | 0
301872 | 301872 |  | 301872 | 301872
0 |  |  | 0
0 |  |  | 0
3913 | 3913 |  | 3913 | 3913
12500 | 12500 |  | 12300 | 12300
3500 | 3500 |  | 3487 | 3487
7550 | 7550 |  | 7495 | 7495
13200 | 13200 |  | 12600 | 12600
36400 | 36400 |  | 35880 | 35880
20160 | 20160 |  | 19872 | 19872
20160 | 20160 |  | 19872 | 19872
153330 | 153330 |  | 147603 | 147603
262068 | 262068 |  | 257770 | 257770
11625 | 11625 |  | 11187.5 | 11187.5
55350 | 55350 |  | 54360 | 54360
58080 | 58080 |  | 57440 | 57440
411807 | 411807 |  | 409215 | 409215
18398 | 18398 |  | 17920 | 17920
17745 | 17745 |  | 17420 | 17420
13800 | 13800 |  | 13300 | 13300
33000 | 33000 |  | 32250 | 32250
9264 | 9264 |  | 9072 | 9072
180185 | 180185 |  | 176493 | 176493
48098 | 48098 |  | 47368 | 47368
61600 | 61600 |  | 57700 | 57700
0 |  |  | 0
30000 | 30000 |  | 27860 | 27860
0 |  |  | 0
3823750 | 3823750 |  | 3823750 | 3823750
1642914 | 1642914 |  | 800394 | 800394
1800000 | 1800000 |  | 988000 | 988000
569746 | 569746 |  | 565000 | 565000
1459602.15 | 1459602.15 |  | 1328418.15 | 1328418.15
337509 | 337509 |  | 336917 | 336917
1284852 | 1284852 |  | 805272 | 805272
1284852 | 1284852 |  | 805272 | 805272
1392784 | 1392784 |  | 1298000 | 1298000
1268285 | 1268285 |  | 1199029.2 | 1199029.2
1938000 | 1938000 |  | 1228000.08 | 1228000.08
1198400.04 | 1198400.04 |  | 568068 | 568068
747066 | 747066 |  | 747066 | 747066
111615 | 111615 |  | 111390 | 111390
194400 | 194400 |  | 188000 | 188000
33783 | 33783 |  | 33025 | 33025
0 |  |  | 0
558016.02 | 558016.02 |  | 316100.76 | 316100.76
0 |  |  | 0
36315 | 36315 |  | 0
128653 | 128653 |  | 128653 | 128653
19215 | 19215 |  | 19215 | 19215
800000 | 800000 |  | 799112 | 799112
117900 | 117900 |  | 115200 | 115200
96762 | 96762 |  | 95647.25 | 95647.25
129950 | 129950 |  | 123125 | 123125
86779 | 86779 |  | 80958 | 80958
7848 | 7848 |  | 7827 | 7827
19000 | 19000 |  | 18240 | 18240
49250 | 49250 |  | 48665 | 48665
7200 | 7200 |  | 7000 | 7000
9300 | 9300 |  | 9100 | 9100
3300 | 3300 |  | 3280 | 3280
44250 | 44250 |  | 43375 | 43375
6000 | 6000 |  | 5990 | 5990
28437 | 28437 |  | 28150 | 28150
7650 | 7650 |  | 7650 | 7650
72787 | 72787 |  | 71840 | 71840
25000 | 25000 |  | 20000 | 20000
42390 | 42390 |  | 40060 | 40060
1792 | 1792 |  | 1664 | 1664
30000 | 30000 |  | 29600 | 29600
90600 | 90600 |  | 89592 | 89592
18150 | 18150 |  | 17600 | 17600
8145 | 8145 |  | 7862 | 7862
18860 | 18860 |  | 18510 | 18510
24920 | 24920 |  | 24560 | 24560
1792 | 1792 |  | 1664 | 1664
90960 | 90960 |  | 90040 | 90040
22000 | 22000 |  | 22000 | 22000
589500 | 589500 |  | 0
2671500 | 2671500 |  | 0
711620 | 711620 |  | 694025 | 694025
134773 | 134773 |  | 134742 | 134742
52580 | 52580 |  | 52580 | 52580
23600 | 23600 |  | 23600 | 23600
52440 | 52440 |  | 0
180845 | 180845 |  | 179100 | 179100
98477 | 98477 |  | 0
251235 | 251235 |  | 223700 | 223700
1795645 | 1795645 |  | 1227045 | 1227045
420000 | 420000 |  | 419400 | 419400
2658600 | 2658600 |  | 2658600 | 2658600
1165743 | 1165743 |  | 1085470 | 1085470
1163438 | 1163438 |  | 1107001 | 1107001
810504 | 810504 |  | 689500 | 689500
220620 | 220620 |  | 196500 | 196500
334344 | 334344 |  | 284200 | 284200
659800 | 659800 |  | 590250 | 590250
1765998 | 1765998 |  | 1539588 | 1539588
181830 | 181830 |  | 179550 | 179550
0 |  |  | 0
0 |  |  | 0
2284480 | 2284480 |  | 2206600 | 2206600
0 |  |  | 0
0 |  |  | 0
51950 | 51950 |  | 51500 | 51500
0 |  |  | 0
679368 | 679368 |  | 679368 | 679368
0 |  |  | 0
197818 | 197818 |  | 197818 | 197818
2900 | 2900 |  | 2900 | 2900
7736 | 7736 |  | 7736 | 7736
19200 | 19200 |  | 19200 | 19200
7443 | 7443 |  | 7443 | 7443
8650 | 8650 |  | 8650 | 8650
1150 | 1150 |  | 1150 | 1150
8570 | 8570 |  | 8570 | 8570
4070 | 4070 |  | 4070 | 4070
36315 | 36315 |  | 36165 | 36165
10000 | 10000 |  | 10000 | 10000
58960 | 58960 |  | 58310 | 58310
71807 | 71807 |  | 71350 | 71350
244184 | 244184 |  | 243868 | 243868
40394 | 40394 |  | 39990 | 39990
39748 | 39748 |  | 39645 | 39645
280485 | 280485 |  | 278287 | 278287
243361 | 243361 |  | 241406 | 241406
22000 | 22000 |  | 22000 | 22000
53620 | 53620 |  | 49046 | 49046
6150 | 6150 |  | 6000 | 6000
15375 | 15375 |  | 15000 | 15000
21410 | 21410 |  | 21200 | 21200
50684 | 50684 |  | 49415 | 49415
80740.49 | 80740.49 |  | 80703.49 | 80703.49
436762 | 436762 |  | 427925 | 427925
119221 | 119221 |  | 118350 | 118350
14000 | 14000 |  | 13972 | 13972
1400 | 1400 |  | 1337.5 | 1337.5
30000 | 30000 |  | 30000 | 30000
346500 | 346500 |  | 340000 | 340000
187834 | 187834 |  | 186130 | 186130
21945 | 21945 |  | 21666 | 21666
54100 | 54100 |  | 53110 | 53110
49200 | 49200 |  | 48000 | 48000
3280 | 3280 |  | 3200 | 3200
36300 | 36300 |  | 35920 | 35920
2430 | 2430 |  | 2400 | 2400
29680 | 29680 |  | 28090 | 28090
5376 | 5376 |  | 5088 | 5088
28500 | 28500 |  | 0
5950 | 5950 |  | 5950 | 5950
7558 | 7558 |  | 7522 | 7522
78040 | 78040 |  | 78010 | 78010
10000 | 10000 |  | 0
4070 | 4070 |  | 4070 | 4070
1700 | 1700 |  | 1700 | 1700
82300 | 82300 |  | 82300 | 82300
234203 | 234203 |  | 233864 | 233864
212596 | 212596 |  | 233864 | 233864
112900 | 112900 |  | 112180 | 112180
14710 | 14710 |  | 0
11991 | 11991 |  | 11970 | 11970
14004 | 14004 |  | 0
282875 | 282875 |  | 279750 | 279750
5696 | 5696 |  | 0
4500 | 4500 |  | 4500 | 4500
10500 | 10500 |  | 10500 | 10500
78500 | 78500 |  | 78500 | 78500
4070 | 4070 |  | 4070 | 4070
52995 | 52995 |  | 52995 | 52995
9600 | 9600 |  | 9600 | 9600
700 | 700 |  | 700 | 700
3350 | 3350 |  | 3350 | 3350
10002 | 10002 |  | 10002 | 10002
850 | 850 |  | 850 | 850
399000 | 399000 |  | 399000 | 399000
399000 | 399000 |  | 399000 | 399000
360440 | 360440 |  | 0
828222 | 828222 |  | 0
969608 | 969608 |  | 0
180000 | 180000 |  | 0
9093 | 9093 |  | 0
25000 | 25000 |  | 0
26977 | 26977 |  | 26937 | 26937
7840 | 7840 |  | 7825 | 7825
36544 | 36544 |  | 36262 | 36262
91401 | 91401 |  | 90791 | 90791
55916 | 55916 |  | 51922 | 51922
10150 | 10150 |  | 10140 | 10140
20900 | 20900 |  | 20900 | 20900
7590 | 7590 |  | 7584 | 7584
272716 | 272716 |  | 269970 | 269970
110447.85 | 110447.85 |  | 110053.18 | 110053.18
101805 | 101805 |  | 101462.5 | 101462.5
30300 | 30300 |  | 29900 | 29900
30300 | 30300 |  | 29900 | 29900
50010 | 50010 |  | 48343 | 48343
133500 | 133500 |  | 132000 | 132000
133500 | 133500 |  | 132000 | 132000
133500 | 133500 |  | 132000 | 132000
70631 | 70631 |  | 39068 | 39068
0 |  |  | 0
285772 | 285772 |  | 0
7000 | 7000 |  | 0
3300000 | 3300000 |  | 0
1007300 | 1007300 |  | 0
17053 | 17053 |  | 0
79605 | 79605 |  | 0
24289 | 24289 |  | 0
1792 | 1792 |  | 1664 | 1664
1792 | 1792 |  | 1664 | 1664
71242.51 | 71242.51 |  | 0
296539.37 | 296539.37 |  | 0
296539.37 | 296539.37 |  | 0
296539.37 | 296539.37 |  | 0
360000 | 360000 |  | 0
3655000 | 3655000 |  | 0
451976 | 451976 |  | 330400 | 330400
3125 | 3125 |  | 3125 | 3125
13200 | 13200 |  | 12000 | 12000
18000 | 18000 |  | 18000 | 18000
21120 | 21120 |  | 21120 | 21120
49461.25 | 49461.25 |  | 49304 | 49304
45100 | 45100 |  | 44000 | 44000
280430 | 280430 |  | 279931.04 | 279931.04
8960 | 8960 |  | 8640 | 8640
74520 | 74520 |  | 72900 | 72900
567438.51 | 567438.51 |  | 560696.51 | 560696.51
0 |  |  | 0
457860 | 457860 |  | 451530 | 451530
0 |  |  | 0
1897678.28 | 1897678.28 |  | 1872753.19 | 1872753.19
1394873.65 | 1394873.65 |  | 1394583.49 | 1394583.49
3901087.09 | 3901087.09 |  | 3860799.32 | 3860799.32
16200 | 16200 |  | 16200 | 16200
9740 | 9740 |  | 9740 | 9740
28500 | 28500 |  | 28200 | 28200
15400 | 15400 |  | 15200 | 15200
9062 | 9062 |  | 8770 | 8770
7809 | 7809 |  | 7744.5 | 7744.5
6000 | 6000 |  | 5800 | 5800
12300 | 12300 |  | 12200 | 12200
153194 | 153194 |  | 0
156000 | 156000 |  | 0
508500 | 508500 |  | 0
97500 | 97500 |  | 0
14980 | 14980 |  | 0
6197937.4 | 6197937.4 |  | 0
3494681.2 | 3494681.2 |  | 0
5730 | 5730 |  | 0
11700 | 11700 |  | 0
10089.96 | 10089.96 |  | 0
21801.5 | 21801.5 |  | 0
4367830.5 | 4367830.5 |  | 0
200000 | 200000 |  | 0
45075 | 45075 |  | 0
3281000 | 3281000 |  | 0
890483 | 890483 |  | 0
270000 | 270000 |  | 0
57500 | 57500 |  | 0
39655 | 39655 |  | 0
132571 | 132571 |  | 0
3924 | 3924 |  | 0
513190.86 | 513190.86 |  | 0
688750 | 688750 |  | 0
7717 | 7717 |  | 0
35000 | 35000 |  | 0
9000 | 9000 |  | 0
1792 | 1792 |  | 0
4212 | 4212 |  | 0
21750 | 21750 |  | 0

## PUBLIC BIDDING
ANNEX B
|  | (Provincial Government of Davao de Oro) Procurement Monitoring Report as of JULY/30/2022 | [18 empty] | (Provincial Government of Davao de Oro) Procurement Monitoring Report as of July/30/2022
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Mode of Procurement
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  | LIST OF OBSERVERS |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Delivery/Completion/Acceptance (If Applicable) | REMARKS (explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES
22-3518 | FOOD SUPPLIES | PHO | PB | 07.13.2022 | [11 empty] | GF | 554575 | 554575 |  | 0 |  |  | Mr. Allan Rey N. Esmael | [6 empty] | RETURNED TO R.O.
22-5434 | 5.0 HP CASSETTE TYOE NON-INVERTER | PACCO | PB | 07.13.2022 | 8.1.2022 | n/a | 8.9.2022 | 8.9.2022 | 8.12.2022 | 8.12.2022 | 8.16.2022 | 9.27.2022 |  |  |  | GF | 192000 | 192000 |  | 183796.58 | 183796.58 |  | Mr. Allan Rey N. Esmael | n/a | 8.9.2022 | 8.9.2022 | 8.12.2022 | 8.12.2022
22-C0480 | LABORATORY REGEANTS | PEEMO | PB | 07.13.2022 | [11 empty] | GF | 1021544 | 1021544 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | RETURNED TO R.O.
22-5330 | RICE (WELL MILLED) | PGO-PS | PB | 07.13.2022 | 7.10.2022 | n/a | 7.26.2022 | 7.26.2022 | 7.28-29.2022 | 7.28-29.2022 | 8.2.2022 | 8.19.2022 |  | 8.22.2022 | 8.22.2022 | GF | 213750 | 213750 |  | 213750 | 213750 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 7.21.2022 | n/a | n/a
22-4717 | TOTAL STATION TOPOGRAPHIC SURVEY | PAGRO | PB | 07.13.2022 | 8.1.2022 | n/a | 8.9.2022 | 8.9.2022 | 8.12.2022 | 8.12.2022 | 8.16.2022 | 9.22.2022 |  | 9.22.2022 | 9.22.2022 | GF | 500000 | 500000 |  | 494000 | 494000 |  | Mr. Allan Rey N. Esmael | n/a | 8.9.2022 | 8.9.2022 | 8.12.2022 | 8.12.2022
22-4716 | DRONE FOR MAPPING/SURVEYING | PAGRO | PB | 07.13.2022 | 7.10.2022 | n/a | 7.26.2022 | 7.26.2022 | 7.28-29.2022 | 7.28-29.2022 | 8.2.2022 | 9.16.2022 |  | 10.3.2022 | 10.3.2022 | GF | 200000 | 200000 |  | 200000 | 200000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 7.21.2022 | n/a | n/a
22-C0863 | REAGENTS | PEEMO | PB | 07.19.2022 | 9.9.2022 | 8.2.2022 | 10.4.2022 | 10.4.2022 | 10.6-7.2022 | 10.6-7.2022 | 10.11.2022 | 11.17.2022 |  |  |  | GF | 2104992 | 2104992 |  | 658101 | 658101 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.29.2022 | n/a | n/a |  | P.O. FOR DELIVERY
22-C0865 | ELECTROLYTES REAGENT | PEEMO | PB | 07.19.2022 | 7.26.2022 | n/a | 8.2.2022 | 8.2.2022 | 8.5.2022 | 8.5.2022 | 8.9.2022 | 9.27.2022 |  | 9.30.2022 | 9.30.2022 | GF | 448000 | 448000 |  | 441600 | 441600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 7.28.2022 | n/a | n/a
22-C0862 | REAGENTS | PEEMO | PB | 07.19.2022 | 7.26.2022 | n/a | 8.2.2022 | 8.2.2022 | 8.5.2022 | 8.5.2022 | 8.9.2022 | 9.29.2022 |  |  |  | GF | 841544 | 841544 |  | 775405.6 | 775405.6 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 7.28.2022 | n/a | n/a |  | P.O. FOR DELIVERY
22-5708 | ADBLUE, 20 LTRS/PAIL | PEO-EQPT. POOL | PB | 07.26.2022 | 8.13.2022 | n/a | 8.23.2022 | 8.23.2022 | 8.25-26.2022 | 8.25-26.2022 | 9.20.2022 | 11.3.2022 |  | 11.7.2022 | 11.7.2022 | GF | 503700 | 503700 |  | 447125 | 447125 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.18.2022 | n/a | n/a
22-5490 | TIRES (HEAVY EQUIPEMENT) | PEO-EQPT. POOL | PB | 07.26.2022 | 8.1.2022 | 8.9.2022 | 8.23.2022 | 8.23.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.6.2022 | 10.25.2022 |  | 11.8.2022 | 11.8.2022 | GF | 2894000 | 2894000 |  | 1647000 | 1647000 |  | Mr. Allan Rey N. Esmael | 8.4.2022 | n/a | 8.18.2022 | n/a | n/a
22-5690 | JOB ORDER: LABOR & MATERIALS FOR RODENT ABATEMENT MAINTENANCE SERVICES | PGSO | PB | 07.26.2022 | 8.1.2022 | n/a | 8.23.2022 | 8.23.2022 | 8.25-26.2022 | 8.25-26.2022 | 8.30.2022 | 10.28.2022 |  |  |  | GF | 180000 | 180000 |  | 162000 | 162000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.18.2022 | n/a | n/a |  | P,O, FOR DELIVERY
22-3602 | FABRICATION AND INSTALLATION | PDRRMO | PB | 08.02.2022 | 8.5.2022 | n/a | 8.16.2022 | 8.16.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.6.2022 |  |  |  |  | GF | 966000 | 966000 |  | 890000.4 | 890000.4 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.11.2022 | n/a | n/a |  | P.O FOR SERVE
22-C0089 | COMPUTER SUPPLIES | PICTO | PB | 08.02.2022 | 8.8.2022 | n/a | 8.16.2022 | 8.16.2022 | 8.19.2022 | 8.19.2022 | 8.23.2022 | 10.11.2022 |  |  |  | GF | 265000 | 265000 |  | 265000 | 265000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.11.2022 | n/a | n/a |  | P.O. FOR DELIVERY
22-5876 | LAPTOP (CLERICAL WORK) FOR USE OF MOBILE WORK STATION OF OFFICE APPLICATION | PHRMDO | PB | 08.02.2022 | 8.8.2022 | n/a | 8.16.2022 | 8.16.2022 | 8.19.2022 | 8.19.2022 | 8.23.2022 | 9.28.2022 |  | 10.4.2022 | 10.4.2022 | GF | 209970 | 209970 |  | 188997 | 188997 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.11.2022 | n/a | n/a
22-5620 | FOOD SUPPLIES | PAO-ADMIN | PB | 08.02.2022 | 8.8.2022 | n/a | 8.16.2022 | 8.16.2022 | 8.19.2022 | 8.19.2022 | 8.23.2022 | 9.9.2022 |  | 10.4.2022 | 10.4.2022 | GF | 450000 | 450000 |  | 432250 | 432250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.11.2022 | n/a | n/a
22-5861 | MOBILE TENT TRAPAL COVER | PAO ADMIN | PB | 08.02.2022 | 8.8.2022 | n/a | 8.16.2022 | 8.16.2022 | 8.19.2022 | 8.19.2022 | 8.23.2022 | 9.23.2022 |  | 11.15.2022 | 11.15.2022 | GF | 784000 | 784000 |  | 698095 | 698095 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.11.2022 | n/a | n/a
22-6278 | SUPPLY, DELIVERY, INSTALLATION AND COMMISSIONING OF 5 BUCKET MILKING MACHINE WITH COMPLETE ACCESSORIES AND MATERIALS | PVET | PB | 08.09.2022 | 8.15.2022 | n/a | 8.23.2022 | 8.23.2022 | 8.25-26.2022 | 8.25-26.2022 | 8.30.2022 | 9.27.2022 |  |  |  | GF | 500000 | 500000 |  | 378000 | 378000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.18.2022 | n/a | n/a |  | P.O. FOR DELIVERY
22-C0941 | MEDICAL SUPPLIES | PEEMO | PB | 08.16.2022 | 8.20.2022 | n/a | 8.30.2022 | 8.30.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.20.2022 | 10.25.2022 |  | 10.27.2022 | 10.27.2022 | GF | 959820 | 959820 |  | 503990 | 503990 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.24.2022 | n/a | n/a
22-C0943 | LABORATORY SUPPLIES | PEEMO | PB | 08.16.2022 | 8.19.2022 | n/a | 8.30.2022 | 8.30.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.6.2022 | 9.27.2022 |  | 10.18.2022 | 10.18.2022 | GF | 528679.6 | 528679.6 |  | 427672 | 427672 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.24.2022 | n/a | n/a
22-C0944 | MEDICAL SUPPLIES | PEEMO | PB | 08.16.2022 | 8.19.2022 | n/a | 8.30.2022 | 8.30.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.6.2022 | 9.27.2022 |  | 10.11.2022 | 10.11.2022 | GF | 312500 | 312500 |  | 160300 | 160300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.24.2022 | n/a | n/a
22-C0936 | DRUGS AND MEDICINES | PEEMO | PB | 08.16.2022 | 8.20.2022 | n/a | 8.30.2022 | 8.30.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.20.2022 |  |  |  |  | GF | 786651 | 786651 |  | 738292 | 738292 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.24.2022 | n/a | n/a |  | P.O. FOR SERVE
22-C0937 | FLUIDS | PEEMO | PB | 08.16.2022 | 8.9.2022 | n/a | 8.30.2022 | 8.30.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.6.2022 | 10.11.2022 |  | 10.15.2022 | 10.15.2022 | GF | 442950 | 442950 |  | 368730 | 368730 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.24.2022 | n/a | n/a
22-6251 | SPAREPARTS (HOSPITAL EQUIPMENT) | DDOPH MONTEVISTA | PB | 08.16.2022 | 8.19.2022 | n/a | 8.30.2022 | 8.30.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.6.2022 | 9.27.2022 |  | 10.28.2022 | 10.28.2022 | GF | 235680 | 235680 |  | 235300 | 235300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.24.2022 | n/a | n/a
22-6266 | REPLACE OF ACCUVIX XG ASSY DDM: DDM 07 (M196-01040B) | DDOPH MONTEVISTA | PB | 08.16.2022 | [11 empty] | GF | 290000 | 290000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O
22-6079 | FOOD SUPPLIES | PHO | PB | 08.16.2022 | [11 empty] | GF | 1118740 | 1118740 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
22-C0900 | FOOD SUPPLIES | PHO | PB | 08.16.2022 | [11 empty] | TF | 1420040 | 1420040 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | RETURNED TO R.O.
22-6070 | FOOD SUPPLIES | PHO | PB | 08.16.2022 | 8.23.2022 | 8.30.2022 | 9.20.2022 | 9.20.2022 | 9.22-23.2022 | 9.22-23.2022 | 9.27.2022 |  |  |  |  | TF | 1006550 | 1006550 |  | 864620 | 864620 |  | Mr. Allan Rey N. Esmael | 8.24.2022 | n/a | 9.15.2022 | n/a | n/a |  | P.O. FOR SERVE
22-6093 | COMPUTER SUPPLIES | PHO | PB | 08.16.2022 | 8.19.2022 | n/a | 8.30.2022 | 8.30.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.6.2022 | 10.4.2022 |  | 10.4.2022 | 10.4.2022 | TF | 205000 | 205000 |  | 118325 | 118325 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.24.2022 | n/a | n/a
22-6099 | FOOD SUPPLIES | PHO | PB | 08.16.2022 | 8.19.2022 | n/a | 8.30.2022 | 8.30.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.6.2022 | 9.26.2022 |  | 10.4.2022 | 10.4.2022 | TF | 650000 | 650000 |  | 605000 | 605000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.24.2022 | n/a | n/a
22-C0974 | MEDICAL SUPPLIES | PHO | PB | 08.16.2022 | 8.19.2022 | n/a | 8.30.2022 | 8.30.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.6.2022 | 10.6.2022 |  | 11.9.2022 | 11.9.2022 | GF | 269589 | 269589 |  | 247193.8 | 247193.8 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.24.2022 | n/a | n/a
22-C0973 | DRUGS AND MEDICINES | PHO | PB | 08.16.2022 | 8.23.2022 | 8.30.2022 | 9.20.2022 | 9.20.2022 | 9.22-23.2022 | 9.22-23.2022 | 9.27.2022 | 11.4.2022 |  | 11.7.2022 | 11.7.2022 | GF | 1623503 | 1623503 |  | 824650.4 | 824650.4 |  | Mr. Allan Rey N. Esmael | 8.24.2022 | n/a | 9.15.2022 | n/a | n/a
22-6215 | OFFICIAL DELIVERY RECEIPT FOR SAND | PTO | PB | 08.16.2022 | [11 empty] | GF | 360000 | 360000 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | RETURNED TO R.O.
22-C0970 | FOOD SUPPLIES | PAO-ADMIN | PB | 08.16.2022 | [11 empty] | GF | 316500 | 316500 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | RETURNED TO R.O.
22-5838 | RICE (WELL MILLED) | PAO-ADMIN | PB | 08.16.2022 | 8.19.2022 | n/a | 8.30.2022 | 8.30.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.6.2022 | 9.29.2022 |  | 10.4.2022 | 10.4.2022 | GF | 225000 | 225000 |  | 210000 | 210000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.24.2022 | n/a | n/a
22-6141 | RABBIES VACCINE | PVET | PB | 08.16.2022 | 8.23.2022 | n/a | 9.20.2022 | 9.20.2022 | 9.22-23.2022 | 9.22-23.2022 | 9.27.2022 | 10.25.2022 |  | 10.28.2022 | 10.28.2022 | GF | 304630 | 304630 |  | 282340 | 282340 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.15.2022 | n/a | n/a
22-6273 | SWINE BREEDER GILT (5 MONTHS OLD AT LEAST 85 TO 90 KG.) | PVET | PB | 08.16.2022 | 8.19.2022 | n/a | 8.30.2022 | 8.30.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.6.2022 | 10.14.2022 |  |  |  | GF | 490000 | 490000 |  | 487900 | 487900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 8.24.2022 | n/a | n/a |  | P.O. FOR DELIVERY
22-6922 | SPAREPARTS (MOTORCYCLE) | PGSO | PB | 08.23.2022 | 8.26.2022 | n/a | 9.6.2022 | 9.6.2022 | 9.10-11.2022 | 9.10-11.2022 | 9.20.2022 | 10.21.2022 |  | 10.21.2022 | 10.21.2022 | GF | 413660 | 413660 |  | 305230 | 305230 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.1.2022 | n/a | n/a
22-6919 | SPAREPARTS (LIGHT VEHICLE) | PGSO | PB | 08.23.2022 | 8.26.2022 | n/a | 9.6.2022 | 9.6.2022 | 9.10-11.2022 | 9.10-11.2022 | 9.20.2022 | 11.9.2022 |  | 11.24.2022 | 11.24.2022 | GF | 317161 | 317161 |  | 179720 | 179720 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.1.2022 | n/a | n/a
22-6920 | VARIOUS TIRES (LIGHT VEHICLE) | PGSO | PB | 08.23.2022 | 8.26.2022 | n/a | 9.6.2022 | 9.6.2022 | 9.10-11.2022 | 9.10-11.2022 | 9.20.2022 | 11.9.2022 |  | 11.11.2022 | 11.11.2022 | GF | 813060 | 813060 |  | 402600 | 402600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.1.2022 | n/a | n/a
22-C0928 | ELECTRICAL SUPPLIES | PEEMO | PB | 08.23.2022 | 8.26.2022 | n/a | 9.6.2022 | 9.6.2022 | 9.10-11.2022 | 9.10-11.2022 | 9.20.2022 |  |  |  |  | GF | 411228 | 411228 |  | 370484 | 370484 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.1.2022 | n/a | n/a |  | P.O. FOR SERVE
22-C0915 | JANITORIAL SUPPLIES | PEEMO | PB | 08.23.2022 | 8.26.2022 | n/a | 9.6.2022 | 9.6.2022 | 9.10-11.2022 | 9.10-11.2022 | 9.20.2022 |  |  |  |  | GF | 381240 | 381240 |  | 380011 | 380011 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.1.2022 | n/a | n/a |  | P.O. FOR SERVE
22-C0926 | TIRES (TUBELESS) | PEEMO | PB | 08.23.2022 | 8.26.2022 | n/a | 9.6.2022 | 9.6.2022 | 9.10-11.2022 | 9.10-11.2022 | 9.20.2022 |  |  |  |  | GF | 380480 | 380480 |  | 195080 | 195080 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.1.2022 | n/a | n/a |  | P.O. FOR SERVE
22-C0912 | OFFICE SUPPLIES | PEEMO | PB | 08.23.2022 | 8.26.2022 | n/a | 9.6.2022 | 9.6.2022 | 9.10-11.2022 | 9.10-11.2022 | 9.20.2022 |  |  |  |  | GF | 435367 | 435367 |  | 397932 | 397932 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.1.2022 | n/a | n/a |  | P.O. FOR SERVE
22-6096 | LED SMART TV | PHO | PB | 08.23.2022 | [11 empty] | TF | 50000 | 50000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
22-6098 | 43" LED TV | PHO | PB | 08.23.2022 | [11 empty] | TF | 140000 | 140000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
22-6100 | DLP 3500-5000 LUMENS PROJECTOR W/ SCREEN, SHORT THROW | PHO | PB | 08.23.2022 | [11 empty] | TF | 150000 | 150000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
22-C0997 | VETERINARY DRUGS AND BIOLOGICS | PVET | PB | 08.23.2022 | 8.26.2022 | n/a | 9.6.2022 | 9.6.2022 | 9.10-11.2022 | 9.10-11.2022 | 9.20.2022 | 10.25.2022 |  | 11.10.2022 | 11.10.2022 | GF | 293918 | 293918 |  | 293918 | 293918 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.1.2022 | n/a | n/a
22-C1008 | FABRICATION AND INSTALLATION OF BILLBOARD LABOR , MATERIALS, SIZE: 4x8 sq.ft. | PENRO | PB | 08.30.2022 | 10.1.2022 | n/a | 10.11.2022 | 10.11.2022 | 10.13-14.2022 | 10.13-14.2022 | 10.18.2022 |  |  |  |  | GF | 308000 | 308000 |  | 290000 | 290000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 10.6.2022 | n/a | n/a |  | P.O. FOR SERVE
22-C1006 | COMPUTER SUPPLIES AND LAPTOP | PENRO | PB | 08.30.2022 | 8.23.2022 | n/a | 9.20.2022 | 9.20.2022 | 9.22-23.2022 | 9.22-23.2022 | 10.4.2022 | 11.4.2022 |  |  |  | CO | 463090 | 463090 |  | 374680 | 374680 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.15.2022 | n/a | n/a |  | P.O. FOR DELIVERY
22-5255 | UNMANNED AERIAL VEHICLE | PDDRMO | PB | 6.10.2022 | 7.19.2022 | 7.26.2022 | 8.9.2022 | 8.9.2022 | 8.25-26.2022 | 8.25-26.2022 | 8.30.2022 | 11.4.2022 |  |  |  | GF | 1567960 | 1567960 |  | 1488000 | 1488000 |  | Mr. Allan Rey N. Esmael | 7.21.2022 | n/a | 8.4.2022 | n/a | n/a
22-5666 | SUPPLY AND INSTALLATION OF GLASS, | PAO | PB | 8.2.2022 | 8.8.2022 | 8.16.2022 | 8.30.2022 | 8.30.2022 | 9.1-2.2022 | 9.1-2.2022 | 9.6.2022 | 9.21.2022 |  | 11.18.2022 | 11.18.2022 | GF | 1046551 | 1046551 |  | 926551 | 926551 |  | Mr. Allan Rey N. Esmael | 8.11.2022 | n/a | 8.24.2022 | n/a | n/a
22-5261 | Benzalkonium Chloride Solution | PDRRMO | PB | 6.10.2022 | 7.10.2022 | n/a | 7.26.2022 | 7.26.2022 | 7.28-29.2022 | 7.28-29.2022 | 8.2.2022 | 9.14.2022 |  | 9.15.2022 | 9.15.2022 | GF | 999600 | 999600 |  | 553350 | 553350 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 7.21.2022 | n/a | n/a
22-4098 | Construction of Multipurpose Hall @ Barabat, | PGO | PB | 05.27.2022 | 10.7.2022 | 10.18.2022 | 11.2.2022 | 11.2.2022 | [7 empty] | GF | 1937753.2 | 1937753.2 |  | 0 |  |  | Mr. Allan Rey N. Esmael | 8.11.2022 | n/a | n/a | n/a | n/a
22-4200 | Construction of Stage and Bleachers @ Melale | PGO | PB | 05.27.2022 | 10.7.2022 | 10.18.2022 | 11.2.2022 | 11.2.2022 | [7 empty] | GF | 2912879.05 | 2912879.05 |  | 0 |  |  | Mr. Allan Rey N. Esmael | 8.11.2022 | n/a | n/a | n/a | n/a
22-6138 | POSTER, CALENDAR | PGO - IPRD | PB | 9.6.2022 | 9.10.2022 | n/a | 9.20.2022 | 9.20.2022 | 9.22-23.2022 | 9.22-23.2022 | 9.27.2022 |  |  |  |  | GF | 330000 | 330000 |  | 179450 | 179450 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.15.2022 | n/a | n/a |  | P.O. FOR SERVE
22-7008 | SUPPLY AND DELIVERY OF MATERIALS FOR | PEO | PB | 9.20.2022 | [11 empty] | GF | 654846.1 | 654846.1 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a
22-7042 | SUPPLY AND DELIVERY OF MATERIALS FOR | PEO | PB | 9.20.2022 | [11 empty] | GF | 271832.55 | 271832.55 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a
22-6939 | SUPPLY AND DELIVERY OF MATERIALS FOR | PEO | PB | 9.20.2022 | [11 empty] | GF | 592368.5 | 592368.5 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a
22-6610 | SUPPLY AND DELIVERY OF MATERIALS FOR | PEO | PB | 9.20.2022 | [11 empty] | GF | 1770155.1 | 1770155.1 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a
22-C1003 | OFFICE SUPPLIES | PGSO | PB | 9.20.2022 | 9.28.2022 | n/a | 10.4.2022 | 10.4.2022 | 10.6-7.2022 | 10.6-7.2022 | 10.11.2022 | 11.4.2022 |  | 11.14.2022 | 11.14.2022 | GF | 583697 | 583697 |  | 486605 | 486605 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.29.2022 | n/a | n/a
22-C1000 | JANITORIAL SUPPLIES | PGSO | PB | 9.20.2022 | 9.27.2022 | n/a | 10.4.2022 | 10.4.2022 | 10.6-7.2022 | 10.6-7.2022 | 10.11.2022 |  |  |  |  | GF | 364444 | 364444 |  | 302150.7 | 302150.7 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.29.2022 | n/a | n/a |  | P.O. FOR SERVE
22-C1004 | COMPUTER SUPPLIES | PGSO | PB | 9.20.2022 | 9.28.2022 | n/a | 10.4.2022 | 10.4.2022 | 10.6-7.2022 | 10.6-7.2022 | 10.11.2022 | 11.4.2022 |  | 11.14.2022 | 11.14.2022 | GF | 318901 | 318901 |  | 252317 | 252317 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.29.2022 | n/a | n/a
22-6427 | SERVICE VEHICLE PICK-UP TYPE | PAGRO | PB | 9.20.2022 | 8.2.2022 | [10 empty] | GF | 1550000 | 1550000 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | REBID; LACK OF
22-C1025 | AGRICULTURAL SUPPLIES | PAGRO | PB | 9.20.2022 | 9.27.2022 | n/a | 10.4.2022 | 10.4.2022 | 10.6-7.2022 | 10.6-7.2022 | 10.11.2022 | 11.9.2022 |  |  |  | GF | 999300 | 999300 |  | 999020 | 999020 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.29.2022 | n/a | n/a |  | P.O. FOR DELIVERY
22-6472 | FUNITURE AND FIXTURES | PIAO | PB | 9.20.2022 | 10.7.2022 | n/a | 10.18.2022 | 10.18.2022 | 11.4.2022 | 11.4.2022 | 11.8.2022 |  |  |  |  | GF | 197500 | 197500 |  | 189000 | 189000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 11.3.2022 | n/a | n/a |  | P.O. FOR SERVE
22-C1039 | MEALS WITH ACCOMMODATION | PHO | PB | 9.20.2022 | 9.28.2022 | n/a | 10.18.2022 | 10.18.2022 | 10.21.2022 | 10.21.2022 | 11.8.2022 |  |  |  |  | GF | 2538780 | 2538780 |  | 2538780 | 2538780 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 11.3.2022 | n/a | n/a |  | P.O. FOR SERVE
22-7106 | COMPUTER PRINTER 3 in 1 tank type | PGO - SEF | PB | 9.27.2022 | 10.1.2022 | n/a | 10.25.2022 | 10.25.2022 | 11.4.2022 | 11.4.2022 | 11.8.2022 |  |  |  |  | GF | 3240000 | 3240000 |  | 2624400 | 2624400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 11.3.2022 | n/a | n/a |  | P.O. FOR SERVE
22-7125 | COMPUTER TABLET | PGO - SEF | PB | 9.27.2022 | 10.15.2022 | n/a | 10.25.2022 | 10.25.2022 | 11.4.2022 | 11.4.2022 | 11.8.2022 |  |  |  |  | GF | 749500 | 749500 |  | 725000 | 725000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 11.3.2022 | n/a | n/a |  | P.O. FOR SERVE
22-7334 | CONSTRUCTION OF 1 UNIT 2 CLASSROOM | PGO - SEF | PB | 9.27.2022 | [11 empty] | GF | 2399227.92 | 2399227.92 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | REBID
22-7122 | CONSTRUCTION OF GYM, PALOC NHS | PGO - SEF | PB | 9.27.2022 | 10.7.2022 | 10.18.2022 | 11.2.2022 | 11.2.2022 | [7 empty] | GF | 4954026.16 | 4954026.16 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | REBID
22-6393 | HANGING WEIGHING SCALE (0-59 months) | PHO | PB | 9.27.2022 | 10.1.2022 | n/a | 10.11.2022 | 10.11.2022 | 10.13-14.2022 | 10.13-14.2022 | 10.18.2022 |  |  |  |  | GF | 399000 | 399000 |  | 213740 | 213740 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 10.6.2022 | n/a | n/a |  | P.O. FOR SERVE
22-7399 | CONSTRUCTION OF MULTI-PURPOSE HALL | PEO | PB | 10.6.2022 | [11 empty] | GF | 1394873.65 | 1394873.65 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a
22-6100 | DLP 3500-5000 LUMENS PROJECTOR W/ | PHO | PB | 10.6.2022 | [11 empty] | GF | 150000 | 150000 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a
22-C1074 | LABORATORY SUPPLIES/ RE-AGENT | PGO-PS | PB | 10.6.2022 | 10.7.2022 | n/a | 10.18.2022 | 10.18.2022 | 11.4.2022 | 11.4.2022 | 11.8.2022 |  |  |  |  | GF | 372950 | 372950 |  | 310600 | 310600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 11.3.2022 | n/a | n/a
22-7619 | EQUIPMENT AND SOFTWARE | VGO | PB | 10.11.2022 | [11 empty] | GF | 1650000 | 1650000 |  | 0 |  |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-7790 | CONSTRUCTION OF COVERED COURT | PGO-PS | PB | 10.11.2022 | [11 empty] | GF | 3751603.89 | 3751603.89 |  | 0 |  |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-2266 | SOIL INVESTAGATION TEST | PPDO | PB | 10.11.2022 | 11.4.2022 | n/a | 11.15.2022 | 11.15.2022 | 11.17-18.2022 | 11.17-18.2022 | 11.22.2022 |  |  |  |  | GF | 240000 | 240000 |  | 238560 | 238560 |  | Ms. Grace V. Quintana | n/a | n/a | 11.10.2022 | n/a | n/a
22-7337 | MEALS WITH ACCOMMODATION AND | PGO-SEF | PB | 10.11.2022 | 11.4.2022 | n/a | 11.15.2022 | 11.15.2022 | 11.17-18-2022 | 11.17-18.2022 | 11.22.2022 |  |  |  |  | GF | 711330 | 711330 |  | 711330 | 711330 |  | Ms. Grace V. Quintana | n/a | n/a | 11.17.2022 | n/a | n/a
22-7599 | PRINTING ANG PUBLICATION RESEARCH | PGO-SEF | PB | 10.11.2022 | 10.22.2022 | n/a | 11.8.2022 | 11.8.2022 | 11.17-18.2022 | 11.17-18.2022 | 11.22.2022 |  |  |  |  | GF | 699800 | 699800 |  | 528999.68 | 528999.68 |  | Ms. Grace V. Quintana | n/a | n/a | 11.17.2022 | n/a | n/a
22-7367 | LED SMART TV 50" | PGO-SEF | PB | 10.11.2022 | 11.4.2022 | n/a | 11.15.2022 | 11.15.2022 | 11.17-18-2022 | 11.17-18.2022 | 11.22.2022 |  |  |  |  | GF | 50000 | 50000 |  | 42000 | 42000 |  | Ms. Grace V. Quintana | n/a | n/a | 11.17.2022 | n/a | n/a
22-7429 | DRONE CAMERA AND ACCESSORIES | PGO-SEF | PB | 10.11.2022 | [11 empty] | GF | 100000 | 100000 |  | 0 |  |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-C1054 | DRUGS AND MEDS | PEEMO | PB | 10.11.2022 | [11 empty] | GF | 9324575.76 | 9324575.76 |  | 0 |  |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-8035 | FLUIDS | PEEMO | PB | 10.11.2022 | 10.12.2022 | n/a | 11.8.2022 | 11.8.2022 | 11.18.2022 | 11.18.2022 | 11.29.2022 |  |  |  |  | GF | 674886 | 674886 |  | 525440 | 525440 |  | Ms. Grace V. Quintana | n/a | n/a | 11.24.2022 | n/a | n/a |  | P.O. FOR SERVE
22-C0880 | COMPUTER DESKTOP, i5 (9th GENERATION) | PAO ADMIN | PB | 10.18.2022 | [11 empty] | GF | 237980 | 237980 |  | 0 |  |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-C1063 | SUPPLY AND DELIVERY OF HOSPITAL AND | PGO | PB | 9.27.2022 | 10.1.2022 | n/a | 10.11.2022 | 10.11.2022 | 10.13-14.2022 | 10.13-14.2022 | 10.18.2022 |  |  |  |  | GF | 663000 | 663000 |  | 192800 | 192800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 10.6.2022 | n/a | n/a
22-7500 | SUPPLY AND DELIVERY OF HOSPITAL AND | PGO | PB | 9.27.2022 | 10.1.2022 | n/a | 10.11.2022 | 10.11.2022 | 10.13-14.2022 | 10.13-14.2022 | 10.18.2022 |  |  |  |  | GF | 460283.4 | 460283.4 |  | 338434 | 338434 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 10.6.2022 | n/a | n/a
22-8002 | SUPPLY AND INSTALLATION OF ALLUMINUM | PAO-ADMIN | PB | 10.25.2022 | 11.4.2022 | n/a | 11.15.2022 | 11.15.2022 | 11.17-18.2022 | 11.17-18.2022 | 11.22.2022 |  |  |  |  | GF | 525422.17 | 525422.17 |  | 524000 | 524000 |  | Engr. Michael C. Salarda | n/a | n/a | 11.10.2022 | n/a | n/a
22-C1122 | PAINTING MATERIALS | PAO-ADMIN | PB | 10.25.2022 | 11.22.2022 | n/a | 11.29.2022 | 11.29.2022 | [7 empty] | GF | 26886 | 26886 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
22-C1122 | CONSTRUCTION SUPPLIES | PAO-ADMIN | PB | 10.25.2022 | n/a | n/a | 11.29.2022 | 11.29.2022 | n/a | n/a | [5 empty] | GF | 731838.6 | 731838.6 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
22-7567 | WHEEL BOLT FOR SADDAM | PGSO | PB | 10.25.2022 | 9.26.2022 | [10 empty] | GF | 119400 | 119400 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
22-8008 | COMPLETE STUDIO LIGHTS | PGO-SEF | PB | 11.8.2022 | 10.11.2022 | [10 empty] | GF | 60000 | 60000 |  | 11740 | 11740 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-8158 | DSLR CAMERA WITH COMPLETE | PGO-SEF | PB | 11.8.2022 | 10.18.2022 | [10 empty] | GF | 150000 | 150000 |  | 16480 | 16480 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-8162 | TV MONITOR/PLASMA | PGO-SEF | PB | 11.8.2022 | 10.18.2022 | [10 empty] | GF | 200000 | 200000 |  | 3800 | 3800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-8161 | PORTABLE TELEPROMPTER | PGO-SEF | PB | 11.8.2022 | [11 empty] | GF | 32000 | 32000 |  | 18920 | 18920 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-8163 | TV STUDIO TABLE | PGO-SEF | PB | 11.8.2022 | 10.18.2022 | [10 empty] | GF | 50000 | 50000 |  | 39270 | 39270 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-7989 | GREEN SCREEN BACK DROP | PGO-SEF | PB | 11.8.2022 | [11 empty] | GF | 20000 | 20000 |  | 27000 | 27000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-8027 | VISION MIXER | PGO-SEF | PB | 11.8.2022 | 10.11.2022 | [10 empty] | GF | 180000 | 180000 |  | 36408 | 36408 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-8011 | HEAVY DUTY ADJUSTABLE | PGO-SEF | PB | 11.8.2022 | [11 empty] | GF | 30000 | 30000 |  | 11200 | 11200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-8028 | LAPEL MICRPHONE WITH BUILT-IN | PGO-SEF | PB | 11.8.2022 | [11 empty] | GF | 15590 | 15590 |  | 15590 | 15590 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-7200 | CONSTRUCTION OF SOCIAL HALL | PGO-SEF | PB | 11.8.2022 | 8.25.2022 | [10 empty] | GF | 1950688.46 | 1950688.46 |  | 11654 | 11654 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-8210 | COMPUTER DESKTOP, i5 (9th Generation) | PAO | PB | 11.8.2022 | [11 empty] | GF | 49000 | 49000 |  | 17635 | 17635 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-C1015 | COMPUTER SUPPLIES and LAPTOP | PAGRO | PB | 11.8.2022 | [11 empty] | GF | 400790 | 400790 |  | 52236 | 52236 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-C1065 | CONSTRUCTION SUPPLIES | PGO-PS | PB | 11.8.2022 | [11 empty] | GF | 297133 | 297133 |  | 6270 | 6270 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-7556 | PORTLAND, CEMENT (40kg/s) | PGO-PS | PB | 11.8.2022 | 9.26.2022 | [10 empty] | GF | 297700 | 297700 |  | 14774 | 14774 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-7987 | PAPER, BOND, PG A4, 210mm x 297mm, | PGO-SEF | PB | 11.8.2022 | 10.11.2022 | [10 empty] | GF | 1495000 | 1495000 |  | 2500 | 2500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-C1058 | COMPUTER TABLET | PGO-SEF | PB | 11.8.2022 | [11 empty] | GF | 172950 | 172950 |  | 54000 | 54000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-7476 | PROFESSIONAL VIDEO CAMERA/ | PGO-SEF | PB | 11.8.2022 | 9.20.2022 | [10 empty] | GF | 300000 | 300000 |  | 75000 | 75000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-7984 | INK EPSON, T6641 BLACK, T6642 CYAN, | PGO-SEF | PB | 11.8.2022 | 10.11.2022 | [10 empty] | GF | 500580 | 500580 |  | 16900 | 16900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-C1161 | FURNITURE AND FIXTURES | PDRRMO | PB | 11.8.2022 | [11 empty] | GF | 580550 | 580550 |  | 25387.5 | 25387.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-7499 | SUPPLY AND DELIVERY OF LABORATORY | PGO-PS | PB | 10.4.2022 | 10.1.2022 | n/a | 10.25.2022 | 10.25.2022 | 11.7.2022 | 11.7.2022 | 11.8.2022 |  |  |  |  | GF | 1146795 | 1146795 |  | 175853.99 | 175853.99 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 11.3.2022 | n/a | n/a |  | P.O. FOR SERVE
22-8361 | PORTLAND CEMENT | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [11 empty] | 87360 | 87360 |  | 0
| PORTLAND CEMENT | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [11 empty] | 87360 | 87360 |  | 0
| PORTLAND CEMENT | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [11 empty] | 87360 | 87360 |  | 0
| PORTLAND CEMENT | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [11 empty] | 87360 | 87360 |  | 0
| PORTLAND CEMENT | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [11 empty] | 92040 | 92040 |  | 0
| PORTLAND CEMENT | PGO-PS | PB | 11.15.2022 | n/a | [11 empty] | 1560 | 1560 |  | 0
22-8361 | PORTLAND CEMENT | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [11 empty] | 92040 | 92040 |  | 0
22-8363 | ROOFING MATERIALS | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [10 empty] | GF | 51477 | 51477 |  | 125000 | 125000 |  |  | n/a | n/a | n/a | n/a | n/a
| ROOFING MATERIALS | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [10 empty] | GF | 51477 | 51477 |  | 445695 | 445695 |  |  | n/a | n/a | 05.12.2022 | n/a | n/a |  | FOR DELIVERY
| ROOFING MATERIALS | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [10 empty] | GF | 51477 | 51477 |  | 539219 | 539219 |  |  | n/a | n/a | 05.12.2022 | n/a | n/a |  | P.O FOR APPROVAL
| ROOFING MATERIALS | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [10 empty] | GF | 51477 | 51477 |  | 261741 | 261741 |  |  | n/a | n/a | 05.12.2022 | n/a | n/a |  | P.O FOR APPROVAL
| ROOFING MATERIALS | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [10 empty] | GF | 51477 | 51477 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| ROOFING MATERIALS | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [10 empty] | GF | 51477 | 51477 |  | 0 |  |  |  |  | n/a | n/a | n/a | n/a
| ROOFING MATERIALS | PGO-PS | PB | 11.15.2022 | [11 empty] | GF | 25070 | 25070 |  | 0 |  |  |  |  | n/a |  | n/a | n/a
| CONSTRUCTION MATERIALS | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [10 empty] | GF | 356051 | 356051 |  | 0 |  |  |  |  | n/a |  | n/a | n/a
| CONSTRUCTION MATERIALS | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [10 empty] | GF | 359879 | 359879 |  | 0 |  |  |  |  | n/a |  | n/a | n/a
22-8363 | CONSTRUCTION MATERIALS | PGO-PS | PB | 11.15.2022 | 10.26.2022 | [10 empty] | GF | 100873 | 100873 |  | 0 |  |  |  |  | n/a | n/a | n/a | n/a |  | RETURNED TO R.O
22-C1087 | ELECTRONIC SUPPLIES | PGO-PS | PB | 11.15.2022 | [11 empty] | GF | 0 |  |  | 0 |  |  |  |  | n/a | n/a | n/a | n/a
| ELECTRONIC SUPPLIES | PGO-PS | PB | 11.15.2022 | [11 empty] | GF | 62698 | 62698 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| ELECTRONIC SUPPLIES | PGO-PS | PB | 11.15.2022 | [11 empty] | GF | 21985 | 21985 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| ELECTRICAL SUPPLIES | PGO-PS | PB | 11.15.2022 | [11 empty] | GF | 25884 | 25884 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| ELECTRICAL SUPPLIES | PGO-PS | PB | 11.15.2022 | [11 empty] | GF | 25000 | 25000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1087 | ELECTRICAL SUPPLIES | PGO-PS | PB | 11.15.2022 | [11 empty] | GF | 11400 | 11400 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8324 | CONSTRUCTION OF BLEACHERS | PGO-PS | PB | 11.15.2022 | 10.25.2022 | [10 empty] | GF | 1853215.33 | 1853215.33 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1167 | RICE (WELL MILLED) 50 kg. | PGO | PB | 11.15.2022 | [11 empty] | GF | 900000 | 900000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8105 | JOB ORDER: INSTALLATION OF CCTV | PDRRMO | PB | 11.15.2022 | [11 empty] | GF | 160000 | 160000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8167 | USAR EMERGENCY RESPONSE VEHICLE | PDRRMO | PB | 11.15.2022 | 10.19.2022 | [10 empty] | GF | 6500000 | 6500000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1187 | DESKTOP COMPUTER and LAPTOP | PDRRMO | PB | 11.15.2022 | [11 empty] | GF | 495000 | 495000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-7183 | REHABILITATION OF DRAINAGE STRUCTURE | PDRRMO | PB | 11.15.2022 | 8.25.2022 | [10 empty] | GF | 2268269.88 | 2268269.88 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-7372 | ADVERTISEMENT (PRINT ADS) | PAO-ID | PB | 11.15.2022 | 9.6.2022 | [10 empty] | GF | 100000 | 100000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8179 | FURNITURE AND FIXTURES | PAO-ADMIN | PB | 11.15.2022 |  | 11.29.2022 | [9 empty] | GF | 1704650 | 1704650 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8545 | FLATBED SCANNER | COA | PB | 11.15.2022 | 11.3.2022 | [10 empty] | GF | 93495 | 93495 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8317 | COMPUTER LAPTOP, PORTABLE SOUND | PIAO | PB | 11.15.2022 | 10.25.2022 | [10 empty] | GF | 96388 | 96388 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8317 | COMPUTER DESKTOP | PACCO | PB | 11.15.2022 | 10.25.2022 | [10 empty] | GF | 97800 | 97800 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1249 | ELECTROLYTES REAGENT W/ ISO | PGO-PS | PB | 11.15.2022 | [11 empty] | GF | 392000 | 392000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1261 | RICE (WELL MILLED) 50 KG/SACK | PEEMO | PB | 11.15.2022 | [11 empty] | GF | 607500 | 607500 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1265 | LUBRICANTS | PEEMO | PB | 11.15.2022 | [11 empty] | GF | 79152.5 | 79152.5 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8850 | MEDICAL SUPPLIES | PGO-PS | PB | 11.15.2022 | [11 empty] | GF | 1198000 | 1198000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8845 | MEDICAL SUPPLIES | PGO-PS | PB | 11.15.2022 | [11 empty] | GF | 1198000 | 1198000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1064 | SUPPLY AND DELIVERY OF MEDICAL | PGO-PS | PB | 9.27.2022 | 10.1.2022 | 10.11.2022 | 10.25.2022 | 10.25.2022 | 11.11.2022 | 11.11.2022 | [5 empty] | GF | 5994990 | 5994990 |  | 3162747 | 3162747 |  |  | n/a | n/a | 10.20.2022 | n/a | n/a |  | P.O. FOR SERVE
22-C1289 | ORDINARY STICKER, STICKER | PDRRMO | PB | 11.22.2022 | [11 empty] | GF | 546560 | 546560 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a
22-C1213 | COMPUTER SOFTWARE | PHO | PB | 11.22.2022 | [11 empty] | GF | 516848 | 516848 |  | 0 |  |  |  | n/a | n/a | 05.24.2022 | n/a | n/a |  | P.O FOR APPROVAL
22-8879 | COMPUTER DESKTOP (MID RANGE) | PHO | PB | 11.22.2022 | [11 empty] | GF | 146700 | 146700 |  | 0 |  |  |  | n/a | n/a | 05.31.2022 | n/a | n/a |  | P.O FOR APPROVAL
22-8527 | DATA BASE SERVER PACKAGE | PICTO | PB | 11.22.2022 | [11 empty] | GF | 330000 | 330000 |  | 0 |  |  |  | n/a | n/a | 05.24.2022 | n/a | n/a
22-8214 | CHILDREN'S DESKTOP AND CHAIR | PGO-SEF | PB | 11.22.2022 | [11 empty] | GF | 1199350 | 1199350 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-7369 | SOUNDSYSTEM WITH COMPLETE | PGO-SEF | PB | 11.22.2022 | [11 empty] | GF | 170000 | 170000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1182 | COLORED PRINTER W/ SCANNER | PGO-SEF | PB | 11.22.2022 | [11 empty] | GF | 240900 | 240900 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | FOR DELIVERY
22-C1030 | OFFICE SUPPLIES | PGSO | PB | 11.22.2022 | [11 empty] | GF | 27675 | 27675 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a
22-8731 | PORTLAND CEMENT | PEO-RCPC | PB | 11.22.2022 | [11 empty] | GF | 390000 | 390000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8860 | UPGRADING OF HOSPITAL BUILDING | PEO | PB | 11.22.2022 | [11 empty] | GF | 1583244.96 | 1583244.96 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8856 | UPDATING OF HOSPITAL BUILDING | PEO | PB | 11.22.2022 | [11 empty] | GF | 1549654.01 | 1549654.01 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1234 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 47296 | 47296 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1286 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 111615 | 111615 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8554 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 1630 | 1630 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1277 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 111615 | 111615 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1065 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 594833 | 594833 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1266 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 71221 | 71221 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1287 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 111615 | 111615 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1196 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 47296 | 47296 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1273 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 515883 | 515883 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8786 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 35097 | 35097 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1199 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 47296 | 47296 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1226 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 14050 | 14050 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1274 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 453628 | 453628 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1068 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 1301998 | 1301998 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8908 | CONSTRUCTION SUPPLIES | PEO | PB | 11.22.2022 | [11 empty] | GF | 131870 | 131870 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8726 | DRAWER GUIDE, HEAVY DUTY BEARING | PEO | PB | 11.22.2022 | [11 empty] | GF | 9875 | 9875 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1276 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 2160 | 2160 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1219 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 2160 | 2160 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1217 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 2160 | 2160 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8880 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 18168 | 18168 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8892 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 30825 | 30825 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1255 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 7860 | 7860 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1233 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 2160 | 2160 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1246 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 77159.7 | 77159.7 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1267 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | TF | 58293.57 | 58293.57 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1258 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 2160 | 2160 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8803 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 60600.15 | 60600.15 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1256 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 110985.3 | 110985.3 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1257 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 2160 | 2160 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1270 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 74010.6 | 74010.6 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1225 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 2160 | 2160 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8816 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 88113.27 | 88113.27 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8910 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 1248 | 1248 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1293 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 2160 | 2160 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8902 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 11880 | 11880 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-C1216 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 2160 | 2160 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | FOR DELIVERY
22-C1198 | GEMELINA LUMBER OR EQUIVALENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 2160 | 2160 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
22-8868 | PORTLAND CEMENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 92040 | 92040 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O FOR APPROVAL
22-8890 | PORTLAND CEMENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 70980 | 70980 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | FOR DELIVERY
22-8735 | PORTLAND CEMENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 241540 | 241540 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | FOR DELIVERY
22-8781 | PORTLAND CEMENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 299260 | 299260 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | FOR DELIVERY
22-8812 | PORTLAND CEMENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 712140 | 712140 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | FOR DELIVERY
22-7586 | PORTLAND CEMENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 309140 | 309140 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O
22-8339 | PORTLAND CEMENT | PEO | PB | 11.22.2022 | [11 empty] | GF | 87360 | 87360 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O
22-C1379 | RICE (WELL MILLED) | PGO | PB | 11.29.2022 | [11 empty] | GF | 2200 | 2200 |  | 2200 | 2200 |  |  | n/a | n/a | n/a | n/a | n/a
22-9143 | PUBLICATION (AS PER SAMPLE) | PTO | PB | 11.29.2022 | [11 empty] | GF | 7731 | 7731 |  | 7731 | 7731 |  |  | n/a | n/a | n/a | n/a | n/a

## SB-SA-SVP-NP-SVP
ANNEX B
|  | (Provincial Government of Davao de Oro) Procurement Monitoring Report as of JULY/30/2022 | [18 empty] | (Provincial Government of Davao de Oro) Procurement Monitoring Report as of June/30/2022
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Mode of Procurement | [8 empty] | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  | LIST OF OBSERVERS |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Delivery/Completion/Acceptance (If Applicable) | REMARKS (explaining changes from the APP) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5429 | UTILITY/PLASTIC BOX (20 LTRS) | PACCO | SVP | 07.13.2022 | 7.28.2022 | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.9.2022 |  | 9.29.2022 | 9.29.2022 | GF | 200000 | 200000 |  | 199500 | 199500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-959 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5427 | LABORATORY REAGENTS | PEEMO | SVP | 07.13.2022 | [11 empty] | GF | 100000 | 100000 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
22-5447 | LABORATORY SUPPLIES | PEEMO | SVP | 07.13.2022 | [11 empty] | GF | 48000 | 48000 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
22-5415 | FLASH DRIVE 32GB | PVET | SB | 07.13.2022 | [11 empty] | GF | 3200 | 3200 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5436 | JANITORIAL SUPPLIES | PVET | SB | 07.13.2022 | [11 empty] | GF | 3325 | 3325 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0809 | SPAPREPARTS (LIGHT VEHICLE) | PGSO | SA | 07.13.2022 | n/a | n/a | n/a | n/a | 9.12.2022 | n/a | n/a | 9.15.2022 |  |  |  | GF | 12250 | 12250 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-06-869 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5370 | SPAREPARTS (ISUZU FORWARD) | PDRRMO | SA | 07.13.2022 | n/a | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.16.2022 |  | 9.21.2022 | 9.21.2022 | TF | 15425 | 15425 |  | 15320 | 15320 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-942 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5379 | OFFICE SUPPLIES | PHRMDO | SVP | 07.13.2022 | [11 empty] | GF | 100000 | 100000 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
22-C0807 | OFFICE SUPPLIES | PEO | SB | 7.13.2022 | 7.28.2022 | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.9.2022 |  | 9.13.2022 | 9.13.2022 | GF | 218185 | 218185 |  | 217575 | 217575 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-975 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5365 | COMPUTER SUPPLIES | PEO | SB | 07.13.2022 | 6.14.2022 | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.16.2022 |  | 9.29.2022 | 9.29.2022 | GF | 191800 | 191800 |  | 183820 | 183820 |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a
22-08-943 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5371 | TARPAULIN | PEO | SVP | 07.13.2022 | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.14.2022 |  |  |  | GF | 32000 | 32000 |  | 32000 | 32000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-965 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5381 | MINERAL WATER | PGO | SVP | 07.13.2022 | n/a | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 |  |  |  |  | GF | 22500 | 22500 |  | 22000 | 22000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O FOR SERVE
22-08-955 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5555 | FOOD SUPPLIES (MEALS & SNACKS) | PAO-TOURISM | SVP | 07.19.2022 | 6.21.2022 | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.14.2022 |  |  |  | GF | 100000 | 100000 |  | 100000 | 100000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-08-946 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5561 | TARPAULIN | PAO-TOURISM | SVP | 07.19.2022 | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.14.2022 |  |  |  | GF | 17500 | 17500 |  | 17500 | 17500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-08-966 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0868 | HEMATOLOGY CONTROL | PEEMO | SVP | 07.19.2022 | 7.28.2022 | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 10.11.2022 |  | 11.22.2022 | 11.22.2022 | GF | 180000 | 180000 |  | 180000 | 180000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-952 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0867 | HBA1c TEST (GLYCATED HAEMOGLOBIN A1c) | PEEMO | SVP | 07.19.2022 | n/a | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.27.2022 |  | 9.30.2022 | 9.30.2022 | GF | 48000 | 48000 |  | 48000 | 48000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-953 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5658 | FOOD SUPPLIES (MEALS & SNACKS) | VGO | SVP | 07.26.2022 | 7.11.2022 | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.26.2022 |  | 9.22.2022 | 9.22.2022 | GF | 80000 | 80000 |  | 80000 | 80000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-948 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5641 | AIRCON MAINTENANCE | SPO | SVP | 07.26.2022 | 7.28.2022 | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.9.2022 |  | 10.12.2022 | 10.12.2022 | GF | 65000 | 65000 |  | 65000 | 65000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-963 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5698 | FOOD SUPPLIES | COA | SVP | 07.26.2022 | 7.13.2022 | n/a | n/a | 7.28.2022 | n/a | n/a | 8.2.2022 | 9.2.2022 |  | 8.3.2022 | 8.3.2022 | GF | 72000 | 72000 |  | 72000 | 72000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-940 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
22-5500 | BATTERIES (HEAVY EQUIPEMENT) | PEO-EQPT. POOL | SVP | 07.26.2022 | 6.20.2022 | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.16.2022 |  | 9.22.2022 | 9.22.2022 | GF | 136000 | 136000 |  | 133600 | 133600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-951 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0827 | EQUIPMENT POOL SUPPLIES | PEO-EQPT. POOL | SVP | 07.26.2022 | 7.28.2022 | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.14.2022 |  | 11.8.2022 | 11.8.2022 | GF | 76000 | 76000 |  | 75850 | 75850 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-958 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0854 | FOOD SUPPLIES | PHRMDO | SVP | 07.26.2022 | n/a | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.14.2022 |  | 11.8.2022 | 11.8.2022 | GF | 199250 | 199250 |  | 199250 | 199250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-947 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5851 | GENERAL CLEANING OF 2 SEPTIC TANKS | PGSO | SVP | 07.26.2022 | n/a | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.9.2022 |  | 9.13.2022 | 9.13.2022 | GF | 36000 | 36000 |  | 36000 | 36000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-949 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-08-063 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5638 | FOOD SUPPLIES | PGSO | SVP | 07.26.2022 | 7.11.2022 | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.14.2022 |  | 9.13.2022 | 9.13.2022 | GF | 60000 | 60000 |  | 60000 | 60000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-950 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0877 | AGRICULTURAL SUPPLIES | PGSO | SVP | 07.26.2022 | 7.28.2022 | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.14.2022 |  | 9.23.2022 | 9.23.2022 | GF | 78080 | 78080 |  | 78071.5 | 78071.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-962 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-08-939 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-09-103 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6222 | FOOD SUPPLIES | PSWDO | SVP | 08.02.2022 | 8.4.2022 | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.26.2022 |  | 8.16.2022 | 8.16.2022 | GF | 200000 | 200000 |  | 200000 | 200000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-970 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5828 | REFRIGERATOR 5 CU. FT. | PAO-ADMIN | SVP | 08.02.2022 | [11 empty] | GF | 10600 | 10600 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0881 | FAN STAND 18"/WATER DISPENSER (HOT & COLD) | PAO-ADMIN | SVP | 08.02.2022 | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.14.2022 |  | 10.27.2022 | 10.27.2022 | GF | 37637.5 | 37637.5 |  | 37635 | 37635 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-969 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5869 | COLORED PRINTER, 3N1 TANK/COMPUTER SUPPLIES | PAO-ADMIN | SVP | 08.02.2022 | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.9.2022 |  | 9.20.2022 | 9.20.2022 | GF | 24125 | 24125 |  | 20450 | 20450 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-973 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6248 | MAIN BOARD/PARAMETER BOARD | DDOPH | SVP | 08.16.2022 | [11 empty] | GF | 50000 | 50000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | RETURNED TO R.O.
|  | MONTEVISTA | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6250 | JOB ORDER (REPAIR AND MAINTENANCE OF HOSPITAL EQUIPMENT) | DDOPH MONTEVISTA | SVP | 08.16.2022 | [11 empty] | GF | 16000 | 16000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
22-6238 | JOB ORDER: PREVENTIVE MAINTENANCE & | DDPH MONTEVISTA | SVP | 9.6.2022 | 7.28.2022 | n/a | n/a | 9.22.2022 | n/a | n/a | 9.27.2022 | 10.25.2022 |  | 11.14.2022 | 11.14.2022 | GF | 60000 | 60000 |  | 60000 | 60000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-179 | CALIBRATION PM FOR SHIMADZO RAD | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| SPEED MF | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
| GRAVEL QUARRY RESOURCES AND | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| STICKER OUTDOOR | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5908 | ACCOUNTABLE FORMS #906 | PTO | NP | 08.16.2022 | 7.20.2022 | n/a | n/a | 10.6.2022 | n/a | n/a | 10.11.2022 |  |  |  |  | GF | 375000 | 375000 |  | 211560 | 211560 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-203 | (COMMUNITY RAX CERTIFICATE INDIVUAL) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6447 | LED PANEL LIGHT/LED SLIM DOWNLIGHT | VGO | SVP | 08.16.2022 | 8.19.2022 | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.20.2022 |  | 9.23.2022 | 9.23.2022 | GF | 71000 | 71000 |  | 71000 | 71000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-053 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5552 | SPAREPARTS (LIGHT VEHICLE) | PGSO | SA | 08.23.2022 | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.25.2022 |  | 9.27.2022 | 9.27.2022 | GF | 11340 | 11340 |  | 11380 | 11380 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-117 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6947 | SPAREPARTS (MOTORCYCLE) | PGSO | SA | 08.23.2022 | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 9.19.2022 | 9.19.2022 | GF | 5650 | 5650 |  | 5650 | 5650 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-096 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6955 | SPAREPARTS (LIGHT VEHICLE) | PGSO | SA | 08.23.2022 | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.25.2022 |  | 9.27.2022 | 9.27.2022 | GF | 19965 | 19965 |  | 19958 | 19958 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-119 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6941 | SPAREPARTS (LIGHT VEHICLE) | PGSO | SA | 08.23.2022 | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 11.4.2022 |  | 11.4.2022 | 11.4.2022 | GF | 24540 | 24540 |  | 24540 | 24540 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-115 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6912 | SPAREPARTS (LIGHT VEHICLE) | PGSO | SA | 08.23.2022 | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.25.2022 |  | 9.27.2022 | 9.27.2022 | GF | 14000 | 14000 |  | 13995 | 13995 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-118 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[20 empty] | 0 |  |  | Engr. Michael C. Salarda
22-6223 | SPAREPARTS (LIGHT VEHICLE) | PGSO | SA | 08.23.2022 | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.26.2022 |  | 10.3.2022 | 10.3.2022 | GF | 25545 | 25545 |  | 25545 | 25545 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-116 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6951 | SPAREPARTS (LIGHT VEHICLE) | PGSO | SA | 08.23.2022 | 8.17.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 11.21.2022 |  | 11.23.2022 | 11.23.2022 | GF | 84738 | 84738 |  | 82170 | 82170 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-09-120 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6948 | SPAREPARTS (MOTORCYCLE) | PGSO | SA | 08.23.2022 | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 9.19.2022 | 9.19.2022 | GF | 2100 | 2100 |  | 2100 | 2100 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-095 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0921 | RICE (WELL MILLED) | PEEMO | SVP | 08.23.2022 | 8.25.2022 | n/a | n/a | 9.22.2022 | n/a | n/a | 9.27.2022 | 10.26.2022 |  | 10.27.2022 | 10.27.2022 | GF | 551250 | 551250 |  | 546350 | 546350 |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a
22-09-172 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-09-164 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0917 | FOOD SUPPLIES (GROCERIES) | PEEMO | SVP | 08.23.2022 | 8.26.2022 | n/a | 9.6.2022 | 9.6.2022 | 9.10-11.2022 | 9.10-11.2022 | 9.20.2022 | 10.25.2022 |  | 11.4.2022 | 11.4.2022 | GF | 206689 | 206689 |  | 204379 | 204379 |  | Mr. Allan Rey N. Esmael | n/a | n/a | 9.1.2022 | n/a | n/a
22-09-163 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6691 | SPAREPARTS (REPAIR & MAINTENANCE) | PEO-EP | SA | 08.23.2022 | [11 empty] | GF | 200000 | 200000 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6562 | GEMELINA LUMBER OR EQUIVALENT | PAO-TOURISM | SVP | 08.23.2022 | [11 empty] | GF | 8750 | 8750 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1007 | LABORATORY SUPPLIES | PENRO | SVP | 08.30.2022 | 8.31.2022 | n/a | n/a | 11.10.2022 | n/a | n/a | 11.15.2022 |  |  |  |  | GF | 130420 | 130420 |  | 117020 | 117020 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-231 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6981 | CONVEYOR BELT (14x3 ply) | PENRO | SVP | 08.30.2022 | n/a | n/a | n/a | 9.22.2022 | n/a | n/a | 9.27.2022 | 10.26.2022 |  | 11.2.2022 | 11.2.2022 | GF | 22500 | 22500 |  | 22425 | 22425 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-175 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6984 | LABORATORY SUPPLIES | PENRO | SVP | 08.30.2022 | [11 empty] | GF | 44000 | 44000 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0769 | JANITORIAL SUPPLIES | PGO | SB | n/a | n/a | n/a | n/a | 7.14.2022 | n/a | n/a | 7.19.2022 | 9.2.2022 |  | 9.9.2022 | 9.9.2022 | GF | 27634 | 27634 |  | 27634 | 27634 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-07-924 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5091 | OFFICE SUPPLIES | PGO | SB | 6.15.2022 | n/a | n/a | n/a | 7.14.2022 | n/a | n/a | 7.19.2022 | 8.23.2022 |  | 9.1.2022 | 9.1.2022 | GF | 56315 | 56315 |  | 56315 | 56315 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-07-925 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5081 | INK, EPSON | PGO | SB | n/a | n/a | n/a | n/a | 7.14.2022 | n/a | n/a | 7.19.2022 | 8.19.2022 |  | 8.26.2022 | 8.26.2022 | GF | 6050 | 6050 |  | 5995 | 5995 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-07-926 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5104 | RING BINDER AND PVC COVER | PACCO | SB | n/a | n/a | n/a | n/a | 7.14.2022 | n/a | n/a | 7.19.2022 | 8.19.2022 |  | 9.6.2022 | 9.6.2022 | GF | 10800 | 10800 |  | 10800 | 10800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-07-927 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-4712 | ALCOHOL, RUBBING 70% ETHYL, 500ML | PAGRO | SB | n/a | n/a | n/a | n/a | 7.14.2022 | n/a | n/a | 7.19.2022 | 8.19.2022 |  | 9.6.2022 | 9.6.2022 | GF | 4750 | 4750 |  | 4750 | 4750 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-07-928 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0746 | COMPUTER SUPPLIES | PAGRO | SB | n/a | n/a | n/a | n/a | 7.14.2022 | n/a | n/a | 7.19.2022 | 8.19.2022 |  | 8.26.2022 | 8.26.2022 | GF | 30000 | 30000 |  | 30000 | 30000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-07-929 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-4091 | SURGICAL MASK, 3 PLY | PVO | SVP | n/a | n/a | n/a | n/a | 7.14.2022 | n/a | n/a | 7.19.2022 | 8.19.2022 |  | 9.6.2022 | 9.6.2022 | GF | 480 | 480 |  | 480 | 480 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-07-930 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0698 | CONSTRUCTION SUPPLIES | PENRO | SVP | n/a | 06.04.2022 | n/a | n/a | 7.14.2022 | n/a | n/a | 7.19.2022 | 8.19.2022 |  | 8.30.2022 | 8.30.2022 | GF | 147868.8 | 147868.8 |  | 147867 | 147867 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-07-931 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0722 | CHB MOULDER | PEO | SVP | n/a | n/a | n/a | n/a | 7.14.2022 | n/a | n/a | 7.19.2022 | 10.6.2022 |  |  |  | GF | 26250 | 26250 |  | 26170 | 26170 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-07-932 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0720 | TARPAULIN | PEO | SVP | n/a | n/a | n/a | n/a | 7.14.2022 | n/a | n/a | 7.19.2022 | 10.5.2022 |  |  |  | GF | 4800 | 4800 |  | 4800 | 4800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-07-933 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0721 | FIRE EXTINGUISHER, 10LBS CAPACITY, | PEO | SVP | n/a | n/a | n/a | n/a | 7.14.2022 | n/a | n/a | 7.19.2022 | 10.6.2022 |  | 10.10.2022 | 10.10.2022 | GF | 13650 | 13650 |  | 9600 | 9600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-07-934 | WALL MOUNTED | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-08-062 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-09-105 | TINTING, AND REMOVAL OF CRACKED/ | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| DAMAGE WINDOW GLASS. | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-08-935 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-3815 | SPAREPARTS | PDDRMO | SA | n/a | n/a | n/a | n/a | 7.28.2022 | n/a | n/a | 8.2.2022 | 9.2.2022 |  | 7.4.2022 | 7.4.2022 | TF | 14205 | 14205 |  | 14205 | 14205 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-938 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5645 | COMPUTER SUPPLIES | SPO-SEC | SB | n/a | n/a | n/a | n/a | 7.28.2022 | n/a | n/a | 8.2.2022 | 9.9.2022 |  | 9.15.2022 | 9.15.2022 | GF | 24000 | 24000 |  | 23925 | 23925 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-944 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5646 | OFFICE SUPPLIES | SPO-SEC | SB | n/a | n/a | n/a | n/a | 7.28.2022 | n/a | n/a | 8.2.2022 | 9.9.2022 |  | 9.15.2022 | 9.15.2022 | GF | 2400 | 2400 |  | 2287 | 2287 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-945 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5639 | MINERAL WATER, 5 GAL. | SPO-SEC | SVP | n/a | n/a | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.9.2022 |  | 8.25.2022 | 8.25.2022 | GF | 6750 | 6750 |  | 6600 | 6600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-954 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0876 | WELDIN G AND WORKING GLOVES | PGSO | SVP | n/a | n/a | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.14.2022 |  | 9.29.2022 | 9.29.2022 | GF | 6500 | 6500 |  | 6500 | 6500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-956 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5874 | GRASCUTTING MATERIALS | PGSO | SVP | n/a | n/a | n/a | n/a | 8.4.2022 | n/a | n/a | 8.9.2022 | 9.14.2022 |  | 10.21.2022 | 10.21.2022 | GF | 19050 | 19050 |  | 19000 | 19000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-957 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-08-941 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
CW22-033 | Elem. School, Cagan, Brgy. Andap, New Bataan | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
CW22-032 | NHS, Brgy. Melale, Laak | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
22-5885 | JANITORIAL SUPPLIES | PAO | SB | n/a | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.9.2022 |  | 9.13.2022 | 9.13.2022 | GF | 23282 | 23282 |  | 23206 | 23206 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-976 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5558 | EXTERNAL HARDDISK | PAO | SB | n/a | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.9.2022 |  | 9.22.2022 | 9.22.2022 | GF | 14000 | 14000 |  | 14000 | 14000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-977 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0884 | OFFICE SUPPLIES | PAO | SB | n/a | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.9.2022 |  | 9.13.2022 | 9.13.2022 | GF | 24050 | 24050 |  | 23940 | 23940 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-978 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0882 | COMPUTER SUPPLIES | PHRMDO | SB | n/a | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.14.2022 |  | 9.21.2022 | 9.21.2022 | GF | 40000 | 40000 |  | 39980 | 39980 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-979 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5607 | INK SUPPLIES | PBO | SB | n/a | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.9.2022 |  | 9.15.2022 | 9.15.2022 | GF | 3025 | 3025 |  | 3024 | 3024 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-980 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5886 | OFFICE SUPPLIES | PAO | SB | n/a | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.14.2022 |  | 10.7.2022 | 10.7.2022 | GF | 18300 | 18300 |  | 18275 | 18275 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-981 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5608 | BOND PAPER SUPPLIES | PBO | SB | n/a | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.9.2022 |  | 9.15.2022 | 9.15.2022 | GF | 7275 | 7275 |  | 7260 | 7260 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-982 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5651 | DRUM CARTRIDGE | VGO | SVP | n/a | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.9.2022 |  | 9.12.2022 | 9.12.2022 | GF | 15000 | 15000 |  | 15000 | 15000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-964 | [19 empty] | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0852 | FOOD - BEVERAGE SUPPLY | SPO | SVP | n/a | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.9.2022 |  | 9.22.2022 | 9.22.2022 | GF | 28075 | 28075 |  | 27975 | 27975 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-967 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5657 | FOOD - BEVERAGE SUPPLY | VGO | SVP | n/a | 7.28.2022 | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.9.2022 |  | 9.22.2022 | 9.22.2022 | GF | 54415 | 54415 |  | 54215 | 54215 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-968 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5870 | STEEL FILING CABINET | PAO | SVP | n/a | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.9.2022 |  | 9.13.2022 | 9.13.2022 | GF | 44000 | 44000 |  | 44000 | 44000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-971 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0886 | MINERAL WATER 330 ML | PAO | SVP | n/a | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 11.25.2022 |  |  |  | GF | 19650 | 19650 |  | 19650 | 19650 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-08-972 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5881 | SURGICAL MASK AND WORKING GLVOES | PAO | SVP | n/a | n/a | n/a | n/a | 8.11.2022 | n/a | n/a | 8.16.2022 | 9.9.2022 |  | 9.20.2022 | 9.20.2022 | GF | 11100 | 11100 |  | 11100 | 11100 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-974 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6501 | OFFICE SUPPLIES | PTO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 10.17.2022 | 10.17.2022 | GF | 19999 | 19999 |  | 19995 | 19995 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-985 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6316 | OFFICE SUPPLIES | PTO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 9.29.2022 | 9.29.2022 | GF | 7300 | 7300 |  | 7300 | 7300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-986 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6314 | COMPUTER SUPPLIES | PTO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 10.3.2022 | 10.3.2022 | GF | 7317 | 7317 |  | 7317 | 7317 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-987 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6352 | COMPUTER SUPPLIES | PTO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.26.2022 |  | 10.3.2022 | 10.3.2022 | GF | 18851 | 18851 |  | 18851 | 18851 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-988 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6475 | COMPUTER SUPPLIES | PTO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.12.2022 |  | 10.3.2022 | 10.3.2022 | GF | 9700 | 9700 |  | 9700 | 9700 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-989 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6553 | FLASH DRIVE | PHRMDO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.20.2022 |  | 9.30.2022 | 9.30.2022 | GF | 1000 | 1000 |  | 999 | 999 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-990 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6593 | FLASH DRIVE | PHRMDO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  | 9.16.2022 | 9.16.2022 | GF | 1000 | 1000 |  | 999 | 999 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-991 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6276 | COMPUTER SUPPLIES | PAO | SB | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 10.3.2022 | 10.3.2022 | GF | 87192 | 87192 |  | 87191 | 87191 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-992 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0978 | COMPUTER SUPPLIES | PHO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.15.2022 |  | 9.23.2022 | 9.23.2022 | GF | 26432 | 26432 |  | 26431 | 26431 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-993 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6082 | COMPUTER SUPPLIES | PHO | SB | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.13.2022 |  | 9.21.2022 | 9.21.2022 | TF | 60585 | 60585 |  | 57500 | 57500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-994 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6337 | OFFICE SUPPLIES | PVO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 9.21.2022 | 9.21.2022 | GF | 5964 | 5964 |  | 5925.5 | 5925.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | FOR DELIVERY
22-08-995 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0949 | BATTERY AND BATTERY CHARGE | PAO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 9.26.2022 | 9.26.2022 | GF | 11800 | 11800 |  | 11798 | 11798 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-996 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0961 | COMPUTER SUPPLIES | PVO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.15.2022 |  | 9.23.2022 | 9.23.2022 | GF | 7050 | 7050 |  | 7049 | 7049 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-997 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6484 | JANITORIAL SUPPLIES | PVO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 9.21.2022 | 9.21.2022 | GF | 3715 | 3715 |  | 3708.5 | 3708.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-998 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0960 | OFFICE SUPPLIES | PVO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  | 9.21.2022 | 9.21.2022 | GF | 3377 | 3377 |  | 3376.5 | 3376.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-999 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6072 | COMPUTER SUPPLIES | PHO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.13.2022 |  | 9.16.2022 | 9.16.2022 | TF | 7782 | 7782 |  | 7781 | 7781 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-001 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6287 | DETERGENT BAR AND POWDER | PVO | SB | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 9.29.2022 | 9.29.2022 | GF | 5060 | 5060 |  | 5032 | 5032 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-002 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5834 | MEDICAL SUPPLIES | PGO | SB | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.19.2022 |  | 9.20.2022 | 9.20.2022 | GF | 122500 | 122500 |  | 120500 | 120500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-003 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5882 | CONSTRUCTION PROTECTIVE SUPPLIES | PAO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  | 9.20.2022 | 9.20.2022 | GF | 23750 | 23750 |  | 23725 | 23725 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-004 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6322 | MEALS AND SNACKS | PVO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  | 9.20.2022 | 9.20.2022 | GF | 10000 | 10000 |  | 10000 | 10000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-005 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6279 | MEALS AND SNACKS | PASSO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 9.20.2022 | 9.20.2022 | GF | 33125 | 33125 |  | 33125 | 33125 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-006 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5514 | BULB FLUORESCENT | PEO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.15.2022 |  | 9.22.2022 | 9.22.2022 | GF | 9470 | 9470 |  | 9425 | 9425 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-007 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5879 | CONSTRUCTION SUPPLIES | PAO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  | 9.15.2022 | 9.15.2022 | GF | 5500 | 5500 |  | 5450 | 5450 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-008 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6412 | TARPAULIN - AS PER DESIGN | SPO SEC. | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  |  |  | GF | 10000 | 10000 |  | 10000 | 10000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-08-009 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6147 | TARPAULIN - AS PER DESIGN | PVO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.12.2022 |  |  |  | GF | 725 | 725 |  | 725 | 725 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-08-010 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0901 | MEALS AND SNACKS | PBO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  |  |  | GF | 35625 | 35625 |  | 35625 | 35625 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-08-011 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0965 | MEALS AND SNACKS | PGO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.12.2022 |  |  |  | GF | 140000 | 140000 |  | 140000 | 140000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-08-012 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0914 | PRINTING, PRESCRIPTION/RX | PEEMO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 |  |  |  |  | GF | 39600 | 39600 |  | 39600 | 39600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-08-013 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6078 | TARPAULIN - AS PER DESIGN | PHO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.12.2022 |  |  |  | GF | 3000 | 3000 |  | 3000 | 3000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-08-014 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6589 | TARPAULIN - AS PER DESIGN | PHRMDO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  |  |  | GF | 10500 | 10500 |  | 10500 | 10500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-08-015 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5847 | TARPAULIN - AS PER DESIGN | PGO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  |  |  | GF | 2500 | 2500 |  | 2500 | 2500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O FOR DELIVERY
22-08-016 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6417 | POWER SPRAYER | SPO SEC. | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 9.23.2022 | 9.23.2022 | GF | 10000 | 10000 |  | 9975 | 9975 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-017 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6445 | MEALS (VIP) AND SNACKS (HEAVY) | SPO SEC. | SVP | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.13.2022 |  | 9.23.2022 | 9.23.2022 | GF | 80000 | 80000 |  | 80000 | 80000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-018 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6487 | EARTAG PEN | PVO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  | 10.3.2022 | 10.3.2022 | GF | 1000 | 1000 |  | 999.5 | 999.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-019 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0954 | VETERINARY EQUIPMENTS | PVO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 11.7.2022 | 11.7.2022 | GF | 10732 | 10732 |  | 10715 | 10715 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-020 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6479 | FERTILIZER AND HERBICIDE | PVO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 9.23.2022 | 9.23.2022 | GF | 49880 | 49880 |  | 49680 | 49680 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-021 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6152 | VETERINARY SUPPLIES | PVO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 9.30.2022 | 9.30.2022 | GF | 14425 | 14425 |  | 14248 | 14248 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-022 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0955 | CORN SEEDS AND HERBICIDES | PVO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.20.2022 |  | 9.23.2022 | 9.23.2022 | GF | 40620 | 40620 |  | 40594 | 40594 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-023 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6514 | MEALS WITH ACCOMMODATION | PHO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 9.23.2022 | 9.23.2022 | GF | 78600 | 78600 |  | 78000 | 78000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-024 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6162 | MEALS WITH ACCOMMODATION | PHO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 9.23.2022 | 9.23.2022 | GF | 61570 | 61570 |  | 61100 | 61100 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O
22-08-025 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0935 | CONSTRUCTION SUPPLIES | PEEMO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.27.2022 |  | 10.25.2022 | 10.25.2022 | GF | 146010 | 146010 |  | 137805 | 137805 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-026 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0907 | MINERAL WATER 5 GAL. | PEEMO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 |  |  |  |  | GF | 51975 | 51975 |  | 50820 | 50820 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-08-027 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6280 | MEALS | PAO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  | 1.26.2022 | 1.26.2022 | GF | 60000 | 60000 |  | 60000 | 60000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-028 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0963 | PLAQUE AND TOKEN | PGO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  |  |  | GF | 69500 | 69500 |  | 69500 | 69500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-029 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6414 | COLORED PRINTER | SPO SEC. | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.21.2022 |  | 9.21.2022 | 9.21.2022 | GF | 25680 | 25680 |  | 25470 | 25470 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-030 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6101 | MEALS AND SNACKS | PHO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  | 9.21.2022 | 9.21.2022 | GF | 17625 | 17625 |  | 17625 | 17625 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-031 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0980 | PHOTOCOPYING SUPPLIES | PHRMDO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  | 9.12.2022 | 9.12.2022 | GF | 54000 | 54000 |  | 54000 | 54000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-032 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6355 | MONOBLOCK PLASTIC CHAIR | PVO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.26.2022 |  | 9.26.2022 | 9.26.2022 | GF | 4850 | 4850 |  | 4850 | 4850 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-033 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6438 | VACCUM CLEANER | SPO SEC. | SVP | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 10.12.2022 | 10.12.2022 | GF | 62853.3 | 62853.3 |  | 62850 | 62850 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O
22-08-034 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6084 | HOUSEKEEPING SUPPLIES | PHO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.9.2022 |  | 9.15.2022 | 9.15.2022 | GF | 8200 | 8200 |  | 8197.5 | 8197.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O
22-08-035 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6478 | DOORSIGN AND TABLESIGN | VGO | SVP | n/a | n/a | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 9.23.2022 | 9.23.2022 | GF | 20500 | 20500 |  | 20500 | 20500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O
22-08-036 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6087 | OUTDOOR CAMPING SUPPLIES | PHO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 9.14.2022 |  | 9.21.2022 | 9.21.2022 | GF | 51370 | 51370 |  | 51335 | 51335 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O
22-08-037 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0972 | MEALS AND SNACKS | PHO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 | 10.5.2022 |  | 9.21.2022 | 9.21.2022 | GF | 174375 | 174375 |  | 174375 | 174375 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O
22-08-038 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6519 | MEALS AND SNACKS | PEEMO | SVP | n/a | 8.18.2022 | n/a | n/a | 8.18.2022 | n/a | n/a | 8.23.2022 |  |  |  |  | GF | 149975 | 149975 |  | 149975 | 149975 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O
22-08-039 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0956 | RECHARGEABLE NIMH BATTER WITH | SPO SEC. | SB | n/a | 8.19.2022 | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.23.2022 |  | 10.4.2022 | 10.4.2022 | GF | 57637.5 | 57637.5 |  | 57637.5 | 57637.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-054 | CHARGER AND PRINTER | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0957 | COMPUTER EQUIPMENT | SPO SEC. | SB | n/a | 8.15.2022 | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.28.2022 |  | 10.27.2022 | 10.27.2022 | GF | 87650 | 87650 |  | 87645 | 87645 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-055 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6275 | COMPUTER EQUIPMENT | PAO | SB | n/a | 8.15.2022 | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.27.2022 |  | 10.27.2022 | 10.27.2022 | GF | 101890 | 101890 |  | 101865 | 101865 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-056 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6441 | INK SUPPLIES | SPO SEC | SB | n/a | n/a | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.19.2022 |  | 10.3.2022 | 10.3.2022 | GF | 7140 | 7140 |  | 7137 | 7137 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-057 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6086 | OFFICE SUPPLIES | PHO | SB | n/a | 8.15.2022 | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.20.2022 |  | 9.29.2022 | 9.29.2022 | GF | 125860 | 125860 |  | 153080.75 | 153080.75 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-058 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0975 | JANITORIAL SUPPLIES | PHO | SB | n/a | 8.15.2022 | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 10.7.2022 |  | 10.11.2022 | 10.11.2022 | GF | 86678 | 86678 |  | 86296 | 86296 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-059 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5842 | OFFICE SUPPLIES | PGO | SB | n/a | n/a | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.28.2022 |  | 10.12.2022 | 10.12.2022 | GF | 25705 | 25705 |  | 25703 | 25703 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-060 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0977 | OFFICE SUPPLIES | PHO | SB | n/a | 8.15.2022 | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.27.2022 |  | 10.6.2022 | 10.6.2022 | GF | 72287 | 72287 |  | 71837 | 71837 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-061 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6415 | PLUMBING SUPPLIES | SPO SEC. | SVP | n/a | n/a | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.21.2022 |  | 9.23.2022 | 9.23.2022 | GF | 4252.5 | 4252.5 |  | 4210 | 4210 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-046 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0934 | PLUMBING SUPPLIES | PEEMO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.27.2022 |  | 10.7.2022 | 10.7.2022 | GF | 56190 | 56190 |  | 54500 | 54500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-047 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6333 | PRINTER DOT MATRIX LQ310 | PTO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.19.2022 |  | 10.3.2022 | 10.3.2022 | GF | 128000 | 128000 |  | 128000 | 128000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-048 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6547 | FOOD SUPPLIES | PSWDO | SVP | n/a | n/a | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.29.2022 |  | 10.10.2022 | 10.10.2022 | GF | 36050 | 36050 |  | 36008 | 36008 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-049 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6664 | RICE WELL MILLED | PSWDO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.29.2022 |  | 10.3.2022 | 10.3.2022 | GF | 130500 | 130500 |  | 130442 | 130442 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-050 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6403 | RAINCOAT | PVO | SVP | n/a | n/a | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 9.29.2022 |  | 10.11.2022 | 10.11.2022 | GF | 7600 | 7600 |  | 7600 | 7600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-051 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5470 | BRAKE FLUID AND MOTOR OIL | PGSO | SVP | n/a | 8.15.2022 | n/a | n/a | 8.24.2022 | n/a | n/a | 8.30.2022 | 10.7.2022 |  | 10.11.2022 | 10.11.2022 | GF | 282180 | 282180 |  | 281400 | 281400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-08-052 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6999 | SUPPLY AND INSTALLTION OF SERVICE | PGSO | SVP | 9.6.2022 | 8.17.2022 | n/a | n/a | 9.22.2022 | n/a | n/a | 9.27.2022 | 11.4.2022 |  |  |  | GF | 156072 | 156072 |  | 154511.3 | 154511.3 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-173 | ELEVATOR | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7177 | COMPUTER SOFTWARE | PICTO | SVP | 9.6.2022 | n/a | n/a | n/a | 9.22.2022 | n/a | n/a | 9.27.2022 |  |  |  |  | GF | 43000 | 43000 |  | 42735 | 42735 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-09-178 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7205 | PUBLIC IP ADDRESS | PICTO | SVP | 9.6.2022 | n/a | n/a | n/a | 9.22.2022 | n/a | n/a | 9.27.2022 | 10.25.2022 |  |  |  | GF | 38500 | 38500 |  | 38500 | 38500 |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | P.O. FOR SERVE
22-09-177 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-09-185 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5628 | STAINLESS DOWN PIPE AND TUBE | SPO SEC. | SA | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 |  |  |  |  | GF | 5500 | 5500 |  | 5500 | 5500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-4821 | SPAREPARTS AND OIL | SPO SEC | SA | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 |  |  |  |  | GF | 5300 | 5300 |  | 5300 | 5300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6076 | OFFICE SUPPLIES | PHO | SB | n/a | 7.26.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 10.17.2022 | 10.17.2022 | GF | 92289.5 | 92289.5 |  | 91589 | 91589 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-097 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6592 | PHOTO PAPER 20S/PACK (9 PACKS) | PHRMDO | SB | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 9.28.2022 | 9.28.2022 | GF | 936 | 936 |  | 936 | 936 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-098 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6246 | TONER FOR LBP 2900 | SPO SEC | SB | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 10.10.2022 | 10.10.2022 | GF | 18000 | 18000 |  | 18000 | 18000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-099 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6556 | JANITORIAL SUPPLIES | PAO | SB | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  |  |  | GF | 7545 | 7545 |  | 7528.5 | 7528.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-09-100 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6836 | COMPUTER KEYBOARD (10PCS) | PIAO | SB | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  |  |  | GF | 4000 | 4000 |  | 3990 | 3990 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-09-101 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6534 | FLASH DRIVE (3PCS) | PGSO | SB | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.28.2022 |  | 10.14.2022 | 10.14.2022 | GF | 3000 | 3000 |  | 2997 | 2997 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-102 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6448 | POWER PLANNER 580W | VGO | SVP | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.22.2022 |  |  |  | GF | 9959 | 9959 |  | 9900 | 9900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-09-065 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0931 | CEMENT 40KG/SACK (70 BAGS) | PEEMO | SVP | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.27.2022 |  | 10.5.2022 | 10.5.2022 | GF | 18200 | 18200 |  | 18200 | 18200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-066 | ` | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5835 | PRINTING AND BINDING TRAINING MODULES | PGO | SVP | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.22.2022 |  |  |  | GF | 37250 | 37250 |  | 37250 | 37250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-09-067 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6583 | 16-PORT SINGLE LINE TELEPHONE CARD | PAO | SVP | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.23.2022 |  | 9.26.2022 | 9.26.2022 | GF | 37000 | 37000 |  | 37000 | 37000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-068 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6092 | PORTABLE TROLLEY SPEAKER | PHO | SVP | n/a | 7.26.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.22.2022 |  | 9.27.2022 | 9.27.2022 | GF | 168000 | 168000 |  | 167500 | 167500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-069 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6595 | JOB ORDER: LABOR, MATERIALS & | PGSO | SVP | n/a | 8.8.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.28.2022 |  | 10.7.2022 | 10.7.2022 | GF | 112500 | 112500 |  | 112500 | 112500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-070 | INSTALLATION OF OFFICE NAMEPLATE | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0950 | KITCHEN SUPPLIES | PVO | SVP | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 10.10.2022 | 10.10.2022 | GF | 3644.4 | 3644.4 |  | 3644.4 | 3644.4 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-071 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
20-6075 | STORAGE BOX 155L (2 UNITS) | PHO | SVP | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 10.10.2022 | 10.10.2022 | GF | 2000 | 2000 |  | 2000 | 2000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-072 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6090 | BALLOONS - FLYING (250PCS) | PHO | SVP | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  |  |  | GF | 8750 | 8750 |  | 8750 | 8750 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O FOR DELIVERY
22-09-073 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0895 | MEALS AND SNACKS | PHRMDO | SVP | n/a | 8.19.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 1.26.2022 | 1.26.2022 | GF | 283225 | 283225 |  | 282342 | 282342 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-074 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6446 | PUSH BUTTON URINAL (5 UNITS) | VGO | SVP | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 10.5.2022 | 10.5.2022 | GF | 10800 | 10800 |  | 10775 | 10775 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-075 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0932 | EXHAUST FAN (20 UNITS) | PEEMO | SVP | n/a | 8.15.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.27.2022 |  | 10.12.2022 | 10.12.2022 | GF | 55000 | 55000 |  | 54900 | 54900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-076 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0930 | RIB TYPE ROOFING | PEEMO | SVP | n/a | 8.15.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.27.2022 |  | 10.5.2022 | 10.5.2022 | GF | 83835 | 83835 |  | 83375 | 83375 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-077 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0893 | ELECTRICAL EQUPMENT AND SUPPLIES | PAO | SVP | n/a | 8.19.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.23.2022 |  |  |  | GF | 109050 | 109050 |  | 105020 | 105020 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O FOR DELIVERY
22-09-078 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0938 | LABORATORY SUPPLIES | PEEMO | SVP | n/a | 8.19.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.27.2022 |  | 9.30.2022 | 9.30.2022 | GF | 90998.4 | 90998.4 |  | 57200 | 57200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-079 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0942 | GLUCOS STRIPS | PEEMO | SVP | n/a | 8.19.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.27.2022 |  | 10.28.2022 | 10.28.2022 | GF | 151200 | 151200 |  | 148050 | 148050 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-080 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6085 | COLORED PRINTER (15 UNITS) | PHO | SVP | n/a | 7.26.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.23.2022 |  | 10.7.2022 | 10.7.2022 | GF | 112500 | 112500 |  | 111000 | 111000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-081 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6624 | PLUMBING SUPPLY | PVO | SVP | n/a | 8.9.21022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 10.4.2022 | 10.4.2022 | GF | 284388 | 284388 |  | 284216 | 284216 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-082 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6917 | FIELDWORK PROTECTIVE SUPPLIES | PAO | SVP | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 10.10.2022 |  | 10.24.2022 | 10.24.2022 | GF | 17184 | 17184 |  | 17160 | 17160 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-083 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6626 | CEMENT 40KG/SACK (264 BAGS) | PVO | SVP | n/a | 8.9.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.23.2022 |  | 9.29.2022 | 9.29.2022 | GF | 68640 | 68640 |  | 68640 | 68640 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-084 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6549 | WATER DISPENSE (HOT AND COLD) | PAO | SVP | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 10.27.2022 | 10.27.2022 | GF | 7087.5 | 7087.5 |  | 7050 | 7050 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-085 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6878 | RICE COOKER (4 PCS) | PTO | SVP | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 9.29.2022 | 9.29.2022 | GF | 4200 | 4200 |  | 4160 | 4160 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-086 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6396 | PLAQUE (8 PCS) | PHO | SVP | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.22.2022 |  |  |  | GF | 9220 | 9220 |  | 9200 | 9200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-09-087 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0899 | PLAQUE (155 PCS) | PHRMDO | SVP | n/a | 8.24.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.22.2022 |  | 9.30.2022 | 9.30.2022 | GF | 152250 | 152250 |  | 150900 | 150900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-088 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5892 | ACRYLIC TABLE PARTITION | PPDO | SVP | n/a | 7.20.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.22.2022 |  | 9.30.2022 | 9.30.2022 | GF | 158550 | 158550 |  | 158000 | 158000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-089 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0927 | ENGINE OIL AND LUBRICANTS | PEEMO | SVP | n/a | 8.24.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 9.29.2022 | 9.29.2022 | GF | 119075.4 | 119075.4 |  | 118615 | 118615 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-090 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0924 | AIR CLEANER AND FILTER | PEEMO | SVP | n/a | 8.24.2022 | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 |  |  |  |  | GF | 106630 | 106630 |  | 106396 | 106396 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-09-091 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6618 | SAFETY GEARS | PVO | SVP | n/a | n/a | n/a | n/a | 9.1.2022 | n/a | n/a | 9.6.2022 | 9.26.2022 |  | 10.12.2022 | 10.12.2022 | GF | 13925 | 13925 |  | 13830 | 13830 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-092 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
| CONSTRUCTION OF DRAINAGE, POBLACION | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| MARAGUSAN NHS. | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
| CONSTRUCTION OF TEACHERS COTTAGE, | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| PANGANASON ES. | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
| CONSTRUCTION OF DAY CARE CENTER | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| BINABA, BRGY. NAPNAPAN | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6921 | SUPPLY AND DELIVERY OF MATERIALS FOR | PEO | SVP | 9.20.2022 | [11 empty] | GF | 142983.74 | 142983.74 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a
| WOMEN CRISIS CENTER, NABUNTURAN | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
| CONSTRUCTION OF MULTI-PURPOSE BLDG. | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| PARASAN INTEGRATED SCHOOL BRGY. TIBAGON | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6602 | SUPPLY AND DELIVERY OF MATERIALS FOR | PEO | SVP | 9.20.2022 | [11 empty] | GF | 28448.45 | 28448.45 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a
| THE IMPROVEMENT OF REGIONAL | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| EVACUATION CENTER, NABUNTURAN | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7292 | GEMELINA LUMBER | PTO | SVP | 9.20.2022 | n/a | [10 empty] | GF | 6416.55 | 6416.55 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | CANCELLED
[17 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
22-11-295 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6467 | 3.0 TR, FLOOR MOUNTAINED | PIAO | NP | 9.20.2022 | 8.3.2022 | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 90000 | 90000 |  | 83995 | 83995 |  | Mr. Allan Rey N. Esmael |  | n/a | n/a | n/a | n/a |  | FROM PB TO NP
22-12-330 | AIRCONDITIONING UNIT WITH | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator | [6 empty] | (2 failed biddings)
| INSTALLATION | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-11-294 | AND VENUE | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6522 | OFFICE SUPPLIES | PGSO | SB | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.25.2022 |  | 11.3.2022 | 11.3.2022 | GF | 10558 | 10558 |  | 10558 | 10558 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-121 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5949 | OFFICE SUPPLIES | PAO | SB | n/a | 7.21.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.26.2022 |  | 11.10.2022 | 11.10.2022 | GF | 195293 | 195293 |  | 191633 | 191633 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-122 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0911 | PRINTING SUPPLIES | PEEMO | SB | n/a | 7.21.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 |  |  |  |  | GF | 96019.6 | 96019.6 |  | 95736.75 | 95736.75 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-09-123 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6882 | SELF INKING STAMPS (20 PCS0 | PTO | SB | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 11.7.2022 |  | 11.17.2022 | 11.17.2022 | GF | 6500 | 6500 |  | 6500 | 6500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-124 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5924 | COMPUTER SUPPLIES | PAO | SB | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 11.7.2022 |  |  |  | GF | 26740 | 26740 |  | 26740 | 26740 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-09-125 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6901 | TONER FOR LBP 2900 (11PCS) | PGSO | SB | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.25.2022 |  | 11.3.2022 | 11.3.2022 | GF | 19800 | 19800 |  | 19800 | 19800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-126 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6876 | JANITORIAL SUPPLIES | PTO | SB | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.25.2022 |  | 10.28.2022 | 10.28.2022 | GF | 10844 | 10844 |  | 10844 | 10844 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-127 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6538 | JANITORIAL SUPPLIES | PGSO | SB | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.25.2022 |  | 11.3.2022 | 11.3.2022 | GF | 5306 | 5306 |  | 5306 | 5306 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-128 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6701 | TARPAULIN - AS PER DESIGN | VGO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.26.2022 |  |  |  | GF | 10000 | 10000 |  | 9800 | 9800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-09-129 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6712 | TARPAULIN - AS PER DESIGN | PPDO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.30.2022 |  |  |  | GF | 25000 | 25000 |  | 24500 | 24500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-09-130 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6559 | CONSTRUCTION SUPPLIES | PAO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.26.2022 |  | 10.27.2022 | 10.27.2022 | GF | 4340 | 4340 |  | 4326 | 4326 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-131 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6634 | CONSTRUCTION SUPPLIES | PVO | SVP | n/a | 8.9.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 11.3.2022 |  | 11.24.2022 | 11.24.2022 | GF | 167069 | 167069 |  | 166052 | 166052 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-132 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6930 | GASOLINE ENGINE OIL (150L) | PGSO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.26.2022 |  | 11.4.2022 | 11.4.2022 | GF | 48000 | 48000 |  | 47250 | 47250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-133 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6926 | SPAREPARTS | PGSO | SVP | n/a | 8.16.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.27.2022 |  | 11.2.2022 | 11.2.2022 | GF | 208230 | 208230 |  | 207240 | 207240 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-134 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0925 | BATTERY 12V (12PCS) | PGSO | SVP | n/a | 8.24.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.25.2022 |  | 10.27.2022 | 10.27.2022 | GF | 83500 | 83500 |  | 82850 | 82850 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-135 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7026 | LOT 2: MEALS AND ACCOMMODATION | PHO | SVP | n/a | 8.19.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 11.8.2022 |  | 11.24.2022 | 11.24.2022 | GF | 78600 | 78600 |  | 78600 | 78600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-136 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0991 | LOT 2: MEALS AND SNACKS | PSWDO | SVP | n/a | 8.31.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.25.2022 |  | 10.27.2022 | 10.27.2022 | GF | 54925 | 54925 |  | 54925 | 54925 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-138 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7026 | LOT 1: PACKED MEALS AND SNACKS | PHO | SVP | n/a | 8.19.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 |  |  |  |  | GF | 475975 | 475975 |  | 475975 | 475975 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-09-139 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6057 | MEALS AND SNACKS | PAO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.25.2022 |  | 1.26.2022 | 1.26.2022 | GF | 32875 | 32875 |  | 32875 | 32875 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-140 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6158 | TARPAULIN - AS PER DESIGN | PHO | SVP | n/a | 7.27.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 11.2.2022 |  |  |  | GF | 200000 | 200000 |  | 200000 | 200000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-09-141 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6646 | TARPAULIN - AS PER DESIGN | PVO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.25.2022 |  |  |  | GF | 1600 | 1600 |  | 1600 | 1600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-09-142 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6640 | PAINTING SUPPLIES | PVO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 11.3.2022 |  | 11.7.2022 | 11.7.2022 | GF | 12029 | 12029 |  | 12027 | 12027 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-143 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0981 | PAINTING SUPPLIES | PAO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.26.2022 |  | 11.2.2022 | 11.2.2022 | GF | 6832 | 6832 |  | 6832 | 6832 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-144 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6641 | ROOFING (PRE-PAINTED BENDED | PVO | SVP | n/a | 8.9.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.26.2022 |  | 11.7.2022 | 11.7.2022 | GF | 74644.4 | 74644.4 |  | 74450 | 74450 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-145 | AND RIB-TYPE) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6881 | KITCHEN SUPPLIES | PTO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.24.2022 |  | 10.28.2022 | 10.28.2022 | GF | 20562 | 20562 |  | 20544 | 20544 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-146 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6081 | CALENDAR PLANNER, FLYER FAN, | PHO | SVP | n/a | 7.26.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.28.2022 |  |  |  | GF | 96726 | 96726 |  | 95476 | 95476 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-09-147 | MAGAZINE POSTER | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0971 | TARPAULIN - AS PER DESIGN | PHO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 11.2.2022 |  |  |  | GF | 22750 | 22750 |  | 22750 | 22750 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-09-148 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6902 | STEEL CABINET 4 DRAWERS | PENRO | SVP | n/a | 8.12.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 11.4.2022 |  | 11.8.2022 | 11.8.2022 | GF | 116640 | 116640 |  | 116000 | 116000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-149 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6940 | CEMENT 40KG/SACK (25 BAGS) | PENRO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.28.2022 |  | 11.10.2022 | 11.10.2022 | GF | 6500 | 6500 |  | 6500 | 6500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-150 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6904 | MARINE PLYWOOD TYPE I GRADE C | PENRO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 11.3.2022 |  | 11.10.2022 | 11.10.2022 | GF | 4210 | 4210 |  | 4200 | 4200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-151 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7029 | INDEX CARDS (AS PER SAMPLE) | PACCO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.28.2022 |  | 11.25.2022 | 11.25.2022 | GF | 17450 | 17450 |  | 17400 | 17400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-152 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6613 | CONSTRUCTION AND ELECTRICAL SUPPLY | PVO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 11.2.2022 |  | 11.10.2022 | 11.10.2022 | GF | 13615 | 13615 |  | 13544 | 13544 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-153 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6964 | ELECTRICAL SUPPLIES | PTO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.25.2022 |  | 11.3.2022 | 11.3.2022 | GF | 8680 | 8680 |  | 8580 | 8580 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-154 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6870 | PACKED MEALS AND SNACKS | PGO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.25.2022 |  | 11.3.2022 | 11.3.2022 | GF | 28125 | 28125 |  | 27975 | 27975 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-155 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7199 | PACKED MEALS AND SNACKS | PENRO | SVP | n/a | n/a | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.26.2022 |  | 11.3.2022 | 11.3.2022 | GF | 31250 | 31250 |  | 31000 | 31000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-156 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0991 | LOT 1: MEALS AND ACCOMMODATION | PSWDO | SVP | n/a | 8.31.2022 | n/a | n/a | 9.15.2022 | n/a | n/a | 9.20.2022 | 10.26.2022 |  | 11.3.2022 | 11.3.2022 | GF | 89080 | 89080 |  | 89080 | 89080 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-157 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-11-297 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-11-299 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
CW22-034 | AT KILAGDING NHS | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
CW22-035 | MARAGUSAN | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7539 | PLASTIC STORAGE BOX | PGO | SVP | 9.27.2022 | 9.23.2022 | n/a | n/a | 10.6.2022 | n/a | n/a | 10.11.2022 | 11.24.2022 |  | 11.28.2022 | 11.28.2022 | GF | 510400 | 510400 |  | 445005 | 445005 |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | P.O. FOR SERVE
22-10-207 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7014 | YEAST EXTRACT 500g/btl | PAO | SVP | 9.27.2022 | n/a | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 5500 | 5500 |  | 5495 | 5495 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-291 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
no PO No. | INFANTOMETER and WOODEN HEIGHT | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| BOARD | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7394 | SUPPLY AND INSTALLATION OF STEEL | PEO | SVP | 9.27.2022 | [11 empty] | GF | 39060 | 39060 |  | 0 |  |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a
| WINDOWS FOR THE CONSTRUCTION OF | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| 2 CLASSROOM BUILDING at MACOPA ES. | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1023 | JOB ORDER- REHABILITATION OF 120 ft. | PICTO | SVP | 9.27.2022 | 10.3.2022 | n/a | n/a | 10.6.2022 | n/a | n/a | 10.11.2022 | 11.9.2022 |  |  |  | GF | 242000 | 242000 |  | 231800 | 231800 |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | P.O. FOR DELIVERY
22-10-206 | MONOPLE TOWER FOR REPEATER SITE | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
| IN TUBURAN, MAWAB. | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6570 | BRAKE PAD AND BRAKE SHOE | SPO - SEC. | SA | n/a | n/a | n/a | n/a | 9.22.2022 | n/a | n/a | 9.27.2022 |  |  |  |  | GF | 27000 | 27000 |  | 26900 | 26900 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-170 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6903 | COMPUTER KEYBOARD (10PCS) MOUSE (8pcs) | PENRO | SB | n/a | n/a | n/a | n/a | 9.22.2022 | n/a | n/a | 9.27.2022 | 11.3.2022 |  |  |  | GF | 6400 | 6400 |  | 6390 | 6390 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-171 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7175 | MEALS AND SNACKS | PAO | SVP | n/a | 8.25.2022 | n/a | n/a | 9.22.2022 | n/a | n/a | 9.27.2022 | 10.24.2022 |  | 1.26.2022 | 1.26.2022 | GF | 69925 | 69925 |  | 69086 | 69086 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-174 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6900 | DURARIB 1040 (PRE-PAINTED, LONGSPAN | PENRO | SVP | n/a | n/a | n/a | n/a | 9.22.2022 | n/a | n/a | 9.27.2022 | 10.26.2022 |  | 11.10.2022 | 11.10.2022 | GF | 8625 | 8625 |  | 8250 | 8250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-176 | ROOFING) COLOR RED | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7101 | BLACK NET 60% SHADING (3M x 100M) | PAGRO | SVP | n/a | n/a | n/a | n/a | 9.22.2022 | n/a | n/a | 9.27.2022 | 10.26.2022 |  |  |  | GF | 20000 | 20000 |  | 19990 | 19990 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-180 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0889 | MINERAL WATER (33ML and 5 GAL.) | PGSO | SVP | n/a | 8.31.2022 | n/a | n/a | 9.22.2022 | n/a | n/a | 9.27.2022 |  |  |  |  | GF | 176940 | 176940 |  | 158220 | 158220 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-09-181 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7743 | MEALS | PGO | SVP | 10.6.2022 | 10.3.2022 | n/a | n/a | 10.6.2022 | n/a | n/a | 10.11.2022 | 11.3.2022 |  |  |  | GF | 99900 | 99900 |  | 98235 | 98235 |  | Mr. Allan Rey N. Esmael |  | n/a |  | n/a | n/a |  | P.O. FOR DELIVERY
22-10-204 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7290 | PAPER CUTTER | PIAO | SB | n/a | n/a | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 10.25.2022 |  | 10.28.2022 | 10.28.2022 | GF | 4180 | 4180 |  | 4000 | 4000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-200 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7291 | TOILET TISSUE (50 ROLLS) | PIAO | SB | n/a | n/a | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 10.24.2022 |  | 10.28.2022 | 10.28.2022 | GF | 900 | 900 |  | 800 | 800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-201 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6988 | CONSTRUCTION - WELDING MATERIALS | PGSO | SVP | n/a | n/a | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 10.26.2022 |  |  |  | GF | 41820 | 41820 |  | 41820 | 41820 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-186 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6135 | MAGAZINE PRINTING - AS PER SAMPLE | PAO | SVP | n/a | n/a | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 10.28.2022 |  |  |  | GF | 102000 | 102000 |  | 102000 | 102000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-187 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1040 | INK PRINTER (1 UNIT); TABLE FOR | PAGRO | SVP | n/a | 9.22.2022 | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 10.28.2022 |  |  |  | GF | 69500 | 69500 |  | 69485 | 69485 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-188 | GEOREFERENCING (2 UNITS) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7411 | MEALS AND SNACKS WITH FREE DELIVERY | PSWDO | SVP | n/a | 9.9.2022 | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 10.25.2022 |  |  |  | GF | 209950 | 209950 |  | 209950 | 209950 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-189 | ANYWHERE WITHIN DAVAO DE ORO | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7171 | UTP CABLE CAT 6 (COLOR BLURE, 3 ROLLS) | PICTO | SVP | n/a | n/a | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 10.26.2022 |  | 11.4.2022 | 11.4.2022 | GF | 24600 | 24600 |  | 24570 | 24570 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | DELIVERED
22-10-190 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5909 | HELMET - FULL FACED (8PCS); RAIN COAT | PPDO | SVP | n/a | 7.20.2022 | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 10.28.2022 |  | 11.7.2022 | 11.7.2022 | GF | 60500 | 60500 |  | 60320 | 60320 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-191 | PANTS AND JACKET (10 PAIRS) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7289 | KNIFE | PIAO | SVP | n/a | n/a | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 10.24.2022 |  | 10.28.2022 | 10.28.2022 | GF | 550 | 550 |  | 545 | 545 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-192 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7168 | EXHAUST FAN (2 UNITS) | PICTO | SVP | n/a | n/a | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 10.24.2022 |  | 10.28.2022 | 10.28.2022 | GF | 5160 | 5160 |  | 4500 | 4500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | DELIVERED
22-10-193 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1056 | COTTON GLOVES (6 PAIRS) ; | PVO | SVP | n/a | n/a | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 10.25.2022 |  |  |  | GF | 670 | 670 |  | 670 | 670 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-194 | PAIL RUBBER (5 PCS) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7097 | MEALS (VIP) AND SNACKS (HEAVY) | PGSO | SVP | n/a | 8.23.2022 | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 11.4.2022 |  |  |  | GF | 108000 | 108000 |  | 105300 | 105300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-195 | 270 HEADS | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7542 | SNACKS (LIGHT) | PGO | SVP | n/a | n/a | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 10.24.2022 |  |  |  | GF | 49950 | 49950 |  | 49617 | 49617 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-196 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5582 | MEALS AND SNACKS WITH VENUE WITHIN | PGO | SVP | n/a | 6.27.2022 | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 10.24.2022 |  | 1.26.2022 | 1.26.2022 | GF | 52500 | 52500 |  | 52050 | 52050 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-197 | DAVAO DE ORO | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6536 | MEALS AND SNACKS WITH FREE DELIVERY | PGO | SVP | n/a | 8.5.2022 | n/a | n/a | 9.29.2022 | n/a | n/a | 10.4.2022 | 11.4.2022 |  | 1.26.2022 | 1.26.2022 | GF | 975000 | 963000 |  | 963000 | 963000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-198 | ANYWHERE WITHIN DAVAO DE ORO | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1011 | AGRICULTURAL SUPPLIES | PAGRO | SVP | 10.11.2022 | 10.12.2022 | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 58336 | 58336 |  | 58275.5 | 58275.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-272 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1017 | CONSTRUCTION SUPPLIES | PAGRO | SVP | 10.11.2022 | 10.12.2022 | [10 empty] | GF | 86723 | 86723 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-263 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7573 | PORTLAND CEMENT | PGO-PS | SVP | 10.11.2022 | 9.26.2022 | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 87360 | 87360 |  | 87360 | 87360 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-11-280 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7562 | ANDROID CELLPHONE | PPDO | SVP | 10.11.2022 | 9.26.2022 | [10 empty] | GF | 90000 | 90000 |  | 0 |  |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-10-257 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-11-327 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0959 | MEALS WITH VENUE | PDRRMO | SVP | 10.11.2022 | 10.12.2022 | [9 empty] | 04.20.2022 | GF | 809625 | 809625 |  | 0 |  |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-10-258 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1050 | ELECTRICAL SUPPLIES | PGSO | SVP | 10.11.2022 | 10.5.2022 | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 649550 | 649550 |  | 611460 | 611460 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-11-279 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7370 | OFFICE EQUIPMENT | PGO-SEF | SVP | 10.11.2022 | 9.6.2022 | [10 empty] | GF | 75800 | 75800 |  | 0 |  |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-10-259 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7430 | FIELD AUDIO RECORDER | PGO-SEF | SVP | 10.11.2022 | n/a | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 39000 | 39000 |  | 38900 | 38900 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-11-308 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6546 | TOKEN (AS PER SAMPLE) | PAO-ID | SVP | 10.11.2022 | n/a | [10 empty] | GF | 30000 | 30000 |  | 0 |  |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-10-250 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-12-368 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7707 | MEALS AND SNACKS | PSWDO | SVP | n/a | 10.3.2022 | n/a | n/a | 10.6.2022 | n/a | n/a | 10.11.2022 |  |  |  |  | GF | 234075 | 234075 |  | 231257 | 231257 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-505 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7049 | MINERAL WATER (5 GAL. - 25 CONS) | PGSO | SVP | n/a | n/a | n/a | n/a | 10.6.2022 | n/a | n/a | 10.11.2022 | 11.3.2022 |  |  |  | GF | 1125 | 1125 |  | 1000 | 1000 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-10-208 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7490 | MEDICAL OXYGEN REFILL | PGO | SVP | n/a | 9.21.2022 | n/a | n/a | 10.6.2022 | n/a | n/a | 10.11.2022 | 10.27.2022 |  |  |  | GF | 11053560 | 11053560 |  | 11053560 | 11053560 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-10-209 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1086 | MEALS VIP AND SNACKS | SPO SEC | NP-SVP | 10.18.2022 | 10.18.2022 | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 220000 | 220000 |  | 217800 | 217800 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-11-274 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7758 | BEVERAGES (GROCERIES) | SPO SEC | NP-SVP | 10.18.2022 | n/a | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 11500 | 11500 |  | 11434 | 11434 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-11-290 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7765 | JOB ORDER (bookbinding) BOOKBINDING OF | SPO SEC | NP-SVP | 10.18.2022 | 10.3.2022 | n/a | n/a | 11.10.2022 | n/a | n/a | 11.15.2022 |  |  |  |  | GF | 100000 | 100000 |  | 98500 | 98500 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-11-232 | RESOLUTIONS AND PROVINCIAL | [15 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
| ORDINANCES | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7777 | LED PANEL LIGHT P660-40W-DL and | VGO | NP-SVP | 10.18.2022 | 10.3.2022 | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 105375 | 105375 |  | 104950 | 104950 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-11-288 | POLYTHELENE TAPE | [15 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7930 | MEALS W/ VENUE, MEALS WITHOUT VENUE | PHRMDO | NP-SVP | 10.18.2022 | 10.7.2022 | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 305000 | 305000 |  | 304550 | 304550 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-11-275 | AND SNACKS A (LIGHT) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
| WITHIN DAVAO DE ORO | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7986 | OFFICIAL DELIVERY RECEIPT | PTO | NP-SVP | 10.18.2022 | 10.1.2022 | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 356500 | 356500 |  | 356500 | 356500 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-11-287 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1045 | 43" LED TV SPECIFICATION: *FULL HD* | PHO | SVP | 10.18.2022 | 11.16.2022 | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 190000 | 190000 |  | 190000 | 190000 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P,O, FOR SERVE
22-12-341 | 1920X1080* BUILT IN SPEAKER (2) SOUND* | [15 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
| WITH REMOTE CONTROL | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-5843 | MEALS VIP and SNACKS A (LIGHT) | PAO ADMIN | NP-SVP | 10.18.2022 | 7.19.2022 | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 109875 | 109875 |  | 105480 | 105480 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
22-11-273 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-8017 | TIRES (TUBELESS) | PDRRMO | NP-SVP | 10.18.2022 | [11 empty] | GF | 335060 | 335060 |  | 0 |  |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-8110 | ELECTRICAL SUPPLIES | VGO | NP-SVP | 10.18.2022 | [11 empty] | GF | 8905 | 8905 |  | 0 |  |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-8107 | PAINTING SUPPLIES | VGO | NP-SVP | 10.18.2022 | n/a | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 7240 | 7240 |  | 7208 | 7208 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-286 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-8114 | OFFICE SUPPLIES | VGO | NP-SVP | 10.18.2022 | n/a | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 1300 | 1300 |  | 1280 | 1280 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-285 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-7301 | BRAKE PAD AND BRAKE SHOE | PDRRMO | SA | n/a | n/a | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 |  |  |  |  | GF | 24300 | 24300 |  | 24300 | 24300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-219 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-7302 | BRAKE PAD AND BRAKE SHOE | PDRRMO | SA | n/a | n/a | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 | 11.7.2022 |  | 11.9.2022 | 11.9.2022 | GF | 24300 | 24300 |  | 24300 | 24300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-220 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-7283 | BRAKE PAD | PDRRMO | SA | n/a | n/a | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 | 11.9.2022 |  | 10.31.2022 | 10.31.2022 | GF | 13750 | 13750 |  | 13650 | 13650 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-221 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-7433 | SPAREPARTS | PGSO | SA | n/a | 9.13.2022 | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 |  |  |  |  | GF | 184835 | 184835 |  | 184210 | 184210 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-222 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-7486 | SPAREPARTS | PGSO | SA | n/a | 9.21.2022 | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 |  |  |  |  | GF | 62890 | 62890 |  | 62550 | 62550 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-223 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-7298 | SPAREPARTS | SPO SEC | SA | n/a | 9.1.2022 | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 |  |  |  |  | GF | 64460 | 64460 |  | 63300 | 63300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-224 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-7280 | BRAKEPAD | PDRRMO | SA | n/a | na/ | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 |  |  |  |  | GF | 13750 | 13750 |  | 13650 | 13650 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-225 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-6235 | PACKED MEALS AND SNACKS | PGO | SVP | n/a | n/a | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 | 11.7.2022 |  | 11.9.2022 | 11.9.2022 | GF | 33750 | 33750 |  | 33150 | 33150 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-226 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-C1014 | MEALS AND SNACKS | PHRMDO | SVP | n/a | 10.7.2022 | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 |  |  |  |  | GF | 64125 | 64125 |  | 62943 | 62943 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-227 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-6196 | MEALS WITH ACCOMMODATION AND | PHO | SVP | n/a | 7.27.2022 | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 |  |  |  |  | GF | 288200 | 288200 |  | 288200 | 288200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-228 | VENUE | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-C1032 | MEDICAL DEVICES | PHO | SVP | n/a | 9.28.2022 | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 |  |  |  |  | GF | 53300 | 53300 |  | 52500 | 52500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-229 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-7070 | CACAO CLEAN SEEDS (60KGS) | PAGRO | SVP | n/a | n/a | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 |  |  |  |  | GF | 3960 | 3960 |  | 3960 | 3960 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-230 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-7341 | PLAQUE AS PER DESIGN (30PCS) | PGO-SEF | SVP | n/a | n/a | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 |  |  |  |  | GF | 45000 | 45000 |  | 44400 | 44400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-231 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-C1002 | OFFICE EQUIPMENT AND MATERIALS | PGSO | SVP | n/a | n/a | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 |  |  |  |  | GF | 17290 | 17290 |  | 17148.5 | 17148.5 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-232 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-7338 | MEALS (VIP - 102HEADS) AND SNACKS | PGO-SEF | SVP | n/a | 9.6.2022 | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 |  |  |  |  | GF | 61200 | 61200 |  | 60588 | 60588 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-233 | (HEAVY - 204HEADS) VENUE WITHIN | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
| TAGUM CITY | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-6690 | CUTTING EDGES WITH BOLTS, NUTS, AND | PEO | SVP | n/a | 3.3.2022 | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 |  |  |  |  | GF | 70000 | 70000 |  | 69750 | 69750 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-234 | WASHER FOR MOTOR GRADER | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-C1078 | ELECTRICAL SUPPLIES | PGO | SVP | n/a | 10.5.2022 | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 | 11.3.2022 |  | 11.8.2022 | 11.8.2022 | GF | 91698.47 | 91698.47 |  | 87980 | 87980 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-235 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-C1085 | INTERNET MATERIALS | PGO | SVP | n/a | n/a | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 | 11.3.2022 |  | 11.7.2022 | 11.7.2022 | GF | 30700 | 30700 |  | 30649 | 30649 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-10-236 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-10-237 | REFILL | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-6521 | TV PROGRAM (PACKAGE DEAL, 1MIN PPE/ | PAO | NP | n/a | 8.4.2022 | n/a | n/a | 10.13.2022 | n/a | n/a | 10.18.2022 | 11.7.2022 |  |  |  | GF | 480000 | 480000 |  | 480000 | 480000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR DELIVERY
22-10-238 | SCHEDULE; 16 PACKAGES) | [15 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-C1092 | OTHER SUPPLIES/MATERIALS | PSWDO | SVP | 10.25.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 48670 | 48670 |  | 48610 | 48610 |  | Mr. Allan Rey N. Esmael | n/a | n/a |  | n/a | n/a |  | P.O. FOR SERVE
22-12-352 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-7719 | AIRCONDITIONING UNIT WINDOW | PSWDO | SVP | 10.25.2022 | 10.3.2022 | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 54800 | 54800 |  | 54600 | 54600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P,O. FOR SERVE
22-12-337 | [16 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-C1203 | OFFICE SUPPLIES | PSWDO | SVP | 10.25.2022 | 10.3.2022 | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 105325 | 105325 |  | 105295 | 105295 |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-353 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-7729 | FOOD SUPPLIES | PSWDO | SVP | 10.25.2022 | n/a | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 24370 | 24370 |  | 24370 | 24370 |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-300 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-7992 | GEMELINA, LUMBER OR EQUIVALENT | PAO-ADMIN | SVP | 10.25.2022 | n/a | [10 empty] | GF | 15190 | 15190 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
| GEMELINA. LUMBER OR EQUIVALENT | PAO-INV. | SVP | 10.25.2022 | n/a | [10 empty] | GF | 11250 | 11250 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-C1150 | SPARE PARTS | PDRRMO | SVP | 10.25.2022 | 10.27.2022 | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 183000 | 183000 |  | 182760 | 182760 |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-8087 | COMPUTER SUPPLIES | PDRRMO | SVP | 10.25.2022 | n/a | [10 empty] | GF | 27080 | 27080 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-7855 | TOOLS | PDRRMO | SVP | 10.25.2022 | n/a | [10 empty] | GF | 13500 | 13500 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-6811 | BATTERY 12V 13 PLATES MAINTENANCE | PDRRMO | SVP | 10.25.2022 | 8.11.2022 | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 61200 | 61200 |  | 60750 | 60750 |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-336 | FREE | [15 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-7862 | BINDING MACHINE | PDRRMO | SVP | 10.25.2022 | n/a | n/a | n/a | 11.10.2022 | n/a | n/a | 11.15.2022 |  |  |  |  | GF | 30000 | 30000 |  | 30000 | 30000 |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-234 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-7755 | COMPUTER SUPPLIES | PPDO | SB | 10.25.2022 | n/a | [10 empty] | GF | 14205 | 14205 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
| SPARE PARTS (FOR LIGHT and HEAVY | PGSO | SVP | 10.25.2022 | n/a | [10 empty] | GF | 3300 | 3300 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
| EQUIPMENT) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
| SPARE PARTS (FOR LIGHT VEHICLE) | PGSO | SVP | 10.25.2022 | n/a | [10 empty] | GF | 2100 | 2100 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-7300 | SPARE PARTS (FOR LIGHT VEHICLE) | PGSO | SA | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 3300 | 3300 |  | 3300 | 3300 |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-331 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-7435 | SPARE PARTS (FOR LIGHT VEHICLE) | PGSO | SA | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 24300 | 24300 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-7336 | SPARE PARTS (FOR LIGHT VEHICLE) | PGSO | SA | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 24350 | 24350 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-7612 | SPARE PARTS (HEAVY EQUIPMENT) | PGSO | SA | 10.25.2022 | n/a | n/a | n/a | 11.10.2022 | n/a | n/a | 11.15.2022 |  |  |  |  | GF | 11200 | 11200 |  | 11000 | 11000 |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-230 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-C1051 | CONSTRUCTION MATERIALS | PGSO | SVP | 10.25.2022 | 10.27.2022 | [10 empty] | GF | 137768 | 137768 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
| SPAREPARTS (MOTORCYCLE) | PGSO | SVP | 10.25.2022 | n/a | [10 empty] | GF | 12550 | 12550 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-7534 | SPAREPARTS (MOTORCYCLE) | PGSO | SVP | 10.25.2022 | n/a | [10 empty] | GF | 24150 | 24150 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
| SPAREPARTS (MOTORCYCLE) | PGSO | SVP | 10.25.2022 | n/a | [10 empty] | GF | 22465 | 22465 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-C1149 | COMPUTER SUPPLIES/SPARE PARTS | PEEMO | SVP | 10.25.2022 | n/a | [10 empty] | GF | 7040 | 7040 |  | 0 |  |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-7795 | DRAWER LATERAL STEEL CABINET | PAO | SVP | 10.25.2022 | n/a | n/a | n/a | 11.10.2022 | n/a | n/a | 11.15.2022 |  |  |  |  | GF | 15500 | 15500 |  | 15500 | 15500 |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-233 |  | INVESTMENT | [14 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-C1095 | COMPUTER EQUIPMENT | PAO | SVP | 10.25.2022 | n/a | n/a | n/aa | 11.17.2022 | na | na | 11.22.2022 |  |  |  |  | GF | 24120 | 24120 |  | 24100 | 24100 |  | Engr. Michael C. Salarda | n/a | n/a | n/a | n/a | n/a
22-11-311 |  | TOURISM | [14 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Mr. Allan Rey N. Esmael
22-C1096 | OFFICE SUPPLIES | PAO | SB | 10.25.2022 | n/a | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 23735 | 23735 |  | 23674.25 | 23674.25 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-271 |  | TOURISM | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
|  | Equipment | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
|  | pool | [14 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-10-270 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7487 | SPAREPARTS | PGSO | SA | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 17060 | 17060 |  | 17060 | 17060 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-239 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7484 | SPAREPARTS | PGSO | SA | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 32385 | 32385 |  | 32385 | 32385 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-240 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1016 | OFFICE SUPPLIES | PAGRO | SB | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 13800 | 13800 |  | 13771 | 13771 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-241 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1042 | COMPUTER SUPPLIES | PAGRO | SB | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 12800 | 12800 |  | 12739 | 12739 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-242 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7340 | OFFICE SUPPLIES | PGO-SEF | SB | n/a | 9.6.2022 | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 66005 | 66005 |  | 64945 | 64945 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-243 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7764 | HEADSET (FOR DESKTOP COMPUTER) | SPO-SEC. | SB | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 3310 | 3310 |  | 3300 | 3300 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-245 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7763 | EXTERNAL DRIVE (2TB and 1TB) | SPO-SEC. | SB | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 16000 | 16000 |  | 15985 | 15985 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-246 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7785 | GRASS CUTTER | VGO | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 18000 | 18000 |  | 17950 | 17950 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-247 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7342 | EVENT UNIFORM (SHIRT-SUBLIMATION- | PGO-SEF | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 40000 | 40000 |  | 38400 | 38400 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-248 | 80 PCS.) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7789 | BRASS MARKER (30" x 16") AS PER DESIGN | SPO SEC. | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 17000 | 17000 |  | 16950 | 16950 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-249 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-6546 | TOKEN (AS PER SAMPLE) | PAO | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 30000 | 30000 |  | 29400 | 29400 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-250 |  | INVESTMENT | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7787 | PLAQUE (AS PER DESIGN) (1PC.) | VGO | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 2500 | 2500 |  | 2480 | 2480 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-251 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7786 | TABLESIGN 14,X5 X 3 IN 3/8 CLEAR | VGO | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 4500 | 4500 |  | 4480 | 4480 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-252 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7648 | GEMELINA LUMBER OF EQUIVALENT | PVO | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 15510.15 | 15510.15 |  | 15510.15 | 15510.15 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-253 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-8001 | DOOR CONSTRUCTION SUPPLIES | PTO | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 41517 | 41517 |  | 41100 | 41100 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-254 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7788 | OFFICE EQUIPMENT | SPO SEC. | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 39943.25 | 39943.25 |  | 39935 | 39935 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-255 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7991 | MONOBLOC CHAIR, FOLDING TABLE | PTO | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 21500 | 21500 |  | 21483 | 21483 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-256 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7562 | ANDROID CELLPHONE FOR GEO TAGGING | PPDO | SVP | n/a | 9.26.2022 | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 90000 | 90000 |  | 89910 | 89910 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-257 | (WITH SPECS - 3 UNITS) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C0959 | MEALS WITH VENUE; PACKED MEALS AND | PDRRMO | SVP | n/a | 10.12.2022 | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 809625 | 809625 |  | 797515 | 797515 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-258 | SNACKS | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7370 | STEEL CABINET AND SOFA | PGO-SEF | SVP | n/a | 9.6.2022 | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 75800 | 75800 |  | 75735 | 75735 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-259 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1110 | MEALS AND SNACKS | PSWDO | SVP | n/a | 10.12.2022 | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 193775 | 193775 |  | 191403 | 191403 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-260 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7775 | CERAMIC FLOOR TILES (600MM x 600MM - | VGO | SVP | n/a | 10.3.2022 | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 62500 | 62500 |  | 62000 | 62000 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-261 | 100 PCS) AND STICKWELL (4L - 30 GAL.) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1089 | MINERAL WATER (5 GAL. 882 CONS.) | SPO SEC. | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 39690 | 39690 |  | 35280 | 35280 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-262 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-C1017 | CONSTRUCTION SUPPLIES | PAGRO | SVP | n/a | 10.12.2022 | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 86723 | 86723 |  | 86611 | 86611 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-263 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7913 | PACKED MEALS (200 HEADS) | PAO | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 35000 | 35000 |  | 34800 | 34800 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-264 |  | TOURISM | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7793 | VULCANIZING PATCH | PEO EQPT. | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 14750 | 14750 |  | 14650 | 14650 |  | Ms. Grace V. Quintana | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-265 |  | POOL | [14 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda Valdez
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7428 | MINERAL WATER (5 GAL. - 25 CONS.) | PGSO | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 1125 | 1125 |  | 1000 | 1000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-266 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8110 | ELECTRICAL SUPPLIES | VGO | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 8905 | 8905 |  | 8880 | 8880 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-267 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7824 | MINERAL WATER (5 GAL. - 444 CONS.) | PHO | SVP | n/a | n/a | n/a | n/a | 10.20.2022 | n/a | n/a | 10.25.2022 |  |  |  |  | GF | 19980 | 19980 |  | 17760 | 17760 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-10-268 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
| ACCESSORIES | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
| PHOTOGRAPHY CAMERA TRIPOD | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
| SPEAKER | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
| KIOKMAY ES, LAAK | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7365 | COLORED PRINTER W/ SCANNER | PGO-SEF | SVP | 11.8.2022 | 9.6.2022 | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 60000 | 60000 |  | 59992 | 59992 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-310 | 3 in 1 TANK TYPE | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-6537 | FOOD SUPPLIES | PGO | SVP | 11.8.2022 | 8.5.2022 | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 190500 | 190500 |  | 190440 | 190440 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-309 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-6527 | TARPAULIN - as per design | PGO | SVP | 11.8.2022 | 8.5.2022 | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 50000 | 50000 |  | 48000 | 48000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-321 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7770 | 100W SOLAR LIGHT OUTDOOR | PGO | SVP | 11.8.2022 | 10.3.2022 | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 154000 | 154000 |  | 152250 | 152250 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-319 | WATER PROOF LED | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7958 | PACKED MEAL B and SNACKS B (light) | PGO | SVP | 11.8.2022 | 10.10.2022 | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 140000 | 140000 |  | 138708 | 138708 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-307 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8207 | REFRIGERATOR, 5cu. Ft. | PAO | SVP | 11.8.2022 | n/a | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 16450 | 16450 |  | 16350 | 16350 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-320 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
| (CLERICAL and MID RANGE) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-C1144 | SPARE PARTS | PDRRMO | SVP | 11.8.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 43194 | 43194 |  | 38580 | 38580 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P,O, FOR SERVE
22-12-340 | (HEAVY AND LIGHT EQUIPMENT) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8238 | INK EPSON 003 BLACK, INK EPSON | PTO | SB | 11.8.2022 | [11 empty] | GF | 10250 | 10250 |  | 76188 | 76188 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| T6641 BLACK | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8240 | INK EPSON 003 BLACK, INK EPSON | PTO | SB | 11.8.2022 | [11 empty] | GF | 10250 | 10250 |  | 34613 | 34613 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
| T6641 BLACK | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-C1136 | COMPUTER SUPPLIES/SPARE PARTS | PENRO | SB | 11.8.2022 | 11.16.2022 | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 59700 | 59700 |  | 59615 | 59615 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P,O, FOR SERVE
22-12-332 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7980 | SWEAT SHIRT (CUSTOMIZED W/ PATCHES) | PENRO | SVP | 11.8.2022 | n/a | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 39000 | 39000 |  | 38675 | 38675 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-306 | as per design | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7996 | SUPPLY AND INSTALLATION OF GLASS | PENRO | SVP | 11.8.2022 | n/a | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 5040 | 5040 |  | 5040 | 5040 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-315 | WINDOW WITH ALUMINUM FRAME | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8072 | JANITORIAL SUPPLIES | PENRO | SVP | 11.8.2022 | n/a | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 1906 | 1906 |  | 1906 | 1906 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-316 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7932 | OFFICE EQUIPMENT | PAGRO | SVP | 11.8.2022 | n/a | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 49948 | 49948 |  | 48600 | 48600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-317 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-C1100 | CONSTRUCTION SUPPLIES | PAGRO | SVP | 11.8.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 26864 | 26864 |  | 26674 | 26674 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P,O, FOR SERVE
22-12-339 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8237 | OFFICE SUPPLIES | PTO | SB | 11.8.2022 | [11 empty] | GF | 39670 | 39670 |  | 33500 | 33500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8241 | OFFICE SUPPLIES | PTO | SB | 11.8.2022 | [11 empty] | GF | 39750 | 39750 |  | 8175 | 8175 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8134 | #1 LADDLE | PTO | SVP | 11.8.2022 | [11 empty] | GF | 720 | 720 |  | 209500 | 209500 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8133 | TRASH CAN WITH COVER | PTO | SVP | 11.8.2022 | [11 empty] | GF | 2295 | 2295 |  | 99175 | 99175 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8271 | BATTERY, RECHARGEABLE SEALED | PACCCO | SVP | 11.8.2022 | n/a | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 7200 | 7200 |  | 7200 | 7200 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-322 | LEAD-ACID 12V 7AH | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8274 | COMPUTER SUPPLIES/SPARE PARTS | PACCO | SVP | 11.8.2022 | 10.24.2022 | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 87848 | 87848 |  | 87760 | 87760 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-304 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8428 | CHAIR, MONOBLOC W/OUT ARM and | PTO | SVP | 11.8.2022 | n/a | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 26800 | 26800 |  | 26780 | 26780 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-314 | TRAINING FOLDING TABLE (Blow Molded) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8323 | MEAL WITHOUT VENUE and SNACKS B | PIAO | SVP | 11.8.2022 | n/a | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 25000 | 25000 |  | 24800 | 24800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-305 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
| 70 gsm. | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
(consol | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-8008) | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
(consol | ACCESSORIES | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-8008) | [16 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
| T6643 MAGENTA, T6644 YELLOW | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-C1170 | COMPUTER SUPPLIES/SPARE PARTS | PGSO | SVP | 11.8.2022 | 11.11.2022 | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 78177 | 78177 |  | 77970 | 77970 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-312 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-C1171 | OFFICE SUPPLIES | PGSO | SVP | 11.8.2022 | n/a | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 9953 | 9953 |  | 9953 | 9953 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-313 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-C1183 | ACCESSORIES AND DECORATION | PGSO | SVP | 11.8.2022 | 11.11.2022 | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 79526 | 79526 |  | 79503 | 79503 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-338 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7854 | TARPAULIN - as per design | PDRRMO | SVP | 11.8.2022 | 10.6.2022 | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 100000 | 100000 |  | 96000 | 96000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-303 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7874 | OFFICE SUPPLIES | PDRRMO | SB | 11.8.2022 | n/a | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 9060 | 9060 |  | 8990 | 8990 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-323 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
22-C1292 | OFFICE SUPPLIES | PTO | SB | n/a | 11.11.2022 | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 79390 | 79390 |  | 79210 | 79210 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
22-11-324 | [22 empty] | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-8087 | COMPUTER SUPPLIES/SPARE PARTS | PDRRMO | SVP | 11.8.2022 | 10.14.2022 | [10 empty] | GF | 91410 | 91410 |  | 22000 | 22000 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-11-298 | SUPPLIES FOR THE USE OF | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
| VARIOUS HOSPITALS | [15 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-C1114 | LABORATORY SUPPLIES | PVO | SVP | n/a | n/a | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 11430 | 11430 |  | 11417 | 11417 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-276 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-C1131 | APPLIANCES | PSWDO | SVP | n/a | 10.18.2022 | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 53800 | 53800 |  | 50800 | 50800 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-277 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7663 | LIQUID NITROGEN | PVO | SVP | n/a | 9.30.2022 | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 86400 | 86400 |  | 86400 | 86400 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-278 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7105 | RUBBER BOOTS FOR MOTORCYCLE | PAGRO | SVP | n/a | n/a | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 7800 | 7800 |  | 7776 | 7776 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-281 | (12 SETS) | [15 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7774 | CEMENT (40KG/SACK;55 BAGS) | VGO | SVP | n/a | n/a | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 14300 | 14300 |  | 14300 | 14300 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-282 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-C1127 | KITCHEN SUPPLIES | PSWDO | SVP | n/a | n/a | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 30293 | 30293 |  | 30034 | 30034 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-283 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-C1130 | DOMESTIC SUPPLIES | PSWDO | SVP | n/a | 10.18.2022 | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 62092 | 62092 |  | 61447.4 | 61447.4 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-284 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7873 | SAND BAG - LARGE 100S (200 PACKS) | PDRRMO | SVP | n/a | n/a | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 31000 | 31000 |  | 30600 | 30600 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-289 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-7929 | LABORATORY SUPPLIES | PAGRO | SVP | n/a | n/a | n/a | n/a | 11.3.2022 | n/a | n/a | 11.8.2022 |  |  |  |  | GF | 6708 | 6708 |  | 6708 | 6708 |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-11-292 | [16 empty] | 0 |  |  | 0 |  |  | Ms. Grace V. Quintana
[17 empty] | 0 |  |  | 0 |  |  | Ms. Carmencita Valdez
22-C1052 | AIRCONDITION SPARE PARTS | PGSO | SVP | 11.15.2022 | 11.16.2022 | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 83621 | 83621 |  | 66590 | 66590 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-346 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1192 | SPARE PARTS (MOTORCYCLE) | PGSO | SVP | 11.15.2022 | 11.16.2022 | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 64475 | 64475 |  | 64475 | 64475 |  |  | n/a | n/a | n/a | n/a | n/a |  | P,O. FOR SERVE
22-12-347 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-2029 | SPARE PARTS (MOTORCYCLE) | PGSO | SA | 11.15.2022 | n/a | [10 empty] | GF | 2600 | 2600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8297 | SUPPLY AND INSTALLATION OF FIXED | PGSO | SVP | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 17850 | 17850 |  | 17850 | 17850 |  |  | n/a | n/a | n/a | n/a | n/a |  | P,O. FOR SERVE
22-12-348 | GLASS - 1 UNIT (21sq. Ft.) | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1020 | AGRICULTURAL SUPPLIES | PGSO | SVP | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 12550 | 12550 |  | 12530 | 12530 |  |  | n/a | n/a | n/a | n/a | n/a |  | P,O, FOR SERVE
22-12-349 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8362 | GEMELINA LUMBER, COCO OR | PGO-PS | SVP | 11.15.2022 | n/a | [11 empty] | 23087.85 | 23087.85 |  | 0
| EQUIVALENT | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| GEMELINA LUMBER, COCO OR | PGO-PS | SVP | 11.15.2022 | n/a | [11 empty] | 23087 | 23087 |  | 0
| EQUIVALENT | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| GEMELINA LUMBER, COCO OR | PGO-PS | SVP | 11.15.2022 | n/a | [11 empty] | 23087 | 23087 |  | 0
| EQUIVALENT | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| GEMELINA LUMBER, COCO OR | PGO-PS | SVP | 11.15.2022 | n/a | [12 empty] | 23087.85
| EQUIVALENT | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| GEMELINA LUMBER, COCO OR | PGO-PS | SVP | 11.15.2022 | n/a | [10 empty] | GF | 23087.85 | 23087.85 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| EQUIVALENT | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| GEMELINA LUMBER, COCO OR | PGO-PS | SVP | 11.15.2022 | n/a | [10 empty] | GF | 23087.85 | 23087.85 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| EQUIVALENT | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| GEMELINA LUMBER, COCO OR | PGO-PS | SVP | 11.15.2022 | n/a | [10 empty] | GF | 23087.85 | 23087.85 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| EQUIVALENT | [15 empty] | 0 |  |  | 0
| GEMELINA LUMBER, COCO OR | PDRRMO | SVP | 11.15.2022 | n/a | [10 empty] | GF | 3360.15 | 3360.15 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
EQUIVALENT
[17 empty] | 0 |  |  | 0
22-8362 | GEMELINA LUMBER, COCO OR | PGO-PS | SVP | 11.15.2022 | n/a | [10 empty] | GF | 2160 | 2160 |  | 125000 | 125000 |  |  | n/a | n/a | n/a | n/a | n/a
| EQUIVALENT | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
0
[17 empty] | 0 |  |  | 0
0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| (BENDED PRE-PAINTED, 0.40mm) | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| (COVERED COURT), BRGY. INAMBATAN, | [15 empty] | 0 |  |  | 0
| MONKAYO | [15 empty] | 0 |  |  | 0
22-8338 | MEDICAL KIT | PGO-PS | SVP | 11.15.2022 | n/a | [10 empty] | GF | 1925 | 1925 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8338 | MEDICAL KIT | PGO-PS | SVP | 11.15.2022 | n/a | [10 empty] | GF | 1925 | 1925 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8383 | SUPPLY AND INSTALLATION OF | PGO-PS | SVP | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 1680 | 1680 |  | 1680 | 1680 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-344 | GLASS JALOUSIE WINDOW | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8915 | MEALS AND SNACKS A (light) | PGO | SVP | 11.15.2022 | 11.11.2022 | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 259950 | 259950 |  | 256372 | 256372 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-345 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8676 | MEALS WITHOUT VENUE and SNACKS A | PGO | SVP | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 45000 | 45000 |  | 38916 | 38916 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-359 | (HEAVY) | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8182 | FLASH DRIVE 16GB | PGO | SB | 11.15.2022 | n/a | [10 empty] | GF | 5000 | 5000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | FOR DELIVERY
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| VOICE RECORDED, 4GB INTERNAL MEMORY | PGO | SB | 11.15.2022 | n/a | [10 empty] | GF | 3300 | 3300 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| USB CABLE AND MEMORU CARD SLOT | [15 empty] | 0 |  |  | 0
| WITH LAPEL MIC. | [15 empty] | 0 |  |  | 0
| OFFICE SUPPLIES | PGO | SB | 11.15.2022 | n/a | [10 empty] | GF | 36053 | 36053 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8182 | OFFICE SUPPLIES | PGO | SB | 11.15.2022 | n/a | [10 empty] | GF | 10215.5 | 10215.5 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-7933 | MEALS WITH VENUE and SNACKS B (LIGHT) | PGO | SVP | 11.15.2022 | 10.7.2022 | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 354000 | 354000 |  | 350460 | 350460 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-355 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-7916 | PACKED MEAL A and SNACKS B (LIGHT) | PGO | SVP | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 33750 | 33750 |  | 33712.5 | 33712.5 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-356 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8183 | JANITORIAL SUPPLIES | PGO | SVP | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 4055 | 4055 |  | 4030 | 4030 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-333 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1012 | AUTOMATED RAIN GUAGE STATION | PDRRMO |  | 11.15.2022 | n/a | [10 empty] | GF | 5000 | 5000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8089 | ELECTRICAL SUPPLIES | PDRRMO | SVP | 11.15.2022 | n/a | [10 empty] | GF | 12682 | 12682 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| CAMERA SYSTEM LABOR & MATERIAL | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| (MIDRANGE) | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| (ALERIA SECTION ALONG NABUNTURAN- | [15 empty] | 0 |  |  | 0
| GABI-COMPOSTELA ROAD) | [15 empty] | 0 |  |  | 0
22-8065 | MINERAL WATER, 5 gal. | PDRRMO | SVP | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 19980 | 19980 |  | 17760 | 17760 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-357 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8442 | TF WIRE TWISTED STRANDED 2 CORE #16 | PDRRMO | SVP | 11.15.2022 | n/a | [10 empty] | GF | 45000 | 45000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1232 | INK, EPSON ECOTANK | PDRRMO | SB | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 27080 | 27080 |  | 27080 | 27080 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-334 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8433 | CEILING SPEAKER 6-7 WATTS and PUBLIC | PDRRMO | SVP | 11.15.2022 | n/a | [10 empty] | GF | 34500 | 34500 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| ADDRESS AMPLIFIER 250 WATTS | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1066 | CONSTRUCTION SUPPLIES | PDRRMO | SVP | 11.15.2022 | n/a | [10 empty] | GF | 5815 | 5815 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1066 | PORTLAND CEMENT | PDRRMO | SVP | 11.15.2022 | n/a | [10 empty] | GF | 20020 | 20020 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8081 | TROLLEY SPEAKER, PORTABLE | PDRRMO | SVP | 11.15.2022 | 10.14.2022 | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 67200 | 67200 |  | 66800 | 66800 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-363 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1237 | TIRES TUBELESS | PDRRMO | SVP | 11.15.2022 | [11 empty] | GF | 341420 | 341420 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-7923 | CLERICAL CHAIR WITH ARM REST | PAO- | SVP | 11.15.2022 | n/a | n/a | n/a | 11.17.2022 | n/a | n/a | 11.22.2022 |  |  |  |  | GF | 17500 | 17500 |  | 17493 | 17493 |  |  | n/a | n/a | n/a | n/a | n/a
22-11-318 |  | TOURISM | [14 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8644 | T-SHIRT PRINTING | PAO-PESO | SVP | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 32500 | 32500 |  | 32500 | 32500 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-358 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8399 | INK EPSON (BLACK, CYAN, MAGENTA) | PAO-PESO | SB | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 17600 | 17600 |  | 17504 | 17504 |  |  | n/a | n/a | n/a | n/a | n/a
22-12-335 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1031 | FOLDING SINGLE CAMPING BED, STEEL | PHO | NP-SVP | 11.15.2022 | n/a | [10 empty] | GF | 48735 | 48735 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| FILING CABINET, WASHING MACHINE | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-6392 | KITCHENWARE AND UTENSILS | PHO | NP-SVP | 11.15.2022 | n/a | [10 empty] | GF | 30250 | 30250 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8284 | CACAO WET BEANS | PAGRO | NP-SVP | 11.15.2022 | n/a | [10 empty] | GF | 8500 | 8500 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8073 | MEALS AND SNACKS | PAGRO | NP-SVP | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 20100 | 20100 |  | 20059.4 | 20059.4 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-362 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8313 | DYNAMIC MICROPHONE | PIAO | NP-SVP | 11.15.2022 | n/a | [10 empty] | GF | 2500 | 2500 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| SYSTEM PROJECTOR | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8536 | PIPE COPPER TUBE | PACCO | NP-SVP | 11.15.2022 | n/a | [10 empty] | GF | 22500 | 22500 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8561 | TELEVISION | PTO | NP-SVP | 11.15.2022 | n/a | n/a | n/a | 11.24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 25000 | 25000 |  | 25000 | 25000 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-360 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8560 | AMPLIFIER | PTO | NP-SVP | 11.15.2022 | n/a | [10 empty] | GF | 15000 | 15000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C0579 | FERTILIZERS | PAGRO | NP-SVP | 11.15.2022 | n/a | [10 empty] | GF | 46900 | 46900 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8380 | JOB ORDER: REPAIR OF MOTOR VEHICLE | DDOPH | NP-SVP | 11.15.2022 | 10.26.2022 | [10 empty] | GF | 265820.6 | 265820.6 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
|  | MONTEVISTA | [14 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1259 | GROCERY ITEMS | PEEMO | NP-SVP | 11.15.2022 | 11.23.2022 | n/a | n/a | 11/24.2022 | n/a | n/a | 11.29.2022 |  |  |  |  | GF | 218249 | 218249 |  | 217757 | 217757 |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O. FOR SERVE
22-12-367 | [16 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8853 | HBA1C TEST (GLYCATED HAEMOGLOBIN A1C) | PGO-PS | NP-SVP | 11.15.2022 | n/a | [10 empty] | GF | 48000 | 48000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1322 | FLUIDS | PEEMO | NP-SVP | 11.15.2022 | [11 empty] | GF | 304164 | 304164 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1120 | SPAREPARTS | PAGRO | NP-SVP | 11.15.2022 | [11 empty] | GF | 235063.1 | 235063.1 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-11-235 | SUPPLIES | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-1166 | MEALS AND SNACKS | PGO | NP-SVP | 11.22.2022 | [11 empty] | GF | 177500 | 177500 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-4261 | FUEL FILTER FOR GEN. SET | COA | NP-SVP | 11.22.2022 | [11 empty] | GF | 9270 | 9270 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a
| V-BELT - 8PR 143 FOR GEN SET | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8822 | MEALS W/ VENUE AND SNACKS A (LIGHT) | PHRMDO | NP-SVP | 11.22.2022 | [11 empty] | GF | 100000 | 100000 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1215 | GEMELINA LUMBER OR EQUIVALENT | PAO | NP-SVP | 11.22.2022 | [11 empty] | GF | 26440 | 26440 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a
|  | TOURISM | [14 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| REFLECTORIZE | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1153 | CHEMICALS | PENRO | NP-SVP | 11.22.2022 | [11 empty] | GF | 61423 | 61423 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1154 | LABORATORY SUPPLIES | PENRO | NP-SVP | 11.22.2022 | [11 empty] | GF | 53465 | 53465 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8003 | AGRICULTURAL SUPPLIES | PENRO | NP-SVP | 11.22.2022 | [11 empty] | GF | 83150 | 83150 |  | 0 |  |  |  | 05.24.2022 | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8921 | GLASSES (for Laboratory use) | PENRO | NP-SVP | 11.22.2022 | [11 empty] | GF | 19006 | 19006 |  | 0 |  |  |  | n/a | n/a | 05.24.2022 | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8891 | CONFERENCE ROOM WINDOW 1 BLINDS | PAO | NP-SVP | 11.22.2022 | [11 empty] | GF | 16400 | 16400 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
|  | ADMIN | [14 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8343 | TABLE NAME HOLDER | PAO | NP-SVP | 11.22.2022 | [11 empty] | GF | 4000 | 4000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O FOR APPROVAL
|  | ADMIN | [14 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1291 | OFFICE SUPPLIES | PAO | SB | 11.22.2022 | [11 empty] | GF | 77669 | 77669 |  | 0 |  |  |  | n/a | n/a | 05.24.2022 | n/a | n/a |  | FOR DELIVERY
|  | ADMIN | [14 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8344 | PAINTING MATERIALS | PASSO | NP-SVP | 11.22.2022 | [11 empty] | GF | 21020 | 21020 |  | 0 |  |  |  | n/a | n/a | 05.24.2022 | n/a | n/a |  | P.O FOR APPROVAL
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8343 | CONSTRUCTION MATERIALS | PASSO | NP-SVP | 11.22.2022 | [11 empty] | GF | 6210 | 6210 |  | 0 |  |  |  | n/a | n/a | 05.24.2022 | n/a | n/a |  | P.O FOR APPROVAL
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8930 | HARD DISK, 1 TERABYTE AND UPS | PASSO | NP-SVP | 11.22.2022 | [11 empty] | GF | 22500 | 22500 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O
| W/ BUILT IN AVR | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8979 | PACKED MEALS B and SNACKS B (LIGHT) | PASSO | NP-SVP | 11.22.2022 | [11 empty] | GF | 11750 | 11750 |  | 0 |  |  |  | 05.24.2022 | n/a | 06.07.2022 | n/a | n/a |  | P.O FOR APPROVAL
| transformer and electrical supplies | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8807 | SHIRT POLO W/ COLOR COMBINATION | PHO | NP-SVP | 11.22.2022 | [11 empty] | GF | 103050 | 103050 |  | 0 |  |  |  | n/a | n/a | 05.24.2022 | n/a | n/a |  | P.O FOR APPROVAL
| T-SHIRT JERSEY | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8623 | WIRE EXTENSION 30 MTRS. AND WIRE | PHO | NP-SVP | 11.22.2022 | [11 empty] | GF | 10340 | 10340 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| EXTENSION W/ HANDLE 15 MTRS. | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8525 | AIRCON SPLIT TYPE WALL MOUNTED 3.0 HP | PICTO | NP-SVP | 11.22.2022 | [11 empty] | GF | 150000 | 150000 |  | 0 |  |  |  | 06.07.2022 | n/a | 06.17.2022 | n/a | n/a |  | P.O FOR APPROVAL
| AND AIRCON WINDOW TYPE 2.0 HP | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1269 | CEILING SPEAKER 6-7 WATTS W/ MATCHING | PICTO | NP-SVP | 11.22.2022 | [11 empty] | GF | 49940 | 49940 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| TRANSOFRMER AND ELECTRICAL SUPPLIES | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1227 | COMPUTER SUPPLIES/SPARE PARTS | PICTO | NP-SVP | 11.22.2022 | [11 empty] | GF | 119870 | 119870 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| ACCESSORIES | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1224 | GEMELINA LUMBER OR EQUIVALENT | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | GF | 2160 | 2160 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8340 | GEMELINA LUMBER OR EQUIVALENT | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | GF | 23087.85 | 23087.85 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1218 | GEMELINA LUMBER OR EQUIVALENT | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | GF | 2160 | 2160 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8408 | PORTLAND CEMENT | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | GF | 292500 | 292500 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8571 | NAILS, ORDINARY PLYWOOD TYPE II | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | GF | 1630 | 1630 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
| LOCAL C | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8550 | NAILS, ORDINARY PLYWOOD TYPE II | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | GF | 1630 | 1630 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
| LOCAL C | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8434 | NAILS, ORDINARY PLYWOOD TYPE II | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | GF | 1630 | 1630 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
| LOCAL C | [18 empty] | 0
[17 empty] | 0 |  |  | 0
22-8563 | NAILS, ORDINARY PLYWOOD TYPE II | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | GF | 1630 | 1630 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
| LOCAL C | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8440 | TARPAULIN - AS PER DESIGN | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | GF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8543 | TARPAULIN - AS PER DESIGN | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | GF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R,O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8574 | TARPAULIN - AS PER DESIGN | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | GF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R,O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8566 | TARPAULIN - AS PER DESIGN | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | TF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R,O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8417 | TARPAULIN - AS PER DESIGN | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | GF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8341 | ROOFING MATERIALS | PGO-PS | NP-SVP | 11.22.2022 | [11 empty] | GF | 51477 | 51477 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8926 | SPARE PARTS (LIGHT VEHICLE) | SPO-SEC | SA | 11.22.2022 | [11 empty] | GF | 100710 | 100710 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-2784 | BRAKE PAD, GEN BRAKE, SHOE GEN | SPO-SEC | SA | 11.22.2022 | [11 empty] | GF | 27000 | 27000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1336 | SPARE PARTS (MOTOR VEHICLE) | SPO-SEC | SA | 11.22.2022 | [11 empty] | GF | 8450 | 8450 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8955 | JOB ORDER (REPAIR OF MOTOR VEHICLE) | SPO-SEC | SA | 11.22.2022 | [11 empty] | GF | 6860 | 6860 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| (WHEEL ALIGNMENT AND WHEEL | [15 empty] | 0 |  |  | 0
| BALANCING) | [15 empty] | 0 |  |  | 0
22-C1337 | BELT STEERING, JOB ORDER (REPAIR | SPO-SEC | SA | 11.22.2022 | [11 empty] | GF | 21000 | 21000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| OF MOTOR VEHICLE) (SUCTION CONTROL | [15 empty] | 0 |  |  | 0
| VALVE) | [15 empty] | 0 |  |  | 0
22-C1335 | SPARE PARTS (MOTOR VEHICLE) | SPO-SEC | SA | 11.22.2022 | [11 empty] | GF | 39812 | 39812 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| JOB ORDER FOR MOTOR VEHICLE | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-1345 | SPAREPARTS (MOTOR VEHICLE) | SPO-SEC | SA | 11.22.2022 | [11 empty] | GF | 20610 | 20610 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8957 | SPAREPARTS (MOTOR VEHICLE) | SPO-SEC | SA | 11.22.2022 | [11 empty] | GF | 37256 | 37256 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-2842 | CLIP STABILIZER BUSHING, LINK KIT, | SPO-SEC | SA | 11.22.2022 | [11 empty] | GF | 12000 | 12000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| STABILIZER FOR NVRA-YD25 | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| HEAVY DUTY WITH DRAWER | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| ACCESSORIES AND STUDIO LIGHTS | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| DESKTOP COMPUTER CORE I7 LAPTOP | [15 empty] | 0 |  |  | 0
| (HIGH END) | [15 empty] | 0 |  |  | 0
22-8216 | WIRE EXTENSION WITH OUTLETS | PGO-SEF | NP-SVP | 11.22.2022 | [11 empty] | GF | 5600 | 5600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | P.O FOR APPROVAL
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8246 | ROOFING MATERIALS | PGO-SEF | NP-SVP | 11.22.2022 | [11 empty] | GF | 63352.5 | 63352.5 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1174 | CONSTRUCTION MATERIALS | PGO-SEF | NP-SVP | 11.22.2022 | [11 empty] | GF | 7930 | 7930 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C0737 | IMPULSE SEALER. WEIGHING SCALE | PAGRO | NP-SVP | 11.22.2022 | [11 empty] | GF | 16240 | 16240 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| (60KGS CAPACITY) | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8901 | FEED INGREDIENTS (for fishery development) | PAGRO | NP-SVP | 11.22.2022 | [11 empty] | GF | 76240 | 76240 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| LOCAL C | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-1448 | STAMP, RUBBER (2-lines - machine cut) | PAGRO | NP-SVP | 11.22.2022 | [11 empty] | GF | 1000 | 1000 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| LOCAL C | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C0294 | ADLAY SEEDS, COFFEE SEEDS, UPLAND | PAGRO | NP-SVP | 11.22.2022 | [11 empty] | GF | 129150 | 129150 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| RICE SEEDS | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-4575 | EMPTY PLASTIC DRUM (200 LITERS) | PAGRO | NP-SVP | 11.22.2022 | [11 empty] | GF | 4725 | 4725 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-4768 | PAIL, PLASTIC W/ COVER, MEDIUM | PAGRO | NP-SVP | 11.22.2022 | [11 empty] | GF | 1250 | 1250 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-4691 | GULAMAN BAR (2 PCS./ PER PACK, | PAGRO | NP-SVP | 11.22.2022 | [11 empty] | GF | 17182 | 17182 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
| OATMEAL, YEAST EXTRACT) | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-4690 | MOLASSES | PAGRO | NP-SVP | 11.22.2022 | [11 empty] | GF | 400 | 400 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1077 | MINERAL WATER (330 ML AND 5 GAL.) | PGSO | NP-SVP | 11.22.2022 | [11 empty] | GF | 144050 | 144050 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8854 | JANITORIAL SUPPLIES | PGSO | NP-SVP | 11.22.2022 | [11 empty] | GF | 4115 | 4115 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8843 | JANITORIAL SUPPLIES | PGSO | NP-SVP | 11.22.2022 | [11 empty] | GF | 4703 | 4703 |  | 0 |  |  |  | n/a | n/a | 06.07.2022 | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8855 | OFFICE SUPPLIES | PGSO | NP-SVP | 11.22.2022 | [11 empty] | GF | 39534 | 39534 |  | 0 |  |  |  | n/a | n/a | 06.07.2022 | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8848 | VENETIAN BLINDS, VERTICAL | PGSO | NP-SVP | 11.22.2022 | [11 empty] | GF | 16500 | 16500 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8844 | MICROPHONE, WIRELESS PROFESSIONAL | PGSO | NP-SVP | 11.22.2022 | [11 empty] | GF | 8200 | 8200 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8851 | COMPUTER SUPPLIES | PGSO | SB | 11.22.2022 | [11 empty] | GF | 31200 | 31200 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8954 | PLUMBING MATERIALS | PGSO | NP-SVP | 11.22.2022 | [11 empty] | GF | 117410 | 117410 |  | 0 |  |  |  | n/a | n/a |  | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1185 | CONSTRUCTION SUPPLIES | PGSO | NP-SVP | 11.22.2022 | [11 empty] | GF | 22891.75 | 22891.75 |  | 0 |  |  |  | n/a | n/a | 06.07.2022 | n/a | n/a |  | RETURNED TO R.O.
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1325 | CABLE TIE, NYLON 6" RUGBY | PGSO | NP-SVP | 11.22.2022 | [11 empty] | GF | 20150 | 20150 |  | 0 |  |  |  | n/a | n/a | 06.07.2022 | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1349 | SPAREPARTS (MOTORCYCLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 20050 | 20050 |  | 0 |  |  |  | n/a | n/a | 06.07.2022 | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1354 | JOB ORDER (REPAIR OF MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 51400 | 51400 |  | 0 |  |  |  | 05.31.2022 | n/a | 06.17.2022 | n/a | n/a
| SPAREPARTS (LIGHT VEHICLE) | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-1353 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 75770 | 75770 |  | 0 |  |  |  | n/a | n/a | 06.07.2022 | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-7145 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 2410 | 2410 |  | 0 |  |  |  | n/a | n/a | 06.07.2022 | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-7534 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 12550 | 12550 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-7045 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 22465 | 22465 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-7537 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 24150 | 24150 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-7354 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 2100 | 2100 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-1194 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 48650 | 48650 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1350 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 93235 | 93235 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1307 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 68541 | 68541 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-5019 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 8912 | 8912 |  | 0 |  |  |  | n/a | n/a | 06.14.2022 | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-4982 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 16450 | 16450 |  | 0 |  |  |  | n/a | n/a | 06.07.2022 | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-4988 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 20052 | 20052 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-4987 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 14422 | 14422 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-4980 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 7889 | 7889 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-5012 | SPAREPARTS (MOTOR VEHICLE) | PGSO | SA | 11.22.2022 | [11 empty] | GF | 46304.8 | 46304.8 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8732 | JANITORIAL SUPPLIES | PEO-RCPC | NP-SVP | 11.22.2022 | [11 empty] | GF | 31535 | 31535 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8713 | UPS W/ BUILT-IN AVR (600VA and 1000VA) | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 57287 | 57287 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| FACILITIES AT DDOPH-LAAK | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| FACILITIES AT DDOPH-MARAGUSAN | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-7572 | ROOFING MATERIALS | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 143587 | 143587 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8884 | ROOFING MATERIALS | PEO | NP-SVP | 11.22.2022 | [10 empty] | 06.24.2022 | GF | 51477 | 51477 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8787- | ROOFING MATERIALS | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 42578.4 | 42578.4 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-C1278 | ROOFING MATERIALS | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 93630.9 | 93630.9 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8903 | RIB TYPE, PRE-PAINTED, LONG SPAN | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 28080 | 28080 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
| ROOFING | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8553 | TARPAULIN (as per design) | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8637 | TARPAULIN (as per design) | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8548 | TARPAULIN (as per design) | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8569 | TARPAULIN (as per design) | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8740 | TARPAULIN (as per design) | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8425 | TARPAULIN (as per design) | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8449 | TARPAULIN (as per design) | PEO | NP-SVP | 11.22.2022 | [11 empty] | TF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8580 | TARPAULIN (as per design) | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8817 | TARPAULIN (as per design) | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
22-8911 | TARPAULIN (as per design) | PEO | NP-SVP | 11.22.2022 | [11 empty] | GF | 1600 | 1600 |  | 0 |  |  |  | n/a | n/a | n/a | n/a | n/a
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
| TYPE 400mm, DRAWER HANDLE 100mm | [15 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0
[17 empty] | 0 |  |  | 0

## CIVIL WORKS
ANNEX B
|  | (Provincial Government of Davao de Oro) Procurement Monitoring Report as of JULY/30/2022 | [18 empty] | (Provincial Government of Davao de Oro) Procurement Monitoring Report as of July/30/2022
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Mode of Procurement
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  | LIST OF OBSERVERS | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Delivery/Completion/Acceptance (If Applicable) | REMARKS (explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES
22-4098 | Construction of Multipurpose Hall @ Barabat, | PGO | PB | 05.27.2022 | 10.7.2022 | 10.18.2022 | 11.2.2022 | 11.2.2022 | [7 empty] | GF | 1937753.2 | 1937753.2 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a
CW22-033 | Elem. School, Cagan, Brgy. Andap, New Bataan | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-4200 | Construction of Stage and Bleachers @ Melale | PGO | PB | 05.27.2022 | 10.7.2022 | 10.18.2022 | 11.2.2022 | 11.2.2022 | [7 empty] | GF | 2912879.05 | 2912879.05 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a | n/a | n/a | n/a
CW22-032 | NHS, Brgy. Melale, Laak | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
Engr. Michael C. Salarda
22-7344 | CONSTRUCTION OF 1 UNIT 2 CLASSROOM | PGO - SEF | PB | 9.27.2022 | [11 empty] | GF | 2399227.92 | 2399227.92 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a |  | n/a | n/a |  | REBID
CW22-034 | AT KILAGDING NHS | [15 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda
22-7122 | CONSTRUCTION OF GYM, PALOC NHS | PGO - SEF | PB | 9.27.2022 | 10.7.2022 | 10.18.2022 | 11.2.2022 | 11.2.2022
CW22-035 | MARAGUSAN | [14 empty] | GF | 4954026.16 | 4954026.16 |  | 0 |  |  | Mr. Allan Rey N. Esmael | n/a |  | n/a | n/a |  | REBID
[17 empty] | 0 |  |  | 0 |  |  | Ms. Leonarda M. Nator
[17 empty] | 0 |  |  | 0 |  |  | Engr. Michael C. Salarda

## computation
2399227.92 |  | 2399227.92 | 2279270.51 |  | 2279270.51 | 119957.41
1937753.2 |  | 1937753.2 | 1934245.57 |  | 1934245.57 | 3507.63
4954026.15 |  | 4954026.15 | 4093839.9 |  | 4093839.9 | 860186.25 | 22-7122
3965208.25 |  | 3965208.25 | 3945070.71 |  | 3945070.71 | 20137.54
1583224.96 |  | 1583224.96 | 1533241.65 |  | 1533241.65 | 49983.31
1029200 | 1029200 |  | 1029200 | 1029200 |  | -
2912879.05 |  | 2912879.05 | 2882860.9 |  | 2882860.9 | 30018.15 |  |  |  | 659042
65000 | 65000 |  | 64500 | 64500 |  | 500 |  |  |  | 0
12000 | 12000 |  | 11500 | 11500 |  | 500 |  |  |  | 0
399038 | 399038 |  | 396698 | 396698 |  | 2340 |  |  |  | 9750824
3706042.5 | 3706042.5 |  | 3140312.5 | 3140312.5 |  | 565730 |  |  |  | 0
240000 | 240000 |  | 180000 | 180000 |  | 60000 |  |  |  | 0
676300 | 676300 |  | 675750 | 675750 |  | 550 |  |  |  | 2110970
1224950 | 1224950 |  | 1183950 | 1183950 |  | 41000 |  |  |  | 0
5000000 | 5000000 |  | 4992082 | 4992082 |  | 7918
103150 | 103150 |  | 57650 | 57650 |  | 45500 |  |  |  | 12520836 | #REF!
6500000 | 6500000 |  | 5589999 | 5589999 |  | 910001
160000 | 160000 |  | 119000 | 119000 |  | 41000
189000 | 189000 |  | 173880 | 173880 |  | 15120
906157 | 906157 |  | 826228 | 826228 |  | 79929
6023 | 6023 |  | 6023 | 6023 |  | 0
9740 | 9740 |  | 9740 | 9740 |  | 0
63812 | 63812 |  | 63812 | 63812 |  | 0
16200 | 16200 |  | 16200 | 16200 |  | 0
2783700 | 2783700 |  | 2783700 | 2783700 |  | 0
4025000 | 4025000 |  | 4025000 | 4025000 |  | 0
4593 | 4593 |  | 4440 | 4440 |  | 153
82855 | 82855 |  | 82755 | 82755 |  | 100
7200 | 7200 |  | 7170 | 7170 |  | 30
16828 | 16828 |  | 15626 | 15626 |  | 1202
16879.8 | 16879.8 |  | 16800 | 16800 |  | 79.8
30240 | 30240 |  | 28917 | 28917 |  | 1323
28948 | 28948 |  | 28917 | 28917 |  | 31
26472 | 26472 |  | 25652 | 25652 |  | 820
172632 | 172632 |  | 171300 | 171300 |  | 1332
58564 | 58564 |  | 57596 | 57596 |  | 968
103870 | 103870 |  | 102870 | 102870 |  | 1000
8600 | 8600 |  | 8100 | 8100 |  | 500
6400 | 6400 |  | 6385 | 6385 |  | 15
4984 | 4984 |  | 4895 | 4895 |  | 89
100000 | 100000 |  | 98000 | 98000 |  | 2000
41483 | 41483 |  | 41391 | 41391 |  | 92
505479 | 505479 |  | 499855 | 499855 |  | 5624
47314 | 47314 |  | 46160 | 46160 |  | 1154
1320 | 1320 |  | 1315 | 1315 |  | 5
45870 | 45870 |  | 45375 | 45375 |  | 495
13060 | 13060 |  | 12905 | 12905 |  | 155
11625 | 11625 |  | 11250 | 11250 |  | 375
5500 | 5500 |  | 5250 | 5250 |  | 250
1550000 | 1550000 |  | 1549000 | 1549000 |  | 1000
1838827 | 1838827 |  | 1699067 | 1699067 |  | 139760
1838827 | 1838827 |  | 1699067 | 1699067 |  | 139760
1531087 | 1531087 |  | 1247416 | 1247416 |  | 283671
1780000 | 1780000 |  | 1505000 | 1505000 |  | 275000
45075 | 45075 |  | 45075 | 45075 |  | 0
4989979.79 |  | 4989979.79 | 4844040.38 |  | 4844040.38 | 145939.41
1216901.49 |  | 1216901.49 | 1198171.05 |  | 1198171.05 | 18730.44
4839332.08 |  | 4839332.08 | 4789339.41 |  | 4789339.41 | 49992.67
4983677.95 |  | 4983677.95 | 4933595.15 |  | 4933595.15 | 50082.8
11325045.94 |  | 11325045.94 | 11291501.41 |  | 11291501.41 | 33544.53
3739970 | 3739970 |  | 2453165 | 2453165 |  | 1286805
5967036 | 5967036 |  | 5961543 | 5961543 |  | 5493
160940 | 160940 |  | 159862 | 159862 |  | 1078
337902 | 337902 |  | 337396.77 | 337396.77 |  | 505.23
782000 | 782000 |  | 780000 | 780000 |  | 2000
281370 | 281370 |  | 229680 | 229680 |  | 51690
838084 | 838084 |  | 837560.25 | 837560.25 |  | 523.75
800400 | 800400 |  | 783000 | 783000 |  | 17400
386094 | 386094 |  | 378085 | 378085 |  | 8009
551583 | 551583 |  | 537675 | 537675 |  | 13908
90900 | 90900 |  | 89000 | 89000 |  | 1900
856256 | 856256 |  | 848590 | 848590 |  | 7666
580140 | 580140 |  | 399180 | 399180 |  | 180960
245861 | 245861 |  | 160817 | 160817 |  | 85044
290532 | 290532 |  | 237685 | 237685 |  | 52847
1709362 | 1709362 |  | 1150560 | 1150560 |  | 558802
1456432.2 |  | 1456432.2 | 786615.9 | 786615.9 |  | 669816.3
799560 | 799560 |  | 720850 | 720850 |  | 78710
12600 | 12600 |  | 12600 | 12600 |  | 0
4500 | 4500 |  | 4500 | 4500 |  | 0
249985 | 249985 |  | 247700 | 247700 |  | 2285
4204 | 4204 |  | 4200 |  | 4200 | 4
171862 | 171862 |  | 171498 |  | 171498 | 364
9191 | 9191 |  | 9119 |  | 9119 | 72
32530 | 32530 |  | 31730 |  | 31730 | 800
73418 | 73418 |  | 73149.5 |  | 73149.5 | 268.5 |  | 23-1594
691645 | 691645 |  | 640866 |  | 640866 | 50779
24000 | 24000 |  | 23880 |  | 23880 | 120
84000 | 84000 |  | 83825 |  | 83825 | 175
525000 | 525000 |  | 523000 |  | 523000 | 2000
453631 | 453631 |  | 442108 |  | 442108 | 11523
99990.5 | 99990.5 |  | 99962 |  | 99962 | 28.5
1165923 | 1165923 |  | 1093370 |  | 1093370 | 72553
167423 | 167423 |  | 127590 |  | 1279590 | 39833
695600 | 695600 |  | 444000 |  | 444000 | 251600
673510 | 673510 |  | 417700 |  | 417700 | 255810
678149 | 678149 |  | 618700 |  | 618700 | 59449
25500 | 25500 |  | 25500 |  | 25500 | 0
18484 | 18484 |  | 18076 |  | 18076 | 408
796804 | 796804 |  | 796804 |  | 796804 | 0
17745 | 17745 |  | 17550 |  | 17550 | 195
1532 | 1532 |  | 1532 |  | 1532 | 0
20691 | 20691 |  | 20472 |  | 20472 | 219
11200 | 11200 |  | 11000 |  | 11000 | 200
28440 | 28440 |  | 28144 |  | 28144 | 296
14344 | 14344 |  | 14116 |  | 14116 | 228
10890 | 10890 |  | 10780 |  | 10780 | 110
49938 | 49938 |  | 49610 |  | 49610 | 328
25143 | 25143 |  | 24997 |  | 24997 | 146
1300 | 1300 |  | 1300 |  | 1300 | 0
5000 | 5000 |  | 4400 |  | 4400 | 600
484925 | 484925 |  | 470135 |  | 470135 | 14790
499416 | 499416 |  | 489205 |  | 489205 | 10211
4551 | 4551 |  | 4440 |  | 4440 | 111
16693 | 16693 |  | 16680 | 16680 |  | 13
410886 | 410886 |  | 390180 | 390180 |  | 20706
92642 | 92642 |  | 91650 | 91650 |  | 992
27593 | 27593 |  | 26920 | 26920 |  | 673
6949 | 6949 |  | 6846.25 | 6846.25 |  | 102.75
7090 | 7090 |  | 7074 | 7074 |  | 16
20072 | 20072 |  | 17390 | 17390 |  | 2682
141200 | 141200 |  | 134000 | 134000 |  | 7200
9394 | 9394 |  | 9150 | 9150 |  | 244
270478 | 270478 |  | 267195 | 267195 |  | 3283
103550 | 103550 |  | 103279 | 103279 |  | 271
26236 | 26236 |  | 26212 | 26212 |  | 24
40000 | 40000 |  | 39800 | 39800 |  | 200
7000 | 7000 |  | 7000 | 7000 |  | 0
86666 | 86666 |  | 86561 | 86561 |  | 105
112350 | 112350 |  | 111270 | 111270 |  | 1080
16420 | 16420 |  | 16282 | 16282 |  | 138
25894 | 25894 |  | 25680 | 25680 |  | 214
27797 | 27797 |  | 27132 | 27132 |  | 665
5500 | 5500 |  | 5480 | 5480 |  | 20
360000 | 360000 |  | 346050 | 346050 |  | 13950
74955 | 74955 |  | 73970 | 73970 |  | 985
25000 | 25000 |  | 24500 | 24500 |  | 500
16600 | 16600 |  | 16580 | 16580 |  | 20
10000 | 10000 |  | 10000 | 10000 |  | 0
24000 | 24000 |  | 23840 | 23840 |  | 160
28960 | 28960 |  | 28653 | 28653 |  | 307
73600 | 73600 |  | 51570 | 51570 |  | 22030
63579 | 63579 |  | 63170 | 63170 |  | 409
16500 | 16500 |  | 16250 | 16250 |  | 250
30660 | 30660 |  | 28470 | 28470 |  | 2190
68900 | 68900 |  | 68500 | 68500 |  | 400
28500 | 28500 |  | 28000 | 28000 |  | 500
173522 | 173522 |  | 173224 | 173224 |  | 298
7000 | 7000 |  | 6800 | 6800 |  | 200
68924 | 68924 |  | 68860 | 68860 |  | 64
26741 | 26741 |  | 26000 | 26000 |  | 741
15375 | 15375 |  | 15000 | 15000 |  | 375
20904 | 20904 |  | 20688 | 20688 |  | 216
8320 | 8320 |  | 8050 | 8050 |  | 270
15865 | 15865 |  | 15610 | 15610 |  | 255
74520 | 74520 |  | 72900 | 72900 |  | 1620
9264 | 9264 |  | 9120 | 9120 |  | 144
71848 | 71848 |  | 71847.55 | 71847.55 |  | 0.45
125000 | 125000 |  | 123500 | 123500 |  | 1500
21675 | 21675 |  | 21628 | 21628 |  | 47
7885 | 7885 |  | 7590 | 7590 |  | 295
22875 | 22875 |  | 22875 | 22875 |  | 0
10450 | 10450 |  | 10400 | 10400 |  | 50
31467 | 31467 |  | 31367 | 31367 |  | 100
8400 | 8400 |  | 8250 | 8250 |  | 150
9900 | 9900 |  | 9890 | 9890 |  | 10
36900 | 36900 |  | 35250 | 35250 |  | 1650
4778137.59 |  | 4778137.59 | 4727954 |  | 4727954 | 50183.59
2495161.76 |  | 2495161.76 | 2454983.84 |  | 2454983.84 | 40177.92
4874674.43 |  | 4874674.43 | 4844040.38 |  | 4844040.38 | 30634.05
200150 | 200150 |  | 197500 | 197500 |  | 2650
16152 | 16152 |  | 16152 | 16152 |  | 0
99948 | 99948 |  | 99916 | 99916 |  | 32
76420 | 76420 |  | 74970 | 74970 |  | 1450
177200 | 177200 |  | 172350 | 172350 |  | 4850
78961 |  | 78961 | 77834.75 |  | 77834.75 | 1126.25
5600 | 5600 |  | 5600 | 5600 |  | 0
5600 | 5600 |  | 5600 | 5600 |  | 0
9960 | 9960 |  | 9960 | 9960 |  | 0
20110 | 20110 |  | 20110 | 20110 |  | 0
155857 | 155857 |  | 154582.75 | 154582.75 |  | 1274.25
36000 | 36000 |  | 34500 | 34500 |  | 1500
102923 | 102923 |  | 102608 | 102608 |  | 315
181830 | 181830 |  | 179550 | 179550 |  | 2280
168505 | 168505 |  | 165605 | 165605 |  | 2900
69640 | 69640 |  | 0 |  |  | 69640
290605 | 290605 |  | 122659 | 122659 |  | 167946
49500 | 49500 |  | 45000 | 45000 |  | 4500
290605 | 290605 |  | 288752 | 288752 |  | 1853
141220 | 141220 |  | 0 |  |  | 141220
166440 | 166440 |  | 166440 | 166440 |  | 0
344209 | 344209 |  | 0 |  |  | 344209
105000 | 105000 |  | 103000 | 103000 |  | 2000
68764 | 68764 |  | 63220 | 63220 |  | 5544
11500 | 11500 |  | 11446 | 11446 |  | 54
18125 | 18125 |  | 18088 | 18088 |  | 37
20996 | 20996 |  | 20780 | 20780 |  | 216
19783 | 19783 |  | 19380 | 19380 |  | 403
99625 | 99625 |  | 94250 | 94250 |  | 5375
19695 | 19695 |  | 19532.5 | 19532.5 |  | 162.5
39485 | 39485 |  | 39352.5 | 39352.5 |  | 132.5
3300 | 3300 |  | 2937 | 2937 |  | 363
9996 | 9996 |  | 9817.5 | 9817.5 |  | 178.5
15000 | 15000 |  | 14850 | 14850 |  | 150
93956 | 93956 |  | 93480 | 93480 |  | 476
137200 | 137200 |  | 134800 | 134800 |  | 2400
3789923.2 |  | 3789923.2 | 3739823.02 |  | 3739823.02 | 50100.18
4817791.76 |  | 4817791.76 | 4786961.94 |  | 4786961.94 | 30829.82
10000 | 10000 |  | 0 |  |  | 10000
10000 | 10000 |  | 0 |  |  | 10000
27592 | 27592 |  | 0 |  |  | 27592
138000 | 138000 |  | 135900 | 135900 |  | 2100
14100 | 14100 |  | 14100 | 14100 |  | 0
20494 | 20494 |  | 20494 | 20494 |  | 0
7650 | 7650 |  | 7650 | 7650 |  | 0
148830 | 148830 |  | 148830 | 148830 |  | 0
7890 | 7890 |  | 7890 | 7890 |  | 0
97550 | 97550 |  | 97550 | 97550 |  | 0
34430 | 34430 |  | 34430 | 34430 |  | 0
267150 | 267150 |  | 266879 | 266879 |  | 271
198322 | 198322 |  | 195986 | 195986 |  | 2336
336885 | 336885 |  | 332145 | 332145 |  | 4740
8937 | 8937 |  | 8901 | 8901 |  | 36
20468 | 20468 |  | 18398 | 18398 |  | 2070
225112.5 | 225112.5 |  | 218200 | 218200 |  | 6912.5
10425 | 10425 |  | 10300 | 10300 |  | 125
208480 | 208480 |  | 198900 | 198900 |  | 9580
2136959 | 2136959 |  | 2089350 | 2089350 |  | 47609
6600 | 6600 |  | 6590 | 6590 |  | 10
37740 | 37740 |  | 36900 | 36900 |  | 840
1640 | 1640 |  | 1200 | 1200 |  | 440
153780 | 153780 |  | 39600 | 39600 |  | 114180
1011000 | 1011000 |  | 976000 | 976000 |  | 35000
6984 | 6984 |  | 6565 | 6565 |  | 419
128111 | 128111 |  | 127318 | 127318 |  | 793
137097 | 137097 |  | 136588 | 136588 |  | 509
54769 | 54769 |  | 54517 | 54517 |  | 252
67002 | 67002 |  | 66538 | 66538 |  | 464
143517 | 143517 |  | 142607 | 142607 |  | 910
4199 | 4199 |  | 4195 | 4195 |  | 4
21840 | 21840 |  | 21800 | 21800 |  | 40
17240 | 17240 |  | 17221 | 17221 |  | 19
121000 | 121000 |  | 119000 | 119000 |  | 2000
665700 | 665700 |  | 662530 | 662530 |  | 3170
13635 | 13635 |  | 13581 | 13581 |  | 54
39506 | 39506 |  | 39196 | 39196 |  | 310
399294 | 399294 |  | 396659 | 396659 |  | 2635
165918 | 165918 |  | 164997 | 164997 |  | 921
179310.6 | 179310.6 |  | 178843.43 | 178843.43 |  | 467.17
28652 | 28652 |  | 28517 | 28517 |  | 135
111615 | 111615 |  | 111457.5 | 111457.5 |  | 157.5
153422.28 | 153422.28 |  | 153351 | 153351 |  | 71.28
29218 | 29218 |  | 29170 | 29170 |  | 48
232190 | 232190 |  | 232190 | 232190 |  | 0
2160 | 2160 |  | 2148 | 2148 |  | 12
2160 | 2160 |  | 2148 | 2148 |  | 12
2160 | 2160 |  | 2148 | 2148 |  | 12
57930 | 57930 |  | 56980 | 56980 |  | 950
289037 | 289037 |  | 287052 | 287052 |  | 1985
72763 | 72763 |  | 72453 | 72453 |  | 310
163077 | 163077 |  | 162895 | 162895 |  | 182
615308 | 615308 |  | 605102 | 605102 |  | 10206
88113.27 | 88113.27 |  | 85717.93 | 85717.93 |  | 2395.34
56943.57 | 56943.57 |  | 54894.57 | 54894.57 |  | 2049
304795 | 304795 |  | 250290.25 | 250290.25 |  | 54504.75
3116990 | 3116990 |  | 2369900 | 2369900 |  | 747090
45075 | 45075 |  | 45075 | 45075 |  | 0
876086 | 876086 |  | 756236 | 756236 |  | 119850
6649 | 6649 |  | 6633 | 6633 |  | 16
19200 | 19200 |  | 19192 | 19192 |  | 8
308479.4 | 308479.4 |  | 300885 | 300885 |  | 7594.4
40236.5 | 40236.5 |  | 39808 | 39808 |  | 428.5
28000 | 28000 |  | 26000 | 26000 |  | 2000
634552 | 634552 |  | 567800 | 567800 |  | 66752
162978 | 162978 |  | 160016 | 160016 |  | 2962
468787 | 468787 |  | 467784 | 467784 |  | 1003
20550 | 20550 |  | 20175 | 20175 |  | 375
4500 | 4500 |  | 4500 | 4500 |  | 0
30264 | 30264 |  | 29700 | 29700 |  | 564
346055 | 346055 |  | 328925 | 328925 |  | 17130
84700 | 84700 |  | 83909 | 83909 |  | 791
42076 | 42076 |  | 42060 | 42060 |  | 16
57265 | 57265 |  | 55082 | 55082 |  | 2183
17274 | 17274 |  | 17220 | 17220 |  | 54
218316 | 218316 |  | 189743 | 189743 |  | 28573
137250 | 137250 |  | 136250 | 136250 |  | 1000
33800 | 33800 |  | 33800 | 33800 |  | 0
460982 | 460982 |  | 456252 | 456252 |  | 4730
1950 | 1950 |  | 1950 | 1950 |  | 0
45600 | 45600 |  | 45600 | 45600 |  |  | 0 |  | 23-2354
17880 | 17880 |  | 0 |  |  | 17880
13471 | 13471 |  | 13025 | 13025 |  | 446
18894 | 18894 |  | 18331 | 18331 |  | 563
12000 | 12000 |  | 12000 | 12000 |  | 0
151695 | 151695 |  | 151580 | 151580 |  | 115
697287 | 697287 |  | 579600 | 579600 |  | 117687
831425 | 831425 |  | 743046 | 743046 |  | 88379
135000 | 135000 |  | 134240 | 134240 |  | 760
127350 | 127350 |  | 125525 | 125525 |  | 1825
57564 | 57564 |  | 57060 | 57060 |  | 504
4145 | 4145 |  | 3990 | 3990 |  | 155
20000 | 20000 |  | 19900 | 19900 |  | 100
20000 | 20000 |  | 19800 | 19800 |  | 200
18150 | 18150 |  | 17600 | 17600 |  | 550
500 | 500 |  | 450 | 450 |  | 50
51000 | 51000 |  | 48960 | 48960 |  | 2040
75710 | 75710 |  | 75710 | 75710 |  | 0
15094 | 15094 |  | 14846 | 14846 |  | 248
30890.15 | 30890.15 |  | 30727.82 | 30727.82 |  | 162.33
49456 | 49456 |  | 49327 | 49327 |  | 129
49456 | 49456 |  | 49456 | 49456 |  | 0
49456 | 49456 |  | 49327 | 49327 |  | 129
161685 | 161685 |  | 161253 | 161253 |  | 432
24800 | 24800 |  | 24710 | 24710 |  | 90
3600 | 3600 |  | 3555 | 3555 |  | 45
216100 | 216100 |  | 215912 | 215912 |  | 188
216100 | 216100 |  | 215912 | 215912 |  | 188
14000 | 14000 |  | 13720 | 13720 |  | 280
19556 | 19556 |  | 19348 | 19348 |  | 208
28630 | 28630 |  | 28622 | 28622 |  | 8
28630 | 28630 |  | 28622 | 28622 |  | 8
23042 | 23042 |  | 22770 | 22770 |  | 272
20552 | 20552 |  | 19084 | 19084 |  | 1468
2230 | 2230 |  | 2222 | 2222 |  | 8
74846 | 74846 |  | 74595 | 74595 |  | 251
288063 | 288063 |  | 282338 | 282338 |  | 5725
1100 | 1100 |  | 1090 | 1090 |  | 10
27580 | 27580 |  | 25610 | 25610 |  | 1970
14820 | 14820 |  | 14760 | 14760 |  | 60
3129 | 3129 |  | 3087 | 3087 |  | 42
99400 | 99400 |  | 74900 | 74900 |  | 24500
2780 | 2780 |  | 2740 | 2740 |  | 40
6160 | 6160 |  | 6125 | 6125 |  | 35
3000 | 3000 |  | 2990 | 2990 |  | 10
4200 | 4200 |  | 3900 | 3900 |  | 300
13124 | 13124 |  | 13010 | 13010 |  | 114
53016 | 53016 |  | 52892 | 52892 |  | 124
26840 | 26840 |  | 26800 | 26800 |  | 40
12320 | 12320 |  | 12300 | 12300 |  | 20
423118 | 423118 |  | 413340 | 413340 |  | 9778
355715 | 355715 |  | 352740 | 352740 |  | 2975
200721 | 200721 |  | 199692.5 | 199692.5 |  | 1028.5
310860 | 310860 |  | 310040 | 310040 |  | 820
13000 | 13000 |  | 12890 | 12890 |  | 110
138837 | 138837 |  | 137760 | 137760 |  | 1077
34000 | 34000 |  | 33500 | 33500 |  | 500
29750 | 29750 |  | 29725 | 29725 |  | 25
22000 | 22000 |  | 21960 | 21960 |  | 40
15516 | 15516 |  | 15462 | 15462 |  | 54
68435 | 68435 |  | 68100 | 68100 |  | 335
19200 | 19200 |  | 19200 | 19200 |  | 0
139348 | 139348 |  | 137410 | 137410 |  | 1938
21900 | 21900 |  | 21900 | 21900 |  | 0
5600 | 5600 |  | 5600 | 5600 |  | 0
5600 | 5600 |  | 5600 | 5600 |  | 0
16700 | 16700 |  | 16700 | 16700 |  | 0
88340 | 88340 |  | 88340 | 88340 |  | 0
15420 | 15420 |  | 15420 | 15420 |  | 0
2453700 | 2453700 |  | 2453700 | 2453700 |  | 0
25500 | 25500 |  | 25500 | 25500 |  | 0
575153 | 575153 |  | 564992 | 564992 |  | 10161
12800 | 12800 |  | 12800 | 12800 |  | 0
28340 | 28340 |  | 28340 | 28340 |  | 0
36300 | 36300 |  | 36300 | 36300 |  | 0
12400 | 12400 |  | 12400 | 12400 |  | 0
9960 | 9960 |  | 9960 | 9960 |  | 0
47191 | 47191 |  | 47191 | 47191 |  | 0
18310 | 18310 |  | 16926 | 16926 |  | 1384
23821 | 23821 |  | 23604 | 23604 |  | 217
139161 | 139161 |  | 135640 | 135640 |  | 3521
120800 | 120800 |  | 120580 | 120580 |  | 220
45000 | 45000 |  | 44955 | 44955 |  | 45
116000 | 116000 |  | 114400 | 114400 |  | 1600
74900 | 74900 |  | 73562.5 | 73562.5 |  | 1337.5
17532 | 17532 |  | 17518 | 17518 |  | 14
125413 | 125413 |  | 121965 | 121965 |  | 3448
8169 | 8169 |  | 8019 | 8019 |  | 150
52675 | 52675 |  | 52660 | 52660 |  | 15
68179 | 68179 |  | 67604 | 67604 |  | 575
63762 | 63762 |  | 63705 | 63705 |  | 57
156600 | 156600 |  | 156516 | 156516 |  | 84
920 | 920 |  | 916 | 916 |  | 4
143587 | 143587 |  | 143555 | 143555 |  | 32
131870 | 131870 |  | 131559.5 | 131559.5 |  | 310.5
111615 | 111615 |  | 111560 | 111560 |  | 55
138837 | 138837 |  | 138813 | 138813 |  | 24
111615 | 111615 |  | 111560 | 111560 |  | 55
142052 | 142052 |  | 141622 | 141622 |  | 430
93631 | 93631 |  | 93434 | 93434 |  | 197
138837 | 138837 |  | 138399 | 138399 |  | 438
143517 | 143517 |  | 143100 | 143100 |  | 417
15400 | 15400 |  | 15200 | 15200 |  | 200
4070 | 4070 |  | 4000 | 4000 |  | 70
79310 | 79310 |  | 79235 | 79235 |  | 75
269316 | 269316 |  | 269210 | 269210 |  | 106
5666 | 5666 |  | 5660 | 5660 |  | 6
13434 | 13434 |  | 12970 | 12970 |  | 464
19435 | 19435 |  | 19389 | 19389 |  | 46
52568 | 52568 |  | 52476 | 52476 |  | 92
2050 | 2050 |  | 2000 | 2000 |  | 50
15000 | 15000 |  | 14800 | 14800 |  | 200
8350 | 8350 |  | 8350 | 8350 |  | 0
14830 | 14830 |  | 14830 | 14830 |  | 0
20000 | 20000 |  | 20000 | 20000 |  | 0
7400 | 7400 |  | 7400 | 7400 |  | 0
4602 | 4602 |  | 4598 | 4598 |  | 4
26345 | 26345 |  | 26000 | 26000 |  | 345
61198 | 61198 |  | 59689 | 59689 |  | 1509
71538 | 71538 |  | 67931.4 | 67931.4 |  | 3606.6
109511 | 109511 |  | 107901 | 107901 |  | 1610
299732.8 | 299732.8 |  | 224575 | 224575 |  | 75157.8
11740 | 11740 |  | 11100 | 11100 |  | 640
24660 | 24660 |  | 24270 | 24270 |  | 390
25860 | 25860 |  | 25298 | 25298 |  | 562
21400 | 21400 |  | 21400 | 21400 |  | 0
5600 | 5600 |  | 5600 | 5600 |  | 0
76033 | 76033 |  | 74167 |  | 74167 | 1866
251235 | 251235 |  | 223700 |  | 223700 | 27535
415671 | 415671 |  | 370086 |  | 370086 | 45585
236060 | 236060 |  | 87000 | 87000 |  | 149060
660847 | 660847 |  | 659660 | 659660 |  | 1187
329370 | 329370 |  | 325810 | 325810 |  | 3560
213899.3 | 213899.3 |  | 211760.31 | 211760.31 |  | 2138.99
983489.85 | 983489.85 |  | 980935.85 | 980935.85 |  | 2554
671992.7 | 671992.7 |  | 669932.06 | 669932.06 |  | 2060.64
957420.55 | 957420.55 |  | 954850.4 | 954850.4 |  | 2570.15
534665 | 534665 |  | 531783.59 | 531783.59 |  | 2881.41
658913 | 658913 |  | 656467.21 | 656467.21 |  | 2445.79
321750 | 321750 |  | 273000 | 273000 |  | 48750
897213 | 897213 |  | 451220 | 451220 |  | 445993
288000 | 288000 |  | 287760 | 287760 |  | 240
16500 | 16500 |  | 16140 | 16140 |  | 360
16750 | 16750 |  | 15100 | 15100 |  | 1650
2235 | 2235 |  | 2205 | 2205 |  | 30
3200 | 3200 |  | 3200 | 3200 |  | 0
36250 | 36250 |  | 35810 | 35810 |  | 440
160000 | 160000 |  | 155000 | 155000 |  | 5000
8155 | 8155 |  | 7990 | 7990 |  | 165
98409 | 98409 |  | 97140 | 97140 |  | 1269
153376 | 153376 |  | 150720 | 150720 |  | 2656
30866 | 30866 |  | 22660 | 22660 |  | 8206
115000 | 115000 |  | 54000 | 54000 |  | 61000
208025 | 208025 |  | 204984 | 204984 |  | 3041
8940 | 8940 |  | 8881 | 8881 |  | 59
10000 | 10000 |  | 9750 | 9750 |  | 250
97439 | 97439 |  | 97391 | 97391 |  | 48
1245 | 1245 |  | 1245 | 1245 |  | 0
269316 | 269316 |  | 269210 | 269210 |  | 106
28160 | 28160 |  | 27904 | 27904 |  | 256
25088 | 25088 |  | 23296 | 23296 |  | 1792
554630 |  |  | 553610 |  | 553610 | 1020
7700 | 7700 |  | 2240 | 2240 |  | 5460
1925 | 1925 |  | 560 | 560 |  | 1365
1925 | 1925 |  | 560 | 560 |  | 1365
1792 | 1792 |  | 1664 | 1664 |  | 128
122550 | 122550 |  | 114630 | 114630 |  | 7920
35340 | 35340 |  | 34300 | 34300 |  | 1040
153996 | 153996 |  | 150240 | 150240 |  | 3756
15800 | 15800 |  | 15250 | 15250 |  | 550
11300 | 11300 |  | 9930 | 9930 |  | 1370
29642 | 29642 |  | 29600 | 29600 |  | 42
11200 | 11200 |  | 11200 | 11200 |  | 0
85650 | 85560 |  | 85650 | 85650 |  |  | 0
6500 | 6500 |  | 6370 | 6370 |  | 130
1183166.18 | 1183166.18 |  | 1183166.18 | 1183166.18 |  |  | 0
900000 | 900000 |  | 897960 | 897960 |  | 2040
1244072 | 1244072 |  | 1192869 | 1192869 |  | 51203
2623799.14 | 2623799.14 |  | 2607542.28 | 2607542.28 |  | 16256.86
997938 | 997938 |  | 969963 | 969963 |  | 27975
500000 | 500000 |  | 396875 | 396875 |  | 103125
399990 | 399990 |  | 237129 | 237129 |  | 162861
300000 | 300000 |  | 214500 | 214500 |  | 85500
797013 | 797013 |  | 323367.8 | 323367.8 |  | 473645.2
346608 | 346608 |  | 213259 | 213259 |  | 133349
329632 | 329632 |  | 327799 | 327799 |  | 1833
931654 | 931654 |  | 930883.05 | 930883.05 |  | 770.95
150000 | 150000 |  | 89000 | 89000 |  | 61000
150311 | 150311 |  | 132728 | 132728 |  | 17583
399872 | 399872 |  | 353096 | 353096 |  | 46776
150311 | 150311 |  | 132728 | 132728 |  | 17583
796016 | 796016 |  | 550056 | 550056 |  | 245960
8440000 | 8440000 |  | 4987000 | 4987000 |  | 3453000
100000 | 100000 |  | 85800 | 85800 |  | 14200
534000 | 534000 |  | 375000 | 375000 |  | 159000
408924 | 408924 |  | 243087.4 | 243087.4 |  | 165836.6
994168.4 | 994168.4 |  | 731506 | 731506 |  | 262662.4
652110 | 652110 |  | 650018 | 650018 |  | 2092
49533 | 49533 |  | 42873 | 42873 |  | 6660
135900 | 135900 |  | 135900 | 135900 |  | 0
364500 | 364500 |  | 364500 | 364500 |  | 0
301872 | 301872 |  | 301872 | 301872 |  | 0
3913 | 3913 |  | 3913 | 3913 |  | 0
12500 | 12500 |  | 12300 | 12300 |  | 200
3500 | 3500 |  | 3487 | 3487 |  | 13
7550 | 7550 |  | 7495 | 7495 |  | 55
13200 | 13200 |  | 12600 | 12600 |  | 600
36400 | 36400 |  | 35880 | 35880 |  | 520
20160 | 20160 |  | 19872 | 19872 |  | 288
20160 | 20160 |  | 19872 | 19872 |  | 288
153330 | 153330 |  | 147603 | 147603 |  | 5727
262068 | 262068 |  | 257770 | 257770 |  | 4298
11625 | 11625 |  | 11187.5 | 11187.5 |  | 437.5
55350 | 55350 |  | 54360 | 54360 |  | 990
58080 | 58080 |  | 57440 | 57440 |  | 640
411807 | 411807 |  | 409215 | 409215 |  | 2592
18398 | 18398 |  | 17920 | 17920 |  | 478
17745 | 17745 |  | 17420 | 17420 |  | 325
13800 | 13800 |  | 13300 | 13300 |  | 500
33000 | 33000 |  | 32250 | 32250 |  | 750
9264 | 9264 |  | 9072 | 9072 |  | 192
180185 | 180185 |  | 176493 | 176493 |  | 3692
48098 | 48098 |  | 47368 | 47368 |  | 730
61600 | 61600 |  | 57700 | 57700 |  | 3900
30000 | 30000 |  | 27860 | 27860 |  | 2140
1642914 | 1642914 |  | 800394 | 800394 |  | 842520
1800000 | 1800000 |  | 988000 | 988000 |  | 812000
569746 | 569746 |  | 565000 | 565000 |  | 4746
1459602.15 | 1459602.15 |  | 1328418.15 | 1328418.15 |  | 131184
337509 | 337509 |  | 336917 | 336917 |  | 592
1284852 | 1284852 |  | 805272 | 805272 |  | 479580
1284852 | 1284852 |  | 805272 | 805272 |  | 479580
1392784 | 1392784 |  | 1298000 | 1298000 |  | 94784
1268285 | 1268285 |  | 1199029.2 | 1199029.2 |  | 69255.8
1938000 | 1938000 |  | 1228000.08 | 1228000.08 |  | 709999.92
1198400.04 | 1198400.04 |  | 568068 | 568068 |  | 630332.04
747066 | 747066 |  | 747066 | 747066 |  | 0
111615 | 111615 |  | 111390 | 111390 |  | 225
194400 | 194400 |  | 188000 | 188000 |  | 6400
33783 | 33783 |  | 33025 | 33025 |  | 758
558016.02 | 558016.02 |  | 316100.76 | 316100.76 |  | 241915.26
128653 | 128653 |  | 128653 | 128653 |  | 0
19215 | 19215 |  | 19215 | 19215 |  | 0
800000 | 800000 |  | 799112 | 799112 |  | 888
117900 | 117900 |  | 115200 | 115200 |  | 2700
96762 | 96762 |  | 95647.25 | 95647.25 |  | 1114.75
129950 | 129950 |  | 123125 | 123125 |  | 6825
86779 | 86779 |  | 80958 | 80958 |  | 5821
7848 | 7848 |  | 7827 | 7827 |  | 21
19000 | 19000 |  | 18240 | 18240 |  | 760
49250 | 49250 |  | 48665 | 48665 |  | 585
7200 | 7200 |  | 7000 | 7000 |  | 200
9300 | 9300 |  | 9100 | 9100 |  | 200
3300 | 3300 |  | 3280 | 3280 |  | 20
44250 | 44250 |  | 43375 | 43375 |  | 875
6000 | 6000 |  | 5990 | 5990 |  | 10
28437 | 28437 |  | 28150 | 28150 |  | 287
7650 | 7650 |  | 7650 | 7650 |  | 0
72787 | 72787 |  | 71840 | 71840 |  | 947
25000 | 25000 |  | 20000 | 20000 |  | 5000
42390 | 42390 |  | 40060 | 40060 |  | 2330
1792 | 1792 |  | 1664 | 1664 |  | 128
30000 | 30000 |  | 29600 | 29600 |  | 400
90600 | 90600 |  | 89592 | 89592 |  | 1008
18150 | 18150 |  | 17600 | 17600 |  | 550
8145 | 8145 |  | 7862 | 7862 |  | 283
18860 | 18860 |  | 18510 | 18510 |  | 350
24920 | 24920 |  | 24560 | 24560 |  | 360
1792 | 1792 |  | 1664 | 1664 |  | 128
90960 | 90960 |  | 90040 | 90040 |  | 920
22000 | 22000 |  | 22000 | 22000 |  | 0
711620 | 711620 |  | 694025 | 694025 |  | 17595
134773 | 134773 |  | 134742 | 134742 |  | 31
52580 | 52580 |  | 52580 | 52580 |  | 0
23600 | 23600 |  | 23600 | 23600 |  | 0
180845 | 180845 |  | 179100 | 179100 |  | 1745
251235 | 251235 |  | 223700 | 223700 |  | 27535
1795645 | 1795645 |  | 1227045 | 1227045 |  | 568600
420000 | 420000 |  | 419400 | 419400 |  | 600
2658600 | 2658600 |  | 2658600 | 2658600 |  | 0
1165743 | 1165743 |  | 1085470 | 1085470 |  | 80273
1163438 | 1163438 |  | 1107001 | 1107001 |  | 56437
810504 | 810504 |  | 689500 | 689500 |  | 121004
220620 | 220620 |  | 196500 | 196500 |  | 24120
334344 | 334344 |  | 284200 | 284200 |  | 50144
659800 | 659800 |  | 590250 | 590250 |  | 69550
1765998 | 1765998 |  | 1539588 | 1539588 |  | 226410
181830 | 181830 |  | 179550 | 179550 |  | 2280
2284480 | 2284480 |  | 2206600 | 2206600 |  | 77880
51950 | 51950 |  | 51500 | 51500 |  | 450
679368 | 679368 |  | 679368 | 679368 |  | 0
197818 | 197818 |  | 197818 | 197818 |  | 0
2900 | 2900 |  | 2900 | 2900 |  | 0
7736 | 7736 |  | 7736 | 7736 |  | 0
19200 | 19200 |  | 19200 | 19200 |  | 0
7443 | 7443 |  | 7443 | 7443 |  | 0
8650 | 8650 |  | 8650 | 8650 |  | 0
1150 | 1150 |  | 1150 | 1150 |  | 0
8570 | 8570 |  | 8570 | 8570 |  | 0
4070 | 4070 |  | 4070 | 4070 |  | 0
36315 | 36315 |  | 36165 | 36165 |  | 150
10000 | 10000 |  | 10000 | 10000 |  | 0
58960 | 58960 |  | 58310 | 58310 |  | 650
71807 | 71807 |  | 71350 | 71350 |  | 457
244184 | 244184 |  | 243868 | 243868 |  | 316
40394 | 40394 |  | 39990 | 39990 |  | 404
39748 | 39748 |  | 39645 | 39645 |  | 103
280485 | 280485 |  | 278287 | 278287 |  | 2198
243361 | 243361 |  | 241406 | 241406 |  | 1955
22000 | 22000 |  | 22000 | 22000 |  | 0
53620 | 53620 |  | 49046 | 49046 |  | 4574
6150 | 6150 |  | 6000 | 6000 |  | 150
15375 | 15375 |  | 15000 | 15000 |  | 375
21410 | 21410 |  | 21200 | 21200 |  | 210
50684 | 50684 |  | 49415 | 49415 |  | 1269
80740.49 | 80740.49 |  | 80703.49 | 80703.49 |  | 37
436762 | 436762 |  | 427925 | 427925 |  | 8837
119221 | 119221 |  | 118350 | 118350 |  | 871
14000 | 14000 |  | 13972 | 13972 |  | 28
1400 | 1400 |  | 1337.5 | 1337.5 |  | 62.5
30000 | 30000 |  | 30000 | 30000 |  | 0
346500 | 346500 |  | 340000 | 340000 |  | 6500
187834 | 187834 |  | 186130 | 186130 |  | 1704
21945 | 21945 |  | 21666 | 21666 |  | 279
54100 | 54100 |  | 53110 | 53110 |  | 990
49200 | 49200 |  | 48000 | 48000 |  | 1200
3280 | 3280 |  | 3200 | 3200 |  | 80
36300 | 36300 |  | 35920 | 35920 |  | 380
2430 | 2430 |  | 2400 | 2400 |  | 30
29680 | 29680 |  | 28090 | 28090 |  | 1590
5376 | 5376 |  | 5088 | 5088 |  | 288
5950 | 5950 |  | 5950 | 5950 |  | 0
7558 | 7558 |  | 7522 | 7522 |  | 36
78040 | 78040 |  | 78010 | 78010 |  | 30
4070 | 4070 |  | 4070 | 4070 |  | 0
1700 | 1700 |  | 1700 | 1700 |  | 0
82300 | 82300 |  | 82300 | 82300 |  | 0
234203 | 234203 |  | 233864 | 233864 |  | 339
212596 | 212596 |  | 212596 | 212596 |  | 0
112900 | 112900 |  | 112180 | 112180 |  | 720
11991 | 11991 |  | 11970 | 11970 |  | 21
282875 | 282875 |  | 279750 | 279750 |  | 3125
4500 | 4500 |  | 4500 | 4500 |  | 0
10500 | 10500 |  | 10500 | 10500 |  | 0
78500 | 78500 |  | 78500 | 78500 |  | 0
4070 | 4070 |  | 4070 | 4070 |  | 0
52995 | 52995 |  | 52995 | 52995 |  | 0
9600 | 9600 |  | 9600 | 9600 |  | 0
700 | 700 |  | 700 | 700 |  | 0
3350 | 3350 |  | 3350 | 3350 |  | 0
10002 | 10002 |  | 10002 | 10002 |  | 0
850 | 850 |  | 850 | 850 |  | 0
399000 | 399000 |  | 399000 | 399000 |  | 0
399000 | 399000 |  | 399000 | 399000 |  | 0
26977 | 26977 |  | 26937 | 26937 |  | 40
7840 | 7840 |  | 7825 | 7825 |  | 15
36544 | 36544 |  | 36262 | 36262 |  | 282
91401 | 91401 |  | 90791 | 90791 |  | 610
55916 | 55916 |  | 51922 | 51922 |  | 3994
10150 | 10150 |  | 10140 | 10140 |  | 10
20900 | 20900 |  | 20900 | 20900 |  | 0
7590 | 7590 |  | 7584 | 7584 |  | 6
272716 | 272716 |  | 269970 | 269970 |  | 2746
110447.85 | 110447.85 |  | 110053.18 | 110053.18 |  | 394.67
101805 | 101805 |  | 101462.5 | 101462.5 |  | 342.5
30300 | 30300 |  | 29900 | 29900 |  | 400
30300 | 30300 |  | 29900 | 29900 |  | 400
50010 | 50010 |  | 48343 | 48343 |  | 1667
133500 | 133500 |  | 132000 | 132000 |  | 1500
133500 | 133500 |  | 132000 | 132000 |  | 1500
133500 | 133500 |  | 132000 | 132000 |  | 1500
70631 | 70631 |  | 39068 | 39068 |  | 31563
1792 | 1792 |  | 1664 | 1664 |  | 128
1792 | 1792 |  | 1664 | 1664 |  | 128
451976 | 451976 |  | 330400 | 330400 |  | 121576
3125 | 3125 |  | 3125 | 3125 |  | 0
13200 | 13200 |  | 12000 | 12000 |  | 1200
18000 | 18000 |  | 18000 | 18000 |  | 0
21120 | 21120 |  | 21120 | 21120 |  | 0
49461.25 | 49461.25 |  | 49304 | 49304 |  | 157.25
45100 | 45100 |  | 44000 | 44000 |  | 1100
280430 | 280430 |  | 279931.04 | 279931.04 |  | 498.96
8960 | 8960 |  | 8640 | 8640 |  | 320
74520 | 74520 |  | 72900 | 72900 |  | 1620
457860 | 457860 |  | 451530 | 451530 |  | 6330
1897678.28 | 1897678.28 |  | 1872753.19 | 1872753.19 |  | 24925.09
1394873.65 | 1394873.65 |  | 1394583.49 | 1394583.49 |  | 290.16
3901087.09 | 3901087.09 |  | 3860799.32 | 3860799.32 |  | 40287.77
16200 | 16200 |  | 16200 | 16200
9740 | 9740 |  | 9740 | 9740
28500 | 28500 |  | 28200 | 28200 |  | 300
15400 | 15400 |  | 15200 | 15200 |  | 200
9062 | 9062 |  | 8770 | 8770 |  | 292
7809 | 7809 |  | 7744.5 | 7744.5 |  | 64.5
6000 | 6000 |  | 5800 | 5800 |  | 200
12300 | 12300 |  | 12200 | 12200 |  | 100
136000 |  |  | 135500 |  |  | 500
249992237.53 |  |  | 226831471.22 |  | 23160766.31 | 23160766.31
249992237.53 |  |  | 226831471.22 |  | 23160766.31

## Sheet1
18828107.57 | 23-c1138 |  |  | 5640871.57
4299812.8 | dm23-001
49210120 | mdls23-001
666400
659042
9750824
2110970
1630742
15984538.6
579553723.21 |  | 484194999.04 | 95358724.17