## PMR
PROVINCE OF DAVAO DE ORO | [9 empty] | Procurement Monitoring Report as of December 26, 2025
[5 empty] | Actual Procurement Activities | [13 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Column1 | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES
25-C0495 | Office Equipment | PICTO | No | Competitive Bidding | 2025-05-21 | 2025-05-26 | 2025-06-03 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-08 | 2025-08-13 | 2025-08-18 | 2025-08-25 |  | 2025-08-29 | 2025-10-14 | 2025-10-14 | GoP | 2141890 |  | 2141890 | 1794050 |  | 1794050 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-06-02 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | Completed
25-C0511 | Communication Equipment And Computer Supplies/Spare Parts | PICTO | No | Competitive Bidding | 2025-05-21 | 2025-05-26 | 2025-06-03 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-08 | 2025-08-13 | 2025-08-20 | 2025-08-25 |  | 2025-09-02 | 2025-10-13 | 2025-10-13 | GoP | 2564543 |  | 2564543 | 1755800 |  | 1755800 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-06-02 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | Completed
25-C0502 | Packed Meals And Snacks | PSWDO | No | Competitive Bidding | 2025-05-27 | 2025-06-02 | 2025-06-10 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-08 | 2025-08-13 | 2025-08-15 | 2025-08-25 |  | 2025-09-02 | 2025-12-16 | 2025-12-16 | GoP | 1479880 |  | 1479880 | 1153288 |  | 1153288 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-06-02 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | Completed
25-2761 | Refrigerated Centrifuge | PHO | No | Competitive Bidding | 2025-05-27 | 2025-06-02 | 2025-06-10 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-08 | 2025-08-13 | 2025-08-15 | 2025-08-25 |  | 2025-08-29 | 2025-12-12 | 2025-12-12 | GoP | 3850000 |  | 3850000 | 1980000 |  | 1980000 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-06-02 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | Completed
25-C0442 REBID | Construction Materials | PEO | No | Competitive Bidding | N/A | 2025-06-09 | 2025-06-17 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-08 | 2025-08-13 | 2025-08-15 | 2025-08-25 |  | 2025-09-02 | 2025-09-18 | 2025-09-18 | GoP | 1568799.2 |  | 1568799.2 | 1144395 |  | 1144395 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-06-16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | Completed
25-C0570 | Agricultural Supplies (Seeds/Seedlings) | PAGRO | No | Competitive Bidding | 2025-06-09 | 2025-06-16 | 2025-06-24 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-13 | 2025-08-20 | 2025-08-25 |  | 2025-09-08 | 2025-10-02 | 2025-10-02 | GoP | 2124665 |  | 2124665 | 1671450 |  | 1671450 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-06-23 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | Completed
25-C0471 REBID | Portland Cement | PEO | No | Competitive Bidding | N/A | 2025-06-09 | 2025-06-17 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-08 | 2025-08-13 | 2025-08-20 | 2025-08-25 |  | 2025-09-02 | 2025-12-16 | 2025-12-16 | GoP | 1277029 |  | 1277029 | 999414 |  | 999414 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-06-16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | Completed
25-C0571 REBID | Agricultural Supplies | PAGRO | No | Competitive Bidding | 2025-06-10 | 2025-08-05 | 2025-08-13 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-29 | 2025-09-03 | 2025-09-10 | 2025-09-11 |  | 2025-09-15 | 2025-10-01 | 2025-10-01 | GoP | 1349455 |  | 1349455 | 1283828 |  | 1283828 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-08 | 2025-08-22 | 2025-08-22 | 2025-08-22 | N/A | N/A | Completed
25-C0664 | Packed Meals And Snacks | PHO | No | Competitive Bidding | N/A | 2025-08-05 | 2025-08-13 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-29 | 2025-09-03 | 2025-09-09 | 2025-09-11 |  | 2025-09-15 | 2025-11-18 | 2025-11-18 | GoP | 1206290 |  | 1206290 | 890870 |  | 890870 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-08 | 2025-08-22 | 2025-08-22 | 2025-08-22 | N/A | N/A | Completed
25-C0530 | Rice (Well Milled) 50Kg/Sack | PGO-PPOC | No | Competitive Bidding | 2025-06-24 | 2025-08-05 | 2025-08-13 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-29 | 2025-09-03 | 2025-09-08 | 2025-09-10 |  | 2025-09-16 | 2025-09-26 | 2025-09-26 | GoP | 2354000 |  | 2354000 | 2306920 |  | 2306920 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-08 | 2025-08-22 | 2025-08-22 | 2025-08-22 | N/A | N/A | Completed
25-3869 | Commercial Feeds | PVO | No | Competitive Bidding | N/A | 2025-08-05 | 2025-08-13 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-29 | 2025-09-03 | 2025-09-09 | 2025-09-11 |  | 2025-09-23 | 2025-11-05 | 2025-11-05 | GoP | 1566193 |  | 1566193 | 1338670 |  | 1338670 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-08 | 2025-08-22 | 2025-08-22 | 2025-08-22 | N/A | N/A | Completed
25-3854 LOT 1 | Livestocks | PVO | No | Competitive Bidding | 2025-06-17 | 2025-08-05 | 2025-08-13 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-29 | 2025-09-03 | 2025-09-09 | 2025-09-11 |  | 2025-09-23 | 2025-11-05 | 2025-11-05 | GoP | 1265220 |  | 1265220 | 1260220 |  | 1260220 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-08 | 2025-08-22 | 2025-08-22 | 2025-08-22 | N/A | N/A | Completed
25-3854 LOT 2 | Livestocks | PVO | No | Competitive Bidding | 2025-06-17 | 2025-08-05 | 2025-08-13 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-10-14 | 2025-10-16 | 2025-10-20 | 2025-10-21 |  | 2025-11-04 | 2025-11-05 | 2025-11-05 | GoP | 1046100 |  | 1046100 | 962250 |  | 962250 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-08 | 2025-08-22 | 2025-08-22 | 2025-08-22 | N/A | N/A | Completed
25-3854 LOT 3 | Livestocks | PVO | No | Competitive Bidding | 2025-06-17 | 2025-08-05 | 2025-08-13 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-10-14 | 2025-10-16 | 2025-10-20 | 2025-10-21 |  | 2025-11-04 | 2025-11-05 | 2025-11-05 | GoP | 1188000 |  | 1188000 | 1028700 |  | 1028700 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-08 | 2025-08-22 | 2025-08-22 | 2025-08-22 | N/A | N/A | Completed
25-3854 LOT 4 | Livestocks | PVO | No | Competitive Bidding | 2025-06-17 | 2025-08-05 | 2025-08-13 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-10-14 | 2025-10-16 | 2025-10-20 | 2025-10-21 |  | 2025-11-04 | 2025-11-05 | 2025-11-05 | GoP | 3300000 |  | 3300000 | 2430000 |  | 2430000 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-08 | 2025-08-22 | 2025-08-22 | 2025-08-22 | N/A | N/A | Completed
25-C0614 | Rice (Well Milled) 50Kg/Sack | PEEMO | No | Competitive Bidding | 2025-06-24 | 2025-08-05 | N/A | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-22 | 2025-08-27 | 2025-09-04 | 2025-09-05 |  | 2025-09-15 | 2025-09-23 | 2025-09-23 | GoP | 803000 |  | 803000 | 657000 |  | 657000 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N.A | 2025-08-08 | 2025-08-08 | 2025-08-08 | N/A | N/A | Completed
25-C0186 | Tires | PEEMO | No | Competitive Bidding | 2025-06-24 | 2025-08-05 | N/A | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-15 | 2025-08-20 | 2025-09-05 | 2025-09-11 |  | 2025-09-12 | 2025-09-15 | 2025-09-15 | GoP | 851600 |  | 851600 | 531000 |  | 531000 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N.A | 2025-08-08 | 2025-08-08 | 2025-08-08 | N/A | N/A | Completed
25-C0579 | Veterinary Drugs And Biologics | PVO | No | Competitive Bidding | N/A | 2025-08-05 | N/A | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-22 | 2025-09-03 | 2025-09-09 | 2025-09-11 |  | 2025-09-29 | 2025-10-27 | 2025-10-27 | GoP | 859845 |  | 859845 | 709455 |  | 709455 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N.A | 2025-08-08 | 2025-08-08 | 2025-08-08 | N/A | N/A | Completed
25-C0575 | Drugs And Medicines | PHO | No | Competitive Bidding | N/A | 2025-08-05 | N/A | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-22 | 2025-09-24 | 2025-09-26 | 2025-10-03 |  | 2025-10-07 | 2025-10-24 | 2025-10-24 | GoP | 925046 |  | 925046 | 689075 |  | 689075 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N.A | 2025-08-08 | 2025-08-08 | 2025-08-08 | N/A | N/A | Completed
25-C0592 | Office Supplies | PEEMO | No | Competitive Bidding | 2025-08-01 | 2025-08-12 | 2025-08-20 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-05 | 2025-09-10 | 2025-09-16 | 2025-09-19 |  | 2025-09-29 | 2025-10-07 | 2025-10-07 | GoP | 1087218 |  | 1087218 | 999705 |  | 999705 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-15 | 2025-08-29 | 2025-08-29 | 2025-08-29 | N/A | N/A | Completed
25-3193 | Hybrid Yellow Corn Seeds | PAGRO | No | Competitive Bidding | 2025-08-01 | 2025-08-12 | 2025-08-20 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-12 | 2025-09-24 | 2025-09-29 | 2025-10-03 |  | 2025-10-08 | 2025-10-14 | 2025-10-14 | GoP | 1669800 |  | 1669800 | 1668700 |  | 1668700 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-15 | 2025-08-29 | 2025-08-29 | 2025-08-29 | N/A | N/A | Completed
25-C0602 | Medical and Laboratory Supplies | PEEMO | No | Competitive Bidding | 2025-08-01 | 2025-08-12 | 2025-08-20 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-05 | 2025-09-10 | 2025-09-16 | 2025-09-19 |  | 2025-09-29 | 2025-11-03 | 2025-11-03 | GoP | 5212338 |  | 5212338 | 5211317 |  | 5211317 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-15 | 2025-08-29 | 2025-08-29 | 2025-08-29 | N/A | N/A | Completed
25-C0696 | Spare parts (Motorcycle) | PGSO | No | Competitive Bidding | 2025-08-20 | 2025-08-26 | 2025-09-03 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-15 |  | 2025-10-27 | 2025-11-05 | 2025-11-05 | GoP | 1392460 |  | 1392460 | 1389800 |  | 1389800 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-29 | 2025-09-16 | 2025-09-16 | 2025-09-16 | N/A | N/A | Completed
25-C0660 | Spare parts (Light Vehicles and Heavy Equipment), and Construction Materials | PEO | No | Competitive Bidding | 2025-08-06 | 2025-08-26 | 2025-09-03 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-15 |  | 2025-10-22 | 2025-11-11 | 2025-11-11 | GoP | 3255901 |  | 3255901 | 3076005 |  | 3076005 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-29 | 2025-09-16 | 2025-09-16 | 2025-09-16 | N/A | N/A | Completed
25-C0482 | Laboratory Supplies/Reagent | PEEMO | No | Competitive Bidding | 2025-08-06 | 2025-08-12 | N/A | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-09-01 | 2025-09-03 | 2025-09-09 | 2025-09-11 |  | 2025-09-26 | 2025-10-08 | 2025-10-08 | GoP | 687150 |  | 687150 | 457500 |  | 457500 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N.A | 2025-08-15 | 2025-08-15 | 2025-08-15 | N/A | N/A | Completed
25-C0586 | Janitorial Supplies | PEEMO | No | Competitive Bidding | 2025-08-06 | 2025-09-01 | 2025-09-10 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-15 |  | 2025-10-21 | 2025-11-28 | 2025-11-28 | GoP | 1111494 |  | 1111494 | 1105494 |  | 1105494 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-09-05 | 2025-09-16 | 2025-09-16 | 2025-09-16 | N/A | N/A | Completed
25-2987 | Drugs And Medicines | PHO | No | Competitive Bidding | N/A | 2025-09-09 | 2025-09-24 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-14 | 2025-10-16 | 2025-10-17 | 2025-10-28 |  | 2025-11-04 | 2025-12-05 | 2025-12-05 | GoP | 3733280.8 |  | 3733280.8 | 3732372.8 |  | 3732372.8 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-09-16 | 2025-10-03 | 2025-10-03 | 2025-10-03 | N/A | N/A | Completed
25-C0699 | Construction Materials | PGSO | No | Competitive Bidding | 2025-09-03 | 2025-09-09 | 2025-09-24 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-14 | 2025-10-22 | 2025-10-27 | 2025-10-28 |  | 2025-11-12 | 2025-12-12 | 2025-12-12 | GoP | 2770069.64 |  | 2770069.64 | 2769628.56 |  | 2769628.56 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-09-16 | 2025-10-03 | 2025-10-03 | 2025-10-03 | N/A | N/A | Completed
25-5046 | Supply and Installation of Wall Mounted Non-Inverter Type Air Conditioner and 5 Tonner Ceiling Cassette Type Conditioner | PGSO | No | Competitive Bidding | 2025-09-03 | 2025-09-09 | 2025-09-24 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-14 | 2025-10-16 | 2025-10-21 | 2025-10-22 |  | 2025-10-29 | 2025-11-28 | 2025-11-28 | GoP | 1043400 |  | 1043400 | 1041200 |  | 1041200 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-09-16 | 2025-10-03 | 2025-10-03 | 2025-10-03 | N/A | N/A | Completed
25-C0566 | Agricultural Supplies | PAGRO | No | Competitive Bidding | 2025-08-20 | 2025-09-16 | 2025-09-24 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-14 | 2025-10-16 | 2025-10-20 | 2025-10-22 |  | 2025-10-29 | 2025-12-12 | 2025-12-12 | GoP | 1699805.6 |  | 1699805.6 | 1695005.6 |  | 1695005.6 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-09-16 | 2025-10-03 | 2025-10-03 | 2025-10-03 | N/A | N/A | Completed
25-5416 | Tires | PEO | No | Competitive Bidding | 2025-10-01 | 2025-10-08 | 2025-10-16 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-13 | 2025-11-14 | 2025-11-24 | 2025-11-24 |  | 2025-11-28 | 2025-12-01 | 2025-12-01 | GoP | 3616014 |  | 3616014 | 3607600 |  | 3607600 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-13 | 2025-10-27 | 2025-10-27 | 2025-10-27 | N/A | N/A | Completed
25-C0754 | Spare Parts (Light Vehicle) | PGSO | No | Competitive Bidding | 2025-10-16 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-24 | 2025-12-05 | 2025-12-09 | 2025-12-10 |  | 2025-12-11 | 2025-12-15 | 2025-12-15 | GoP | 4016569 |  | 4016569 | 3959790 |  | 3959790 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | Completed
25-C0889 | Fertilizers | PAGRO | No | Competitive Bidding | 2025-10-16 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-20 | 2025-11-26 | 2025-12-02 | 2025-12-02 |  | 2025-12-12 | 2025-12-15 | 2025-12-15 | GoP | 7578601.6 |  | 7578601.6 | 7578601.6 |  | 7578601.6 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | Completed
25-3753 | Concreting of Road at Tuburan Pabahay, Mawab, Davao de Oro [(Concreting of 112.31 ln.m. road (2mts width) and 85.86 ln.m. road (3 mts width)] | PEO | No | Competitive Bidding | N/A | 2025-05-26 | 2025-06-03 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-08 | 2025-08-20 | 2025-08-27 | 2025-09-05 |  | 2025-09-11 | N/A | N/A | GoP | 2878681.5 |  | 2878681.5 | 2868492.55 |  | 2868492.55 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-06-02 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | Completed
25-3756 | Construction of Gym at Purok Maligaya, Barangay Tagugpo, Pantukan, Davao de Oro [Construction of Five (5) bays Gym] | PEO | No | Competitive Bidding | N/A | 2025-05-26 | 2025-06-03 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-08 | 2025-08-20 | 2025-08-27 | 2025-09-05 |  | 2025-09-11 | N/A | N/A | GoP | 3624100.36 |  | 3624100.36 | 3613668.12 |  | 3613668.12 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-06-02 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | Completed
25-3137 | Rehabilitation of Hanging Bridge at Brgy. Fuentes, Pantukan, Davao de Oro [Rehabilitation of 48 ln.m. Foot Bridge (Floor Deck, Railings and Steel Cable)] | PEO | No | Competitive Bidding | N/A | 2025-06-16 | 2025-06-24 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-08 | 2025-08-20 | 2025-08-27 | 2025-09-05 |  | 2025-09-11 | N/A | N/A | GoP | 2391247.01 |  | 2391247.01 | 2381040.3 |  | 2381040.3 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | Completed
25-3303 | Rehabilitation/Improvement of Social Hall at Alimadmad Integrated School, Purok 4, Brgy. Conception, Montevista, Davao de Oro [Improvement of Social Hall (Extension of 2.5m at left left and right side)] | PEO | No | Competitive Bidding | 2025-04-30 | 2025-06-16 | 2025-06-24 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-08 | 2025-08-20 | 2025-08-27 | 2025-09-05 |  | 2025-09-11 | N/A | N/A | GoP | 1540810.09 |  | 1540810.09 | 1530697.95 |  | 1530697.95 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | Completed
25-3304 | Rehabilitation/Improvement of Social Hall at Alimadmad Integrated School, Purok 4, Brgy. Conception, Montevista, Davao de Oro [Improvement of Social Hall (Extension of 2.5m at left left and right side)] | PEO | No | Competitive Bidding | 2025-04-30 | 2025-06-16 | 2025-06-24 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-08 | 2025-08-20 | 2025-08-27 | 2025-09-05 |  | 2025-09-11 | N/A | N/A | GoP | 1540811.09 |  | 1540811.09 | 1530698.95 |  | 1530698.95 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | Completed
25-3147 | Constructiion of Potable Water System at Kidawa, Laak, Davao de Oro | PEO | No | Competitive Bidding | 2025-08-13 | 2025-08-26 | 2025-09-03 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-10-03 | 2025-10-08 | 2025-10-15 | 2025-10-21 |  | 2025-10-25 | N/A | N/A | GoP | 1825241.66 |  | 1825241.66 | 1820210.46 |  | 1820210.46 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-29 | 2025-09-16 | 2025-09-16 | 2025-09-16 | N/A | N/A | Completed
25-4306 | Construction of Bleachers at Brgy. Datu Laak, Davao de Oro | PEO | No | Competitive Bidding | 2025-08-13 | 2025-08-19 | 2025-08-27 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-19 | 2025-10-01 | 2025-10-10 | 2025-10-20 |  | 2025-10-23 | N/A | N/A | GoP | 2374728.36 |  | 2374728.36 | 2369638.28 |  | 2369638.28 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-22 | 2025-09-16 | 2025-09-16 | 2025-09-16 | N/A | N/A | Completed
25-4285 | Construction of Multipurpose Bldg. at Cabuyoan, Mabini, Davao de Oro | PEO | No | Competitive Bidding | 2025-08-13 | 2025-08-19 | 2025-08-27 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-19 | 2025-10-08 | 2025-10-15 | 2025-10-18 |  | 2025-10-23 | N/A | N/A | GoP | 5224717 |  | 5224717 | 5199739.12 |  | 5199739.12 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-22 | 2025-09-16 | 2025-09-16 | 2025-09-16 | N/A | N/A | Completed
25-4368 | Construction of Barangay Hall at Mauswagon, Maragusan, Davao de Oro | PEO | No | Competitive Bidding | 2025-08-13 | 2025-08-19 | 2025-08-27 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-19 | 2025-10-01 | 2025-10-10 | 2025-10-20 |  | 2025-10-23 | N/A | N/A | GoP | 8920087.29 |  | 8920087.29 | 8909537.6 |  | 8909537.6 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-22 | 2025-09-16 | 2025-09-16 | 2025-09-16 | N/A | N/A | Completed
25-4903 | Construction of Brgy. Hall at Brgy. Sisimon, Laak, Davao de Oro (Construction of 142 sq.m. (1 Storey) Brgy. Hall) | PEO | No | Competitive Bidding | 2025-09-10 | 2025-09-30 | 2025-10-08 | 2025-10-22 | 2025-10-22 | 2025-10-22 | 2025-10-30 | 2025-11-12 | 2025-11-17 | 2025-11-23 |  | 2025-11-28 | N/A | N/A | GoP | 5497107.24 |  | 5497107.24 | 5481403.61 |  | 5481403.61 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-03 | 2025-10-17 | 2025-10-17 | 2025-10-17 | N/A | N/A | Completed
25-5210 | Construction of Multi-purpose Bldg. at New Visayas National High School, Brgy. New Visayas, Maco, Davao de Oro | PEO | No | Competitive Bidding | 2025-09-10 | 2025-09-30 | 2025-10-08 | 2025-10-22 | 2025-10-22 | 2025-10-22 | 2025-10-30 | 2025-11-12 | 2025-11-19 | 2025-11-25 |  | 2025-12-01 | N/A | N/A | GoP | 5586503.57 |  | 5586503.57 | 5576477.64 |  | 5576477.64 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-03 | 2025-10-17 | 2025-10-17 | 2025-10-17 | N/A | N/A | Completed
6321 | Medical Supplies | DDOPH-Montevista | No | Shopping A-Cash Advance | N/A | 2025-11-18 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | N/A | N/A |  | N/A | N/A | N/A | GoP | 200000 | 200000 |  | 200000 | 200000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6317 | Food Supplies- Wet Market | DDOPH-Montevista | No | Shopping A-Cash Advance | N/A | 2025-11-18 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | N/A | N/A |  | N/A | N/A | N/A | GoP | 200000 | 200000 |  | 200000 | 200000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6319 | Food Supplies- Wet Market | PAO-PRC | No | Shopping A-Cash Advance | N/A | 2025-11-18 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | N/A | N/A |  | N/A | N/A | N/A | GoP | 191100 | 191100 |  | 191100 | 191100 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6344 | Supply and Delivery of Assorted Lanterns and Christmas Decoration | PGSO | No | Small Value Procurement | N/A | 2025-11-20 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-03 | 2025-12-09 |  | 2025-12-10 | 2025-12-10 | 2025-12-10 | GoP | 1500000 | 1500000 |  | 1500000 | 1500000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6315 | Packed Meals and Snacks | PGO | No | Small Value Procurement | N/A | 2025-11-20 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-05 | 2025-12-09 |  | 2025-12-10 | 2025-12-11 | 2025-12-11 | GoP | 450000 | 450000 |  | 450000 | 450000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-C0960 | Construction Materials | PEO | No | Small Value Procurement | N/A | 2025-11-20 | N/A | N/A | 2025-11-26 | N/A | N/A | 2025-11-26 | 2025-12-01 | 2025-12-02 |  | 2025-12-09 | 2025-12-16 | 2025-12-16 | GoP | 96021 | 96021 |  | 95961 | 95961 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-6192 | Spare parts (Light Vehicle) | PGO | No | Small Value Procurement | N/A | 2025-11-20 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 |  | 2025-12-10 | 2025-12-19 | 2025-12-19 | GoP | 48030 | 48030 |  | 48030 | 48030 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-5117 | Janitorial Supplies/ Housekeeping | PHO | No | Small Value Procurement | N/A | 2025-11-20 | N/A | N/A |  | N/A | N/A | 0 | N/A | 2025-12-02 |  | 2025-12-11 | 2025-12-17 | 2025-12-17 | GoP | 15261 | 15261 |  | 15207 | 15207 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-C0919 | Construction & Electrical Supplies | PEEMO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-05 | 2025-12-09 |  | 2025-12-11 | 2025-12-20 | 2025-12-20 | GoP | 1042606 | 1042606 |  | 1042606 | 1042606 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6240 | Fuel, oil and Lubricants | PEO | No | Small Value Procurement | N/A | 2025-11-21 | N/A | N/A | 2025-12-10 | N/A | N/A | 2025-12-10 | 2025-12-11 | 2025-12-11 |  | 2025-12-14 | 2025-12-14 | 2025-12-14 | GoP | 873000 | 873000 |  | 865260 | 865260 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6303 | Fuel, oil and Lubricants | PEO | No | Small Value Procurement | N/A | 2025-11-21 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-10 | 2025-12-11 |  | 2025-12-15 | 2025-12-21 | 2025-12-21 | GoP | 705700 | 705700 |  | 698400 | 698400 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
4795 | Meals and Snacks with Venue & Accommodation | PHO | No | Small Value Procurement | N/A | 2025-11-21 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-05 | 2025-12-09 |  | 2025-12-11 | 2025-12-16 | 2025-12-16 | GoP | 175500 | 175500 |  | 172250 | 172250 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6358 | Office Equipment | PVO | No | Small Value Procurement | N/A | 2025-11-21 | N/A | N/A | 2025-12-10 | N/A | N/A | 2025-12-10 | 2025-12-11 | 2025-12-11 |  | 2025-12-12 | 2025-12-16 | 2025-12-16 | GoP | 99242 | 99242 |  | 99242 | 99242 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6222 | Spare parts (Light Vehicle) | PGSO | No | Small Value Procurement | N/A | 2025-11-21 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-03 | 2025-12-09 |  | 2025-12-14 | 2025-12-19 | 2025-12-19 | GoP | 78000 | 78000 |  | 78000 | 78000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-6218 | Spare parts (Light Vehicle) | PGSO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-03 | N/A | N/A | 2025-12-03 | N/A | 2025-12-10 |  | 2025-12-11 | 2025-12-11 | 2025-12-11 | GoP | 44150 | 44150 |  | 44150 | 44150 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-6101 | Spare parts (Light Vehicle) | SPO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | N/A | 2025-12-10 |  | 2025-12-11 | 2025-12-19 | 2025-12-19 | GoP | 25300 | 25300 |  | 25300 | 25300 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-6082 | Spare parts (Light Vehicle) | SPO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A |  | N/A | N/A | 2025-12-01 | N/A | 2025-12-10 |  | 2025-12-15 | 2025-12-20 | 2025-12-20 | GoP | 21500 | 21500 |  | 21500 | 21500 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-C0938 | Office Supplies | PAO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | N/A | 2025-12-10 |  | 2025-12-12 | 2025-12-15 | 2025-12-15 | GoP | 6152 | 6152 |  | 6112 | 6112 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-6292 | Spare parts (Light Vehicle) | PGSO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-03 | N/A | N/A | 2025-12-03 | N/A | 2025-12-10 |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | GoP | 3150 | 3150 |  | 3150 | 3150 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5457 | Spare parts (Light Vehicle) | PGSO | No | Small Value Procurement | N/A | 2025-11-21 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-01 | N/A | 2025-12-09 |  | 2025-12-14 | 2025-12-19 | 2025-12-19 | GoP | 2500 | 2500 |  | 2500 | 2500 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-5981 | Spare parts (Light Vehicle) | PGSO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-03 | N/A | N/A | 2025-12-03 | N/A | 2025-12-10 |  | 2025-12-15 | 2025-12-20 | 2025-12-20 | GoP | 1950 | 1950 |  | 1950 | 1950 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-C0964 | Medical Supplies | DDOPH-Montevista | No | Small Value Procurement | 2025-11-21 | 2025-11-24 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-05 | 2025-12-09 |  | 2025-12-12 | 2025-12-16 | 2025-12-16 | GoP | 771776 | 771776 |  | 771472 | 771472 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
5798 | Smart TV, 50' inches | PHO | No | Small Value Procurement | N/A | 2025-11-24 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 |  | 2025-12-10 | 2025-12-11 | 2025-12-11 | GoP | 250000 | 250000 |  | 250000 | 250000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6299 | Other Machineries & Equipment | PAO-Investment | No | Small Value Procurement | N/A | 2025-11-24 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 |  | 2025-12-10 | 2025-12-15 | 2025-12-15 | GoP | 185249 | 185249 |  | 185248 | 185248 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-C0958 | Spare parts (Light Vehicle) | PDRRMO | No | Small Value Procurement | 2025-11-21 | 2025-11-24 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-03 | 2025-12-09 |  | 2025-12-15 | 2025-12-20 | 2025-12-20 | GoP | 72622.5 | 72622.5 |  | 72622.5 | 72622.5 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-5087 | Boots, rubber-knee high | PSWDO | No | Small Value Procurement | 2025-11-21 | 2025-11-24 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | N/A | 2025-12-10 |  | 2025-12-12 | 2025-12-15 | 2025-12-15 | GoP | 25740 | 25740 |  | 25740 | 25740 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-6370 | Spare parts (light Vehicle) | SPO | No | Small Value Procurement | 2025-11-21 | 2025-11-24 | N/A | N/A |  | N/A | N/A | 0 | N/A | 2025-12-09 |  | 2025-12-11 | 2025-12-20 | 2025-12-20 | GoP | 17525 | 17525 |  | 17525 | 17525 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-5388 | Polo shirt (as per design) | PSWDO | No | Small Value Procurement | 2025-11-21 | 2025-11-24 | N/A | N/A | 2025-12-03 | N/A | N/A | 2025-12-03 | N/A | 2025-12-10 |  | 2025-12-12 | 2025-12-20 | 2025-12-20 | GoP | 16500 | 16500 |  | 16500 | 16500 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-0853 | Construction of Slope Protection abutment Bridge | PEO | No | NP-Two Failed Biddings | N/A | 2025-11-24 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-10 | 2025-12-12 |  | 2025-12-16 | N/A | N/A | GoP | 4786424.13 | 4786424.13 |  | 4785400 | 4785400 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6359 | Drugs and Medicines | DDOPH-Montevista | No | Shopping A-Cash Advance | N/A | 2025-11-24 | N/A | N/A | 2025-12-03 | N/A | N/A | 2025-12-03 | N/A | N/A |  | N/A | N/A | N/A | GoP | 200000 | 200000 |  | 200000 | 200000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6316 | Medical Supplies | DDOPH-Pantukan | No | Shopping A-Cash Advance | N/A | 2025-11-24 | N/A | N/A | 2025-12-03 | N/A | N/A | 2025-12-03 | N/A | N/A |  | N/A | N/A | N/A | GoP | 200000 | 200000 |  | 200000 | 200000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6350 | Medical Supplies | DDOPH-Maragusan | No | Shopping A-Cash Advance | N/A | 2025-11-24 | N/A | N/A | 2025-12-03 | N/A | N/A | 2025-12-03 | N/A | N/A |  | N/A | N/A | N/A | GoP | 150000 | 150000 |  | 150000 | 150000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6337 | Spare parts (Light Vehicle) | PGSO | No | Small Value Procurement | N/A | 2025-11-28 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-11 | 2025-12-11 |  | 2025-12-14 | 2025-12-19 | 2025-12-19 | GoP | 63550 | 63550 |  | 63550 | 63550 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-5874 | Spare parts (Light Vehicle) | VGO | No | Small Value Procurement | 2025-11-26 | 2025-11-28 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | N/A | 2025-12-10 |  | 2025-12-11 | 2025-12-20 | 2025-12-20 | GoP | 38000 | 38000 |  | 38000 | 38000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-6364 | Spare parts (Motor cycle) | PGSO | No | Small Value Procurement | 2025-11-26 | 2025-11-28 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | N/A | 2025-12-10 |  | 2025-12-12 | 2025-12-12 | 2025-12-12 | GoP | 37000 | 37000 |  | 37000 | 37000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-6391 | Spare parts (Light Vehicle) | PGSO | No | Small Value Procurement | 2025-11-26 | 2025-11-28 | N/A | N/A | 2025-12-03 | N/A | N/A | 2025-12-03 | N/A | 2025-12-10 |  | 2025-12-11 | 2025-12-20 | 2025-12-01 | GoP | 15500 | 15500 |  | 15500 | 15500 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-6328 | Spare parts (Light Vehicle) | PGSO | No | Small Value Procurement | 2025-11-26 | 2025-11-28 | N/A | N/A | 2025-12-03 | N/A | N/A | 2025-12-03 | N/A | 2025-12-10 |  | 2025-12-11 | 2025-12-20 | 2025-12-20 | GoP | 1750 | 1750 |  | 1750 | 1750 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-C0937 | Other Supplies/Materials | PAGRO | No | Small Value Procurement | 2025-12-01 | 2025-12-02 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | N/A | 2025-12-10 |  | 2025-12-13 | 2025-12-20 | 2025-12-20 | GoP | 25055 | 25055 |  | 25055 | 25055 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6434 | Food Supplies | PDRRMO | No | NP-Emergency Cases | N/A | 2025-12-17 | N/A | N/A | 2025-12-17 | N/A | N/A | 2025-12-17 | 2025-12-17 | 2025-12-17 |  | 2025-12-18 | 2025-12-22 | 2025-12-22 | GoP | 4515000 | 4515000 |  | 4515000 | 4515000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-4589 | Drugs and Medicines | DDOPH-Montevista | No | Shopping A-Cash Advance | N/A | 2025-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 200000 | 200000 |  | 200000 | 200000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-4511 | Drugs and Medicines | DDOPH-Pantukan | No | Shopping A-Cash Advance | N/A | 2025-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 200000 | 200000 |  | 200000 | 200000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-4403 | Food Supplies- Wet Market | DDOPH-Laak | No | Shopping A-Cash Advance | N/A | 2025-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 150000 | 150000 |  | 150000 | 150000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-4407 | Drugs and Medicines | DDOPH-Maragusan | No | Shopping A-Cash Advance | N/A | 2025-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 150000 | 150000 |  | 150000 | 150000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-4513 | Medical Supplies | DDOPH-Maragusan | No | Shopping A-Cash Advance | N/A | 2025-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 150000 | 150000 |  | 150000 | 150000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-4580 | Food Supplies- Wet Market | PAO-PRC | No | Shopping A-Cash Advance | N/A | 2025-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 125440 | 125440 |  | 125440 | 125440 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-4485 | Repair and Maintenance-Machinery and Equipment | DDOPH-Pantukan | No | Shopping A-Cash Advance | N/A | 2025-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 50000 | 50000 |  | 50000 | 50000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-2984 | Repair and maintenance- machinery and equipment | DDOPH-Maragusan | No | Shopping A-Cash Advance | N/A | 2025-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 25000 | 25000 |  | 25000 | 25000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-4514 | Repair and Maintenance-Machinery and Equipment | DDOPH-Maragusan | No | Shopping A-Cash Advance | N/A | 2025-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 15000 | 15000 |  | 15000 | 15000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-4549 | Cooking Gas | DDOPH-Pantukan | No | Shopping A-Cash Advance | N/A | 2025-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 7200 | 7200 |  | 7200 | 7200 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-4404 | Cooking Gas | DDOPH-Laak | No | Shopping A-Cash Advance | N/A | 2025-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 7200 | 7200 |  | 7200 | 7200 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6394 | Food Supplies- Wet Market | DDOPH-Montevista | No | Shopping A-Cash Advance | N/A | 2025-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 200000 | 200000 |  | 200000 | 200000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6389 | Medical Supplies | DDOPH-Montevista | No | Shopping A-Cash Advance | N/A | 2025-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 200000 | 200000 |  | 200000 | 200000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6399 | Food Supplies- Wet Market | PAO-PRC | No | Shopping A-Cash Advance | N/A | 2025-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 183330 | 183330 |  | 183330 | 183330 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6372 | Food Supplies- Wet Market | DDOPH-Maragusan | No | Shopping A-Cash Advance | N/A | 2025-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 140000 | 140000 |  | 140000 | 140000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6374 | Cooking Gas | DDOPH-Maragusan | No | Shopping A-Cash Advance | N/A | 2025-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 10000 | 10000 |  | 10000 | 10000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6392 | Medical Supplies | DDOPH-Pantukan | No | Shopping A-Cash Advance | N/A | 2025-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 200000 | 200000 |  | 200000 | 200000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6418 | Drugs and Medicines | DDOPH-Montevista | No | Shopping A-Cash Advance | N/A | 2025-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 200000 | 200000 |  | 200000 | 200000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6403 | Food Supplies- Wet Market | DDOPH-Montevista | No | Shopping A-Cash Advance | N/A | 2025-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 200000 | 200000 |  | 200000 | 200000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6349 | Food Supplies- Wet Market | DDOPH-Laak | No | Shopping A-Cash Advance | N/A | 2025-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 127808.25 | 127808.25 |  | 127808.25 | 127808.25 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6339 | Food Supplies- Wet Market | DDOPH-Montevista | No | Shopping A-Cash Advance | N/A | 2025-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 103718.75 | 103718.75 |  | 103718.75 | 103718.75 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6381 | Repair and Maintenance- machinery and equipment | DDOPH-Pantukan | No | Shopping A-Cash Advance | N/A | 2025-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 50000 | 50000 |  | 50000 | 50000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6422 | Repair and Maintenance-Transportation Equipment | DDOPH-Montevista | No | Shopping A-Cash Advance | N/A | 2025-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 50000 | 50000 |  | 50000 | 50000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6353 | Cooking Gas | DDOPH-Laak | No | Shopping A-Cash Advance | N/A | 2025-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 6010 | 6010 |  | 6010 | 6010 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6404 | Food Supplies- Wet Market | DDOPH-Montevista | No | Shopping A-Cash Advance | N/A | 2025-12-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 200000 | 200000 |  | 200000 | 200000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6457 | Food Supplies- Wet Market | PAO-PRC | No | Shopping A-Cash Advance | N/A | 2025-12-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 188370 | 188370 |  | 188370 | 188370 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6395 | Repair and Maintenance- Transportation Equipment | DDOPH-Maragusan | No | Shopping A-Cash Advance | N/A | 2025-12-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 25000 | 25000 |  | 25000 | 25000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-6462 | LPG Gas 11kg content only | DDOPH-Montevista | No | Shopping A-Cash Advance | 2025-12-17 | 2026-12-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 13116 | 13116 |  | 13116 | 13116 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-6463 | LPG Gas 11kg content only | DDOPH-Montevista | No | Shopping A-Cash Advance | 2025-12-17 | 2026-12-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 24046 | 24046 |  | 24046 | 24046 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-6461 | LPG Gas 11kg content only | DDOPH-Montevista | No | Shopping A-Cash Advance | 2025-12-17 | 2026-12-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 25139 | 25139 |  | 25139 | 25139 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6363 | Drugs and Medicines | DDOPH-Pantukan | No | Shopping A-Cash Advance | N/A | 2025-11-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 200000 | 200000 |  | 200000 | 200000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
6380 | Food Supplies- Wet Market | PAO-PRC | No | Shopping A-Cash Advance | N/A | 2025-11-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 181440 | 181440 |  | 181440 | 181440 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
4988 | Repair and Maintenance-Transportation Equipment | DDOPH-Laak | No | Shopping A-Cash Advance | N/A | 2025-11-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 25000 | 25000 |  | 25000 | 25000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
25-4897 | Rehabilitation/Improvement of New Bataan NHS Gym, New Bataan, Davao de Oro (Construction of 64.5 In.m. Bleachers, 1 bay Covered Court, Control Room; Improvement of Stage and Rehabilitation of 2 Steel Post) | PEO | No | Competitive Bidding | 2025-10-08 | 2025-11-06 | 2025-11-14 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-12-05 | 2025-12-17 | N/A | N/A |  | N/A | N/A | N/A | GoP | 4964853.1 |  | 4964853.1 | 4957277.52 |  | 4957277.52 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-10 | 2025-11-24 | 2025-11-24 | 2025-11-24 | N/A | N/A | Completed
25-5189 | Improvement/Concreting of San Jose-Lebanon Road, Montevista, Davao de Oro (Concreting of 215.0 meters, Construction of 295.0 In.m Concrete Lined Canal and Installation of 1-910mm dia. RCPC w/ Headwall) | PEO | No | Competitive Bidding | 2025-10-01 | 2025-11-06 | 2025-11-14 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-12-05 | 2025-12-17 | N/A | N/A |  | N/A | N/A | N/A | GoP | 6294461.26 |  | 6294461.26 | 6273614.14 |  | 6273614.14 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-10 | 2025-11-24 | 2025-11-24 | 2025-11-24 | N/A | N/A | Completed
25-5663 | Construction of Hanging Bridge at Sitio Taytayan, Brgy. Andap, New Bataan, Davao de Oro [Construction of 60 ln.m. Foot Bridge with 32 ln.m. Graveled Pathway] | PEO | No | Competitive Bidding | 2025-10-08 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-28 | 2025-12-17 | N/A | N/A |  | N/A | N/A | N/A | GoP | 6172352.32 |  | 6172352.32 | 6167284.23 |  | 6167284.23 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | Completed
25-5692 | Construction of Single Barrel Box Culvert at Brgy. Panoraon, Maco, Davao de Oro [Completion of Single Barrel Box Culvert (Apron at B/S Concrete siding and Wheel Guard), Concreting of 18 ln.m. Installation of 12 ln.m. Metal Guardrail (Downstream side and Desilting of 50 ln.m.]- | PEO | No | Competitive Bidding | 2025-10-08 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-28 | 2025-12-17 | N/A | N/A |  | N/A | N/A | N/A | GoP | 2893037.96 |  | 2893037.96 | 2888782.9 |  | 2888782.9 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | Completed
25-4796 | Rehabilitation /Improvement of Montevista NHS Gym, Montevista, Davao de Oro (Construction of 1 bay Covered Court with Stage, 54 In. m. Bleachers and Demolition of 60 sq.m. Existing Stage) | PEO | No | Competitive Bidding | 2025-10-08 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-28 | 2025-12-17 | N/A | N/A |  | N/A | N/A | N/A | GoP | 4870363.3 |  | 4870363.3 | 4864269.38 |  | 4864269.38 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | Completed
25-4797 | Construction of Social Hall with Stage at Manasa ES, Mabini, Davao de Oro (Construction of (4) Four Bays Social Hall with Stage and 12 In.m Bleacher) | PEO | No | Competitive Bidding | 2025-10-08 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-28 | 2025-12-16 | N/A | N/A |  | N/A | N/A | N/A | GoP | 2541853.24 |  | 2541853.24 | 2536793.53 |  | 2536793.53 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | Completed
25-4801 | Construction of a Multipurpose Building at Brgy. San Roque, New Bataan, Davao de Oro | PEO | No | Competitive Bidding | 2025-10-01 | 2025-11-06 | 2025-11-14 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-12-05 | 2025-12-26 | N/A | N/A |  | N/A | N/A | N/A | GoP | 4938701.73 |  | 4938701.73 | 4933457.15 |  | 4933457.15 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-10 | 2025-11-24 | 2025-11-24 | 2025-11-24 | N/A | N/A | Completed
25-C0846 | Medical Supplies | PEEMO | No | Competitive Bidding | 2025-10-16 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-24 | 2025-12-05 | 2025-12-09 | 2025-12-10 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | GoP | 3030017 |  | 3030017 | 3028558 |  | 3028558 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | Completed
25-5215 | Construction of Multipurpose Building at Libuton ES, Laak, Davao de Oro (Construction of 5 bays Social Hall with Stage) | PEO | No | Competitive Bidding | 2025-10-01 | 2025-11-06 | 2025-11-14 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-12-05 | 2025-12-17 | N/A | N/A |  | N/A | N/A | N/A | GoP | 2819428.66 |  | 2819428.66 | 2818345.06 |  | 2818345.06 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-10 | 2025-11-24 | 2025-11-24 | 2025-11-24 | N/A | N/A | Completed
6263 | Repair and Maintenance-Machinery and Equipment | DDOPH-Maragusan | No | Shopping A-Cash Advance | N/A | 2025-11-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | GoP | 25000 | 25000 |  | 25000 | 25000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | Completed
[19 empty] | Total Allotted Budget of Procurement Activities | 171333432.21 | 20808671.63 | 150524760.58
[19 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 163417989.55 | 20788898.5 | 142629091.05
[19 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 7915442.66
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
ONGOING PROCUREMENT ACTIVITIES
6338 | Transfer, configuration, testing, commissioning and energization of the broadcast tower, antenna, and studio link transmitter from new barili, mawab to san isidro, nabunturan | PAO | No | Small Value Procurement | N/A | 2025-11-20 | N/A | N/A | 2025-11-26 | N/A | N/A | 2025-11-26 | 2025-12-01 | 2025-12-01 | 2025-12-22 | N/A | N/A | N/A | GoP | 1485000 | 1485000 |  | 1485000 | 1485000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0935 | Computer supplies | PGO-PPOPSP | No | Small Value Procurement | N/A | 2025-11-20 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-05 | 2025-12-09 | 2025-12-12 | N/A | N/A | N/A | GoP | 725699 | 725699 |  | 725504 | 725504 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0961 | Safety and Rescue Equipment | PDRRMO | No | Small Value Procurement | N/A | 2025-11-20 | N/A | N/A | 2025-11-26 | N/A | N/A | 2025-11-26 | 2025-12-01 | 2025-12-02 | 2025-12-09 | N/A | N/A | N/A | GoP | 499625 | 499625 |  | 490000 | 490000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0956 | Computer Equipment | PICTO | No | Small Value Procurement | 2025-11-14 | 2025-11-20 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 | 2025-12-12 | N/A | N/A | N/A | GoP | 494550 | 494550 |  | 494510 | 494510 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0715 | Laboratory Supplies | PHO | No | Small Value Procurement | 2025-10-16 | 2025-11-20 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-02 | 2025-12-03 |  | N/A | N/A | N/A | GoP | 429555 | 429555 |  | 429349 | 429349 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
5687 | Computer Equipment | PHO | No | Small Value Procurement | N/A | 2025-11-20 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-05 | 2025-12-09 | 2025-12-22 | N/A | N/A | N/A | GoP | 346040 | 346040 |  | 346015 | 346015 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0962 | Computer supplies | PVO | No | Small Value Procurement | N/A | 2025-11-20 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-05 | 2025-12-09 | 2025-12-12 | N/A | N/A | N/A | GoP | 199460 | 199460 |  | 199430 | 199430 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
3812 | Billi Light/Phototheraphy unit s/N | DDOPH-Montevista | No | Small Value Procurement | N/A | 2025-11-20 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 | 2025-12-10 | N/A | N/A | N/A | GoP | 158000 | 158000 |  | 157900 | 157900 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0949 | Office Equipment | PAO | No | Small Value Procurement | N/A | 2025-11-20 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-05 | 2025-12-09 | 2025-12-12 | N/A | N/A | N/A | GoP | 98355 | 98355 |  | 98310 | 98310 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
5995 | Token, as per sample | PHO | No | Small Value Procurement | N/A | 2025-11-20 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-05 | 2025-12-09 | 2025-12-10 | N/A | N/A | N/A | GoP | 55275 | 55275 |  | 55275 | 55275 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
5840 | Spare parts (Heavy Equipment) | PEO | No | Direct Contracting | N/A | 2025-11-20 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 | 2025-12-22 | N/A | N/A | N/A | GoP | 642425 | 642425 |  | 636197 | 636197 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
6289 | 50KVA Generator Set, Single Phase, 230V, 60Hz, Diesel Fed, Silent Type | PGSO | No | Small Value Procurement | N/A | 2025-11-21 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-05 | 2025-12-09 | 2025-12-25 | N/A | N/A | N/A | GoP | 1078000 | 1078000 |  | 1058000 | 1058000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0920 | Medical Supplies | PEEMO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 | 2025-12-11 | N/A | N/A | N/A | GoP | 858200 | 858200 |  | 820553.65 | 820553.65 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0924 | Drugs and Medicines | DDOPH-Montevista | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-10 | N/A | N/A | 2025-12-10 | 2025-12-11 | 2025-12-11 | 2025-12-23 | N/A | N/A | N/A | GoP | 351695 | 351695 |  | 346940 | 346940 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0908 | Other Machineries & Equipment | PEO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-05 | 2025-12-09 | 2025-12-25 | N/A | N/A | N/A | GoP | 230947 | 230947 |  | 229600 | 229600 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0918 | Packed Meals and Snacks | PSWDO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-05 | 2025-12-09 | 2025-12-11 | N/A | N/A | N/A | GoP | 203930 | 203930 |  | 203930 | 203930 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0915 | Office Equipment | PEO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 | 2025-12-12 | N/A | N/A | N/A | GoP | 113680 | 113680 |  | 110600 | 110600 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-5890 | BNS Kits and Customized Tote bag (as per design) | PAO-IPRD | No | Small Value Procurement | N/A | 2025-11-21 | N/A | N/A | 2025-12-03 | N/A | N/A | 2025-12-03 | N/A | 2025-12-10 | 2025-12-13 | N/A | N/A | N/A | GoP | 39913 | 39913 |  | 39913 | 39913 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-6183 | Spare parts (Light Vehicle) | VGO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | N/A | 2025-12-10 | 2025-12-22 | N/A | N/A | N/A | GoP | 16800 | 16800 |  | 16800 | 16800 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-6309 | Spare parts (Light Vehicle) | PGSO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | N/A | 2025-12-10 | 2025-12-22 | N/A | N/A | N/A | GoP | 15530 | 15530 |  | 15530 | 15530 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-5994 | Polo shirt Embroidered (as per sample) | PHO | No | Small Value Procurement | N/A | 2025-11-21 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | N/A | 2025-12-10 | 2025-12-12 | N/A | N/A | N/A | GoP | 10800 | 10800 |  | 10800 | 10800 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-6327 | Davao de Oro Token (Davao de Oro Bag, Caps, Notepad, Ballpen and 3 pcs Gold Bars) | PHO | No | Small Value Procurement | N/A | 2025-11-21 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | N/A | 2025-12-10 | 2025-12-11 | N/A | N/A | N/A | GoP | 9900 | 9900 |  | 9900 | 9900 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-5118 | Polo shirt with Print (as per sample) | PHO | No | Small Value Procurement | N/A | 2025-11-21 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | N/A | 2025-12-10 | 2025-12-12 | N/A | N/A | N/A | GoP | 9625 | 9625 |  | 9625 | 9625 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-6310 | Spare parts (Motor cycle) | PGSO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | N/A | 2025-12-10 | 2025-12-22 | N/A | N/A | N/A | GoP | 5450 | 5450 |  | 5450 | 5450 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-6323 | Spare parts (light Vehicle) | SPO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-03 | N/A | N/A | 2025-12-03 | N/A | 2025-12-10 | 2025-12-22 | N/A | N/A | N/A | GoP | 4400 | 4400 |  | 4400 | 4400 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-6290 | Spare parts (Motor cycle) | PGSO | No | Small Value Procurement | 2025-11-19 | 2025-11-21 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | N/A | 2025-12-10 | 2025-12-22 | N/A | N/A | N/A | GoP | 3600 | 3600 |  | 3600 | 3600 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
5740 | Plastic Products | PHO | No | Small Value Procurement | N/A | 2025-11-24 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | N/A | 2025-12-09 | 2025-12-15 | N/A | N/A | N/A | GoP | 833332 | 833332 |  | 829640 | 829640 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
5751 | Software Defined-Remote ethernet device 60Rev.1 Appliance with multi-region power adapter/POE injector | PICTO | No | Small Value Procurement | N/A | 2025-11-24 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-03 | 2025-12-09 | 2025-12-15 | N/A | N/A | N/A | GoP | 785835.6 | 785835.6 |  | 785600 | 785600 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
6340 | Job Order (Labor & Materials) | PSWDO | No | Small Value Procurement | N/A | 2025-11-24 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-03 | 2025-12-09 | 2025-12-10 | N/A | N/A | N/A | GoP | 363670.67 | 363670.67 |  | 360000 | 360000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
6227 | Job Order (Labor & Materials) | PICTO | No | Small Value Procurement | N/A | 2025-11-24 | N/A | N/A | 2025-12-01 | N/A | N/A | 2025-12-01 | 2025-12-05 | 2025-12-09 | 2025-12-22 | N/A | N/A | N/A | GoP | 137000 | 137000 |  | 136000 | 136000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
6300 | Other supplies/ Materials | PAO-Investment | No | Small Value Procurement | N/A | 2025-11-24 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | N/A | 2025-12-09 | 2025-12-25 | N/A | N/A | N/A | GoP | 60939 | 60939 |  | 60440 | 60440 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0680 | Construction Supplies | PAGRO | No | Small Value Procurement | 2025-11-21 | 2025-11-24 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | N/A | 2025-12-10 | 2025-12-25 | N/A | N/A | N/A | GoP | 42953.33 | 42953.33 |  | 42953.33 | 42953.33 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0963 | Spare parts (Heavy Equipment) | PEO | No | Direct Contracting | 2025-11-21 | 2025-11-24 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | N/A | 2025-12-10 | 2025-12-22 | N/A | N/A | N/A | GoP | 1013820 | 1013820 |  | 1013820 | 1013820 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
6390 | T-Shirt Printing (as per sample) | PAO | No | Small Value Procurement | N/A | 2025-11-28 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 | 2025-12-12 | N/A | N/A | N/A | GoP | 1083000 | 1083000 |  | 1083000 | 1083000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0921 | Office Equipment | PEEMO | No | Small Value Procurement | 2025-11-19 | 2025-11-28 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 | 2025-12-12 | N/A | N/A | N/A | GoP | 916968 | 916968 |  | 916828 | 916828 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
6346 | Spare parts (Heavy Equipment) | PEO | No | Small Value Procurement | N/A | 2025-11-28 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-10 | 2025-12-10 | 2025-12-22 | N/A | N/A | N/A | GoP | 194381 | 194381 |  | 184460 | 184460 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-6343 | Spare parts (Light Vehicle) | PGSO | No | Small Value Procurement | 2025-11-26 | 2025-11-28 | N/A | N/A | 2025-12-17 | N/A | N/A | 2025-12-17 | N/A | 2025-12-10 | 2025-12-17 | N/A | N/A | N/A | GoP | 37100 | 37100 |  | 37100 | 37100 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-5543 | Spare parts (Light Vehicle) | VGO | No | Small Value Procurement | 2025-10-22 | 2025-11-28 | N/A | N/A | 2025-12-03 | N/A | N/A | 2025-12-03 | N/A | 2025-12-10 | 2025-12-11 | N/A | N/A | N/A | GoP | 19710 | 19710 |  | 19710 | 19710 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-6366 | Spare parts (Light Vehicle) | PGSO | No | Small Value Procurement | 2025-11-26 | 2025-11-28 | N/A | N/A | 2025-12-03 | N/A | N/A | 2025-12-03 | N/A | 2025-12-10 | 2025-12-22 | N/A | N/A | N/A | GoP | 12500 | 12500 |  | 12500 | 12500 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0893 Lot 1 | Seedlings | PAGRO | No | Small Value Procurement | N/A | 2025-12-02 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 | 2025-12-22 | N/A | N/A | N/A | GoP | 360000 | 360000 |  | 360000 | 360000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0893 Lot 2 | Seedlings | PAGRO | No | Small Value Procurement | N/A | 2025-12-02 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 | 2025-12-22 | N/A | N/A | N/A | GoP | 780000 | 780000 |  | 780000 | 780000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-C0893 Lot 3 | Seedlings | PAGRO | No | Small Value Procurement | N/A | 2025-12-02 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 | 2025-12-22 | N/A | N/A | N/A | GoP | 826650 | 826650 |  | 821200 | 821200 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-5669 | Collection of Hospital Waste | DDOPH-Montevista | No | Small Value Procurement | 2025-11-26 | 2025-12-02 | N/A | N/A | 2025-12-05 | N/A | N/A | 2025-12-05 | 2025-12-09 | 2025-12-09 | 2025-12-22 | N/A | N/A | N/A | GoP | 1985000 | 1985000 |  | 1985000 | 1985000 |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
25-4106 | X-Ray Machine with Digital Radiography | DDOPH-Pantukan | No | Competitive Bidding | 2025-08-06 | 2025-11-06 | 2025-11-14 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-12-05 | 2025-12-10 | 2025-12-12 | 2025-12-14 | 2025-12-22 | N/A | N/A | N/A | GoP | 6200000 |  | 6200000 | 6150000 |  | 6150000 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-10 | 2025-11-24 | 2025-11-24 | 2025-11-24 | N/A | N/A | For Delivery
25-3813 | Newborn Hearing Machine | DDOPH-MONTEVISTA | No | Competitive Bidding | N/A | 2025-06-09 | 2025-06-17 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-15 | 2025-08-20 | 2025-08-29 | 2025-09-08 | 2025-10-06 | N/A | N/A | N/A | GoP | 1012000 |  | 1012000 | 845000 |  | 845000 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-06-16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | For Delivery
25-2850 REBID | Tandem Remote Weather Station (San Isidro) | PDRRMO | No | Competitive Bidding | N/A | 2025-06-09 | 2025-06-17 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-08 | 2025-08-13 | 2025-08-20 | 2025-09-05 | 2025-09-11 | N/A | N/A | N/A | GoP | 1993500 |  | 1993500 | 1654006.95 |  | 1654006.95 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-06-16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | N/A | N/A | For Delivery
25-4400 | Supply and Installation of Tunnel Ventilation System | PVO | No | Competitive Bidding | 2025-08-01 | 2025-08-12 | 2025-08-20 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-05 | 2025-09-10 | 2025-09-16 | 2025-09-19 | 2025-09-29 | N/A | N/A | N/A | GoP | 1500000 |  | 1500000 | 1464065.96 |  | 1464065.96 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-15 | 2025-08-29 | 2025-08-29 | 2025-08-29 | N/A | N/A | For Delivery
24-4728 | Expansion of Tissue Culture Facility-Supply and Installation of Greenhouse Facility with Shading and Irrigation System | PAGRO | No | Competitive Bidding | 2025-08-20 | 2025-08-26 | 2025-09-03 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-10-02 | 2025-10-08 | 2025-10-13 | 2025-10-15 | 2025-11-11 | N/A | N/A | N/A | GoP | 2904206.75 |  | 2904206.75 | 2869163.22 |  | 2869163.22 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-08-29 | 2025-09-16 | 2025-09-16 | 2025-09-16 | N/A | N/A | For Delivery
25-4284 | Brand-New Motorcycle | PEO | No | Competitive Bidding | 2025-08-06 | 2025-09-09 | 2025-09-24 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-14 | 2025-10-16 | 2025-10-20 | 2025-10-22 | 2025-11-05 | N/A | N/A | N/A | GoP | 460000 |  | 460000 | 459995 |  | 459995 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-09-16 | 2025-10-03 | 2025-10-03 | 2025-10-03 | N/A | N/A | For Delivery
25-C0876 | Defibrillator, Brand New, with UPS and AVR and Ultrasound Machine, OB- Gyne use with 3 active Probes | DDOPH-MONTEVISTA | No | Competitive Bidding | 2025-11-14 | 2025-11-13 | 2025-11-21 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-05 | 2025-12-10 | 2025-12-12 | 2025-12-14 | 2025-12-22 | N/A | N/A | N/A | GoP | 3369925 |  | 3369925 | 3368700 |  | 3368700 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-18 | 2025-11-27 | 2025-11-27 | 2025-11-27 | N/A | N/A | For Delivery
25-4525 | Supply and Installation of an End to end Multi-hazard Early Warning and Monitoring System Phase III remote CCTV Employing SCADA Technology | PDRRMO | No | Competitive Bidding | 2025-09-03 | 2025-09-16 | 2025-09-24 | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-14 | 2025-10-16 | 2025-10-20 | 2025-10-22 | 2025-11-11 | N/A | N/A | N/A | GoP | 2000000 |  | 2000000 | 1985500 |  | 1985500 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-09-16 | 2025-10-03 | 2025-10-03 | 2025-10-03 | N/A | N/A | For Delivery
25-C0789 | Office Equipment | PICTO | No | Competitive Bidding | 2025-09-24 | 2025-09-30 | 2025-10-08 | 2025-10-22 | 2025-10-22 | 2025-10-22 | 2025-10-30 | 2025-11-05 | 2025-11-11 | 2025-11-13 | 2025-11-17 | N/A | N/A | N/A | GoP | 2391400 |  | 2391400 | 2389640 |  | 2389640 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-03 | 2025-10-17 | 2025-10-17 | 2025-10-17 | N/A | N/A | For Delivery
25-C0890 | Agricultural Supplies | PAGRO | No | Competitive Bidding | 2025-10-16 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-20 | 2025-12-05 | 2025-12-09 | 2025-12-09 | 2025-12-10 | N/A | N/A | N/A | GoP | 2406492 |  | 2406492 | 2396268 |  | 2396268 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | For Delivery
25-6275 | Mechanical Bed, 3 Cranks with IV Stand and Mattres | DDOPH-MONTEVISTA | No | Competitive Bidding | 2025-11-12 | 2025-11-13 | 2025-11-21 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-05 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-22 | N/A | N/A | N/A | GoP | 4266270 |  | 4266270 |  |  |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-18 | 2025-11-27 | 2025-11-27 | 2025-11-27 | N/A | N/A | For Delivery
25-C0451 REBID | Medical and Laboratory Supplies | PHO | No | Competitive Bidding | 2025-08-13 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-24 | 2025-11-26 | 2025-12-01 | 2025-12-02 | 2025-12-22 | N/A | N/A | N/A | GoP | 1328375 |  | 1328375 | 1317995 |  | 1317995 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | For Delivery
25-4234 REBID | Hauling Truck-Dropside Body | PAGRO | No | Competitive Bidding | 2025-08-06 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-25 | 2025-12-03 | 2025-12-11 | 2025-12-11 | 2025-12-22 | N/A | N/A | N/A | GoP | 1482022.67 |  | 1482022.67 | 1481022.67 |  | 1481022.67 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | For Delivery
25-C0812 | Electrical Supplies/Construction | PGO-PPOC | No | Competitive Bidding | 2025-10-01 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-24 | 2025-11-26 | 2025-12-01 | 2025-12-01 | 2025-12-25 | N/A | N/A | N/A | GoP | 2433860 |  | 2433860 | 2413859.28 |  | 2413859.28 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | For Delivery
25-3700 | Medical Supplies | DDOPH-MONTEVISTA | No | Competitive Bidding | 2025-11-12 | 2025-11-13 | 2025-11-21 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-05 | 2025-12-10 | 2025-12-12 | 2025-12-14 | 2025-12-25 | N/A | N/A | N/A | GoP | 3360120 |  | 3360120 | 3272811 |  | 3272811 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-18 | 2025-11-27 | 2025-11-27 | 2025-11-27 | N/A | N/A | For Delivery
25-5254 LOT 1 | Repair of Kobelco Crawler Excavator Equipment | PEO-Motorpool | No | Competitive Bidding | 2025-11-14 | 2025-11-14 | 2025-11-21 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-05 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-25 | N/A | N/A | N/A | GoP | 4427177 |  | 4427177 |  |  |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-18 | 2025-11-27 | 2025-11-27 | 2025-11-27 | N/A | N/A | For Delivery
25-5254 LOT 2 | Repair of Kobelco Crawler Excavator Equipment | PEO-Motorpool | No | Competitive Bidding | 2025-11-14 | 2025-11-14 | 2025-11-21 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-05 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-25 | N/A | N/A | N/A | GoP | 3257968 |  | 3257968 |  |  |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-18 | 2025-11-27 | 2025-11-27 | 2025-11-27 | N/A | N/A | For Delivery
25-5254 LOT 3 | Repair of Kobelco Crawler Excavator Equipment | PEO-Motorpool | No | Competitive Bidding | 2025-11-14 | 2025-11-14 | 2025-11-21 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-05 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-25 | N/A | N/A | N/A | GoP | 3114855 |  | 3114855 |  |  |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-18 | 2025-11-27 | 2025-11-27 | 2025-11-27 | N/A | N/A | For Delivery
25-C0711 REBID | Office Equipment | PGO | No | Competitive Bidding | 2025-08-20 | 2025-11-06 | 2025-11-14 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-28 | 2025-12-05 | 2025-12-09 | 2025-12-09 | 2025-12-22 | N/A | N/A | N/A | GoP | 1597000 |  | 1597000 | 1596760 |  | 1596760 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-10 | 2025-11-24 | 2025-11-24 | 2025-11-24 | N/A | N/A | For Delivery
25-C0922 | Hospital/Medical Equipment | DDOPH-Laak | No | Competitive Bidding | 2025-11-12 | 2025-11-18 | 2025-11-26 | 2025-12-17 | 2025-12-17 | 2025-12-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 1399000 |  | 1399000 |  |  |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-24 | 2025-12-12 | 2025-12-12 | 2025-12-12 | N/A | N/A | On going Procurement Process
25-6362 | Supply and Installation of 1 Unit Passenger Elevator | PGSO | No | Competitive Bidding | 2025-11-26 | 2025-11-27 | 2025-12-05 | 2025-12-17 | 2025-12-17 | 2025-12-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 4500000 |  | 4500000 |  |  |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 12-2-025 | 2025-12-12 | 2025-12-12 | 2025-12-12 | N/A | N/A | On going Procurement Process
25-5389 | Anesthesia Machine with Ventilator and Accessories Brand New | DDOPH-MARAGUSAN | No | Competitive Bidding | 2025-11-26 | 2025-11-27 | 2025-12-05 | 2025-12-17 | 2025-12-17 | 2025-12-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 2500000 |  | 2500000 |  |  |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-12-02 | 2025-12-12 | 2025-12-12 | 2025-12-12 | N/A | N/A | On going Procurement Process
25-6150 | Rehabilitation of FMR from Kilagding Recenia – Kibagiou Road, Laak with Bridge Component | PEO | No | Competitive Bidding | 2025-11-07 | 2025-11-09 | 2025-11-26 | 2025-12-10 | 2025-12-10 | 2025-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP-PRDP | 250480000 |  | 250480000 |  |  |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-24 | 2025-12-12 | 2025-12-12 | 2025-12-12 | N/A | N/A | On going Procurement Process
25-4897 | Rehabilitation/Improvement of New Bataan NHS Gym, New Bataan, Davao de Oro (Construction of 64.5 In.m. Bleachers, 1 bay Covered Court, Control Room; Improvement of Stage and Rehabilitation of 2 Steel Post) | PEO | No | Competitive Bidding | 2025-10-08 | 2025-10-14 | 2025-10-22 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-12-05 | 2025-12-17 | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 4964853.1 |  | 4964853.1 | 4957277.52 |  | 4957277.52 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-16 | 2025-10-31 | 2025-10-27 | 2025-10-27 | N/A | N/A | On going Procurement Process
25-3644 | Rehabilitation of FMR from Kilagding Recenia – Kibagiou Road, Laak with Bridge Component | PEO | No | Competitive Bidding | 2025-09-08 | 2025-09-18 | 2025-09-17 | 2025-10-01 | 2025-10-01 | 2025-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP-PRDP | 240550293.8 |  | 240550293.8 |  |  |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-09-07 | 2025-09-19 | 2025-09-11 | 2025-09-11 | N/A | N/A | On going Procurement Process
25-4823 | Construction of Bleachers at Barangay Malamodao, Maco, Davao de Oro | PEO | No | Competitive Bidding | 2025-11-07 | 2025-11-18 | 2025-11-26 | 2025-12-17 | 2025-12-17 | 2025-12-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 1256617.14 |  | 1256617.14 |  |  |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-24 | 2025-12-12 | 2025-12-12 | 2025-12-12 | N/A | N/A | On going Procurement Process
25-6388 | Rice (Well Milled) (Framework Agreement) | PDRRMO | No | Competitive Bidding | 2025-12-03 | 2025-12-09 | 2025-12-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 14974470 |  | 14974470 |  |  |  | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-12-12 | N/A | N/A | N/A | N/A | N/A | On going Procurement Process
25-5189 | Improvement/Concreting of San Jose-Lebanon Road, Montevista, Davao de Oro (Concreting of 215.0 meters, Construction of 295.0 In.m Concrete Lined Canal and Installation of 1-910mm dia. RCPC w/ Headwall) | PEO | No | Competitive Bidding | 2025-10-01 | 2025-11-06 | 2025-11-14 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-12-05 | 2025-12-17 | 2025-12-26 | N/A | N/A | N/A | N/A | N/A | GoP | 6294461.26 |  | 6294461.26 | 6273614.14 |  | 6273614.14 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-10 | 2025-11-24 | 2025-11-24 | 2025-11-24 | N/A | N/A | Ongoing Procurement Process
25-5663 | Construction of Hanging Bridge at Sitio Taytayan, Brgy. Andap, New Bataan, Davao de Oro [Construction of 60 ln.m. Foot Bridge with 32 ln.m. Graveled Pathway] | PEO | No | Competitive Bidding | 2025-10-08 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-28 | 2025-12-17 | 2025-12-26 | N/A | N/A | N/A | N/A | N/A | GoP | 6172352.32 |  | 6172352.32 | 6167284.23 |  | 6167284.23 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | Ongoing Procurement Process
25-5692 | Construction of Single Barrel Box Culvert at Brgy. Panoraon, Maco, Davao de Oro [Completion of Single Barrel Box Culvert (Apron at B/S Concrete siding and Wheel Guard), Concreting of 18 ln.m. Installation of 12 ln.m. Metal Guardrail (Downstream side and Desilting of 50 ln.m.]- | PEO | No | Competitive Bidding | 2025-10-08 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-28 | 2025-12-17 | 2025-12-26 | N/A | N/A | N/A | N/A | N/A | GoP | 2893037.96 |  | 2893037.96 | 2888782.9 |  | 2888782.9 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | Ongoing Procurement Process
25-4796 | Rehabilitation /Improvement of Montevista NHS Gym, Montevista, Davao de Oro (Construction of 1 bay Covered Court with Stage, 54 In. m. Bleachers and Demolition of 60 sq.m. Existing Stage) | PEO | No | Competitive Bidding | 2025-10-08 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-28 | 2025-12-17 | 2025-12-26 | N/A | N/A | N/A | N/A | N/A | GoP | 4870363.3 |  | 4870363.3 | 4864269.38 |  | 4864269.38 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | Ongoing Procurement Process
25-4797 | Construction of Social Hall with Stage at Manasa ES, Mabini, Davao de Oro (Construction of (4) Four Bays Social Hall with Stage and 12 In.m Bleacher) | PEO | No | Competitive Bidding | 2025-10-08 | 2025-10-28 | 2025-11-05 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-28 | 2025-12-26 | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 2541853.24 |  | 2541853.24 |  |  | 2536793.53 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-10-27 | 2025-11-14 | 2025-11-14 | 2025-11-14 | N/A | N/A | Ongoing Procurement Process
25-4801 | Construction of a Multipurpose Building at Brgy. San Roque, New Bataan, Davao de Oro | PEO | No | Competitive Bidding | 2025-10-01 | 2025-11-06 | 2025-11-14 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-12-05 | 2025-12-26 | N/A | N/A | N/A | N/A | N/A | N/A | GoP | 4938701.73 |  | 4938701.73 | 4933457.15 |  | 4933457.15 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-10 | 2025-11-24 | 2025-11-24 | 2025-11-24 | N/A | N/A | Ongoing Procurement Process
25-5215 | Construction of Multipurpose Building at Libuton ES, Laak, Davao de Oro (Construction of 5 bays Social Hall with Stage) | PEO | No | Competitive Bidding | 2025-10-01 | 2025-11-06 | 2025-11-14 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-12-05 | 2025-12-17 | 2025-12-26 | N/A | N/A | N/A | N/A | N/A | GoP | 2819428.66 |  | 2819428.66 | 2818345.06 |  | 2818345.06 | RONALD B. CARIAGA LEONARDA M. NATOR EDWIN M. ORTIZ RAUF S. NOOR | 2025-11-10 | 2025-11-24 | 2025-11-24 | 2025-11-24 | N/A | N/A | Ongoing Procurement Process
[18 empty] | Total Allotted Budget of On-going Procurement Activities | 0 | 618199917.53 | 17539313.6 | 600660603.93 | 17431382.98 | 17431382.98
[19 empty] | Total Allotted Budget of On-going Procurement Activities | 968782224.61 | 59156656.86 | 901710125.09 | 578038819.66 | 59009179.98 | 354362793.09
***NOTHING FOLLOWS***
|  | Prepared by: |  |  | 2025-10-22: Checked by:; 2025-11-25: Recommending Approval: | Recommended for Approval by: | [6 empty] | Approved by:
|  | (SGD)MELISSA N. SAMENTAR |  |  | 2025-10-22: (SGD) KIRBY RYAN E. SUAREZ, JD, LPT; 2025-11-25: (SGD) IVAN KLEB N. ULGASAN, CESE | IVAN KLEB N. ULGASAN, CESE | [6 empty] | (SGD) ENGR. RAUL G. MABANGLO
|  | Clerk II-BAC Secretariat |  |  | 2025-10-08: Head BAC Secretariat; 2025-11-25: BAC Chairperson | BAC Chairperson | [6 empty] | Head of the Procuring Entity
Formulas:
Inspection & Acceptance = Completed[[#This Row],[Delivery/ Completion]]

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds | Mode of Procurement
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget) | Competitive Bidding
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget) | Limited Source Bidding
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget) | Direct Contracting
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution | Repeat Order
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution | Shopping 52.1(a) - Unforeseen Contingency
Failed under Section 35.1 (b) |  | BAC Resolution |  | Shopping 52.1(b) - Regular Office Supplies and Equipment not available in PS
Failed under Section 35.1 (c) |  | Award |  | Negotiated Procurement - Two Failed Biddings
Failed under Section 41 (b) |  | Cancelled |  | Negotiated Procurement - Emergency Cases
Failed under Section 41 (c) |  |  |  | Negotiated Procurement - Take-Over of Contracts
Contract was extended |  |  |  | Negotiated Procurement - Adjacent or Contiguous
Contract was renewed |  |  |  | Negotiated Procurement - Agency-to-Agency
Cancelled |  |  |  | Negotiated Procurement - Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
Others, please encode directly on the cell |  |  |  | Negotiated Procurement - Highly Technical Consultants
Negotiated Procurement - Defense Cooperation Agreement
Negotiated Procurement - Small Value Procurement
Negotiated Procurement - Lease of Real Property and Venue
Negotiated Procurement - NGO Participation
Negotiated Procurement - Community Participation
Negotiated Procurement - UN Agencies, Int'l Organizations or International Financing Institutions
Negotiated Procurement - Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant Products, Electronic Charging Devices, and Online Subscriptions
Foreign Guidelines - Competitive Bidding
Foreign Guidelines - Alternative Method
Competitive Dialogue
Unsolicited Offer with Bid Matching
Direct Acquisition
Direct Sales
Direct Procurement for Science, Technology, and Innovation
Others, specify in the remarks: Mode of Procurement use <Mode>