## Sheet1
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT GOVERNMENT PROJECTS, PROGRAMS OR ACTIVITIES
Region: XI |  |  |  | Calender Year: | 2025
Province: Davao de Oro |  |  |  | Quarter: | 1
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Construction/Upgrading of CVPH-Pantukan | Brgy. Kingking, Pantukan | 46400000 | 2019-10-24 | 2021-08-27 | 100% | 41617957.33 |  | Completed
Construction/Upgrading of CVPH-Pantukan - Phase II | Brgy. Kingking, Pantukan | 3600000 | 2021-03-13 | 2021-08-27 | 100% | 3233322.99 |  | Completed
Const. of IP House (Balai Mandaya-Mansaka) | Brgy. Pagsabangan, New Bataan | 20000000 | 2020-02-20 | 2025-02-25 | 95.82% | 18550451.78 | 21 | ADMIN. Waiting for the delivery of materials for water system.
Const. of IP House (Balai Tu Mandiba) | Brgy. Prosperidad, Montevista | 20000000 | 2020-02-20 | 2025-02-25 | 96.23% | 18191703.5 | 21 | ADMIN. Waiting for the delivery of materials for water system.
Const. of IP House (Balai na Linagsawan Tu Tribu Dibabawon) | Brgy. Awao, Monkayo | 20000000 | 2020-02-20 | 2025-02-25 | 93.5% | 16827235.09 | 21 | ADMIN. On-going.
Const. of Temporary Treatment & Monitoring Facility | Kingking, Pantukan | 10000000 | 2022-03-30 | 2023-05-09 | 100% | 8495113.26 |  | Completed
Const. Of Water System at Barangay Maparat, Compostela | Maparat, Compostela | 20000000 | 2021-10-07 | 2022-12-31 | 100% | 10998534.4 |  | Completed
Road Upgrading/Improvement at Purok 1, Barangay Panansalan, Compostela | Purok 1, Panansalan, Compostela | 20000000 | 2021-09-07 | 2023-08-15 | 100% | 8825950.13 |  | Completed
Const. of Level II Water System, Barangay Masara | Masara, Maco | 3000000 | 2021-11-11 | 2022-06-24 | 100% | 0 |  | Completed
Improvement of Health Center Calabcab, Maco | Calabcab, Maco | 1500000 | 2021-11-11 | 2022-02-02 | 100% | 1347606.49 |  | Completed
Upgrading of Water Supply System, Brgy. Bahi | Bahi, Maragusan | 3000000 | 2021-11-25 | 2022-06-19 | 100% | 2699977.91 |  | Completed
Conc. of Purok Rizal FMR, Brgy. Coronobe, Maragusan | Coronobe, Maragusan | 5000000 | 2021-09-07 | 2022-01-07 | 100% | 4399975.03 |  | Completed
Rehab. of Prk. Del Pilar-Prk. Jacinto FMR, Barangay Coronobe, Maragusan | Coronobe, Maragusan | 5000000 | 2021-09-07 | 2022-04-30 | 100% | 4499968.59 |  | Completed
Const. of Water Supply System, Brgy. San Jose, Monkayo | San Jose, Monkayo | 13000000 | 2021-10-07 | 2023-02-26 | 100% | 13000000 |  | Completed
Const. of Water Supply System, Brgy. San Isidro, Monkayo | San Isidro, Monkayo | 10000000 | 2021-10-07 | 2023-03-20 | 100% | 7997328.15 |  | Completed
Rehab/Improvement of Water Supply System at Brgy Mt. Diwata, Monkayo | Mount Diwata, Monkayo | 10000000 | 2021-11-25 | 2023-02-10 | 100% | 8499953.13 |  | Completed
Establishment of Feedmills | Pasian, Monkayo | 7500000 | 2019-11-28 | 2025-12-31 | 81.37% | 6103000 |  | Waiting for the completion of Phase 2
Procurement and Delivery of Trichoderma Packs (Support to Fusarium Wilt Mgt) | Provincewide | 5761600 | 2024-01-01 | 2024-12-31 | 31.2% | 1797563.47 |  | On going
Establishment of Multiplier Farm | Pasian, Monkayo | 5627255.16 | 2020-08-22 | 2025-03-31 | 99.97% | 5625353.24 |  | Completed
AFC Support Fund/Consultation Fund 2024 | Provincewide | 140000 | 2024-05-29 | 2025-04-30 |  | 0 |  | On going
Sustainment of Molecular Laboratory Operation | DDOPH-Montevista | 5000000 | 2003-12-04 | 2024-06-30 | 0% | 0 |  | Completed
Health Emergency Allowance (HEA)/OCA | Provincewide | 90354375 | 2024-05-29 | 2024-12-31 | 95.69% | 86462240.79 |  | Completed
Share in PCSO-Lotto LGU Share | Provincewide | 654675.2 | 2023-07-01 | 2024-12-31 | 44.76% | 293060.77 |  | On going
Establishment of 30 SOW Level Swine Multiplier Farm (INSPIRE) Program | Provincewide | 10000000 | 2023-12-15 | 2025-12-31 | 50.29% | 5028928.29 |  | On going
PAFES Operation Fund for Co-Financing in DDO 2023-2025 | Provincewide | 875000 | 2023-07-27 | 2025-06-30 | 92.33% | 807875 |  | On going
Community Empowered through Science & Technology | Provincewide | 1500000 | 2023-12-10 | 2025-12-10 | 69.16% | 1037385 |  | On going
Livestock & Poultry Dev't. Program (Impv't. of Free-Ranged Chicken Production Facility) | Pasian, Monkayo | 100000 | 2024-04-22 | 2025-03-31 | 98.35% | 98350 |  | Completed
Brgy. Watershed Reforestation & Rehab.Project-Prk.5, Sitio Pinaupuan, Naga, Laak | Naga, Laak | 100000 | 2024-04-22 | 2024-07-22 | 99.5% | 99504.5 |  | Completed
Brgy. Watershed Reforestation & Rehab. Project-Prk.7, Sitio Cadan, Kapitunan, Nabunturan | Katipunan, Nabunturan | 100000 | 2024-04-22 | 2024-07-22 | 99.5% | 99504.5 |  | Completed
Brgy. Watershed Reforestation & Rehab. Project-Prk.12, San Miguel, Compostela | San Miguel, Compostela | 100000 | 2024-04-22 | 2024-07-22 | 99.58% | 99584.1 |  | Completed
Brgy. Watershed Reforestation & Rehab. Project-Prk.15, Bantacan, New Bataan | Bantacan, New Bataan | 100000 | 2024-04-22 | 2024-07-22 | 99.5% | 99504.5 |  | Completed
Brgy. Watershed Reforestation & Rehab. Project-Sitio Lanzones, Lahi, Maragusan | Lahi, Maragusan | 100000 | 2024-04-22 | 2024-07-22 | 99.5% | 99504.5 |  | Completed
Medical Assistance to Indigent and Financially Incapacitated Patients | Provincewide | 37746000 | 2024-09-25 | 2024-12-31 | 99.45% | 37536792.06 |  | Completed
Emergency Employment Program 2024-TUPAD | Provincewide | 44581801 | 2024-11-01 | 2025-12-31 | 40.13% | 17888960.19 |  | On going
Assistance to Individual in Crisis Situation (AICS) 2024 | Provincewide | 10000000 | 2024-12-17 | 2025-12-17 | 46.13% | 4613500 |  | On going
Trichoderma Harzianum Project under HVCDP CY 2024 | Provincewide | 1144000 | 2025-01-22 | 2026-02-16 |  |  |  | On going
QRF 2024 (Rehab. & Recovery of Shearline & Low Pressure Area (LPA) affected farmers | Provincewide | 8471420 | 2025-01-22 | 2026-01-22 |  |  |  | PR on process
Implementation of Healthy Learning Institutions | Provincewide | 3700000 | 2025-03-03 | 2025-12-29 |  |  |  | Waiting for Approval of Project Design.
Healthy Communities | Provincewide | 4297964 | 2025-03-05 | 2025-12-29 |  |  |  | Waiting for Approval of Project Design.
0
| TOTAL | 448454090.36 |  |  |  | 336975688.69
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
(SGD.)ARIEL D. MANDAWE, CPA | (SGD.)EVA JEAN S. LICAYAN |  | (SGD.)ENGR. RODERICK M. DIGAMON |  |  | (SGD.)DOROTHY P. MONTEJO-GONZAGA
Provincial Accountant | Provincial Budget Officer |  | Provincial Engineer |  |  | Governor